## All with Discipline Notes
| Topic | Subtopic | Commitment | Source | Project Section | Responsibility | VF Notes | Commitment Status | Comment from Discipline (7/8/2025) | Commitment Completion Date
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | a. The RCBC portion of the culvert system, as well as the dual CMAP at the culvert outlet will remain in place. Work on this portion of the culvert system will not occur until bat activity ceases for the season (and bats are presumably no longer using the culvert for roosting). This time frame is approximately between November 15 and March 15. NCDOT will monitor the culvert with an acoustic detector and/or emergence counts to determine when bat activity ceases for the season. After bat activity ceases for the season, a federally permitted bat biologist will enter the culvert to confirm no bats are present. This will determine when construction activity may safely begin, and/or when it should end to avoid effects to MYGR that may use the culvert system for roosting. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and BSG |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | b. NCDOT will conduct sleeving or replacement of the 60” CMP adjacent to Courtland Ave. and the entrance to Dickson Elementary School (that conveys flow under Hill Street to the RCBC) between October 15 and April 1. | Green Sheet, June 2020 BO | B (Design-Build) | Construction, Design-Build Team and BSG |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | NCDOT will monitor bat activity at the culvert before, during, and after construction. Acoustic monitoring and/or emergence surveys will be conducted between Marchand November. | Green Sheet, June 2020 BO | B (Design-Build) | BSG | Updated to visual surveys in the culvert and acoustic surveys before/during/after. Started in 2024 and submitted a report on it to USFWS early 2025. Can move to old pile | In Progress
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Vegetation Removal | An operational work pad area will be established near the culvert outlets to complete the culvert rehabilitation process, as well as at the inlet near Courtland Avenue where the 60” CMP will be replaced or lined. Vegetation must be cleared to allow room for the work pad. NCDOT will cut plants in the work pad area in a way that will minimize impacts to bats and their activity by implementing the following measures: vegetation will not be removed if the area will be left bare for many months prior to construction; cutting of vegetation will be coordinated with USFWS and will not occur until all bats have left the culvert for the winter. This will be determined through emergence counts and/or acoustic monitoring and a physical check of the culvert for remaining bats; and limiting cutting to only what is necessary to complete the work and no more than 50 feet from culvert inlet/outlets. | Green Sheet, June 2020 BO | B (Design-Build) | Construction, BSG, Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | An equipment staging area will be established adjacent to the work pads near the culvert outlets and inlet areas near Courtland Avenue to complete the culvert rehabilitation process. NCDOT will attempt to use areas that are already cleared of vegetation whenever possible. This area will only be used for culvert rehabilitation activity staging and will not be used for any other project construction purposes. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | b. NCDOT will maintain baseflow to the RCBC and CMAP portion of the culvert (nonstormwater sources) to provide a naturally occurring, continual water source. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | c. NCDOT will either replace or install a liner in the 60” CMP located adjacent to Courtland Ave. and the entrance to Isaac Dickson Elementary School that conveys flow under Hill Street to the RCBC. NCDOT will complete this activity between October 15 and April 1. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | d. NCDOT will install a barrier/baffle (from here referred to as a baffle) in the RCBC between the intersection with the 60” CMP (located adjacent to Courtland Ave. and the entrance to Isaac Dickson Elementary School that conveys flow under Hill Street) and the upstream end of the RCBC to buffer noise and light associated with the CMP replacements further upstream. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Preservation of Riparian Vegetation | a. NCDOT will ensure the Contractor preserves riparian buffer trees where practicable and feasible. | Green Sheet, June 2020 BO | All Sections | Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Roadway Construction Lighting | a. Due to MYGR activity on the landscape, NCDOT will limit all construction-related lighting to whatever is necessary to maintain safety in active work areas closest to the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team, |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Roadway Construction Lighting | b. Construction-related lighting will be indirect in nature and will not project into adjacent forested areas or over the water surface of the French Broad River, Hominy Creek, Emma Branch, or Smith Mill Creek, whenever practicable. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Access Roads | a. NCDOT will revegetate all access roads created for bridge construction and replacement activities where practicable. | Green Sheet, June 2020 BO | All Sections | Construction, REU and Design Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Nighttime Construction Activities | a. NCDOT will limit the use of nighttime construction within 50’ of the French Broad River, Hominy Creek, Emma Branch, or Smith Mill Creek between April 1 and October 15 to only the following activities: causeway construction, drilled shafts, concrete pours, beam setting, and traffic shifts. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Nighttime Construction Activities | b. NCDOT shall commit to restrict the Contractor to no night work at crossings of the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek to minimize potential impacts to lactating females and their pups between June 1 and June 14. Between June 15 through August 1, NCDOT will also commit to restrict the Contractor to no more than 28 total nights of work, with no more than four consecutive nights. Lighting used for construction will be limited to what is necessary to maintain safety standards and will only be directed toward active work areas. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Pre-Demolition Check for Bats | a. If bridge demolition is required between April 1 and October 15, NCDOT will conduct a check of all subject bridges within 30 days of demolition to determine if bats are present. See Term and Condition 12 for checks specific to culverts. T&C 12: In order to carry out Reasonable and Prudent Measure 5, NCDOT will conduct culvert checks for roosting bats within 30 days of rehabilitation or repair for any culverts five feet tall or higher, and 200 feet or longer, scheduled to occur from March 15th through November 15th. If bats are found, a similar protocol will be used to the pre-demolition check for bats in bridges | Green Sheet, June 2020 BO | All Sections | BSG | Coordinate with Division on construction schedules | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Pre-Demolition Check for Bats | b. If bats are present, one of the following options will be implemented (options listed in order of preference). NCDOT will: i. Wait for bats to leave for the season (approximately mid-October to early November) before beginning work; or ii. A biologist will monitor the bridge and work will begin after bats leave the bridge for the evening, or iii. A permitted biologist will exclude bats from work area immediately prior to the start of work using acoustic deterrents, or iv. A permitted biologist will hand remove bats from work area immediately prior to the start of work. v. If pre-demo check determines pups are present, NCDOT will refrain from bridge demolition until it can be determined by a biologist that the pups are volant, and then use the previous options to proceed with demolition. | Green Sheet, June 2020 BO | All Sections | BSG |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Red Safety Lighting | a. As part of NCDOT’s Communication Plan specific to the construction/demolition of the bridges over the French Broad River, NCDOT will place solar-powered, steadystate red lights on the causeways to alert river users to their locations. Generators will not be used to provide power. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Contract Language | Contract language will include the following, or similar language as appropriate for bridges over the French Broad River a. The Contractor will be required to prosecute the work in a continuous and uninterrupted manner from the time work begins until completion of each phase of structure construction, demolition, and completion. The Contractor will not be permitted to suspend operations except for reasons beyond their control or except where the Engineer has authorized a suspension of the Contractor’s operations in writing. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | a. Causeways will not restrict more than 50% of the existing channel width of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with USACE and USFWS prior to permitting. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team | Obsolete
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | b. NCDOT will require the Contractor to use clean rock (free of debris and pollutants) for the construction of the causeways to minimize unnecessary sediment input into the river. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | c. Causeway material will be removed to the extent practicable and either disposed of off-site or used in areas that require permanent stone protection after project completion. NCDOT will also require that concrete barriers (barrier rail) be placed along the downstream edge of each causeway to limit the downstream movement of causeway material during high flow events. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | d. If the final causeway plan is staged, causeway material will be added/removed as needed for each stage to minimize the causeway footprint over the length of the project. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | e. Construction fabric will not be used under the causeway material, as it tends to tear into tiny pieces and float downstream during removal. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | f. Any equipment on the causeways will be removed any time throughout a work day when the water level rises, or is expected to rise overnight, to a point where the equipment could be flooded, or during periods of inactivity (two or more consecutive days). The only exception to this measure is that the drill rig and crane may be left in place for periods of inactivity; however, they must also be removed if the water rises, or is expected to rise, to a point where the drill rig and crane could be flooded. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | g. NCDOT will require its Contractor to have clean, non-leaking equipment, diapers onsite for each causeway, and spill kits located at each causeway. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | h. Causeways needed for the new bridges over the FBR will be designed so that during a 100 year storm event there will not be a rise in water surface elevation outside the Action Area greater than normal seasonal variation. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction and Design-Build Team |  | Cannot be met | This cannot be met. We advised NCDOT of this during procurement. There will naturally be a rise when material is placed in the channel. We also do not know what the Action Area or the seasonal veriation are.
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | a. All construction equipment shall be refueled above the 100-year base flood elevation plus a foot of freeboard and be protected with secondary containment. During crucial periods of construction and demolition, when the drill rig and crane cannot be moved, the drill rig and crane can be refueled while inside the 100-year floodplain provided that spill response materials (such as spill blankets and fueling diapers) are used during the refueling. Hazardous materials, fuel, lubricating oils, or other chemicals will be stored above the 100-year base flood elevation plus a foot of freeboard. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Cannot be met | This cannot be met. The entire construction footprint is essentially inside the 100yr elevation.
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | b. Areas used for borrow or construction by-products will not be located within wetlands or the 100-year base flood elevation plus a foot of freeboard. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Cannot be met | This cannot be met. The entire construction footprint is essentially inside the 100yr elevation.
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | c. When constructing drilled piers for the I-240, I-40 and I-26 French Broad River bridges, a containment system will be developed so material does not enter the river. Material byproduct will be pumped out of the shaft to an upland disposal area to the extent practicable and treated through a proper stilling basin or silt bag. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | d. Construction of all bridges will be accomplished in a manner that prevents uncured concrete from coming into contact with water entering or flowing in the river. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | e. Removal of existing bridges shall be performed so as not to allow debris to fall into the water. If debris is dropped in a waterway, it will be immediately removed. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | f. NCDOT will not place bridge bents in Smith Mill Creek or Emma Branch. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team | Completed | Fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Erosion Control Measures | a. The Soil and Erosion Control (SEC) plan will be in place prior to any ground disturbance for all bridge replacements and construction. When needed, combinations of erosion control measures (such as silt bags in conjunction with a stilling basin) will be used to ensure that the most protective measures are being implemented. | Green Sheet, June 2020 BO | All Sections | Construction, REU, Design-Build Team |  | In Progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Erosion Control Measures | b. NCDOT standard procedures dictate that when a project has both Environmentally Sensitive Areas and a requirement to follow DSSW, and uses the GP NCG01 permit, NCDOT will default to the most-restrictive SEC measure requirement (Appendix H of BO). | Green Sheet, June 2020 BO | All Sections | Construction, REU, Design-Build Team |  | In Progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | i. NCDOT will revisit CP4A with the Merger Team after the BA is submitted to discuss any new avoidance and minimization efforts for major crossings of the French Broad River and Hominy Creek including those in the Biological Assessment. | Green Sheet, June 2020 BO | All Sections | BSG | Completed | Fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | ii. NCDOT will provide USFWS with the final roadway lighting plans and allow 15 days for review upon acknowledgement of receipt of notice. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | Not started | Commitment cannot be fulfilled until lighting plan is finalized
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | iii. NCDOT will continue to identify avoidance and minimization measures to all Waters of the U.S. and ensure that major hydraulic structures associated with the project are designed and installed to minimize negative impacts to stream stability (and therefore, water quality) to the greatest extent practicable. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | In Progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | iv. NCDOT will provide USFWS with the total size of bridge footings in the water as project design progresses and the information becomes available. | Green Sheet, June 2020 BO | All Sections | AC Bid-Build, Design Build Team |  | Not started | Commitment cannot be fulfilled until bridge plans are RFC'd
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | v. NCDOT will provide USFWS with the results of the hydrology modeling (described below) as it becomes available, including change in French Broad velocity with causeways in place, and change in water surface elevation with causeways in place. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Design-Build Team |  | In Progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | vi. Once ROW plans are developed where vegetation will be removed in riparian areas, NCDOT will meet with USFWS and NCWRC to discuss revegetation plans with the goal of establishing native forested buffers in all impacted areas (Hominy Creek, Smith Mill Creek, Emma Branch, and the French Broad River). NCDOT, USFWS and NCWRC will also discuss revegetation for acquired riparian ROW that was not forested when purchased. Additionally, NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG, REU
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | i. The Bid Build Contractor shall meet with NCDOT personnel and USFWS and representatives immediately after contract execution to review the project and project commitments. At this time, the USFWS shall be afforded the opportunity to meet with key Bid Build Contractor members and NCDOT employees to provide education on the effects of artificial lighting, noise, and construction on nearby wildlife habitat and behavior. The Bid Build Contractor shall coordinate with the NCDOT Environmental Analysis Unit to schedule these meetings. This meeting shall be made prior to submitting any required permit modification application. | Green Sheet, June 2020 BO | B (Design-Build) | BSG, Bid-Build Contractor, Construction, NCDOT Construction, |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | ii. The Bid Build Contractor shall provide USFWS with the construction phasing plan for each bridge. | Green Sheet, June 2020 BO | All Non-D-B Sections | Bid-Build Contractor, Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | iii. The Bid Build Contractor and / or NCDOT shall contact USFWS if new information about MYGR is discovered, as it relates to the project. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction, BSG |  | Not started | Commitment cannot be fulfilled until bridge plans are RFC'd
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | iv. The Bid Build Contractor shall report any dead bats found on the construction sites to USFWS. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | v. The Bid Build Contractor shall adhere to project commitments within the ROD and the Biological Opinion relating to Section 7 of the Endangered Species Act. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | i. NCDOT will arrange a meeting between each shortlisted DBT, representatives of the USFWS, and other regulatory agencies prior to the due date for the submission of Technical and Price Proposals. The discussions and answers provided at these meetings are not contractually binding but intend to offer the shortlisted teams an opportunity to inquire as to the permitting process as well as specific team concepts. | Green Sheet, June 2020 BO | B (Design-Build) | BSG |  | Fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | ii. NCDOT will arrange a meeting with the selected Design-Build Team (DBT) to provide an opportunity for USFWS to convey their concern about potential effects to protected species. The DBT shall meet with NCDOT personnel and USFWS and regulatory agency representatives immediately after contract execution to review the project and project commitments. At this time, the USFWS shall be afforded the opportunity to meet with key DBT members and NCDOT employees to provide education on the effects of artificial lighting, noise, and construction on nearby wildlife habitat and behavior. The NCDOT shall coordinate with the DBT and the NCDOT Environmental Analysis Unit to schedule this meeting. This meeting shall be made prior to submitting the permit application. This is prior to the standard pre-con environmental meeting. | Green Sheet, June 2020 BO | B (Design-Build) | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | iii. The DBT shall adhere to project commitments within the ROD and the Biological Opinion relating to Section 7 of the Endangered Species Act. The DBT will be required to prepare information for any event in which NCDOT and FHWA reinitiate Section 7 consultation with the USFWS. It is possible that consultation be reinitiated prior to Concurrence Point 4B and again at Concurrence Point 4C. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | In progress | Commitments have been reviewed and circulated to the appropiate staff, some will occur shortly prior permit application submittal and during construction.
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | iv. NCDOT will continue to identify avoidance and minimization measures to all Waters of the U.S. and ensure that major hydraulic structures associated with the project are designed and installed to minimize negative impacts to stream stability (and therefore, water quality) to the greatest extent practicable. As part of this process, NCDOT and the DBT will continue to coordinate with the Merger Team to identify avoidance and minimization measures and ensure that project impacts are minimized to every practicable extent, including impacts to federally protected species. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | In progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | v. The DBT shall invite USFWS and regulatory agency representatives to the pre-construction meeting for the proposed project, as well as to all subsequent field inspections prior to construction, to ensure compliance with all special project commitments. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | Not Started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | vi. The DBT shall provide USFWS with the sediment and erosion control plan and allow 15 days for review upon acknowledgement of receipt of notice. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | In progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | vii. The DBT shall provide regulatory agency representatives with the demolition plan for all bridges and allow 15 days for review upon acknowledgement of receipt of notice. All agencies will be notified prior to start of demolition so they may have a representative on site. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | Not Started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | viii. The DBT shall provide USFWS with the construction phasing plan for each bridge. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | Not Started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | ix. The DBT and / or NCDOT shall contact USFWS if new information about MYGR is discovered, as it relates to the project. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team, Construction |  | Not Started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | x. The DBT shall report any dead bats found on the construction sites to USFWS. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team, Construction |  | Not Started | Commitment cannot be fulfilled until construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | xi. The DBT shall include an Environmental Coordinator as a member of their Team who will be required to attend all design, merger, and preconstruction meetings, and who will consult bat and mussel experts, as needed. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team |  | In progress | To be fulfilled by Chris Rivenbark and Pete Stafford
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | xii. Once ROW plans are developed where vegetation will be removed in riparian areas, NCDOT will meet with USFWS and NCWRC to discuss revegetation plans with the goal of establishing native forested buffers in all impacted areas (Hominy Creek, Smith Mill Creek, Emma Branch, and the French Broad River). NCDOT, USFWS and NCWRC will also discuss revegetation for acquired riparian ROW that was not forested when purchased. Additionally, NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. Certain ROW areas will not be forested because they must be mowed or maintained at a low height for safety purposes. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG, REU |  | Not Started | Will coordinate post ROW plan development
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | a. NCDOT’s stormwater commitment guidance, will apply at crossings of the French Broad River and its tributaries, and any portion of the NCDOT stormwater conveyance system draining to those waters within the right-of-way. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | In progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | b. NCDOT will prepare a stormwater management plan (SMP) to implement postconstruction stormwater best management practices (BMPs) to the maximum extent practical, consistent with the Department’s National Pollutant Discharge Elimination System (NPDES) Post Construction Stormwater Program. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | In progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | c. When preparing the SMP, NCDOT commits to using a hierarchical BMP selection process, optimized to treat silt, nutrients, and heavy metals. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | In progress | This will be fulfilled
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | d. At each discharge location outside of the 100-year floodplain, the hydraulics engineer will evaluate the feasibility of installing either an infiltration basin or a media filter as described in NCDOT’s BMP Toolbox. If neither is feasible, the hydraulics engineer will select a feasible BMP. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | No longer required per SA | Discuss with contractor
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | e. NCDOT will commit to evaluating the use of emerging BMP technologies that the Department has not yet published in its BMP Toolbox: i. Bioswales ii. Bio embankments iii. Biofiltration conveyances iv. Soil improvement to maximize infiltration | Green Sheet, June 2020 BO | All Sections | NCDOT, Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | f. The NCDOT hydraulics design engineer will consult with the State Hydraulics Engineer and obtain prior approval before proposing one of these BMP technologies in the SMP. | Green Sheet, June 2020 BO | All Sections | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | Crossing numbers in this section refer to Table 1 in Section 2.2.4 and Figures 4A-4D in Appendix A of the Biological Opinion. a. General CM’s for all crossings of the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek: i. Use shorter poles, providing an overall LED light fixture mounting height of 35’ above the pavement surface. ii. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. iii. Use LED light fixtures with a BUG rating of 1-0-3 or less iv. Change the design standards to meet the AASHTO minimum requirements of an average of 0.6 fc at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. v. At all identified crossings, the proposed high mast poles and 45’ poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35’ poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | Green Sheet, June 2020 BO | All Sections | Design-Build Team | Obsolete now
| Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | a. General CM’s for the entire project: i. Use shorter poles, providing an overall LED light fixture mounting height of 35’ above the pavement surface. ii. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. iii. Use LED light fixtures with a BUG rating of 1-0-3 or less iv. Change the design standards to meet the AASHTO minimum requirements of an average of 0.6 fc at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. v. At all identified crossings, the proposed high mast poles and 45’ poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35’ poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | June 2020 BO | All Sections | Design-Build Team | Obsolete now
|  |  | General Conservation Measures that apply to parts of the action area near and over waterways and riparian areas: 1. Use shorter poles, providing an overall LED light figure mounting height of 35 feet above the pavement surface. 2. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. 3. Use LED light fixtures with a BUG rating of 1-0-3 or less 4. Use LED light fixtures with a lower lumen output, reducing overall brightness a. Change the design standards to meet the American Association of State Highway and Transportation Officials (AASHTO) minimum requirements of an average of 0.6 foot-candle (fc) at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. b. At all identified crossings, the proposed high mast poles and 45-foot poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35-foot poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | Dec 2022 BO Mod to clarify above lighting measures | All Sections | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | b. Culvert Outlet – The current design near Southern States property results in zero calculated change to baseline light levels at the culvert opening and ditch leading to the FBR. | Green Sheet, June 2020 BO | Section D | Lighting Design Plans are done by the Department |  | Fulfilled
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | c. Culvert Outlet – NCDOT will meet with landowners adjacent to the roost culvert to discuss replacement or augmentation of existing lighting to reduce existing baseline conditions determined by the NCDOT Roadway Lighting Squad. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Not started | Commitment cannot be fulfilled until lighting plans are fully developed
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | d. Culvert inlet – The original lighting design near the Hill Street culvert inlet had 80’ high mast poles installed between the mainline and Hill Street behind the Isaac Dickson Elementary School. NCDOT is revising this design to replace them with GE light fixtures installed on twin arm poles on the mainline median barrier. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | e. New French Broad Crossing (NFBC) – Use of single arm light poles mounted on the bridge and flyover barriers in place of the 120’ and 100’ high mast poles. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | f. NFBC – 35’ single arm poles with a narrow distribution light fixture and a house side shield will be used. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | g. FBR-1 – The GE fixtures were replaced with the lower BUG rated Cooper fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | h. FBR-1 – Fixtures were redesigned to have the outer ring (as shown in the figures within the lighting document) ending roughly 115’ from the west bank of the FBR. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | i. FBR-2, FBR-3, & FBR-4 – All high mast poles within the connector interchange were removed and replaced with Cooper fixtures mounted on the outer and/or center bridge barrier rail. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | j. FBR-2, FBR-3, & FBR-4 – The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | k. HC-1 – Replacing the GE fixtures with the Cooper fixtures. The crossing is still centered between the Cooper fixtures, as it was for the GE fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | l. HC-1 - Replacing the 120’ high mast pole with an 80’ high mast pole. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | m. HC-2 & HC-3 – Removal of a 120’ high mast pole and replaced with Cooper fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | n. HC-2 & HC-3 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | o. HC-4 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | p. HC-5 & HC-6 – Removal of 80’ high mast pole and replacing with Cooper fixtures along the mainline and ramp in both directions. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | q. HC-5, HC-6, HC-7 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section A and Section C | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | r. All SMC and EBC – Removal of all high mast poles within the connector interchange and replaces them with Cooper fixtures mounted on the outer and/or center bridge barrier. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | s. All SMC and EBC - Cooper fixtures located so the crossings are centered as best as possible between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Not started
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | t. SMC culvert area – Existing high mast pole located within the interchange ramps will be removed. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | a. NCDOT will conduct acoustic monitoring (or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity due to construction. NCDOT will coordinate the locations and time frame for monitoring with USFWS. | Green Sheet, June 2020 BO | All Sections | BSG | Obsolete
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | b. To help determine whether MYGR avoid active construction zones at night, NCDOT will investigate the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. | Green Sheet, June 2020 BO | All Sections | BSG | Obsolete
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | c. NCDOT will conduct additional monitoring/research to at a minimum include additional telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. This additional monitoring will be coordinated with USFWS, NCWRC and NCDOT. Please refer to Term and Condition 10 for clarification. | Green Sheet, June 2020 BO | All Sections | BSG | Obsolete
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | a. NCDOT will replace most, if not all the CMP within the culvert system upstream from the RCBC with RCBC and/or concrete pipe, which will effectively create additional bat roosting habitat. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team |  | In Progress | This will be fulfilled
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | b. NCDOT will meet with landowners adjacent to the roost culvert to discuss replacement or augmentation of existing lighting to reduce existing baseline conditions determined by the NCDOT Roadway Lighting Squad. | Green Sheet, June 2020 BO | Section B (Design-Build) | BSG | Completed
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | c. NCDOT will acquire a permanent drainage easement (PDE) or additional right of way at the culvert inlet (near Courtland Ave.) and outlets, where replanting with containerized, native, woody vegetation will occur. In addition, if NCDOT acquires additional right-of-way or conservation easements along the French Broad River or adjacent to the culvert, NCDOT will replant with native, woody vegetation to provide, in time, a buffer for noise, light, and surface water runoff. NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team |  | Not started | Discuss with contractor
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | NCDOT-Sponsored Gray Bat Research Project | NCDOT, with the cooperation of the USFWS and NCWRC, committed to a three-year study on MYGR within the French Broad River Basin. This study will serve as a conservation measure for NCDOT projects within the Divisions 13 and 14 for a limited time. NCDOT will fund Indiana State University $900,000 to conduct the research project, to gather the information needed to allow NCDOT and USFWS to enter a programmatic consultation to cover MYGR for NCDOT Divisions 13 and 14, as well as help to develop species-specific avoidance and minimization measures. This agreement was reached, in part, for the I-4400/I-4700 (I-26 widening) project in Buncombe and Henderson Counties, but also benefits this project. | Green Sheet, June 2020 BO | All Sections | BSG | Completed. Final report submitted Nov 2020
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Protection of Culvert Roost Entrance | NCDOT will coordinate with USFWS to assess the need to deter trespassing/use of the culvert by humans, and install signage or barriers, as needed. | Green Sheet, June 2020 BO | Section B (Design-Build) | BSG and Division Construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Gray Bat Conservation Funding | NCDOT will provide $350,000 for measures consistent with the recovery objectives outlined in the MYGR recovery plan (Brady et al. 1982). | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Installation of Temporary Bat Roost Panels on Bridges | NCDOT will provide modern bat roost panels or comparable structures that could serve as a temporary alternate roost for bats potentially disturbed by work on the culvert roost for the duration of construction of the I-2513 project. This will be in the place of the panels on four bridges NCDOT has committed to in the BA, which were to be placed on bridges with documented signs of bat use. These bridges are all relatively far from the Hill Street Culvert roost. The USFWS believes that panels placed on one bridge close to the Hill Street Culvert roost has greater potential to minimize take than panels placed on four bridges farther away (Reasonable and Prudent Measure 3). Refer to Term and Condition 9 for more details. | Green Sheet, June 2020 BO | All Sections | BSG | Completed- Installed on 4 bridges in Feb 2022. Monitoring completed Fall 2024
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Appalachian Elktoe | Appalachian Elktoe Conservation Funding | a. NCDOT will provide $500,000 to the North Carolina Nongame Aquatic Projects Fund for the French Broad River Conservation Plan (FBRCP) proposed by USFWS, which will aid in the recovery and conservation of Appalachian elktoe. The funding will be held by the NCWRC. A multi-agency/organization group of mussel species experts, including USFWS, will determine how to expend the funds. b. The French Broad River Conservation Plan proposes to improve aquatic habitat and diversity and to mitigate risks in the French Broad River. It may include the following: i. Species Reintroduction: Developing a normal cohort of companion species will benefit long-term Appalachian elktoe recruitment and survival; mussel species are healthier in dense multi-species mussel beds (Vaughn et al. 2008). ii. Early Warning and Emergency Capacity: A monitoring network and propagation facility devoted to species introduction pairs an early warning system with emergency production capacity to immediately mitigate unforeseen effects to the Appalachian elktoe population should the need arise. iii. Genetic Management Program: A study of the genetic health/potential genetic drift of the population will provide feedback to the previous two program aspects and will fine tune management of Appalachian elktoe. iv. Miscellaneous: Other projects could include development of technologies such as the use of passive integrated transponder (PIT) tags to locate mussels; radio tracking equipment to study movement of mussels during high flow; development of techniques to artificially stabilize habitat for the placement of propagated mussels; and/or a cost-benefit study of watershed improvement options. | Green Sheet, June 2020 BO | All Sections | BSG | Paid off March 2024
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Appalachian Elktoe | French Broad River Geomorphology Monitoring | NCDOT is working with the US Geological Survey (USGS) to evaluate the impacts of construction and temporary causeways on river habitat. This monitoring project encompasses several Transportation Improvement Projects (I-2513, I-4400 and I-4700). Therefore, the monitoring project will span several years to accommodate the varying construction schedules. a. Terrestrial Light Detection and Ranging (T-LiDAR) technology will be used annually to produce a laser scan of river banks. Bathymetric surveys will be conducted concurrently one to two times a year. Bathymetric data will be used to generate a gridded surface representation (digital elevation model, or DEM) of the channel bed for each survey. A similar approach will be applied to T-LiDAR data to evaluate stream bank position between successive surveys. b. Water quality monitoring will include real-time (continuous) data collection of temperature, turbidity, and specific conductance. Discrete water-quality samples will be collected during a variety of flow conditions to measure total suspended sediment (TSS) and suspended sediment concentration (SSC). c. Continuous streamflow, precipitation, and water-quality (temperature, conductance, and turbidity) data will be available online at http://waterdata.usgs.gov/nc/nwis/rt/ and via text and email alerts. Yearly summaries for each monitoring site will be available on demand from the USGS National Water Information System web interface (NWISWeb). Real-time alerts will be available to NCDOT via the NWISWeb when temperature or turbidity concentrations spike or exceed a predetermined threshold. d. If monitoring at the French Broad River reveals excessive bank erosion, bank instability, or sedimentation associated with the bridge replacement, NCDOT will work to identify the cause and will make improvements to address the problems in a timely manner. | Green Sheet, June 2020 BO | All Sections | BSG | Curently underway, receive monthly updates from USGS contract renewed by BSG 2024
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 1. The USFWS must be notified of any project modifications. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG |  | Not started | Initial update will occur at 4B, or sooner pending NCDOT coordination with USFWS. Subsequent updates will occur at 4C and permit modification requests.
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 2. NCDOT will minimize impacts to roosting bats in the culvert roost to the extent possible through coordination with the USFWS for work that occurs between March 15th and November 15th. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 3. NCDOT will provide modern bat roost panels or comparable structures that could serve as a temporary alternate roost for bats potentially disturbed by work on the culvert roost for the duration of construction of the I-2513 project. This will be in the place of the panels on four bridges NCDOT has committed to in the BA, which were to be placed on bridges with documented signs of bat use. These bridges are all relatively far from the Hill Street Culvert roost. The USFWS believes that panels placed on one bridge close to the Hill Street Culvert roost has greater potential to minimize take than panels placed on four bridges farther away. | Green Sheet, June 2020 BO | All Sections | BSG | Duplicate Line
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 4. NCDOT will minimize permanent lighting on waterways in the final lighting design plan to the extent possible, as well as current permanent lighting at the Hill Street Culvert Roost. Current plans for new permanent lighting (Appendix J of the BO) are preliminary in nature. | Green Sheet, June 2020 BO | All Sections | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 5. NCDOT will avoid and minimize potential take of bats roosting in culverts other than the Culvert Roost by conducting culvert checks before rehabilitation or repair work (see Term and Condition 12). | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG | Coordinate schedule with Division and DBT | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 6. NCDOT will adhere to all BMPs for soil and erosion control, and will report to the USFWS (described in Term and Condition 7) if failures occur. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 1. NCDOT will adhere to all measures listed in the Conservation Measures section of this Opinion and in the BA (if not revised in the BO). | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 2. NCDOT will simultaneously notify USACE and USFWS of any permit modification requests. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT |  | Not started | Will occur per permit modification request
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 3. A USFWS biologist will be invited (at least seven days prior) to the preconstruction meeting(s) to review permit conditions and discuss any questions the Contractor has regarding implementation of the project. After the Contractor submits plans for various stages (outlined in post BO coordination Section 2.3.5.2) of the project, a USFWS biologist will review and provide comments (within 15 days upon acknowledgement of receipt of notice) on the plans and will be invited to attend any meetings to discuss implementation of the plans. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 4. During construction, culvert inlets and outlets will be evaluated by the resident engineer with regard to stream stability immediately following installation and quarterly for a period of one year at each location. Indicators of instability, such as head cutting, scour, aggradation, or degradation, will be used to determine the need for corrective actions. | Green Sheet, June 2020 BO | All Sections | Construction |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 5. A final field inspection will be held with the Contractor to evaluate culvert placement and stream stability before the project is considered complete. If instability is detected during any of these reviews, corrective actions will be performed when deemed necessary by the engineer or by the conditions of any federal and state permits required by Section 404/401 of the Clean Water Act. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 6. NCDOT and NCDEQ-DEMLR (land quality) will meet with USFWS to evaluate and discuss erosion control effectiveness if requested. | Green Sheet, June 2020 BO | All Sections | NCDOT, REU |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 7. In the event of any failure of erosion control devices, within 48 hours, NCDOT will send a report to USFWS detailing the cause of the failure, photographs of the failure, and a plan for repair of the erosion control devices and reasonable methods to avoid future failure. NCDOT will notify the USFWS when failures are repaired. | Green Sheet, June 2020 BO | All Sections | NCDOT, REU |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 8. To carry out Reasonable and Prudent Measure 2, the USFWS must be notified before work starts in the culvert. a. Work can only commence when the baffle is installed if work will occur from March 15th through November 15th. b. NCDOT will coordinate with the USFWS to determine the best timing for installing the baffle. c. The USFWS, or an individual approved by USFWS, must be present when trees are cleared near the culvert and when the baffle is installed if installation occurs when bats present. d. The USFWS may request that the baffle is moved, removed, or altered. It may be determined that disturbances from construction are less impactful than potential alterations to the culvert microclimate from the baffle, or noise levels no longer exceed the ambient level. e. If the RCBC outlet is needed to access other portions of the culvert, it will only be used when bats are not present. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team, BSG |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 9. The alternate bat roost structure from Reasonable and Prudent Measure 3 will consist of modern bat modular roost panels or comparable structures installed on a bridge over water as close to the culvert roost as possible, but out of areas disturbed by construction. Panels should be constructed of fiber-reinforced concrete with additives to mimic thermal mass and should be mounted using metal. Bridge selection and panel placement/design should be informed by work currently being conducted by Indiana State University. Panels must be installed before work starts on the culvert roost and should be checked for bat use once in early summer and once in late fall for three years following placement. The details of the location, size, design, and installation of the bat panels will be decided by a committee to include USFWS, NCWRC, and NCDOT. This panel will be installed temporarily for the duration of construction. | Green Sheet, June 2020 BO | All Sections | BSG | Completed- Panels were installed on 4 bridges in Fab 2022. Surveys are complete through Fall 2024
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 10. NCDOT will monitor bat activity before, during, and post construction. a. NCDOT has committed to conducting acoustic monitoring (and/or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity related to construction. NCDOT will coordinate the locations and time frame for monitoring with USFWS. This will include monitoring the culvert roost, including before and after the baffle is installed. b. To investigate whether MYGR avoid active construction zones (including bridges and the Hill Street culvert roost) at night, NCDOT will explore the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. c. NCDOT will conduct additional monitoring/research to include telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. The details of additional monitoring will be decided by a committee to include USFWS, NCWRC and NCDOT. Information gathered will be used to increase our knowledge of impacts to bats to help inform future consultation, to learn more about gray bats in the project area, to better conserve the species, and to track movements of bats and hopefully determine where bats go if they abandon the culvert roost and/or the area. | Green Sheet, June 2020 BO | All Sections | BSG | Updated- See below
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 11. As part of Reasonable and Prudent Measure 4, NCDOT will give the USFWS the opportunity to discuss/review/comment on the lighting design drafts and final design plans (and allow 15 days for review upon acknowledgement of receipt of notice), including on the Bowen Bridge. a. Bowen Bridge: This bridge is being downgraded to carry four lanes of local traffic on the center lanes, and bike and pedestrian paths on the outer lanes. Lighting will be altered to accommodate these changes. i. New lighting for vehicle and bike/pedestrian traffic will not exceed the current level of illumination on the water (an average of 0.10 foot-candle over an area that goes from shore to shore and extends approximately 50’ to the north and south from the structures) as determined by a lighting engineer, and every effort will be made to reduce the level of illumination on the water. ii. NCDOT will work with USFWS to avoid and minimize impacts of light, including: -Light will be 3000 K or below iii. Proposed aesthetic panel lighting will not illuminate the water surface when bats are present (March 15th through November 15th). NCDOT and the City of Asheville will work with the USFWS to determine acceptable light color and levels when bats are present. | Green Sheet, June 2020 BO | All Sections | NCDOT, Lighting design plans are done by the department |  | Not started | Commitment cannot be fulfilled until lighting plans are fully developed
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | Southern States: USFWS will be included in discussions about modifying the lights at Southern States to decrease light spill at the Hill Street culvert entrance. If the land owner does not agree to minimize lighting on their property, NCDOT will work with the USFWS to assess the effectiveness of and minimize light using a barrier (fence or vegetation) on their ROW easement. | Green Sheet, June 2020 BO | Section D | NCDOT, Lighting design plans are done by the department | Completed |  | Lower wattage fixtures already installed with shielding
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 12. In order to carry out Reasonable and Prudent Measure 5, NCDOT will conduct culvert checks for roosting bats within 30 days of rehabilitation or repair for any culverts five feet tall or higher, and 200 feet or longer, scheduled to occur from March 15th through November 15th. If bats are found, a similar protocol will be used to the pre-demolition check for bats in bridges. If bats are present, one of the following options will be implemented (options listed in order of preference). NCDOT will: a. Wait for bats to leave for the season (approximately mid-October to early November) before beginning work; or b. A biologist will monitor the culvert and work will begin after bats leave the culvert for the evening (if work occurs over multiple days, the culvert will need to be monitored each day work occurs), or c. A permitted biologist will exclude bats from work area immediately prior to the start of work using acoustic deterrents (if this method is employed, the culvert will need to be checked each day work occurs to determine efficacy), or d. A permitted biologist will hand remove bats from work area immediately prior to the start of work (the culvert will need to be checked each day work occurs to ensure bats do not return). e. If pre-work check determines pups are present, NCDOT will refrain from culvert work until it can be determined by a biologist that the pups are volant, and then use the previous options to proceed with work. | Green Sheet, June 2020 BO | All Sections | BSG | Coordinate schedule with Division and DBT | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 13. The nearest flyover bridge to the culvert roost will not be closer than 300 feet from the outlet. | Green Sheet, June 2020 BO | All Sections | Design-Build Team |  | Fulfilled | Closest bridge measured at 400ft
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Monitoring and Reporting Requirements | Monitoring and Reporting Requirements | In order to monitor the impacts of incidental take, the NCDOT must report the progress of the Action and its impacts on the species to the USFWS. This section provides the specific instructions for such monitoring and reporting. As necessary and appropriate to fulfill this responsibility, the NCDOT must require any permittee, Contractor, or grantee implement these Terms and Conditions through enforceable terms that are added to the permit, contract, or grant document. Such enforceable terms must include a requirement to immediately notify the NCDOT and USFWS if the amount or extent of incidental take specified in this Incidental Take Statement is exceeded during action implementation. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Monitoring and Reporting Requirements | Monitoring and Reporting Requirements | NCDOT will provide a final report and yearly bat monitoring summaries to the Service by January 31st of each year starting at the end of the bat monitoring season, and concluding up to two years after construction is completed. | Green Sheet, June 2020 BO | All Sections | BSG | Ongoing by BSG, year 1 (2024) completed and sent ot USFWS 2025 | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reinitiation Notice | Reinitiation Notice | Formal consultation for the I-2513 project is concluded. Reinitiation of consultation is required by law if: a. the amount or extent of incidental take is exceeded i. Gray Bats: If construction operations at the bridges cannot be completed after five years from the start of causeway construction without night operations, or culvert system work cannot be completed after four seasons when bats are not present, or 60” CMP work cannot be complete after one season when bats are not present, all work should stop, and the USFWS should be contacted immediately to reinitiate consultation. ii. If a continuing NOV* is issued to NCDOT, the USFWS should be contacted immediately to determine if consultation should be reinitiated with the FHWA. *If severe problems are found that may result in loss of sediment into waterbodies or onto adjacent property owners, a Notice of Violation (NOV) is issued by NCDEQ-Energy Mineral and Land Resources to NCDOT. Consequently, NCDOT and its contractors will react immediately to correct items noted in the NOV. If deficiencies are not corrected within the timeframe directed by the Energy, Mineral and Land Resources NOV, a Continuing NOV will be issued. A Continuing NOV indicates that sufficient progress has not been made to correct environmental deficiencies on a project. b. new information reveals that the Action may affect listed species or designated critical habitat in a manner or to an extent not considered in this BO; c. the Action is modified in a manner that causes effects to listed species or designated critical habitat not considered in this BO; or d. a new species is listed or critical habitat designated that the action may affect. | Green Sheet, June 2020 BO | All Sections | BSG |  | Not started | Commitment cannot be fulfilled until construction
| Conservation Recommendations | Conservation Recommendations | We recommend the FHWA and NCDOT works with the USFWS to determine how roost panels on bridges could be installed permanently (with the option to remove them temporarily for maintenance), contributing to the FHWA 7(a)(1) commitments to proactively work toward recovery of the gray bat. | June 2020 BO | All Sections | FHWA, BSG, USFWS | Not mandatory
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Northern long-eared bat | Endangered Species- Northern long-eared bat | Avoidance and Minimization | The following avoidance and minimization measures have been proposed to minimize adverse effects of the proposed action on Northern long-eared bat (Myotis septentrionalis): a. No alterations of a known hibernacula entrance or interior environment if it impairs an essential behavioral pattern, including sheltering northern long-eared bats (January 1 through December 31); b. No tree removal within a 0.25-mile radius of a known hibernacula (January 1 through December 31); and c. No cutting or destroying a known, occupied maternity roost tree, or any other trees within a 150-foot radius from the known, occupied maternity tree during the period from June 1 through and including July 31. | Green Sheet | All Sections | Construction, BSG | Obsolete- 2023 BO provided take coverage
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | NCDOT committed to addressing disproportionately high and adverse effects on the Burton Street community that cannot be avoided or minimized and is coordinating with the community to provide additional mitigation opportunities to lessen the burden of the project on these residents. The Burton Street Working Group is currently identifying how to implement the strategies identified in the 2018 Burton Street Neighborhood Plan, with certain goals and strategies requiring additional outreach and the engagement of Burton Street residents. NCDOT will carry out all activities for which it has been assigned responsibility in the plan. These include the following: | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve existing sidewalks to meet ADA design standards. | Green Sheet | Section B (Design-Build) | NCDOT
| Environmental Justice | Environmental Justice | Improve pedestrian connections between community resources by installing a sidewalk on Downing Street per agreement of property owners. | 2023 ROD | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve sidewalk connections between commercial corridors and include a pedestrian path from Buffalo Street to Patton Avenue that will connect to future greenway. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Evaluate opportunities for new transit stops, such as near Burton Street and Haywood Road. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Install a sidewalk along Patton Avenue to connect pedestrian path and transit stop. | Green Sheet | Section B (Design-Build) | Design-Build Team |  |  | Confirm sidewalk will be constructed
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Install bus shelters and other improvements at transit stops located near Burton Street. Consider neighborhood specific designs if feasible. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Incorporate a Burton Street history mural on proposed I-26 Connector sound wall if built. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve Community Center infrastructure by including additional parking. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Construct a new park and community gathering space at Smith Mill Creek that will include an access point to the future greenway. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve the Florida Avenue and Patton Avenue intersection by adding pavement markings and left turn signals. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Increase the tree canopy within the interstate buffer along the Burton Street neighborhood where possible. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Although the Burton Street Neighborhood Plan indicates that the Community Baptist Church will be displaced, the project designs have since been refined to eliminate the need to relocate this property. Only a small portion of the parking lot is anticipated to be impacted, and the church will not need to be relocated. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | In order to further mitigate impacts associated with the project design in Section B, modifications have been made along Patton Avenue east of the French Broad River and adjacent to the Hillcrest Apartment community, an identified Environmental Justice community. A public meeting was held on February 15, 2022 with the residents of Hillcrest Apartments to show the proposed modifications and address any concerns from the residents. Modifications include additional sidewalk connectivity from Hillcrest to the realigned Hill Street, including a grassed berm to separate residents from Hill Street. Additionally, a pedestrian bridge is proposed at the entrance of the community to provide access across I-240 to Hill Street. A sidewalk is included on the southeast corner of the property to provide direct access by residents to Patton Avenue and the multi-use path along Patton Avenue. The existing pedestrian bridge east of the Jeff Bowen Bridges, south of Hillcrest is proposed to be removed and the existing pedestrian bridge south of the Isaac Dickson Elementary School is proposed to be replaced. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | Pursuant to Section 106 of the National Historic Preservation Act, the State Historic Preservation Office (HPO) concurred with NCDOT's determination that the project will have no adverse effect upon the following properties identified in or near the Area of Potential Effects (APE) that are already listed in or eligible for the National Register of Historic Places (NRHP): the Biltmore Estate, Buncombe County Bridge 216, Baker Building, the Montford Hills Historic District, and the Haywood Street United Methodist Church. Additionally, HPO concurred with the determination that the project will have no adverse effect upon the following properties provided the environmental commitments stipulated in a Memorandum of Agreement (MOA) are fulfilled: the Asheville School, West Asheville/Aycock School Historic District, Freeman House, the William Worley House, and the Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323). | Green Sheet | All Sections | N/A
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | HPO has concurred with NCDOT's determination that the project will have no adverse effect on one archaeological site (31BN623) identified in or near the APE that is already listed in or eligible for the NRHP, provided environmental commitments stipulated in the MOA are fulfilled. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | The Selected Alternative will have an adverse effect on Riverside Cemetery within the Montford Area Historic District and one archaeological site (31BN826). | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | The MOA shall ensure stipulations are fulfilled for the two adversely effected properties, the five properties determined to have no adverse effect with commitments, and any determined eligible archaeological resource identified during further testing. Commitments included in the MOA are as follows: | Green Sheet | All Sections | N/A
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) | Riverside Cemetery within the Montford Area Historic District (BN0022): After consultation with the SHPO, the Asheville City Parks and Recreation Department, the Montford Neighborhood Association, the City of Asheville Transportation and Planning and Urban Design Departments, and the Preservation Society of Asheville and Buncombe County, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | a. Development of Vibration Monitoring Plan: NCDOT’s Geotechnical Engineering Unit, in consultation with NCDOT Division 13, shall develop a vibration monitoring plan for the Undertaking, to include on-site research during final design as well as monitoring during construction. The recommendations of the plan shall be provided to SHPO and concurring parties (except for the EBCI, CN, UKB, MCN, and Catawba Nation) for their comments prior to adoption. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | b. Baseline Studies: On-site research, done prior to construction, will measure existing vibration exposure, determine sensitivity of key funerary monuments and assign thresholds accordingly. | Green Sheet | Section B (Design-Build) | Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | c. Vibration Monitoring: Vibration monitoring will be conducted on key funerary monuments within Riverside Cemetery, recommended in the aforementioned vibration monitoring plan. When a reading exceeds the established threshold, an alarm will sound and the Contractor or the cemetery manager shall immediately contact NCDOT’s Division 13 Resident Engineer to assess the situation. | Green Sheet | Section B (Design-Build) | Design-Build Team, Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | d. Pre-construction Surveys: NCDOT will conduct pre-construction surveys of all key funerary monuments within Riverside Cemetery to record a “before” condition so that any construction-related damage can be accurately identified. The City of Asheville shall identify the key funerary monuments to be included in the Vibration Monitoring Plan, pre-construction surveys and inventories noted above. | Green Sheet | Section B (Design-Build) | Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | a. Design Noise Report: In accordance with the Department’s Traffic Noise Policy, NCDOT’s Design Build Team, shall complete a Design Noise Report for the Undertaking which includes recommendations for abatement measures for traffic noise impacts. If the Design Noise Report concludes that noise wall barriers along the boundaries of the Montford Historic District are preliminarily deemed to meet feasibility and reasonableness criteria then further consultation on the appearance of the barriers will be required with SHPO and the concurring parties. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | b. Pavement: NCDOT is not proposing pavement as a noise abatement for this project, however, in accordance with all design standards/criteria, NCDOT elects to use low noise pavement surface treatments for any concrete and/or asphalt surfaces and minimize the number of joints on the roadway structures in the vicinity of Riverside Cemetery. NCDOT cannot commit to the utilization of these specific surface treatments in perpetuity or to maintenance schedules that keep the auditory qualities of these lower noise pavement designs at their premium. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | c. Memorandum of Understanding: NCDOT’s Division 13 will develop a Memorandum of Understanding (MOU) with the Asheville City Parks and Recreation Department to outline how the city will notify NCDOT of funerals. Protocols will be established to limit construction noise during such events. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | a. Pre-Construction Tree Survey: It is understood that all existing vegetation and trees within the highway right-of-way parallel to the Riverside Cemetery will likely be removed during construction. To mitigate these impacts along the Riverside Cemetery boundary, NCDOT’s Design-Build Team shall conduct a tree survey of existing trees exceeding 6.0” diameter that are targeted for removal within the existing highway Right-Of-Way, will remain in the existing highway Right-Of-Way, or are within the Riverside Cemetery that their root system may be impacted during construction. The Design-Build Team’s survey shall include in its documentation, but not be limited to the following information: 1) tree species and measurements (DBH, canopy width, and height), 2) approximate age, and 3) overall health/life expectancy, and 4) potential construction impacts, as well as management recommendations for trees adjacent to the highway Right-Of-Way that may be impacted. The recommendation may include, but not limited to, additional fertilization, pruning or overall removal and replacement. | Green Sheet | Section B (Design-Build) | Design-Build Team |  | Not started | Not scheduled
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | b. Planting within highway Right-Of-Way: Re-vegetation of the highway right-of-way parallel to the cemetery boundary will be planned and implemented in accordance with NCDOT’s Guidelines for Planting within Highway Right-of-Way. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | c. Planting within highway Right-Of-Way will be congruent with existing vegetation and trees along the Riverside Cemetery boundary. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | d. Replacement of Trees: If trees within Riverside Cemetery are damaged due to construction within the highway Right-Of-Way then NCDOT will follow the management recommendations in the pre-construction tree survey (additional fertilization, pruning, or overall removal and replacement). Replacement of trees will follow Asheville’s Code of Ordinances Section 7-11-13 (landscape & buffering standards) and Appendix 7-C (recommended species list). All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | e. Right-Of-Way Fence: The fence that marks the highway Right-Of-Way parallel to the cemetery boundary will be a black metal fence that is approved by the Asheville City Parks and Recreation Department, the SHPO, and NCDOT. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | a. Additional areas of concentrated landscaping will be included within the boundaries of Riverside Cemetery adjacent to the highway and will be developed through consultation with the Asheville City Parks and Recreation Department, SHPO, and other concurring parties. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Comitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | b. Landscaping will follow Asheville’s Code of Ordinances Section 7-11-13 (landscape & buffering standards) and Appendix 7-C (recommended species list). All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Comitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | c. Preliminary Post-Construction Landscape Design plans will be provided to SHPO, the Asheville City Parks and Recreation Department, and the concurring parties for their review and comment. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Comitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | d. NCDOT (or its contractor) shall install the landscaping after completion of roadway construction work along the historic boundary of the cemetery. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Comitment cannot be fultilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | a. In accordance with all design standards / criteria, NCDOT’s Design-Build Team will be encouraged to modify the Department’s preliminary design in proximity to the Riverside Cemetery. Specifically, along the Cemetery boundary, the Design-Build Team will be encouraged to lower the US 19/US 23/US 70 roadway and shift the facility westward without incorporating design exceptions or increasing right of way impacts or relocatees. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | b. The retaining wall will be designed to extend along the entire Riverside Cemetery boundary adjacent to the proposed project. | Green Sheet | Section B (Design-Build) | Design-Build Team | Retaining wall has been removed from preliminary plans
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | c. The appearance of the retaining walls along the cemetery’s boundary will be formed concrete walls with a simulated masonry surface treatment. The surface treatment will be designed to resemble stacked stone walls and may be painted, stained, or tinted. Choices of aesthetic wall treatments will be provided to SHPO, the Asheville Transportation Department, the Asheville City Parks and Recreation Department, and the concurring parties for their review and comment prior to final approval. The preferred surface texture and color will be included in NCDOT’s final design. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 6. Roadway Lighting | Roadway lighting will be designed and constructed to minimize the dispersion of light (“spillover”) beyond the highway Right-Of-Way. NCDOT will not install high mast poles adjacent to the cemetery. Instead NCDOT will install single pole, shoulder and/or barrier mounted, lighting with LED illumination in this area. | Green Sheet | Section B (Design-Build) | Lighting Design Plans are done by the Department |  | Fulfilled | Shown in preliminary lighting plans
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | The transmission lines currently on Courtland Place will be rerouted northwest to a point near the southwest boundary of Riverside Cemetery and US 19/US 70. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | a. A 70-foot Permanent Utility Easement (PUE) will be cleared of trees and a single pole erected to hold the lines. Duke Energy will erect the shortest pole that meets the needs of the line in this location. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | b. Prior to construction Duke Energy will flag any “danger trees” located outside the 70-foot PUE that are adjacent to or within the boundaries of the cemetery. If any “danger trees” exist, Duke Energy will consult with NCDOT, SHPO and the Asheville City Parks and Recreation Department prior to any removal of the “danger trees” and will prioritize tree trimming over removal and replacement. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) | After consultation with the SHPO and the property owner, NCDOT agrees to lessen the audible and visual impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) - 1. Noise Abatement | Upon satisfactory completion of the work, NCDOT will reimburse the property owner for the costs to install central heat/AC, storm windows, and insulation based on the lowest of 3 bids provided to NCDOT by the property owner. If the property owner chooses, NCDOT will make payment directly to a third-party contractor(s). | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) - 2. Landscaping | NCDOT (or its contractor) shall install landscaping along the edges of the property facing the new facility after completion of the project. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time period. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) | After consultation with the SHPO and the property owner, NCDOT agrees to lessen the audible and property impacts resulting from the Undertaking by providing funding or services for the following measures | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) - 1. Noise Abatement | Upon satisfactory completion of the work, NCDOT will reimburse the property owner for the costs to install central heat/AC, storm windows, and insulation based on the lowest of 3 bids provided to NCDOT by the property owner. If the property owner chooses, NCDOT will make payment directly to a third-party contractor(s). | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) - 2. Retaining Wall | NCDOT will install a retaining wall, with permanent underground easements, within the property boundary along the western boundary of the property to reduce right-of-way impacts. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) | After consultation with the SHPO, the principal of Aycock School, and the Asheville School District Superintendent, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 1. Parking | To minimize Aycock’s School’s loss of parking spaces, NCDOT has agreed to provide the school with new parking lots and vehicular circulation routes as shown on the plans provided to SHPO on October 7, 2019. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 2. Trees | NCDOT will preserve the screening trees along the west side of classrooms by erecting temporary fencing around the trees and tree protection signs, during construction. | Green Sheet | Section B (Design-Build) | NCDOT |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 3. Fencing | NCDOT will install permanent fencing (a minimum of 6 feet in height and of the school’s chosen materials) between the Greenway and the west side of the school yard. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 4. Protection Measures | NCDOT will protect the trees and Arrowhead monument on school grounds along Haywood Road by erecting tree protection signs and temporary fencing around the trees and monument, during construction. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | After consultation with the SHPO and the Asheville Aesthetics Advisory Committee, NCDOT agrees to remove the cantilevered sidewalk and convert the bridge to a two-lane facility with a minimum 10-foot sidewalk on the existing deck. The existing bridge rails and pedestrian lights will be replaced with designs that meet current safety standards and are congruent with the original “art modern” style of the bridge. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 1. The SHPO concurred in a letter dated June 19, 2020 that the subject undertaking will not adversely affect the bridge. Any changes to the bridge concepts after the execution of this MOA, as shown in the renderings appended to this document, shall require approval from NCDOT structure design and the SHPO. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 2. Any repairs to the historic substructure shall follow the Secretary of the Interior’s Standards for Rehabilitation. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 3. Additional streetscape enhancements such as benches, planters, ornamental lights, or flags shall require approval from NCDOT structure design and the SHPO. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | After consultation with the SHPO, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing services for the following measures. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | 1. Iron markers will be placed at each end of a wall associated with site 31BN623 to mark its extent prior to the placement of fill within the project limits. The exact locations of the markers will be provided to the SHPO for its records. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | 2. Any changes in the vicinity of 31BN623 to the preferred alternative preliminary design after the execution of this MOA shall require approval from the SHPO. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 1. In consultation with the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation NCDOT will develop a Data Recovery Plan (DRP) for Site 31BN826, which has been determined eligible for the NRHP and will be affected by the Undertaking. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 2. If Sites 31BN823, 31BN868, 31BN870, 31BN871, 31BN873 and any new sites are determined eligible for the NRHP through further testing and affected by the Undertaking, NCDOT, in consultation with the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation, will develop, separate DRPs for those sites. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 3. NCDOT will ensure that the DRPs, are implemented after the highway Right-Of-Way is acquired and prior to construction activities within the site location. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 4. Upon completion of the Data Recovery efforts, NCDOT will prepare and forward a Management Summary to the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation detailing the results of the Data Recovery efforts for all the eligible sites. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 5. Upon receipt of the Management Summary, the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation will respond within fifteen (15) days to the recommendations contained within the Management Summary. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 6. Upon acceptance of the recommendations contained in the Management Summary, the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation will issue NCDOT documentation that the Data Recovery field investigations have been completed. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 7. The analysis and report preparation, detailing the eligible sites, will be completed by NCDOT, or their consultant(s), within eighteen (18) months after completion of the fieldwork. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Unanticipated Discoveries | In accordance with 36 CFR 800.11(a), if NCDOT identifies additional cultural resource(s) during construction, all work will be halted within the limits of the resource(s) and the FHWA and the SHPO will be contacted. The NCDOT and FHWA will initiate the appropriate agency and/or Tribal coordination required for a determination of eligibility or recovery effort. If after consultation between the Signatories and concurring parties, additional mitigation is determined necessary, the NCDOT, in consultation with the Signatories and concurring parties, will develop and implement appropriate protection/mitigation measures for the resource(s). Inadvertent or accidental discovery of human remains will be handled in accordance with North Carolina General Statutes 65 and 70. | Green Sheet | All Sections | Design-Build Team, Construction |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | The City of Asheville has requested the inclusion of bicycle and pedestrian betterments in the project design. The construction of the betterments as part of the proposed project will be dependent upon a municipal agreement between NCDOT and the City of Asheville. NCDOT will continue to coordinate with the City of Asheville on the inclusion of bicycle and pedestrian facilities. | Green Sheet | All Sections | PMU, NCDOT
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | The City of Asheville has established an Aesthetics Committee (AC) to work in an advisory capacity to address aesthetic treatments that may be incorporated in the proposed project, dependent upon a municipal agreement between NCDOT and the City of Asheville. NCDOT will continue working with the City to ensure that the agreed upon aesthetic improvements are incorporated into the project. | Green Sheet | All Sections | PMU, NCDOT, |  | Started | Aesthetics package to be submitted in April/May
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | NCDOT will coordinate with the City of Asheville regarding maintenance of traffic on the French Broad River Greenway during development of final plans for the project. | Green Sheet | Section A, Section B (Design-Build), Section C | PMU
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | NCDOT is committed to minimizing the overall footprint of the project to the extent practicable and will continue to work with the I-26 Working Group to improve designs prior to the Design- Build procurement. | Green Sheet | All Sections | PMU
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | River User Safety | River User Safety | NCDOT has developed a communication plan for construction of the project, and NCDOT and its contractors will work with river users, businesses, and recreational river and civic groups to insure public notification of hazards and temporary closures during construction. | Green Sheet | All Sections | Construction, Design-Build Team
NCDOT- Hydraulics Unit | Hydraulics | Hydraulics | The NCDOT Hydraulics Unit will coordinate with the NC Floodplain Mapping Program to determine the status of the project with regard to the applicability of NCDOT’s Memorandum of Agreement or approval of a Conditional Letter of Map Revision (CLOMR) and subsequent final Letter of Map Revision (LOMR). | Green Sheet | All Sections | NCDOT Hydraulics Unit
NCDOT- Hydraulics Unit | Hydraulics | Hydraulics Unit | The Division shall submit sealed as-built construction plans to the Hydraulics Unit upon completion of project construction, certifying that the drainage structures and roadway embankments that are located within 100-year floodplains were built as shown in the construction plans, both horizontally and vertically. | Green Sheet | All Sections | Design-Build Team, NCDOT |  | Not Started | Commitment cannot be fulfilled until constuction
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | Unless otherwise authorized, placement of culverts and other structures in waters and streams shall be placed below the elevation of the streambed by one foot for all culverts with a diameter greater than 48 inches, and 20 percent of the culvert diameter for culverts having a diameter less than 48 inches, to allow low flow passage of water and aquatic life. Design and placement of culverts and other structures including temporary erosion control measures shall not be conducted in a manner that may result in dis-equilibrium of wetlands or streambeds or banks, adjacent to or upstream and downstream of the above structures. The applicant is required to provide evidence that the equilibrium is being maintained if requested in writing by the NCDWR. If this condition is unable to be met due to bedrock or other limiting features encountered during construction, please contact the NCDWR for guidance on how to proceed and to determine whether or not a permit modification will be required. | 401 Permit | All Sections | Design-Build Team, NCDOT |  | In progress | This will be fulfilled
|  | Hydraulics Unit | If multiple pipes or barrels are required, they shall be designed to mimic natural stream cross section as closely as possible including pipes or barrels at flood plain elevation, floodplain benches, and/or sills may be required where appropriate. Widening the stream channel should be avoided. Stream channel widening at the inlet or outlet end of structures typically decrease water velocity causing sediment deposition that requires increased maintenance and disrupts aquatic life passage. | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | In progress | This will be fulfilled
|  | Hydraulics Unit | An erosion and sedimentation control plan will be provided during the final design stage. Best management practices to minimize sedimentation and erosion impacts during construction shall be adhered to, in accordance with the most recent version of North Carolina Sediment and Erosion Control Planning and Design Manual and the most recent version of NCS000250. | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | In progress | This will be fulfilled
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | If concrete is used during construction, a dry work area shall be maintained to prevent direct contact between curing concrete and stream water. Water that inadvertently contacts uncured concrete shall not be discharged to surface waters due to the potential for elevated pH and possible aquatic life and fish kills. Concrete shall be handled in accordance with the NPDES Construction General Permit NCG010000. | 401 Permit | All Sections | Construction, Design-Build Team |  | Not Started | Commitment cannot be fulfilled until constuction
|  | Hydraulics Unit | As part of the Highway Stormwater Program, NCDOT will develop and implement numerous programs on a statewide basis to protect and promote stormwater quality impacted by NCDOT discharges. Programs will be developed to ensure compliance with the National Pollutant Discharge Elimination System (NPDES) permit. NCDOT will incorporate measures to control nonpoint source water quality impacts as described in Best Management Practices for Protection of Surface Waters (NCDOT 1997) and in NCDOT Stormwater Best Management Practices (NCDOT 2014d). | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | Not Started | Commitment cannot be fulfilled until constuction
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | Heavy equipment should be operated from the bank rather than in stream channels in order to minimize sedimentation and reduce the likelihood of introducing other pollutants into streams. This equipment shall be inspected daily and maintained to prevent contamination of surface waters from leaking fuels, lubricants, hydraulic fluids, or other toxic materials. | 401 Permit | All Sections | Construction, Design-Build Team |  | Not Started | Commitment cannot be fulfilled until constuction
|  | Hydraulics Unit | Riprap shall not be placed in the active thalweg channel or placed in the streambed in a manner that precludes aquatic life passage. Bioengineering boulders or structures should be properly designed, sized and installed. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not Started | Commitment cannot be fulfilled until constuction
|  | Hydraulics Unit | Plans and specifications for the construction, expansion, or alternation of a public water system must be approved by the Division of Water Resources/Public Water Supply Section prior to the award of a contract or the initiation of construction as per 15A NCAC 18C. 0300 et. seq., Plans and specifications should be submitted to 1634 Mail Service Center Raleigh, North Carolina 27699-1634. All public water supply systems must comply with state and federal drinking water monitoring requirements. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | Hydraulics Unit | If existing water lines will be relocated during construction, plans for the water line relocation must be submitted to the Division of Water Resources/Public Water Supply Section at 1634 Mail Service Center Raleigh, North Carolina 27699-1634. | 2023 ROD | All Sections | Design-Build Team
NCDOT- Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | The recommended lane changes that improve operations at the Acton Circle and Smokey Park Highway intersection will be included in final design. | Green Sheet | Section A | NCDOT |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | NCDOT has secured a preliminary safety, operational, and engineering acceptability determination by the FHWA-Headquarters office. An Interstate Access Report (IAR) was submitted to the Federal Highway Administration (FHWA) on September 21, 2021. Final approval will be given after the ROD is signed given the selected alternative is consistent with the IAR. | Green Sheet | All Sections | NCDOT
|  | ECAP | Riparian vegetation (native trees and shrubs) shall be preserved to the maximum extent possible. Riparian vegetation must be reestablished within the construction limits of the project by the end of the growing season following completion of construction. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Impacts will be minimized to the greatest extent practable
|  | ECAP | NCDOT will manage invasive plant species on the Department’s right-of-way, as appropriate. |  | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
|  | ECAP | If Temporary access roads or detours are constructed, the site shall be graded to its preconstruction contours and elevations. Disturbed areas shall be seeded or mulched to stabilize the soil and appropriate native woody species shall be planted. When using temporary structures, the area shall be cleared but not grubbed. Clearing the area with chainsaws, movers, bush-hogs, or other mechanized equipment and leaving the stumps and root mat intact allows the area to re-vegetate naturally and minimizes soil disturbance. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Solid Waste | During construction, every feasible effort will be made to minimize the generation of waste, to recycle materials for which viable markets exist, and to use recycled products and materials in the development of the project where suitable. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Solid Waste | Any wastes generated by this project that cannot be beneficially reused or recycled must also be disposed of at a solid waste management facility approved to manage the respective waste type. The Section strongly recommends that any contractors are required to provide proof of proper disposal for all waste generated as part of the project. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Solid Waste | Any hazardous waste generated from the demolition, contraction, operation, maintenance, and/or remediation (e.g. excavated soil) from the proposed project must be managed in accordance with the North Carolina Hazardous Waste Rules. The demolition, construction, operation, maintenance and remediation activities conducted will most likely generate a solid waste, and a determination must be made whether it is a hazardous waste. If a project site generates more than 220 pounds of hazardous waste in a calendar month, the HWS must be notified, and the site must comply with the small amount quantity generator (SQG) requirements. If a project site generates more than 2200 pounds of hazardous waste in a calendar month, the HWS must be notified and the facility must comply with the large quantity generator (LQG) requirements. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Solid Waste | Notification of the proper regional office is requested if “orphan” underground storage tanks (USTS) are discovered during any excavation operation. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Geotechnical Engineering Unit | Geotechnical Engineering Unit: Hazardous Materials | Geotechnical Engineering Unit: Hazardous Materials | A work plan based on final designs will be developed for the landfill site along Riverside Drive to address any contaminated material that may be encountered during construction. Commitments during construction are included in the Preliminary Site Assessment Report (GEL 2019). | Green Sheet | Section D | Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
NCDOT- Geotechnical Engineering Unit | Geotechnical Engineering Unit: Hazardous Materials | Geotechnical Engineering Unit: Hazardous Materials | As part of the work plan, an environmental professional will be present during construction to screen for potentially hazardous conditions and to assess excavated materials for proper handling. | Green Sheet | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | The Asheville Regional Office (ARO) UST Section recommends removal of any abandoned or out-of-use petroleum USTs or Petroleum ASTs within the project area. The UST Section should be contacted regarding use of any proposed or on-site petroleum USTs or ASTs. We may be reached at (828) 296-4500. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | Any petroleum USTs or ASTs must be installed and maintained in accordance with applicable local, state, and federal regulations. For additional information on petroleum ASTs it is advisable that the North Carolina Department of Insurance at (919)661-5880 ext. 239, USEPA (404) 562- 8761, local fire department and Local Building Inspectors be contacted. | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | Any petroleum spills must be contained, and the area of impact must be properly restored. Petroleum spills of significant quantity must be reported to the North Carolina Department of Environmental Quality(NCDEQ) – Division of Waste Management (DWM) UST Section in the ARO. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | Any soils excavated during demolition or construction that show evidence of petroleum contamination, such as stained soil, odors, or free product must be reported immediately to the local Fire Marshall to determine whether explosive or inhalation hazards exist. Also, notify the UST Section of the ARO. Petroleum contaminated soils must be handled in accordance with all applicable regulations. | 2023 ROD | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | Generators are required to determine their generator status and both SQGs & LQGs are required to obtain a site EPA Identification number for the generation of hazardous waste. | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
|  | Geotechnical Engineering Unit: Hazardous Materials | Abandonment of any wells, if required must be in accordance with Title 15A. Subchapter 2C.0100. | 2023 ROD | All Sections | Design-Build Team, NCDOT |  | Not started | Commitment cannot be fultilled until construction
|  | NLEB Avoidance and Minimization Measures - Lighting | When installing new or replacing existing permanent lights, use downward-facing, full cut-off lens lights (with same intensity or less for replacement lighting); or for those transportation agencies using the BUG system developed by the Illuminating Engineering Society, be as close to 0 for all three ratings with a priority of "uplight" of 0 and "backlight" as low as practicable. |  | All Sections | Construction, Design-Build Team | Obsolete
|  | NLEB Avoidance and Minimization Measures - Tree Removal | Ensure tree removal is limited to that specified in project plans and ensure that contractors understand clearing limits and how they are marked in the field (e.g., install bright colored flagging/fencing prior to any tree clearing to ensure contractors stay within clearing limits). |  | All Sections | Construction, Design-Build Team | Obsolete
|  | NLEB Avoidance and Minimization Measures - General | Ensure all operators, employees, and contractors working in areas of known or presumed bat habitat are aware of all FHWA/FRA/FTA (Transportation Agencies) environmental commitments, including all applicable AMMs. |  | All Sections | Construction, Design-Build Team | Obsolete
|  | NLEB Avoidance and Minimization Measures - Hibernacula | For projects located within karst areas, on-site personnel will use best management practices, secondary containment measures, or other standard spill prevention and countermeasures to avoid impacts to possible hibernacula. Where practicable, a 300 foot buffer will be employed to separate fueling areas and other major containment risk activities from caves, sinkholes, losing streams, and springs in karst topography. |  | All Sections | Construction, Design-Build Team | Obsolete
|  | NLEB Avoidance and Minimization Measures - Tree Removal | Modify all phases/aspects of the project (e.g., temporary work areas, alignments) to avoid tree removal. |  | All Sections | Construction, Design-Build Team | Obsolete
|  | NLEB Avoidance and Minimization Measures - Lighting | Direct temporary lighting away from suitable habitat during the active season. |  | All Sections | Construction, Design-Build Team | Obsolete
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | The NCDOT Division Environmental Officer or Environmental Assistant will conduct a pre-construction meeting with all appropriate staff to ensure that the project supervisor and essential staff understand the potential issues with stream and pipe alignment at the permitted site. NCDWR staff shall be invited to the pre-construction meeting. [15A NCAC 02H.0506(b)(2) and (b)(3)] | Green Sheet, 401 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | Compensatory mitigation for 1. 11 acres of wetland is required. We understand that you have chosen to perform compensatory mitigation for impacts to streams and wetlands through the North Carolina Division of Mitigation Service (DMS) (formerly NCEEP), and that the DMS has agreed to implement the mitigation for the project. The DMS has indicated in letters dated August 15, 2023, that they will assume responsibility for satisfying the federal Clean Water Act compensatory mitigation requirements for the above-referenced project, in accordance with the DMS Mitigation Banking Instrument signed July 28, 2010. [15A NCAC 02H .0506 (c)] | Green Sheet, 401 Permit | All Sections | NCDOT , NCDMS | Completed for Section A Permit
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | The Permittee shall comply with all applicable measures for Appalachian Elktoe detailed under the Project Commitments in the Record of Decision dated May 2023. [15A NCAC 02B .0211(1)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | Bridge deck drains shall not discharge directly into the stream. Stormwater shall be directed across the bridge and pre-treated through site-appropriate means (grassed swales, pre-formed scour holes, vegetated buffers, etc.) before entering the stream. To meet the requirements ofNCDOT's NPDES permit NCS000250, please refer to the most recent version of the North Carolina Department of Transportation Stormwater Best Management Practices Toolbox manual for approved measures. [15A NCAC 02H .0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | As a condition of this 401 Water Quality Certification, the bridge demolition and construction must be accomplished in strict compliance with the most recent version ofNCDOT's Best Management Practices for Construction and Maintenance Activities. [15A NCAC02H .0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | If multiple pipes or barrels are required, they shall be designed to mimic natural stream cross section as closely as possible including pipes or barrels at flood plain elevation and/or sills where appropriate. Widening the stream channel should be avoided. Stream channel widening at the inlet or outlet end of structures typically decreases water velocity causing sediment deposition that requires increased maintenance and disrupts aquatic life passage. [15A NCAC 02H.0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Design-Build Team, NCDOT |  | Fulfilled | Not occurring on the project
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | When final design plans are completed for 1-2513 Sections B, C, and D, a modification to the 401 Water Quality Certification shall be submitted to the NC Division of Water Resources. Final designs shall reflect all appropriate avoidance, minimization, and mitigation for impacts to wetlands, streams, and other surface waters. No construction activities that impact any wetlands, streams, or surface waters located in 1-2513 Sections B, C, and D shall begin until after the permittee applies for, and receives a written modification of the 401 Water Quality Certification from the NC Division ofWater Resources. | Green Sheet, 401 Permit | Section B, Section C, Section D | Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | During the construction of the project, no staging of equipment of any kind is permitted in waters of the U.S. or protected riparian buffers. [15 A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The dimension, pattern, and profile of the stream above and below the crossing shall not be modified. Disturbed floodplains and streams shall be restored to natural geomorphic conditions. [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Design-Build Team |  | In progress | This will be fulfilled
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The use of rip-rap above Normal High Water Mark shall be minimized. Any rip-rap placed for stream stabilization shall be placed in stream channels in such a manner that it does not impede aquatic life passage [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The Permittee shall ensure that the final design drawings adhere to the permit and to the permit drawings submitted for approval. [15A NCAC 02H .0507 (c ) and 15A NCAC 02H .0506 (b)(2) and (c )(2)] | 401 Permit | All Sections | NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All work in or adjacent to stream waters shall be conducted in a dry work area. Approved BMP measures from the most current version of NCDOT Construction and Maintenance Activities manual such as sandbags, rock berms, cofferdams and other diversion structures shall be used to prevent excavation in flowing water. [15A NCAC 02H.0506(b)(3) and (c )(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All mechanized equipment operated near surface waters must be regularly inspected and maintained to prevent contamination of stream waters from fuels, lubricants, hydraulic fluids, or other toxic materials. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | No rock, sand or other materials shall be dredged from the stream channel except where authorized by this certification. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Discharging hydroseed mixtures and washing out hydro seeders and other equipment in or adjacent to surface waters in iprohibited. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The permittee and its authorized agents shall conduct its activities in a manner consistent with State water quality standards (including any requirements resulting from compliance with 303(d) of the Clean Water Act) and any other appropiate requirements of State and Federal law. if the NCDWR determines that such standards or laws are not being met (including the failure to sustain an designated or achieved use) or the State or federal law is being violated, ot that further conditions are necessary to assure compliance, the NCDWR may reevaluate and modify this certification [15A NCAC 02B.0200] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All fill slopes located in jurisdictional wetlalnds shall be placed at slopes no flatter than 3:1, unless otherwise authorized by this certification. [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | A copy of this Water Quality Certification shall be maintained on the constructioin site at all times. In addition, the Water Quality Certification and all subsequent modifications, if any, shall be maintained with the on-site project manager. [15A NCAC 02H.0507(c ) and a5A NCAC 02H .0506 (b)(2) and (C )(2) | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The outside buffer, wetland or water boundary located within the construction corridor approved by this authorization shall be clearly marked by highly visible fencing prior to any land disturbing activities. Impacts to areas within the fencing are prohibited unless otherwise authorized by this certification. [15A NCAC 02H.0501 and .0502] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The issuance of this certification does not exempt the Permittee from complying with any and all statutes, rules, regulations, or ordinances that may be imposed by other government agencies (i.e. locan, state, and federal) having jurisdiction, including but not limited to applicable buffer rules, stormwater management rules, soil erosion and sedimentation control requirements, etc. | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The Permittee shall report any violations of this vertification to the Division of Water Resources within 24 hours of discovery. [15A NCAC 02B.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Upon completion of the project (including any impacts at associated borrow or waste sites), the Permittee shall complete and return the enclosed "Certification of Completion Form" to notify the NCDWR when all work included in the 401 Certification has eben completed. [15A NCAC 02H.0502(f)] | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Native riparian vegetaion must be reestablished in the riparian areas within the construction limits of the project by the end of the growing season following completion of construction. [15A NCAC 02B.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | There shall be no excavation from, or waste disposal into, jurisdictional wetlands or waters associated with this permit without appropiate modification. Should waste or borrow sites, or access roads to waste or borrow sites, be located inwetlands or streams, compensatory mitigation will be required since that is a direct impact from road construction activities. [15A NCAC 02H.0506(b)(3) and (c)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Erosion and sediment control practices must be in full compliance with all specifications governing the proper design, installation and operation and maintenance of such Best Management Practices in order to protect surface waters standarts [15A NCAC 02H.0506(b)(3) and (c)(3)]: a. The erosion and sediment control measures for the project must be designed, installed, operated, and maintained in accordance with the most recent version of the North Carolina Sediment and Erosion Control Planning and Design Manual. B. The design, installation, operation, and maintenance of the sediment and erosion control measures must be such that they equal, or exeed, the requirements specified in the most recent version of the North Carolina Sediment and Erosion Control Manual. The devices shall be maintained on all construction sites, borrow sites, and waste pile (spoil) projects, including contractor-owned or leased borrow pits associated with the project. C. For borrow pit sires, the erosion and sediment control measures must be designed, installed, operated, and maintained in accordance with the most recent version of the North Carolina Surface Mining Manual. D. The reclamation measures and implementation must comply with the reclamation in accordance with the requirements of the Sedimentation pollution Control Act. | 401 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Sediment and erosion control measures shall not be placed in wetlands or waters unless otherwise approved by this Certification. [15A NCAC 02H.0506(b)(3) and ©(3)] | 401 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | 1) The entire 7 mile project is identified as STIP I-2513. This permit only authorizes work on Sections I-2513 AA, AB, and AC of STIP I-2513, also known as “Phase 1” for permitting purposes. Construction on the remaining sections/phases of the I-2513 project (i.e., Sections I-2513 B, I-2513 C, and I-2513 D) shall not commence until: (a) final design for those sections/phases has been completed and submitted to the U.S. Army Corps of Engineers (Corps); (b) the Permittee has minimized impacts to waters and wetlands to the maximum extent practicable for those sections/phases and the Corps concurs with this assessment through standard Merger 4B and 4C meetings; (c) any modification(s) to the permit plans for those sections/phases have been approved by the Corps in writing; (d) NCDOT submits final versions of the Bridge Construction and Demolition Plan, River User Safety Plan, and Strategic Communication Plan that adequately address the Corps’ Public Interest Review Factors (to include recreation, safety, navigation, and flood hazards); and (e) a final compensatory mitigation plan for those sections/phases has been submitted by the Permittee and approved by the Corps. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team, NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | All work authorized by this permit shall be performed in strict compliance with the following: The description of work in the revised application dated August 17, 2023. All information submitted in response to the Corps’ requests for additional information. All final environmental commitments that NCDOT has agreed to, to include (but not limited to) the Biological Opinion (BO) and the Amended BO and Conference Opinion (special condition #14 of this permit), and the Section 106 Memorandum of Agreement (special condition #15 of this permit). The attached permit plans titled (1) “I-2513AA/AB”, Permit Drawings Sheets 1- 26, and (2) “I-2513AC”, Permit Drawings Sheets 1-36. The Permittee shall ensure that the construction design plans for this project do not deviate from the approved permit plans referenced above. Any modification to the approved permit plans must be approved by the U.S. Army Corps of Engineers prior to any active construction in waters or wetlands. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team, NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Unauthorized Dredge and/or Fill: Except as authorized by this permit or any U.S. Army Corps of Engineers approved modification to this permit, no excavation, fill, or mechanized land-clearing activities shall take place at any time in the construction or maintenance of this project, within waters or wetlands, nor shall any activities take place that cause the degradation of waters or wetlands. There shall be no excavation from, waste disposal into, or degradation of, jurisdictional wetlands or waters associated with this permit without appropriate modification of this permit, including appropriate compensatory mitigation. This prohibition applies to all borrow and waste activities connected with this project. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Maintain Flows and Circulation Patterns of Waters: Except as specified in the approved permit plans referenced above, no excavation, fill or mechanized land- clearing activities shall take place at any time in the construction or maintenance of this project in such a manner as to impair normal flows and circulation patterns within, into, or out of waters or wetlands, or to reduce the reach of waters or wetlands. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team |  | Not started | Commitment cannot be fulfilled until construction
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Permit Distribution: The Permittee shall require its contractors and/or agents to comply with the terms and conditions of this permit in the construction and maintenance of this project, and shall provide each of its contractors and/or agents associated with the construction or maintenance of this project with a copy of this permit. A copy of this permit, including all conditions, drawings and attachments shall be available at the project site during the construction and maintenance of this project. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Pre-Construction Meeting: The Permittee shall schedule a pre-construction meeting between their representatives, the contractor, and the U.S. Army Corps of Engineers (Corps), Wilmington District, NCDOT Regulatory Project Manager for Division 13, prior to conducting any work in jurisdictional waters of the U.S. to ensure that there is a mutual understanding of all terms and conditions contained in this Department of the Army permit. To schedule this preconstruction meeting, the Permittee shall poll, at least two weeks ahead of any proposed meeting date, the representatives from the Corps and the North Carolina Division of Water Resources as to their availability; this poll shall include multiple potential dates and times for the preconstruction meeting. If other special conditions of this permit require other agency representatives (e.g., U.S. Fish and Wildlife Service, North Carolina Wildlife Resources Commission, etc.) to be invited to the preconstruction meeting, NCDOT shall include those agency representatives in the poll and shall schedule the meeting when all required agency representatives can attend the meeting. To determine if other agency representatives must be included in the poll for the preconstruction meeting, NCDOT shall review all other special conditions of the permit, to include all referenced documents, letters, correspondence, etc. The Permittee shall provide the Corps and all other required agency representatives with a copy of the final permit plans (if different than the approved permit plans referenced above) at least two weeks prior to the preconstruction meeting along with a description of any changes that have been made to the project’s design,construction methodology or construction timeframe. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Notification of Construction Commencement and Completion: The Permittee shall advise the U.S. Army Corps of Engineers in writing at least two (2) weeks prior to beginning the work authorized by this permit and again upon completion of the work authorized by this permit. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Reporting Address: All reports, documentation, and correspondence required by the conditions of this permit shall be submitted to the following: U.S. Army Corps of Engineers, Wilmington District Asheville Regulatory Field Office, Attn: Lori Beckwith, 151 Patton Ave., Room 208, Asheville, NC 28801-5006, or by email to loretta.a.beckwith@usace.army.mil . The Permittee shall reference the following permit number on all submittals: SAW-2004-9986803, STIP Project No. I-2513. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Reporting Violations: Violation of these permit conditions or violation of Section 404 of the Clean Water Act shall be reported to the U.S. Army Corps of Engineers by email to loretta.a.beckwith@usace.army.mil and by telephone at 828-230-0483, or 828-271- 7980 (Asheville Office general number), within 24 hours of the Permittee’s discovery ofthe violation. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Permit Revocation: The Permittee, upon receipt of a notice of revocation of this permit or upon its expiration before completion of the work will, without expense to the United States and in such time and manner as the Secretary of the Army or his authorized representative may direct, restore the water or wetland to its pre-project condition. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Clean Fill: The Permittee shall use only clean fill material for this project. The fill material shall be free from items such as trash, construction debris, metal and plastic products, and concrete block with exposed reinforcement bars. Soils used for fill shall not be contaminated with any toxic substance in concentrations governed by Section 307 of the Clean Water Act. Unless otherwise authorized by this permit, all fill material placed in waters or wetlands shall be generated from an upland source. | Green Sheet, 404 Permit | All Sections | Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Water Contamination: All mechanized equipment shall be regularly inspected and maintained to prevent contamination of waters and wetlands from fuels, lubricants, hydraulic fluids, or other toxic materials. In the event of a spill of petroleum products or any other hazardous waste, the Permittee shall immediately report it to the North Carolina Division of Water Resources at (919) 733-3300 or (800) 858-0368 and provisions of the North Carolina Oil Pollution and Hazardous Substances Control Act shall be followed. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Endangered Species Act: The Permittee shall implement all necessary measures to ensure the authorized activity does not kill, injure, capture, harass, or otherwise harm any federally-listed threatened or endangered species. While accomplishing the authorized work, if the Permittee discovers or observes an injured or dead threatened or endangered species, the Permittee shall immediately notify the U.S. Army Corps of Engineers, Wilmington District, Asheville Field Office, Attn: Lori Beckwith (Corps Project Manager for NCDOT Division 13) at loretta.a.beckwith@usace.army.mil or by telephone at 828-230-0483, or 828-271-7980 (Asheville Office general number), so that the required Federal coordination can occur. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Endangered Species Act consultation: This Department of the Army permit does not authorize you to take a federally listed species. In order to legally take a federally listed species, you must have separate authorization under the Endangered Species Act (ESA) (e.g., an ESA Section 10 permit, or a Biological Opinion (BO) under ESA Section 7, with “incidental take” provisions with which you must comply). The U.S. Fish and Wildlife Service’s (USFWS’s) BO for this project titled, “Biological Opinion I-26 Connector from I-40 to US 19/23/70 North of Asheville Buncombe County, Asheville, North Carolina FWS Log # 02-252”, dated June 19, 2020, was amended on December 14, 2023 by a document titled, “Biological Opinion and Conference Opinion Addendum to the June 19, 2020 Biological Opinion for I-26 Connector from I-40 to US 19/23/70 North of Asheville, Buncombe County, North Carolina Service Log #02-252 NCDOT STIP I-2513”; these documents contain mandatory terms and conditions to implement the reasonable and prudent measures that are associated with incidental take for the species specified in these documents. Your authorization under this permit is conditional upon your compliance with all of the mandatory terms and conditions associated with incidental take of these documents. Failure to comply with the terms and conditions associated with incidental take detailed in these documents, where a take of a federally listed species occurs, would constitute an unauthorized take, and it would also constitute non-compliance with your permit. The USFWS is the appropriate authority to determine compliance with the terms and conditions of these documents/its Opinion(s), and with the ESA. These documents are attached to the permit for this project. | Green Sheet, 404 Permit | All Sections | Design-Build Team, BSG
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | National Historic Preservation Act: NCDOT shall abide by all stipulations identified in the executed Memorandum of Agreement titled, “MEMORANDUM OF AGREEMENT AMONG THE FEDERAL HIGHWAY ADMINISTRATION, the NORTH CAROLINA DEPARTMENT OFTRANSPORTATION, and the NORTH CAROLINA STATE HISTORIC PRESERVATION OFFICE PURSUANT TO 36 CFR 800.6 regarding the I-26 CONNECTOR BUNCOMBE COUNTY, NORTH CAROLINA NCDOT TIP No. I-2513 FA No. MANHF-26-1(53). This MOA is attached to the permit for this project. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Prohibitions on Concrete: The Permittee shall take all measures necessary to prevent live or fresh concrete, including bags of uncured concrete, from coming into contact with any water in or entering into waters of the United States. Water inside coffer dams or casings that has been in contact with concrete shall only be returned to waters of the United States when it no longer poses a threat to aquatic organisms (concrete is set and cured). | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Aquatic Life Movement: No activity may substantially disrupt the necessary life cycle movements of those species of aquatic life indigenous to the waterbody, including those species that normally migrate through the area. All discharges of dredged or fill material within waters of the United States shall be designed and constructed to maintain low flows to sustain the movement of aquatic species. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Unless otherwise requested in the application and depicted on the approved permit plans, culverts greater than 48 inches in diameter shall be buried at least one foot below the bed of the stream. Culverts 48 inches in diameter and less shall be buried or placed on the stream bed as practicable and appropriate to maintain aquatic passage, and every effort shall be made to maintain existing channel slope. The bottom of the culvert shall be placed at a depth below the natural stream bottom to provide for passage during drought or low flow conditions. Culverts shall be designed and constructed in a manner that minimizes destabilization and head cutting. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Measures shall be included in the construction/installation of culverts that will promote the safe passage of fish and other aquatic organisms. The dimension, pattern, and profile of the stream above and below a pipe or culvert shall not be modified by widening the stream channel or by reducing the depth of the stream in connection with the construction activity. The width, height, and gradient of a proposed opening shall be such as to pass the average historical low flow and spring flow without adversely altering flow velocity. Spring flow should be determined from gauge data, if available. Inthe absence of such data, bankfull flow can be used as a comparable level. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | During the clearing phase of the project, heavy equipment shall not be operated in surface waters or stream channels. Temporary stream crossings will be used to access the opposite sides of stream channels. All temporary diversion channels and stream crossings will be constructed of non-erodible materials. Grubbing of riparian vegetation will not occur until immediately before construction begins on a given segment of stream channel. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | No fill or excavation impacts for the purposes of sedimentation and erosion control shall occur within jurisdictional waters, including wetlands, unless the impacts are included on the approved plan drawings and specifically authorized by this permit. This includes, but is not limited to, sediment control fences and other barriers intended to catch sediment losses. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall use appropriate sediment and erosion control practices which equal or exceed those outlined in the most recent version of the “North Carolina Sediment and Erosion Control Planning and Design Manual” to ensure compliance with the appropriate turbidity water quality standard. Erosion and sediment control practices shall be in full compliance with all specifications governing the proper design, installation and operation and maintenance of such Best Management Practices in order to ensure compliance with the appropriate turbidity water quality standards. This shall include, but is not limited to, the immediate installation of silt fencing or similar appropriate devices around all areas subject to soil disturbance or the movement of earthen fill, and the immediate stabilization of all disturbed areas. Additionally, the project shall remain in full compliance with all aspects of the Sedimentation Pollution Control Act of 1973 (North Carolina General Statutes Chapter 113A, Article 4). Adequate sedimentation and erosion control measures shall be implemented prior to any ground disturbing activities to minimize impacts to downstream aquatic resources. These measures shall be inspected and maintained regularly, especially following rainfall events. All fill material shall be adequately stabilized at the earliest practicable date to prevent sediment from entering into adjacent waters or wetlands. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team |  | In progress | This will be fulfilled
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall implement all reasonable and practicable measures to ensure that equipment, structures, work, and operations associated with this project do not adversely affect upstream and/or downstream reaches. Adverse effects include, but are not limited to, channel instability, flooding, and/or stream bank erosion. The Permittee shall routinely monitor for these effects, cease all work when detected, take initial corrective measures to correct actively eroding areas, and notify this office immediately. Permanent corrective measures may require additional authorization by the U.S. Army Corps of Engineers. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall ensure that all excavation and/or construction areas in regulated waters, to inlcude wetlands, are temporarily dewatered during work. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | Temporary Fills: Within thirty (30) days of the date of completing the authorized work, the Permittee shall remove all temporary fills in waters of the United States and restore the affected areas to pre-construction contours and elevations. The affected areas shall be re-vegetated with native, non-invasive vegetation as necessary to minimize erosion and ensure site stability. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Borrow and Waste | To ensure that all borrow and waste activities occur on high ground and do not result in the degradation of adjacent waters and wetlands, except as authorized by this permit, the Permittee shall require its contractors and/or agents to identify all areas to be used as borrow and/or waste sites associated with this project. The Permittee shall provide the U.S. Army Corps of Engineers with appropriate maps indicating the locations of proposed borrow and/or waste sites as soon as such information is available. The Permittee shall submit to the Corps site-specific information needed to ensure that borrow and/or waste sites comply with all applicable Federal requirements, to include compliance with the Endangered Species Act and the National Historic Preservation Act, such as surveys or correspondence with agencies (e.g., the U.S. Fish and Wildlife Service, the North Carolina Historic Preservation Office, etc.). The required information shall also include the location of all aquatic features, if any, out to a distance of 400 feet beyond the nearest boundary of the site. The Permittee shall not approve any borrow and/or waste sites before receiving written confirmation from the Corps that the proposed site meets all Federal requirements, whether or not waters of the U.S.,including wetlands, are located in the proposed borrow and/or waste site. All delineations of aquatic sites on borrow and/or waste sites shall be verified by the U.S. Army Corps of Engineers and shown on the approved reclamation plans. The Permittee shall ensure that all borrow and/or waste sites comply with Special Condition #3 of this permit. Additionally, the Permittee shall produce and maintain documentation of all borrow and waste sites associated with this project. This documentation will include data regarding soils, vegetation, hydrology, any delineation(s) of aquatic sites, and any jurisdictional determinations made by the Corps to clearly demonstrate compliance with Special Condition #3. All information will be available to the U.S. Army Corps of Engineers upon request. The Permittee shall require its contractors to complete and execute reclamation plans for each borrow and/or waste site and provide written documentation that the reclamation plans have been implemented and all work is completed. This documentation will be provided to the U.S. Army Corps of Engineers within 30 days of the completion of the reclamation work. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Compensatory Mitigation | In order to compensate for impacts associated with this permit, mitigation shall be provided in accordance with the provisions outlined on the most recent version of the attached Compensatory Mitigation Responsibility Transfer Form. The requirements of this form, including any special conditions listed on this form, are hereby incorporatedas special conditions of this permit. | Green Sheet, 404 Permit | All Sections | NCDOT, NCDMS
| Conservation Measures to Benefit Protected Species (Causeways- French Broad River, hominy Creek, and Smith Mill Creek) | Conservation Measures to Benefit Protected Species (Causeways- French Broad River, hominy Creek, and Smith Mill Creek) | Causeways will not restrict more than 50% of the existing channel width of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with U.S. Army Corps of Engineers and Service prior to permitting. The updated 2.3.4.2 Causeways – French Broad River, Hominy Creek, and Smith Mill Creek states: • Causeways will not restrict more than 50% of the river or stream flow of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with USACE and USFWS prior to permitting. | 2023 Addendum BO | All Sections | Construction, Design-Build Team, BSG, |  | In progress | This will be fulfilled
| Conservation Measures to Benefit Bats (Timing of Construction) | Conservation Measures to Benefit Bats (Timing of Construction) | Original Measure: NCDOT will monitor bat activity at the [Hill Street] culvert before, during, and after construction. Acoustic monitoring and/or emergence surveys will be conducted between March and November. Update: Based on recent data, the Service, North Carolina Wildlife Resources Commission (NCWRC), and NCDOT decided the best approach to monitoring the culvert would be through a combination of daytime visual surveys within the culvert and acoustic surveys. Visual surveys will be conducted two times per year during the active season (pre- and post-volancy) before, during, and after construction. If visual surveys discover large numbers of roosting bats, counts will switch to emergence surveys. Acoustic monitoring should occur throughout the active season (March 1 – November 15) at the culvert before, during, and post construction with detectors placed at the inlet and outlet. NCDOT will coordinate these monitoring efforts, including the preferred points of ingress and egress, ahead of time with the Service and NCWRC. | 2023 Addendum BO | All Sections | BSG | CLK coordinated with WRC and USFWS for preferred detector locations, scoped EPR ro consuct pre-construction acoustic monitoring of Hill St. culvert (Feb 2024). Year 1 (2024) completed and report submitted to USFWS 2025.
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: NCDOT will conduct acoustic monitoring (or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity due to construction. Update: The above measure is no longer necessary, as described above. | 2023 Addendum BO | All Sections | BSG | CLK coordinated, 2024 year 1 (August 2024), emailed results to WRC and USFWS
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: To help determine whether MYGR avoid active construction zones [including bridges and the Hill Street culvert roost] at night, NCDOT will investigate the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. Update: The use of night vision recording at active construction zones (including bridges and the Hill Street culvert) is no longer necessary. The original commitment was to see if MYGR avoid active construction zones at night. This was investigated via the night vision work conducted by NCDOT at the I-26 bridge over the French Broad River (NCDOT project I-4400/I-4700) and additional work on this is not needed. It was also determined that there weren't other locations like the (I-4400/I-4700) I-26 bridge that lend themselves to successfully doing this type of work. | 2023 Addendum BO | All Sections | BSG | No longer necessary
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: (As stated in T&C 10) NCDOT will conduct additional monitoring/research to include telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. The details of additional monitoring will be decided by a committee to include USFWS, NCWRC and NCDOT. Information gathered will be used to increase our knowledge of impacts to bats to help inform future consultation, to learn more about gray bats in the project area, to better conserve the species, and to track movements of [MYGR] bats and hopefully determine where bats go if they abandon the culvert roost and/or the area. Update: Only the coordinated monitoring of roosts and roost panel monitoring aspects of this measure remain valid. As stated above, information gained on MYGR in the French Broad River basin over the past several years obviates the need to pursue additional monitoring as described in the original measure. Coordinated monitoring in the form of emergence surveys will be conducted at primary bridge roosts. Survey methods will be coordinated with the Service, NCWRC and NCDOT. Surveys will occur two times per summer and will take place in 2024 and 2025 (pre-construction), then four times every other year during project construction, then two years after construction. | 2023 Addendum BO | All Sections | BSG | Measure reworded and represented in other fields,as written this measure is no longer necessary
| Conservation Measures to Benefit Bats (Tree Clearing Minimization) | Conservation Measures to benefit Bats (Tree Clearing Minimization) | The wooded buffer along Hominy Creek between the existing right-of-way and hominy Creek will remain intact. Two locations will have stone rip rap installed at the outlets of two pipes (-RPD- Sta. 23+25.27). Some trees may be trimmed or removed to create an entrance point for the rip rap installation, however, the clearing for the two rip rap installations will be minimal and temporary, and vegetation will return. These two locations are adjacent to a maintained clearing for overhead electric transmission lines. An additional two areas involve clearing within the existing right-of-way to install ditches. The wooded area between the existing right-of-way and Hominy Creek will remain unaffected, which is expected to block lighting from the roadway. Clearing at this location is depicted via pink dashed lines in Appendix B, Figures 12 and 13. | 2023 Addendum BO | Section A, Section C | Design-Build Team, Construction
| Conservation Measures to Benefit Bats (Bat Telemetry Study) | Conservation Measures to Benefit Bats (Bat Telemetry Study) | NCDOT, in coordination with FHWA, shall manage a contract funding a research institution to conduct a 2-year-minimum telemetry study focused on the subject bat species within a 30-mile radius of the I-26 Connector project, with the goal of finding roosting locations and gaining information about commuting and foraging areas and habitat use. The research will include work to capture focal species (MYSO, MYSE, PESU, MYLU) to transmitter/track. Work may involve using acoustics to identify areas of high focal species activity and netting those locations, searching bridges and culverts, and netting nearby known occupied areas as well as Hominy Creek. Additionally, bats could be captured at nearby hibernacula in early spring to track where they go in the summer. Active ground telemetry, aerial telemetry, and fixed tower telemetry may be utilized. The structure and details of the study design and research decisions will be decided by a committee to include the Service, NCWRC, NCDOT, and the contracted researcher(s). | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Structure Surveys) | Conservation Measures to Benefit Bats (Structure Surveys) | Structure Surveys: a)NCDOT shall survey bridges and culverts that meet the criteria detailed in the Standard Operating Procedures: NCDOT Preliminary Bat Habitat Assessments (Structures, Caves, and Mines) (NCDOT 2015), within 2 years of construction for each phase of the project. This measure applies to structures that are proposed for modification or replacement. CM 2.3.3.3 Pre-Demolition Check for Bats in the 2020 BO remains valid. b) NCDOT shall conduct a 2023/2024 winter survey within the 15 originally surveyed culverts most suitable for winter roosting by PESUs and five smaller culverts that have features of high thermal stability that could support cold weather PESU roosting (e.g., concrete with longer lengths). NCDOT will involve the Service in deciding which five smaller culverts to survey. | 2023 Addendum BO | All Sections | BSG | a) completed by RKK summer 2023 for the culverts that were between 3-5' to ensure we captured potential PESU culverts, only >5' were surveyed previously b) completd by NCDOT staff in Dec and Feb 2023/2024
| Conservation Measures to Benefit Bats (Roost Panel Monitoring) | Conservation Measures to Benefit Bats (Roost Panel Monitoring) | NCDOT’s monitoring plan of the Modern Bat Modular Roost Panels as described in the Terms and Conditions outlined in the 2020 BO shall include the Pratt-Whitney roost panels placed on the Biltmore Farms bridge (E. Frederick Law Olmsted Way) over the French Broad River. | 2023 Addendum BO | All Sections | BSG | Completed
| Conservation Measures to Benefit Bats (Bat Conservation Funding) | Conservation Measures to Benefit Bats (Bat Conservation Funding) | NCDOT shall contribute $150,000 to the NCWRC’s North Carolina Non-Game and Aquatics Project Fund (NCNGAPF) to support conservation and recovery efforts for MYSO, MYSE, PESU, and MYLU. This fund and its dispensation will be managed by the Service and NCWRC. At the time of the Addendum BO (Dec 2023), the NCNGAPF has not yet been set up to receive bat payments at NCWRC, it is expected in Jan 2025. This is in addition to the $350,000 first agreed to for gray bat (see above commitment) | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Lighting) | Conservation Measures to Benefit Bats (Lighting) | Lighting a) Smokey Park Highway Interchange: • Lighting at Ragsdale Creek shall not change from baseline condition. The current lighting will remain and the project will not result in changes or increases to the amount of light reaching Ragsdale Creek. • All new low level and high mast lighting installed by NCDOT for I-2513 A, B, C, and D sections shall be 3,000K color temperature, with the exception of the new ramp along Smokey Park Highway. b) I-26/I-40 Interchange Ramp East of Sand Hill Road: • The lighting fixtures installed at this location shall be 3,000K. This is a reduction from the existing lighting of 4000K. • At Trent Branch, high mast poles shall be reduced from existing conditions. At least four high mast poles shall be removed at this location. Replacement lighting shall be on single arm poles to the west of Trent Branch. This updated lighting configuration is designed to reduce lighting on Trent Branch. c) I-26/I-40 Interchange North of Pond Road: • Lighting adjacent to Hominy Creek shall be decreased from existing conditions. The existing lighting at this location is 400-watt high pressure sodium (HPS) with dropped glass lenses. Such fixtures typically produce 50,000 lumens of light each. The light-emitting diode (LED) replacement fixtures will produce less than 35,000 each. The LED fixtures have directional optics which enable light to be directed toward the road, as opposed to the HPS in dropped glass lens fixtures which result in more scattered light. | 2023 Addendum BO | All Sections | Design-Build Team
| Conservation Measures | Reasonable and Prudent Measures for Bats and Appalachian Elktoe | NCDOT shall ensure that the contractor(s) understands and follows the measures listed in the "Conservation Measures", "Reasonable and Prudent Measures" and "Terms and Conditions" sections of this Opinion | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Reasonable and Prudent Measures for Bats and Appalachian Elktoe | NCDOT shall monitor and document any take numbers and the surrogate measures of take and report those to the Service | 2023 Addendum BO | All Sections | BSG, Construction
| Conservation Measures | Terms and Conditions | Ensure that the procedures listed in the “Conservation Measures”, “Reasonable and Prudent Measures”, and “Terms and Conditions” sections of this Opinion are being implemented and that all project plans are being implemented in a manner that ensures the conditions of this Opinion are met. | 2023 Addendum BO | All Sections | Design-Build Team, NCDOT
| Conservation Measures | Terms and Conditions | NCDOT shall ensure that the Service and NCWRC are fully involved and in agreement with the design of the telemetry study. The study design process and subsequent data sharing shall be inclusive of and transparent to the involved agencies. Language will be included in any agreement requiring group consensus on any changes or contract and funding extensions, data sharing, and about following WNS decontamination protocols when working in western NC. Prior to funding approval, the study shall be approved by the Service and NCWRC. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures | Terms and Conditions | Ensure that the telemetry study project description includes a specified minimum level of effort, e.g. minimum number of nights of netting, and/or number and size of culverts/bridges to check, and/or number of acoustic stations | 2023 Addendum BO | All Sections | BSG
| Conservation Measures | Terms and Conditions | NCDOT shall provide oversight and monitoring to ensure that construction contractors abide by all design plans. | 2023 Addendum BO | All Sections | NCDOT, REU
| Conservation Measures | Terms and Conditions | NCDOT shall monitor the surrogate measures of take to ensure that any exceedances are detected in a timely manner | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Terms and Conditions | NCDOT shall immediately notify the Service’s Asheville Field Office should live or deceased MYSO, MYSE, PESU, or MYLU be discovered during project work. | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Conservation Recommendations | Tree Clearing: Avoid tree clearing activities during the most sensitive bat seasons, notably the pup season of May 15 - July 31. During this time, pups are non-volant and unable to fly away from clearing activities. | 2023 Addendum BO | All Sections | Design-Build Team, Construction, BSG | Not Mandatory
| Conservation Measures | Conservation Recommendations | Habitat Protection: Continue pursuit of property acquisition adjacent to the Hill Street culvert. | 2023 Addendum BO | Section B (Design-Build) | BSG | Not Mandatory
| Conservation Measures | Conservation Recommendations | Lighting: Implement additional reductions in high mast poles throughout the action area, especially near waterbodies and riparian areas. | 2023 Addendum BO | All Sections | Design-Build Team | Not Mandatory
| Conservation Measures | Conservation Recommendations | Canton Bridge: Investigate the light that is illuminating one side of the Pigeon River where bats historically traveled and emerged from the bridge, but are now avoiding. The goal of this is to remove or modify the light in a way that removes illumination from the river and riparian corridor. | 2023 Addendum BO | N/A | Design-Build Team, BSG | Not Mandatory
| Conservation Measures | Conservation Recommendations | Riparian Planting: Replant disturbed riparian areas with native, fast-growing trees and shrubs that would serve to stabilize the stream bank, filter runoff and reduce erosion and sedimentation, block light pollution, and generally improve the quality of the habitat for bats and aquatic species. Examples of potential native tree species to plant include: sycamore, tulip poplar, black cherry and river birch. Planting with established (e.g. containerized) young trees can increase the survival rate of plantings and contribute to faster improvement of riparian habitat. | 2023 Addendum BO | All Sections | Design-Build Team, Construction | Not Mandatory
| Conservation Measures | Conservation Recommendations | Noise Considerations for Bats: If suitable roost trees are present near high-decibel activity (81 – 162 dBA) and would experience noise above background levels (41 – 70 dBA), avoid conducting those high-decibel activities during the bat maternity season (May 15 – August 15). Alternatively, activity could avoid the pup season (May 15 - July 31). To minimize noise levels, incorporate sound-dampening devices such as noise shrouds for pile driving. | 2023 Addendum BO | All Sections | Design-Build Team, Construction | Not Mandatory
| Conservation Measures | Monitoring and Reporting Requirements | Yearly monitoring summaries will be cumulative. That is, take the first year’s report and add data from year two. In year three, add data to the report that has years 1 and 2. Update the methods, results, and discussion each year as needed. In this way, the subsequent reports add to and supersede the older reports and provide updated context. The last report will serve as the final report | 2023 Addendum BO | All Sections | BSG | Reports formatted as stated
| Conservation Measures | Monitoring and Reporting Requirements | Include annual updates on the amount of tree clearing throughout the construction project in each year's report | 2023 Addendum BO | All Sections | BSG, Construction, Design-Build Team | Construction and DBT provide tree clearing amounts to BSG
| Conservation Measures | Reinitiation Notice | This concludes formal consultation on the action(s) outlined in the consultation request dated July 24, 2023. As provided in 50 CFR §402.16, reinitiation of formal consultation is required where discretionary Federal agency involvement or control over the action has been retained (or is authorized by law) and if: (1) the amount or extent of incidental take is exceeded; (2) new information reveals effects of the agency action that may affect listed species or critical habitat in a manner or to an extent not considered in this opinion; (3) the agency action is subsequently modified in a manner that causes an effect to the listed species or critical habitat not considered in this opinion; or (4) a new species is listed or critical habitat designated that may be affected by the action. In instances where the amount or extent of incidental take is exceeded, any operations cuasing such take must cease pending reinitiation. | 2023 Addendum BO | All Sections | BSG
|  |  | In addition to the amount of take described in the 2020 Opinion, the following is now included: As explained in the modified BO (USFWS log 02-252, 5/12/2025), the amount of take is expected to increase by 1 individual given the 12,000 square foot additional area of impact. Because impact area (i.e. square footage) serves as a surrogate measure of take for the purposes of this analysis for Appalachian elktoe, the amount of incidental take will be exceeded if the impact area is exceeded. | 2025 Addendum BO | All Sections | BSG | Not a commitment
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | This work shall be conducted in accordance with the requirements of the modified 401 WQC | 2025 Permit Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | The permittee shall ensure that any equipment that is placed on the floodplain overnight, or at any other time, is moved to higher ground (above potential flooding) when either of the folllowing situations is forecasted or anticipated: (1) the water level will rise to a point where the equipment could be flooded (even during work days), and/or (2) the water level is expected to rise overnight, or over a non-work period of time, to a point where the equipment could be flooded | 2025 Permit Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | This modification is applicable only to the additional proposed activities. All of the authorized activities and conditions of the certification associated with the original Water Quality Certification dated October 30, 2023, still apply except where superseded by this certification. | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | Heavy equipment necessary for geotechnical borin gin the French Broad River may be operated within the river channel; however, its usage shall be minimized. In accordance with you rapplication, drill rigs shall follow the planned path as depicted in the French Broad River Path figure included in the application; drill rigs shall be mounted to large-diameter rubber-tire all terrain carriers with low-pressure tires to minimize contact pressures with the riverbed; drilling shall be performed during low water levels within the river (approximately 2 feet); and drill rigs shall be moved to the adjacent floodplain during the night. [15A NCAC 02H.0506(b)(3)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | The turbidity standard of 50 NTUs (Nephelometric Turbidity Units) shall not be exceeded as described in 15 A NCAC 02B .0200. Appropiate sediment and erosion control practices must be used to meet this standard. [15A NCAC 02B .0211 (21)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | In accordance with your application; NCDOT shall protect recreational river user safeth in the project area through the ofllowing protocol: move drill rigs to the floodplain for storage during overnight hours; utilize orange and white mooring buoys in teh water immediately around the drill rigs as a safety area that river users will need to avoid; position workers in the water in waders adjacent to drilling equipment to communicate river users; and maintain a River User Page as a resource for recreational users. [15A NCAC 02H .0506 (b)(1) and (2); 15A NCAC 02H .0507 (c)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team

## All without Notes
| Topic | Subtopic | Commitment | Source | Project Section | Responsibility
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | a. The RCBC portion of the culvert system, as well as the dual CMAP at the culvert outlet will remain in place. Work on this portion of the culvert system will not occur until bat activity ceases for the season (and bats are presumably no longer using the culvert for roosting). This time frame is approximately between November 15 and March 15. NCDOT will monitor the culvert with an acoustic detector and/or emergence counts to determine when bat activity ceases for the season. After bat activity ceases for the season, a federally permitted bat biologist will enter the culvert to confirm no bats are present. This will determine when construction activity may safely begin, and/or when it should end to avoid effects to MYGR that may use the culvert system for roosting. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | b. NCDOT will conduct sleeving or replacement of the 60” CMP adjacent to Courtland Ave. and the entrance to Dickson Elementary School (that conveys flow under Hill Street to the RCBC) between October 15 and April 1. | Green Sheet, June 2020 BO | B (Design-Build) | Construction, Design-Build Team and BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Timing of Construction | NCDOT will monitor bat activity at the culvert before, during, and after construction. Acoustic monitoring and/or emergence surveys will be conducted between Marchand November. | Green Sheet, June 2020 BO | B (Design-Build) | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Vegetation Removal | An operational work pad area will be established near the culvert outlets to complete the culvert rehabilitation process, as well as at the inlet near Courtland Avenue where the 60” CMP will be replaced or lined. Vegetation must be cleared to allow room for the work pad. NCDOT will cut plants in the work pad area in a way that will minimize impacts to bats and their activity by implementing the following measures: vegetation will not be removed if the area will be left bare for many months prior to construction; cutting of vegetation will be coordinated with USFWS and will not occur until all bats have left the culvert for the winter. This will be determined through emergence counts and/or acoustic monitoring and a physical check of the culvert for remaining bats; and limiting cutting to only what is necessary to complete the work and no more than 50 feet from culvert inlet/outlets. | Green Sheet, June 2020 BO | B (Design-Build) | Construction, BSG, Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | An equipment staging area will be established adjacent to the work pads near the culvert outlets and inlet areas near Courtland Avenue to complete the culvert rehabilitation process. NCDOT will attempt to use areas that are already cleared of vegetation whenever possible. This area will only be used for culvert rehabilitation activity staging and will not be used for any other project construction purposes. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | b. NCDOT will maintain baseflow to the RCBC and CMAP portion of the culvert (nonstormwater sources) to provide a naturally occurring, continual water source. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | c. NCDOT will either replace or install a liner in the 60” CMP located adjacent to Courtland Ave. and the entrance to Isaac Dickson Elementary School that conveys flow under Hill Street to the RCBC. NCDOT will complete this activity between October 15 and April 1. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Culvert Roost Construction | Additional Commitments | d. NCDOT will install a barrier/baffle (from here referred to as a baffle) in the RCBC between the intersection with the 60” CMP (located adjacent to Courtland Ave. and the entrance to Isaac Dickson Elementary School that conveys flow under Hill Street) and the upstream end of the RCBC to buffer noise and light associated with the CMP replacements further upstream. | Green Sheet, June 2020 BO | B (Design-Build) | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Preservation of Riparian Vegetation | a. NCDOT will ensure the Contractor preserves riparian buffer trees where practicable and feasible. | Green Sheet, June 2020 BO | All Sections | Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Roadway Construction Lighting | a. Due to MYGR activity on the landscape, NCDOT will limit all construction-related lighting to whatever is necessary to maintain safety in active work areas closest to the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team,
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Road Construction | Roadway Construction Lighting | b. Construction-related lighting will be indirect in nature and will not project into adjacent forested areas or over the water surface of the French Broad River, Hominy Creek, Emma Branch, or Smith Mill Creek, whenever practicable. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Access Roads | a. NCDOT will revegetate all access roads created for bridge construction and replacement activities where practicable. | Green Sheet, June 2020 BO | All Sections | Construction, REU and Design Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Nighttime Construction Activities | a. NCDOT will limit the use of nighttime construction within 50’ of the French Broad River, Hominy Creek, Emma Branch, or Smith Mill Creek between April 1 and October 15 to only the following activities: causeway construction, drilled shafts, concrete pours, beam setting, and traffic shifts. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Nighttime Construction Activities | b. NCDOT shall commit to restrict the Contractor to no night work at crossings of the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek to minimize potential impacts to lactating females and their pups between June 1 and June 14. Between June 15 through August 1, NCDOT will also commit to restrict the Contractor to no more than 28 total nights of work, with no more than four consecutive nights. Lighting used for construction will be limited to what is necessary to maintain safety standards and will only be directed toward active work areas. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Pre-Demolition Check for Bats | a. If bridge demolition is required between April 1 and October 15, NCDOT will conduct a check of all subject bridges within 30 days of demolition to determine if bats are present. See Term and Condition 12 for checks specific to culverts. T&C 12: In order to carry out Reasonable and Prudent Measure 5, NCDOT will conduct culvert checks for roosting bats within 30 days of rehabilitation or repair for any culverts five feet tall or higher, and 200 feet or longer, scheduled to occur from March 15th through November 15th. If bats are found, a similar protocol will be used to the pre-demolition check for bats in bridges | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Pre-Demolition Check for Bats | b. If bats are present, one of the following options will be implemented (options listed in order of preference). NCDOT will: i. Wait for bats to leave for the season (approximately mid-October to early November) before beginning work; or ii. A biologist will monitor the bridge and work will begin after bats leave the bridge for the evening, or iii. A permitted biologist will exclude bats from work area immediately prior to the start of work using acoustic deterrents, or iv. A permitted biologist will hand remove bats from work area immediately prior to the start of work. v. If pre-demo check determines pups are present, NCDOT will refrain from bridge demolition until it can be determined by a biologist that the pups are volant, and then use the previous options to proceed with demolition. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat during Bridge Construction | Red Safety Lighting | a. As part of NCDOT’s Communication Plan specific to the construction/demolition of the bridges over the French Broad River, NCDOT will place solar-powered, steadystate red lights on the causeways to alert river users to their locations. Generators will not be used to provide power. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Contract Language | Contract language will include the following, or similar language as appropriate for bridges over the French Broad River a. The Contractor will be required to prosecute the work in a continuous and uninterrupted manner from the time work begins until completion of each phase of structure construction, demolition, and completion. The Contractor will not be permitted to suspend operations except for reasons beyond their control or except where the Engineer has authorized a suspension of the Contractor’s operations in writing. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | a. Causeways will not restrict more than 50% of the existing channel width of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with USACE and USFWS prior to permitting. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | b. NCDOT will require the Contractor to use clean rock (free of debris and pollutants) for the construction of the causeways to minimize unnecessary sediment input into the river. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | c. Causeway material will be removed to the extent practicable and either disposed of off-site or used in areas that require permanent stone protection after project completion. NCDOT will also require that concrete barriers (barrier rail) be placed along the downstream edge of each causeway to limit the downstream movement of causeway material during high flow events. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | d. If the final causeway plan is staged, causeway material will be added/removed as needed for each stage to minimize the causeway footprint over the length of the project. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | e. Construction fabric will not be used under the causeway material, as it tends to tear into tiny pieces and float downstream during removal. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | f. Any equipment on the causeways will be removed any time throughout a work day when the water level rises, or is expected to rise overnight, to a point where the equipment could be flooded, or during periods of inactivity (two or more consecutive days). The only exception to this measure is that the drill rig and crane may be left in place for periods of inactivity; however, they must also be removed if the water rises, or is expected to rise, to a point where the drill rig and crane could be flooded. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | g. NCDOT will require its Contractor to have clean, non-leaking equipment, diapers onsite for each causeway, and spill kits located at each causeway. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Causeways – French Broad River, Hominy Creek, and Smith Mill Creek | h. Causeways needed for the new bridges over the FBR will be designed so that during a 100 year storm event there will not be a rise in water surface elevation outside the Action Area greater than normal seasonal variation. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | a. All construction equipment shall be refueled above the 100-year base flood elevation plus a foot of freeboard and be protected with secondary containment. During crucial periods of construction and demolition, when the drill rig and crane cannot be moved, the drill rig and crane can be refueled while inside the 100-year floodplain provided that spill response materials (such as spill blankets and fueling diapers) are used during the refueling. Hazardous materials, fuel, lubricating oils, or other chemicals will be stored above the 100-year base flood elevation plus a foot of freeboard. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | b. Areas used for borrow or construction by-products will not be located within wetlands or the 100-year base flood elevation plus a foot of freeboard. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | c. When constructing drilled piers for the I-240, I-40 and I-26 French Broad River bridges, a containment system will be developed so material does not enter the river. Material byproduct will be pumped out of the shaft to an upland disposal area to the extent practicable and treated through a proper stilling basin or silt bag. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | d. Construction of all bridges will be accomplished in a manner that prevents uncured concrete from coming into contact with water entering or flowing in the river. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | e. Removal of existing bridges shall be performed so as not to allow debris to fall into the water. If debris is dropped in a waterway, it will be immediately removed. | Green Sheet, June 2020 BO | All Sections | Construction and Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Bridge Construction | Containment | f. NCDOT will not place bridge bents in Smith Mill Creek or Emma Branch. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Erosion Control Measures | a. The Soil and Erosion Control (SEC) plan will be in place prior to any ground disturbance for all bridge replacements and construction. When needed, combinations of erosion control measures (such as silt bags in conjunction with a stilling basin) will be used to ensure that the most protective measures are being implemented. | Green Sheet, June 2020 BO | All Sections | Construction, REU, Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Erosion Control Measures | b. NCDOT standard procedures dictate that when a project has both Environmentally Sensitive Areas and a requirement to follow DSSW, and uses the GP NCG01 permit, NCDOT will default to the most-restrictive SEC measure requirement (Appendix H of BO). | Green Sheet, June 2020 BO | All Sections | Construction, REU, Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | i. NCDOT will revisit CP4A with the Merger Team after the BA is submitted to discuss any new avoidance and minimization efforts for major crossings of the French Broad River and Hominy Creek including those in the Biological Assessment. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | ii. NCDOT will provide USFWS with the final roadway lighting plans and allow 15 days for review upon acknowledgement of receipt of notice. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | iii. NCDOT will continue to identify avoidance and minimization measures to all Waters of the U.S. and ensure that major hydraulic structures associated with the project are designed and installed to minimize negative impacts to stream stability (and therefore, water quality) to the greatest extent practicable. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | iv. NCDOT will provide USFWS with the total size of bridge footings in the water as project design progresses and the information becomes available. | Green Sheet, June 2020 BO | All Sections | AC Bid-Build, Design Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | v. NCDOT will provide USFWS with the results of the hydrology modeling (described below) as it becomes available, including change in French Broad velocity with causeways in place, and change in water surface elevation with causeways in place. | Green Sheet, June 2020 BO | Section B (Design-Build) and Section C | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)-NCDOT Requirements | vi. Once ROW plans are developed where vegetation will be removed in riparian areas, NCDOT will meet with USFWS and NCWRC to discuss revegetation plans with the goal of establishing native forested buffers in all impacted areas (Hominy Creek, Smith Mill Creek, Emma Branch, and the French Broad River). NCDOT, USFWS and NCWRC will also discuss revegetation for acquired riparian ROW that was not forested when purchased. Additionally, NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG, REU
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | i. The Bid Build Contractor shall meet with NCDOT personnel and USFWS and representatives immediately after contract execution to review the project and project commitments. At this time, the USFWS shall be afforded the opportunity to meet with key Bid Build Contractor members and NCDOT employees to provide education on the effects of artificial lighting, noise, and construction on nearby wildlife habitat and behavior. The Bid Build Contractor shall coordinate with the NCDOT Environmental Analysis Unit to schedule these meetings. This meeting shall be made prior to submitting any required permit modification application. | Green Sheet, June 2020 BO | B (Design-Build) | BSG, Bid-Build Contractor, Construction, NCDOT Construction,
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | ii. The Bid Build Contractor shall provide USFWS with the construction phasing plan for each bridge. | Green Sheet, June 2020 BO | All Non-D-B Sections | Bid-Build Contractor, Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | iii. The Bid Build Contractor and / or NCDOT shall contact USFWS if new information about MYGR is discovered, as it relates to the project. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction, BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | iv. The Bid Build Contractor shall report any dead bats found on the construction sites to USFWS. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Bid Build Contractor Requirements | v. The Bid Build Contractor shall adhere to project commitments within the ROD and the Biological Opinion relating to Section 7 of the Endangered Species Act. | Green Sheet, June 2020 BO | All Sections | Bid-Build Contractor, Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | i. NCDOT will arrange a meeting between each shortlisted DBT, representatives of the USFWS, and other regulatory agencies prior to the due date for the submission of Technical and Price Proposals. The discussions and answers provided at these meetings are not contractually binding but intend to offer the shortlisted teams an opportunity to inquire as to the permitting process as well as specific team concepts. | Green Sheet, June 2020 BO | B (Design-Build) | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | ii. NCDOT will arrange a meeting with the selected Design-Build Team (DBT) to provide an opportunity for USFWS to convey their concern about potential effects to protected species. The DBT shall meet with NCDOT personnel and USFWS and regulatory agency representatives immediately after contract execution to review the project and project commitments. At this time, the USFWS shall be afforded the opportunity to meet with key DBT members and NCDOT employees to provide education on the effects of artificial lighting, noise, and construction on nearby wildlife habitat and behavior. The NCDOT shall coordinate with the DBT and the NCDOT Environmental Analysis Unit to schedule this meeting. This meeting shall be made prior to submitting the permit application. This is prior to the standard pre-con environmental meeting. | Green Sheet, June 2020 BO | B (Design-Build) | BSG
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | iii. The DBT shall adhere to project commitments within the ROD and the Biological Opinion relating to Section 7 of the Endangered Species Act. The DBT will be required to prepare information for any event in which NCDOT and FHWA reinitiate Section 7 consultation with the USFWS. It is possible that consultation be reinitiated prior to Concurrence Point 4B and again at Concurrence Point 4C. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | iv. NCDOT will continue to identify avoidance and minimization measures to all Waters of the U.S. and ensure that major hydraulic structures associated with the project are designed and installed to minimize negative impacts to stream stability (and therefore, water quality) to the greatest extent practicable. As part of this process, NCDOT and the DBT will continue to coordinate with the Merger Team to identify avoidance and minimization measures and ensure that project impacts are minimized to every practicable extent, including impacts to federally protected species. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | v. The DBT shall invite USFWS and regulatory agency representatives to the pre-construction meeting for the proposed project, as well as to all subsequent field inspections prior to construction, to ensure compliance with all special project commitments. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | vi. The DBT shall provide USFWS with the sediment and erosion control plan and allow 15 days for review upon acknowledgement of receipt of notice. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | vii. The DBT shall provide regulatory agency representatives with the demolition plan for all bridges and allow 15 days for review upon acknowledgement of receipt of notice. All agencies will be notified prior to start of demolition so they may have a representative on site. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | viii. The DBT shall provide USFWS with the construction phasing plan for each bridge. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | ix. The DBT and / or NCDOT shall contact USFWS if new information about MYGR is discovered, as it relates to the project. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team, Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | x. The DBT shall report any dead bats found on the construction sites to USFWS. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team, Construction
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | xi. The DBT shall include an Environmental Coordinator as a member of their Team who will be required to attend all design, merger, and preconstruction meetings, and who will consult bat and mussel experts, as needed. | Green Sheet, June 2020 BO | B (Design-Build) | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe during Road Construction and Bridge Replacement | Agency Coordination (Post Biological Opinion Checkpoints)- Design Build Team Requirements | xii. Once ROW plans are developed where vegetation will be removed in riparian areas, NCDOT will meet with USFWS and NCWRC to discuss revegetation plans with the goal of establishing native forested buffers in all impacted areas (Hominy Creek, Smith Mill Creek, Emma Branch, and the French Broad River). NCDOT, USFWS and NCWRC will also discuss revegetation for acquired riparian ROW that was not forested when purchased. Additionally, NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. Certain ROW areas will not be forested because they must be mowed or maintained at a low height for safety purposes. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG, REU
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | a. NCDOT’s stormwater commitment guidance, will apply at crossings of the French Broad River and its tributaries, and any portion of the NCDOT stormwater conveyance system draining to those waters within the right-of-way. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | b. NCDOT will prepare a stormwater management plan (SMP) to implement postconstruction stormwater best management practices (BMPs) to the maximum extent practical, consistent with the Department’s National Pollutant Discharge Elimination System (NPDES) Post Construction Stormwater Program. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | c. When preparing the SMP, NCDOT commits to using a hierarchical BMP selection process, optimized to treat silt, nutrients, and heavy metals. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | d. At each discharge location outside of the 100-year floodplain, the hydraulics engineer will evaluate the feasibility of installing either an infiltration basin or a media filter as described in NCDOT’s BMP Toolbox. If neither is feasible, the hydraulics engineer will select a feasible BMP. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | e. NCDOT will commit to evaluating the use of emerging BMP technologies that the Department has not yet published in its BMP Toolbox: i. Bioswales ii. Bio embankments iii. Biofiltration conveyances iv. Soil improvement to maximize infiltration | Green Sheet, June 2020 BO | All Sections | NCDOT, Design-Build Team
NCDOT Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Stormwater Control Measures | f. The NCDOT hydraulics design engineer will consult with the State Hydraulics Engineer and obtain prior approval before proposing one of these BMP technologies in the SMP. | Green Sheet, June 2020 BO | All Sections | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | Crossing numbers in this section refer to Table 1 in Section 2.2.4 and Figures 4A-4D in Appendix A of the Biological Opinion. a. General CM’s for all crossings of the French Broad River, Hominy Creek, Emma Branch, and Smith Mill Creek: i. Use shorter poles, providing an overall LED light fixture mounting height of 35’ above the pavement surface. ii. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. iii. Use LED light fixtures with a BUG rating of 1-0-3 or less iv. Change the design standards to meet the AASHTO minimum requirements of an average of 0.6 fc at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. v. At all identified crossings, the proposed high mast poles and 45’ poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35’ poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | Green Sheet, June 2020 BO | All Sections | Design-Build Team
| Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | a. General CM’s for the entire project: i. Use shorter poles, providing an overall LED light fixture mounting height of 35’ above the pavement surface. ii. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. iii. Use LED light fixtures with a BUG rating of 1-0-3 or less iv. Change the design standards to meet the AASHTO minimum requirements of an average of 0.6 fc at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. v. At all identified crossings, the proposed high mast poles and 45’ poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35’ poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | June 2020 BO | All Sections | Design-Build Team
|  |  | General Conservation Measures that apply to parts of the action area near and over waterways and riparian areas: 1. Use shorter poles, providing an overall LED light figure mounting height of 35 feet above the pavement surface. 2. Use LED light fixtures with a more rectangular light pattern as well as house side shields to minimize lighting outside of the pavement area. 3. Use LED light fixtures with a BUG rating of 1-0-3 or less 4. Use LED light fixtures with a lower lumen output, reducing overall brightness a. Change the design standards to meet the American Association of State Highway and Transportation Officials (AASHTO) minimum requirements of an average of 0.6 foot-candle (fc) at 4:1 uniformity at all crossing locations identified in the lighting document, from the original design of 0.8 fc at 4:1 uniformity. b. At all identified crossings, the proposed high mast poles and 45-foot poles with GE Cobrahead (GE) fixtures (3-0-3 BUG) were redesigned with 35-foot poles with Cooper Cobrahead (Cooper) fixtures (1-0-3 BUG). | Dec 2022 BO Mod to clarify above lighting measures | All Sections | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | b. Culvert Outlet – The current design near Southern States property results in zero calculated change to baseline light levels at the culvert opening and ditch leading to the FBR. | Green Sheet, June 2020 BO | Section D | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | c. Culvert Outlet – NCDOT will meet with landowners adjacent to the roost culvert to discuss replacement or augmentation of existing lighting to reduce existing baseline conditions determined by the NCDOT Roadway Lighting Squad. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | d. Culvert inlet – The original lighting design near the Hill Street culvert inlet had 80’ high mast poles installed between the mainline and Hill Street behind the Isaac Dickson Elementary School. NCDOT is revising this design to replace them with GE light fixtures installed on twin arm poles on the mainline median barrier. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | e. New French Broad Crossing (NFBC) – Use of single arm light poles mounted on the bridge and flyover barriers in place of the 120’ and 100’ high mast poles. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | f. NFBC – 35’ single arm poles with a narrow distribution light fixture and a house side shield will be used. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | g. FBR-1 – The GE fixtures were replaced with the lower BUG rated Cooper fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | h. FBR-1 – Fixtures were redesigned to have the outer ring (as shown in the figures within the lighting document) ending roughly 115’ from the west bank of the FBR. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | i. FBR-2, FBR-3, & FBR-4 – All high mast poles within the connector interchange were removed and replaced with Cooper fixtures mounted on the outer and/or center bridge barrier rail. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | j. FBR-2, FBR-3, & FBR-4 – The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | k. HC-1 – Replacing the GE fixtures with the Cooper fixtures. The crossing is still centered between the Cooper fixtures, as it was for the GE fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | l. HC-1 - Replacing the 120’ high mast pole with an 80’ high mast pole. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | m. HC-2 & HC-3 – Removal of a 120’ high mast pole and replaced with Cooper fixtures. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | n. HC-2 & HC-3 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | o. HC-4 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | p. HC-5 & HC-6 – Removal of 80’ high mast pole and replacing with Cooper fixtures along the mainline and ramp in both directions. | Green Sheet, June 2020 BO | Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | q. HC-5, HC-6, HC-7 - The Cooper fixtures are located so the crossings are centered between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section A and Section C | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | r. All SMC and EBC – Removal of all high mast poles within the connector interchange and replaces them with Cooper fixtures mounted on the outer and/or center bridge barrier. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | s. All SMC and EBC - Cooper fixtures located so the crossings are centered as best as possible between fixtures where the light level is the lowest. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Measures to Avoid/Minimize Effects to Gray Bat and Appalachian Elktoe During Roadway Operation | Permanent Lighting | t. SMC culvert area – Existing high mast pole located within the interchange ramps will be removed. | Green Sheet, June 2020 BO | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | a. NCDOT will conduct acoustic monitoring (or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity due to construction. NCDOT will coordinate the locations and time frame for monitoring with USFWS. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | b. To help determine whether MYGR avoid active construction zones at night, NCDOT will investigate the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Monitoring for MYGR Return and Activity | c. NCDOT will conduct additional monitoring/research to at a minimum include additional telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. This additional monitoring will be coordinated with USFWS, NCWRC and NCDOT. Please refer to Term and Condition 10 for clarification. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | a. NCDOT will replace most, if not all the CMP within the culvert system upstream from the RCBC with RCBC and/or concrete pipe, which will effectively create additional bat roosting habitat. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | b. NCDOT will meet with landowners adjacent to the roost culvert to discuss replacement or augmentation of existing lighting to reduce existing baseline conditions determined by the NCDOT Roadway Lighting Squad. | Green Sheet, June 2020 BO | Section B (Design-Build) | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Hill Street Culvert Roost Area | c. NCDOT will acquire a permanent drainage easement (PDE) or additional right of way at the culvert inlet (near Courtland Ave.) and outlets, where replanting with containerized, native, woody vegetation will occur. In addition, if NCDOT acquires additional right-of-way or conservation easements along the French Broad River or adjacent to the culvert, NCDOT will replant with native, woody vegetation to provide, in time, a buffer for noise, light, and surface water runoff. NCDOT will coordinate with USFWS and NCWRC to develop a revegetation and invasive species management plan for these areas. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | NCDOT-Sponsored Gray Bat Research Project | NCDOT, with the cooperation of the USFWS and NCWRC, committed to a three-year study on MYGR within the French Broad River Basin. This study will serve as a conservation measure for NCDOT projects within the Divisions 13 and 14 for a limited time. NCDOT will fund Indiana State University $900,000 to conduct the research project, to gather the information needed to allow NCDOT and USFWS to enter a programmatic consultation to cover MYGR for NCDOT Divisions 13 and 14, as well as help to develop species-specific avoidance and minimization measures. This agreement was reached, in part, for the I-4400/I-4700 (I-26 widening) project in Buncombe and Henderson Counties, but also benefits this project. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Protection of Culvert Roost Entrance | NCDOT will coordinate with USFWS to assess the need to deter trespassing/use of the culvert by humans, and install signage or barriers, as needed. | Green Sheet, June 2020 BO | Section B (Design-Build) | BSG and Division Construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Gray Bat Conservation Funding | NCDOT will provide $350,000 for measures consistent with the recovery objectives outlined in the MYGR recovery plan (Brady et al. 1982). | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Gray Bat | Installation of Temporary Bat Roost Panels on Bridges | NCDOT will provide modern bat roost panels or comparable structures that could serve as a temporary alternate roost for bats potentially disturbed by work on the culvert roost for the duration of construction of the I-2513 project. This will be in the place of the panels on four bridges NCDOT has committed to in the BA, which were to be placed on bridges with documented signs of bat use. These bridges are all relatively far from the Hill Street Culvert roost. The USFWS believes that panels placed on one bridge close to the Hill Street Culvert roost has greater potential to minimize take than panels placed on four bridges farther away (Reasonable and Prudent Measure 3). Refer to Term and Condition 9 for more details. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Appalachian Elktoe | Appalachian Elktoe Conservation Funding | a. NCDOT will provide $500,000 to the North Carolina Nongame Aquatic Projects Fund for the French Broad River Conservation Plan (FBRCP) proposed by USFWS, which will aid in the recovery and conservation of Appalachian elktoe. The funding will be held by the NCWRC. A multi-agency/organization group of mussel species experts, including USFWS, will determine how to expend the funds. b. The French Broad River Conservation Plan proposes to improve aquatic habitat and diversity and to mitigate risks in the French Broad River. It may include the following: i. Species Reintroduction: Developing a normal cohort of companion species will benefit long-term Appalachian elktoe recruitment and survival; mussel species are healthier in dense multi-species mussel beds (Vaughn et al. 2008). ii. Early Warning and Emergency Capacity: A monitoring network and propagation facility devoted to species introduction pairs an early warning system with emergency production capacity to immediately mitigate unforeseen effects to the Appalachian elktoe population should the need arise. iii. Genetic Management Program: A study of the genetic health/potential genetic drift of the population will provide feedback to the previous two program aspects and will fine tune management of Appalachian elktoe. iv. Miscellaneous: Other projects could include development of technologies such as the use of passive integrated transponder (PIT) tags to locate mussels; radio tracking equipment to study movement of mussels during high flow; development of techniques to artificially stabilize habitat for the placement of propagated mussels; and/or a cost-benefit study of watershed improvement options. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Conservation Measures to Benefit Appalachian Elktoe | French Broad River Geomorphology Monitoring | NCDOT is working with the US Geological Survey (USGS) to evaluate the impacts of construction and temporary causeways on river habitat. This monitoring project encompasses several Transportation Improvement Projects (I-2513, I-4400 and I-4700). Therefore, the monitoring project will span several years to accommodate the varying construction schedules. a. Terrestrial Light Detection and Ranging (T-LiDAR) technology will be used annually to produce a laser scan of river banks. Bathymetric surveys will be conducted concurrently one to two times a year. Bathymetric data will be used to generate a gridded surface representation (digital elevation model, or DEM) of the channel bed for each survey. A similar approach will be applied to T-LiDAR data to evaluate stream bank position between successive surveys. b. Water quality monitoring will include real-time (continuous) data collection of temperature, turbidity, and specific conductance. Discrete water-quality samples will be collected during a variety of flow conditions to measure total suspended sediment (TSS) and suspended sediment concentration (SSC). c. Continuous streamflow, precipitation, and water-quality (temperature, conductance, and turbidity) data will be available online at http://waterdata.usgs.gov/nc/nwis/rt/ and via text and email alerts. Yearly summaries for each monitoring site will be available on demand from the USGS National Water Information System web interface (NWISWeb). Real-time alerts will be available to NCDOT via the NWISWeb when temperature or turbidity concentrations spike or exceed a predetermined threshold. d. If monitoring at the French Broad River reveals excessive bank erosion, bank instability, or sedimentation associated with the bridge replacement, NCDOT will work to identify the cause and will make improvements to address the problems in a timely manner. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 1. The USFWS must be notified of any project modifications. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 2. NCDOT will minimize impacts to roosting bats in the culvert roost to the extent possible through coordination with the USFWS for work that occurs between March 15th and November 15th. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 3. NCDOT will provide modern bat roost panels or comparable structures that could serve as a temporary alternate roost for bats potentially disturbed by work on the culvert roost for the duration of construction of the I-2513 project. This will be in the place of the panels on four bridges NCDOT has committed to in the BA, which were to be placed on bridges with documented signs of bat use. These bridges are all relatively far from the Hill Street Culvert roost. The USFWS believes that panels placed on one bridge close to the Hill Street Culvert roost has greater potential to minimize take than panels placed on four bridges farther away. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 4. NCDOT will minimize permanent lighting on waterways in the final lighting design plan to the extent possible, as well as current permanent lighting at the Hill Street Culvert Roost. Current plans for new permanent lighting (Appendix J of the BO) are preliminary in nature. | Green Sheet, June 2020 BO | All Sections | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 5. NCDOT will avoid and minimize potential take of bats roosting in culverts other than the Culvert Roost by conducting culvert checks before rehabilitation or repair work (see Term and Condition 12). | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reasonable and Prudent Measures | Reasonable and Prudent Measures for gray bat and Appalachian Elktoe | 6. NCDOT will adhere to all BMPs for soil and erosion control, and will report to the USFWS (described in Term and Condition 7) if failures occur. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 1. NCDOT will adhere to all measures listed in the Conservation Measures section of this Opinion and in the BA (if not revised in the BO). | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 2. NCDOT will simultaneously notify USACE and USFWS of any permit modification requests. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 3. A USFWS biologist will be invited (at least seven days prior) to the preconstruction meeting(s) to review permit conditions and discuss any questions the Contractor has regarding implementation of the project. After the Contractor submits plans for various stages (outlined in post BO coordination Section 2.3.5.2) of the project, a USFWS biologist will review and provide comments (within 15 days upon acknowledgement of receipt of notice) on the plans and will be invited to attend any meetings to discuss implementation of the plans. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, NCDOT
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 4. During construction, culvert inlets and outlets will be evaluated by the resident engineer with regard to stream stability immediately following installation and quarterly for a period of one year at each location. Indicators of instability, such as head cutting, scour, aggradation, or degradation, will be used to determine the need for corrective actions. | Green Sheet, June 2020 BO | All Sections | Construction
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 5. A final field inspection will be held with the Contractor to evaluate culvert placement and stream stability before the project is considered complete. If instability is detected during any of these reviews, corrective actions will be performed when deemed necessary by the engineer or by the conditions of any federal and state permits required by Section 404/401 of the Clean Water Act. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 6. NCDOT and NCDEQ-DEMLR (land quality) will meet with USFWS to evaluate and discuss erosion control effectiveness if requested. | Green Sheet, June 2020 BO | All Sections | NCDOT, REU
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 7. In the event of any failure of erosion control devices, within 48 hours, NCDOT will send a report to USFWS detailing the cause of the failure, photographs of the failure, and a plan for repair of the erosion control devices and reasonable methods to avoid future failure. NCDOT will notify the USFWS when failures are repaired. | Green Sheet, June 2020 BO | All Sections | NCDOT, REU
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 8. To carry out Reasonable and Prudent Measure 2, the USFWS must be notified before work starts in the culvert. a. Work can only commence when the baffle is installed if work will occur from March 15th through November 15th. b. NCDOT will coordinate with the USFWS to determine the best timing for installing the baffle. c. The USFWS, or an individual approved by USFWS, must be present when trees are cleared near the culvert and when the baffle is installed if installation occurs when bats present. d. The USFWS may request that the baffle is moved, removed, or altered. It may be determined that disturbances from construction are less impactful than potential alterations to the culvert microclimate from the baffle, or noise levels no longer exceed the ambient level. e. If the RCBC outlet is needed to access other portions of the culvert, it will only be used when bats are not present. | Green Sheet, June 2020 BO | Section B (Design-Build) | Design-Build Team, BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 9. The alternate bat roost structure from Reasonable and Prudent Measure 3 will consist of modern bat modular roost panels or comparable structures installed on a bridge over water as close to the culvert roost as possible, but out of areas disturbed by construction. Panels should be constructed of fiber-reinforced concrete with additives to mimic thermal mass and should be mounted using metal. Bridge selection and panel placement/design should be informed by work currently being conducted by Indiana State University. Panels must be installed before work starts on the culvert roost and should be checked for bat use once in early summer and once in late fall for three years following placement. The details of the location, size, design, and installation of the bat panels will be decided by a committee to include USFWS, NCWRC, and NCDOT. This panel will be installed temporarily for the duration of construction. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 10. NCDOT will monitor bat activity before, during, and post construction. a. NCDOT has committed to conducting acoustic monitoring (and/or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity related to construction. NCDOT will coordinate the locations and time frame for monitoring with USFWS. This will include monitoring the culvert roost, including before and after the baffle is installed. b. To investigate whether MYGR avoid active construction zones (including bridges and the Hill Street culvert roost) at night, NCDOT will explore the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. c. NCDOT will conduct additional monitoring/research to include telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. The details of additional monitoring will be decided by a committee to include USFWS, NCWRC and NCDOT. Information gathered will be used to increase our knowledge of impacts to bats to help inform future consultation, to learn more about gray bats in the project area, to better conserve the species, and to track movements of bats and hopefully determine where bats go if they abandon the culvert roost and/or the area. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 11. As part of Reasonable and Prudent Measure 4, NCDOT will give the USFWS the opportunity to discuss/review/comment on the lighting design drafts and final design plans (and allow 15 days for review upon acknowledgement of receipt of notice), including on the Bowen Bridge. a. Bowen Bridge: This bridge is being downgraded to carry four lanes of local traffic on the center lanes, and bike and pedestrian paths on the outer lanes. Lighting will be altered to accommodate these changes. i. New lighting for vehicle and bike/pedestrian traffic will not exceed the current level of illumination on the water (an average of 0.10 foot-candle over an area that goes from shore to shore and extends approximately 50’ to the north and south from the structures) as determined by a lighting engineer, and every effort will be made to reduce the level of illumination on the water. ii. NCDOT will work with USFWS to avoid and minimize impacts of light, including: -Light will be 3000 K or below iii. Proposed aesthetic panel lighting will not illuminate the water surface when bats are present (March 15th through November 15th). NCDOT and the City of Asheville will work with the USFWS to determine acceptable light color and levels when bats are present. | Green Sheet, June 2020 BO | All Sections | NCDOT, Lighting design plans are done by the department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | Southern States: USFWS will be included in discussions about modifying the lights at Southern States to decrease light spill at the Hill Street culvert entrance. If the land owner does not agree to minimize lighting on their property, NCDOT will work with the USFWS to assess the effectiveness of and minimize light using a barrier (fence or vegetation) on their ROW easement. | Green Sheet, June 2020 BO | Section D | NCDOT, Lighting design plans are done by the department
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 12. In order to carry out Reasonable and Prudent Measure 5, NCDOT will conduct culvert checks for roosting bats within 30 days of rehabilitation or repair for any culverts five feet tall or higher, and 200 feet or longer, scheduled to occur from March 15th through November 15th. If bats are found, a similar protocol will be used to the pre-demolition check for bats in bridges. If bats are present, one of the following options will be implemented (options listed in order of preference). NCDOT will: a. Wait for bats to leave for the season (approximately mid-October to early November) before beginning work; or b. A biologist will monitor the culvert and work will begin after bats leave the culvert for the evening (if work occurs over multiple days, the culvert will need to be monitored each day work occurs), or c. A permitted biologist will exclude bats from work area immediately prior to the start of work using acoustic deterrents (if this method is employed, the culvert will need to be checked each day work occurs to determine efficacy), or d. A permitted biologist will hand remove bats from work area immediately prior to the start of work (the culvert will need to be checked each day work occurs to ensure bats do not return). e. If pre-work check determines pups are present, NCDOT will refrain from culvert work until it can be determined by a biologist that the pups are volant, and then use the previous options to proceed with work. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Terms and Conditions | Terms and Conditions | 13. The nearest flyover bridge to the culvert roost will not be closer than 300 feet from the outlet. | Green Sheet, June 2020 BO | All Sections | Design-Build Team
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Monitoring and Reporting Requirements | Monitoring and Reporting Requirements | In order to monitor the impacts of incidental take, the NCDOT must report the progress of the Action and its impacts on the species to the USFWS. This section provides the specific instructions for such monitoring and reporting. As necessary and appropriate to fulfill this responsibility, the NCDOT must require any permittee, Contractor, or grantee implement these Terms and Conditions through enforceable terms that are added to the permit, contract, or grant document. Such enforceable terms must include a requirement to immediately notify the NCDOT and USFWS if the amount or extent of incidental take specified in this Incidental Take Statement is exceeded during action implementation. | Green Sheet, June 2020 BO | All Sections | Design-Build Team, BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Monitoring and Reporting Requirements | Monitoring and Reporting Requirements | NCDOT will provide a final report and yearly bat monitoring summaries to the Service by January 31st of each year starting at the end of the bat monitoring season, and concluding up to two years after construction is completed. | Green Sheet, June 2020 BO | All Sections | BSG
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Gray Bat and Appalachian Elktoe | Reinitiation Notice | Reinitiation Notice | Formal consultation for the I-2513 project is concluded. Reinitiation of consultation is required by law if: a. the amount or extent of incidental take is exceeded i. Gray Bats: If construction operations at the bridges cannot be completed after five years from the start of causeway construction without night operations, or culvert system work cannot be completed after four seasons when bats are not present, or 60” CMP work cannot be complete after one season when bats are not present, all work should stop, and the USFWS should be contacted immediately to reinitiate consultation. ii. If a continuing NOV* is issued to NCDOT, the USFWS should be contacted immediately to determine if consultation should be reinitiated with the FHWA. *If severe problems are found that may result in loss of sediment into waterbodies or onto adjacent property owners, a Notice of Violation (NOV) is issued by NCDEQ-Energy Mineral and Land Resources to NCDOT. Consequently, NCDOT and its contractors will react immediately to correct items noted in the NOV. If deficiencies are not corrected within the timeframe directed by the Energy, Mineral and Land Resources NOV, a Continuing NOV will be issued. A Continuing NOV indicates that sufficient progress has not been made to correct environmental deficiencies on a project. b. new information reveals that the Action may affect listed species or designated critical habitat in a manner or to an extent not considered in this BO; c. the Action is modified in a manner that causes effects to listed species or designated critical habitat not considered in this BO; or d. a new species is listed or critical habitat designated that the action may affect. | Green Sheet, June 2020 BO | All Sections | BSG
| Conservation Recommendations | Conservation Recommendations | We recommend the FHWA and NCDOT works with the USFWS to determine how roost panels on bridges could be installed permanently (with the option to remove them temporarily for maintenance), contributing to the FHWA 7(a)(1) commitments to proactively work toward recovery of the gray bat. | June 2020 BO | All Sections | FHWA, BSG, USFWS
NCDOT- Environmental Analysis Unit: Biological Surveys- Endangered Species- Northern long-eared bat | Endangered Species- Northern long-eared bat | Avoidance and Minimization | The following avoidance and minimization measures have been proposed to minimize adverse effects of the proposed action on Northern long-eared bat (Myotis septentrionalis): a. No alterations of a known hibernacula entrance or interior environment if it impairs an essential behavioral pattern, including sheltering northern long-eared bats (January 1 through December 31); b. No tree removal within a 0.25-mile radius of a known hibernacula (January 1 through December 31); and c. No cutting or destroying a known, occupied maternity roost tree, or any other trees within a 150-foot radius from the known, occupied maternity tree during the period from June 1 through and including July 31. | Green Sheet | All Sections | Construction, BSG
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | NCDOT committed to addressing disproportionately high and adverse effects on the Burton Street community that cannot be avoided or minimized and is coordinating with the community to provide additional mitigation opportunities to lessen the burden of the project on these residents. The Burton Street Working Group is currently identifying how to implement the strategies identified in the 2018 Burton Street Neighborhood Plan, with certain goals and strategies requiring additional outreach and the engagement of Burton Street residents. NCDOT will carry out all activities for which it has been assigned responsibility in the plan. These include the following: | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve existing sidewalks to meet ADA design standards. | Green Sheet | Section B (Design-Build) | NCDOT
| Environmental Justice | Environmental Justice | Improve pedestrian connections between community resources by installing a sidewalk on Downing Street per agreement of property owners. | 2023 ROD | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve sidewalk connections between commercial corridors and include a pedestrian path from Buffalo Street to Patton Avenue that will connect to future greenway. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Evaluate opportunities for new transit stops, such as near Burton Street and Haywood Road. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Install a sidewalk along Patton Avenue to connect pedestrian path and transit stop. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Install bus shelters and other improvements at transit stops located near Burton Street. Consider neighborhood specific designs if feasible. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Incorporate a Burton Street history mural on proposed I-26 Connector sound wall if built. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve Community Center infrastructure by including additional parking. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Construct a new park and community gathering space at Smith Mill Creek that will include an access point to the future greenway. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Improve the Florida Avenue and Patton Avenue intersection by adding pavement markings and left turn signals. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Increase the tree canopy within the interstate buffer along the Burton Street neighborhood where possible. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | Although the Burton Street Neighborhood Plan indicates that the Community Baptist Church will be displaced, the project designs have since been refined to eliminate the need to relocate this property. Only a small portion of the parking lot is anticipated to be impacted, and the church will not need to be relocated. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | Environmental Justice | Environmental Justice | In order to further mitigate impacts associated with the project design in Section B, modifications have been made along Patton Avenue east of the French Broad River and adjacent to the Hillcrest Apartment community, an identified Environmental Justice community. A public meeting was held on February 15, 2022 with the residents of Hillcrest Apartments to show the proposed modifications and address any concerns from the residents. Modifications include additional sidewalk connectivity from Hillcrest to the realigned Hill Street, including a grassed berm to separate residents from Hill Street. Additionally, a pedestrian bridge is proposed at the entrance of the community to provide access across I-240 to Hill Street. A sidewalk is included on the southeast corner of the property to provide direct access by residents to Patton Avenue and the multi-use path along Patton Avenue. The existing pedestrian bridge east of the Jeff Bowen Bridges, south of Hillcrest is proposed to be removed and the existing pedestrian bridge south of the Isaac Dickson Elementary School is proposed to be replaced. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | Pursuant to Section 106 of the National Historic Preservation Act, the State Historic Preservation Office (HPO) concurred with NCDOT's determination that the project will have no adverse effect upon the following properties identified in or near the Area of Potential Effects (APE) that are already listed in or eligible for the National Register of Historic Places (NRHP): the Biltmore Estate, Buncombe County Bridge 216, Baker Building, the Montford Hills Historic District, and the Haywood Street United Methodist Church. Additionally, HPO concurred with the determination that the project will have no adverse effect upon the following properties provided the environmental commitments stipulated in a Memorandum of Agreement (MOA) are fulfilled: the Asheville School, West Asheville/Aycock School Historic District, Freeman House, the William Worley House, and the Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323). | Green Sheet | All Sections | N/A
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | HPO has concurred with NCDOT's determination that the project will have no adverse effect on one archaeological site (31BN623) identified in or near the APE that is already listed in or eligible for the NRHP, provided environmental commitments stipulated in the MOA are fulfilled. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | The Selected Alternative will have an adverse effect on Riverside Cemetery within the Montford Area Historic District and one archaeological site (31BN826). | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Cultural Resources | The MOA shall ensure stipulations are fulfilled for the two adversely effected properties, the five properties determined to have no adverse effect with commitments, and any determined eligible archaeological resource identified during further testing. Commitments included in the MOA are as follows: | Green Sheet | All Sections | N/A
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) | Riverside Cemetery within the Montford Area Historic District (BN0022): After consultation with the SHPO, the Asheville City Parks and Recreation Department, the Montford Neighborhood Association, the City of Asheville Transportation and Planning and Urban Design Departments, and the Preservation Society of Asheville and Buncombe County, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | a. Development of Vibration Monitoring Plan: NCDOT’s Geotechnical Engineering Unit, in consultation with NCDOT Division 13, shall develop a vibration monitoring plan for the Undertaking, to include on-site research during final design as well as monitoring during construction. The recommendations of the plan shall be provided to SHPO and concurring parties (except for the EBCI, CN, UKB, MCN, and Catawba Nation) for their comments prior to adoption. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | b. Baseline Studies: On-site research, done prior to construction, will measure existing vibration exposure, determine sensitivity of key funerary monuments and assign thresholds accordingly. | Green Sheet | Section B (Design-Build) | Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | c. Vibration Monitoring: Vibration monitoring will be conducted on key funerary monuments within Riverside Cemetery, recommended in the aforementioned vibration monitoring plan. When a reading exceeds the established threshold, an alarm will sound and the Contractor or the cemetery manager shall immediately contact NCDOT’s Division 13 Resident Engineer to assess the situation. | Green Sheet | Section B (Design-Build) | Design-Build Team, Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 1. Vibration Studies and Monitoring Plan | d. Pre-construction Surveys: NCDOT will conduct pre-construction surveys of all key funerary monuments within Riverside Cemetery to record a “before” condition so that any construction-related damage can be accurately identified. The City of Asheville shall identify the key funerary monuments to be included in the Vibration Monitoring Plan, pre-construction surveys and inventories noted above. | Green Sheet | Section B (Design-Build) | Geotechnical Engineering Unit
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | a. Design Noise Report: In accordance with the Department’s Traffic Noise Policy, NCDOT’s Design Build Team, shall complete a Design Noise Report for the Undertaking which includes recommendations for abatement measures for traffic noise impacts. If the Design Noise Report concludes that noise wall barriers along the boundaries of the Montford Historic District are preliminarily deemed to meet feasibility and reasonableness criteria then further consultation on the appearance of the barriers will be required with SHPO and the concurring parties. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | b. Pavement: NCDOT is not proposing pavement as a noise abatement for this project, however, in accordance with all design standards/criteria, NCDOT elects to use low noise pavement surface treatments for any concrete and/or asphalt surfaces and minimize the number of joints on the roadway structures in the vicinity of Riverside Cemetery. NCDOT cannot commit to the utilization of these specific surface treatments in perpetuity or to maintenance schedules that keep the auditory qualities of these lower noise pavement designs at their premium. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 2. Auditory Effects | c. Memorandum of Understanding: NCDOT’s Division 13 will develop a Memorandum of Understanding (MOU) with the Asheville City Parks and Recreation Department to outline how the city will notify NCDOT of funerals. Protocols will be established to limit construction noise during such events. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | a. Pre-Construction Tree Survey: It is understood that all existing vegetation and trees within the highway right-of-way parallel to the Riverside Cemetery will likely be removed during construction. To mitigate these impacts along the Riverside Cemetery boundary, NCDOT’s Design-Build Team shall conduct a tree survey of existing trees exceeding 6.0” diameter that are targeted for removal within the existing highway Right-Of-Way, will remain in the existing highway Right-Of-Way, or are within the Riverside Cemetery that their root system may be impacted during construction. The Design-Build Team’s survey shall include in its documentation, but not be limited to the following information: 1) tree species and measurements (DBH, canopy width, and height), 2) approximate age, and 3) overall health/life expectancy, and 4) potential construction impacts, as well as management recommendations for trees adjacent to the highway Right-Of-Way that may be impacted. The recommendation may include, but not limited to, additional fertilization, pruning or overall removal and replacement. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | b. Planting within highway Right-Of-Way: Re-vegetation of the highway right-of-way parallel to the cemetery boundary will be planned and implemented in accordance with NCDOT’s Guidelines for Planting within Highway Right-of-Way. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | c. Planting within highway Right-Of-Way will be congruent with existing vegetation and trees along the Riverside Cemetery boundary. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | d. Replacement of Trees: If trees within Riverside Cemetery are damaged due to construction within the highway Right-Of-Way then NCDOT will follow the management recommendations in the pre-construction tree survey (additional fertilization, pruning, or overall removal and replacement). Replacement of trees will follow Asheville’s Code of Ordinances Section 7-11-13 (landscape & buffering standards) and Appendix 7-C (recommended species list). All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 3. Right-of-way | e. Right-Of-Way Fence: The fence that marks the highway Right-Of-Way parallel to the cemetery boundary will be a black metal fence that is approved by the Asheville City Parks and Recreation Department, the SHPO, and NCDOT. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | a. Additional areas of concentrated landscaping will be included within the boundaries of Riverside Cemetery adjacent to the highway and will be developed through consultation with the Asheville City Parks and Recreation Department, SHPO, and other concurring parties. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | b. Landscaping will follow Asheville’s Code of Ordinances Section 7-11-13 (landscape & buffering standards) and Appendix 7-C (recommended species list). All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | c. Preliminary Post-Construction Landscape Design plans will be provided to SHPO, the Asheville City Parks and Recreation Department, and the concurring parties for their review and comment. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 4. Landscaping within Riverside Cemetery | d. NCDOT (or its contractor) shall install the landscaping after completion of roadway construction work along the historic boundary of the cemetery. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | a. In accordance with all design standards / criteria, NCDOT’s Design-Build Team will be encouraged to modify the Department’s preliminary design in proximity to the Riverside Cemetery. Specifically, along the Cemetery boundary, the Design-Build Team will be encouraged to lower the US 19/US 23/US 70 roadway and shift the facility westward without incorporating design exceptions or increasing right of way impacts or relocatees. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | b. The retaining wall will be designed to extend along the entire Riverside Cemetery boundary adjacent to the proposed project. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 5. Roadway Design and Appearance | c. The appearance of the retaining walls along the cemetery’s boundary will be formed concrete walls with a simulated masonry surface treatment. The surface treatment will be designed to resemble stacked stone walls and may be painted, stained, or tinted. Choices of aesthetic wall treatments will be provided to SHPO, the Asheville Transportation Department, the Asheville City Parks and Recreation Department, and the concurring parties for their review and comment prior to final approval. The preferred surface texture and color will be included in NCDOT’s final design. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 6. Roadway Lighting | Roadway lighting will be designed and constructed to minimize the dispersion of light (“spillover”) beyond the highway Right-Of-Way. NCDOT will not install high mast poles adjacent to the cemetery. Instead NCDOT will install single pole, shoulder and/or barrier mounted, lighting with LED illumination in this area. | Green Sheet | Section B (Design-Build) | Lighting Design Plans are done by the Department
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | The transmission lines currently on Courtland Place will be rerouted northwest to a point near the southwest boundary of Riverside Cemetery and US 19/US 70. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | a. A 70-foot Permanent Utility Easement (PUE) will be cleared of trees and a single pole erected to hold the lines. Duke Energy will erect the shortest pole that meets the needs of the line in this location. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Riverside Cemetery within the Montford Area Historic District (BN0022) - 7. Duke Energy Line Relocation | b. Prior to construction Duke Energy will flag any “danger trees” located outside the 70-foot PUE that are adjacent to or within the boundaries of the cemetery. If any “danger trees” exist, Duke Energy will consult with NCDOT, SHPO and the Asheville City Parks and Recreation Department prior to any removal of the “danger trees” and will prioritize tree trimming over removal and replacement. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) | After consultation with the SHPO and the property owner, NCDOT agrees to lessen the audible and visual impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) - 1. Noise Abatement | Upon satisfactory completion of the work, NCDOT will reimburse the property owner for the costs to install central heat/AC, storm windows, and insulation based on the lowest of 3 bids provided to NCDOT by the property owner. If the property owner chooses, NCDOT will make payment directly to a third-party contractor(s). | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Freeman House (BN2470) - 2. Landscaping | NCDOT (or its contractor) shall install landscaping along the edges of the property facing the new facility after completion of the project. All new plant materials will be warranted for three growing seasons and replaced by NCDOT if they fail within that time period. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) | After consultation with the SHPO and the property owner, NCDOT agrees to lessen the audible and property impacts resulting from the Undertaking by providing funding or services for the following measures | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) - 1. Noise Abatement | Upon satisfactory completion of the work, NCDOT will reimburse the property owner for the costs to install central heat/AC, storm windows, and insulation based on the lowest of 3 bids provided to NCDOT by the property owner. If the property owner chooses, NCDOT will make payment directly to a third-party contractor(s). | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | William Worley House (BN2442) - 2. Retaining Wall | NCDOT will install a retaining wall, with permanent underground easements, within the property boundary along the western boundary of the property to reduce right-of-way impacts. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) | After consultation with the SHPO, the principal of Aycock School, and the Asheville School District Superintendent, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing funding or services for the following measures. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 1. Parking | To minimize Aycock’s School’s loss of parking spaces, NCDOT has agreed to provide the school with new parking lots and vehicular circulation routes as shown on the plans provided to SHPO on October 7, 2019. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 2. Trees | NCDOT will preserve the screening trees along the west side of classrooms by erecting temporary fencing around the trees and tree protection signs, during construction. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 3. Fencing | NCDOT will install permanent fencing (a minimum of 6 feet in height and of the school’s chosen materials) between the Greenway and the west side of the school yard. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | West Asheville/Aycock School Historic District (BN1839) - 4. Protection Measures | NCDOT will protect the trees and Arrowhead monument on school grounds along Haywood Road by erecting tree protection signs and temporary fencing around the trees and monument, during construction. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | After consultation with the SHPO and the Asheville Aesthetics Advisory Committee, NCDOT agrees to remove the cantilevered sidewalk and convert the bridge to a two-lane facility with a minimum 10-foot sidewalk on the existing deck. The existing bridge rails and pedestrian lights will be replaced with designs that meet current safety standards and are congruent with the original “art modern” style of the bridge. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 1. The SHPO concurred in a letter dated June 19, 2020 that the subject undertaking will not adversely affect the bridge. Any changes to the bridge concepts after the execution of this MOA, as shown in the renderings appended to this document, shall require approval from NCDOT structure design and the SHPO. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 2. Any repairs to the historic substructure shall follow the Secretary of the Interior’s Standards for Rehabilitation. | Green Sheet | Section B (Design-Build) | Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Great Smoky Mountain Park Bridge (Buncombe County Bridge No. 323) (BN2469 - Patton Avenue Westbound) | 3. Additional streetscape enhancements such as benches, planters, ornamental lights, or flags shall require approval from NCDOT structure design and the SHPO. | Green Sheet | Section B (Design-Build) | NCDOT, Design-Build Team
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | After consultation with the SHPO, NCDOT agrees to lessen the property impacts resulting from the Undertaking by providing services for the following measures. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | 1. Iron markers will be placed at each end of a wall associated with site 31BN623 to mark its extent prior to the placement of fill within the project limits. The exact locations of the markers will be provided to the SHPO for its records. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Archaeological Site 31BN623 (Lower Hominy Hydroelectric Plant) | 2. Any changes in the vicinity of 31BN623 to the preferred alternative preliminary design after the execution of this MOA shall require approval from the SHPO. | Green Sheet | Section A | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 1. In consultation with the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation NCDOT will develop a Data Recovery Plan (DRP) for Site 31BN826, which has been determined eligible for the NRHP and will be affected by the Undertaking. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 2. If Sites 31BN823, 31BN868, 31BN870, 31BN871, 31BN873 and any new sites are determined eligible for the NRHP through further testing and affected by the Undertaking, NCDOT, in consultation with the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation, will develop, separate DRPs for those sites. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 3. NCDOT will ensure that the DRPs, are implemented after the highway Right-Of-Way is acquired and prior to construction activities within the site location. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 4. Upon completion of the Data Recovery efforts, NCDOT will prepare and forward a Management Summary to the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation detailing the results of the Data Recovery efforts for all the eligible sites. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 5. Upon receipt of the Management Summary, the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation will respond within fifteen (15) days to the recommendations contained within the Management Summary. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 6. Upon acceptance of the recommendations contained in the Management Summary, the SHPO, EBCI, CN, UKB, MCN, and Catawba Nation will issue NCDOT documentation that the Data Recovery field investigations have been completed. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Data Recovery at Archaeological Site 31BN826 and Further Deep Testing at Archaeological Sites 31BN823, 31BN826, 31BN868, 31BN870, 31BN871, 31BN873 and 22 Additional Acres | 7. The analysis and report preparation, detailing the eligible sites, will be completed by NCDOT, or their consultant(s), within eighteen (18) months after completion of the fieldwork. | Green Sheet | Section B (Design-Build) | NCDOT
NCDOT- Environmental Analysis Unit: Cultural Resources | Cultural Resources | Unanticipated Discoveries | In accordance with 36 CFR 800.11(a), if NCDOT identifies additional cultural resource(s) during construction, all work will be halted within the limits of the resource(s) and the FHWA and the SHPO will be contacted. The NCDOT and FHWA will initiate the appropriate agency and/or Tribal coordination required for a determination of eligibility or recovery effort. If after consultation between the Signatories and concurring parties, additional mitigation is determined necessary, the NCDOT, in consultation with the Signatories and concurring parties, will develop and implement appropriate protection/mitigation measures for the resource(s). Inadvertent or accidental discovery of human remains will be handled in accordance with North Carolina General Statutes 65 and 70. | Green Sheet | All Sections | Design-Build Team, Construction
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | The City of Asheville has requested the inclusion of bicycle and pedestrian betterments in the project design. The construction of the betterments as part of the proposed project will be dependent upon a municipal agreement between NCDOT and the City of Asheville. NCDOT will continue to coordinate with the City of Asheville on the inclusion of bicycle and pedestrian facilities. | Green Sheet | All Sections | PMU, NCDOT
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | The City of Asheville has established an Aesthetics Committee (AC) to work in an advisory capacity to address aesthetic treatments that may be incorporated in the proposed project, dependent upon a municipal agreement between NCDOT and the City of Asheville. NCDOT will continue working with the City to ensure that the agreed upon aesthetic improvements are incorporated into the project. | Green Sheet | All Sections | PMU, NCDOT,
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | NCDOT will coordinate with the City of Asheville regarding maintenance of traffic on the French Broad River Greenway during development of final plans for the project. | Green Sheet | Section A, Section B (Design-Build), Section C | PMU
NCDOT- Project Management Unit | City of Asheville Coordination | City of Asheville Coordination | NCDOT is committed to minimizing the overall footprint of the project to the extent practicable and will continue to work with the I-26 Working Group to improve designs prior to the Design- Build procurement. | Green Sheet | All Sections | PMU
NCDOT- Environmental Analysis Unit: Public Involvement, Community Studies & Visualization | River User Safety | River User Safety | NCDOT has developed a communication plan for construction of the project, and NCDOT and its contractors will work with river users, businesses, and recreational river and civic groups to insure public notification of hazards and temporary closures during construction. | Green Sheet | All Sections | Construction, Design-Build Team
NCDOT- Hydraulics Unit | Hydraulics | Hydraulics | The NCDOT Hydraulics Unit will coordinate with the NC Floodplain Mapping Program to determine the status of the project with regard to the applicability of NCDOT’s Memorandum of Agreement or approval of a Conditional Letter of Map Revision (CLOMR) and subsequent final Letter of Map Revision (LOMR). | Green Sheet | All Sections | NCDOT Hydraulics Unit
NCDOT- Hydraulics Unit | Hydraulics | Hydraulics Unit | The Division shall submit sealed as-built construction plans to the Hydraulics Unit upon completion of project construction, certifying that the drainage structures and roadway embankments that are located within 100-year floodplains were built as shown in the construction plans, both horizontally and vertically. | Green Sheet | All Sections | Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | Unless otherwise authorized, placement of culverts and other structures in waters and streams shall be placed below the elevation of the streambed by one foot for all culverts with a diameter greater than 48 inches, and 20 percent of the culvert diameter for culverts having a diameter less than 48 inches, to allow low flow passage of water and aquatic life. Design and placement of culverts and other structures including temporary erosion control measures shall not be conducted in a manner that may result in dis-equilibrium of wetlands or streambeds or banks, adjacent to or upstream and downstream of the above structures. The applicant is required to provide evidence that the equilibrium is being maintained if requested in writing by the NCDWR. If this condition is unable to be met due to bedrock or other limiting features encountered during construction, please contact the NCDWR for guidance on how to proceed and to determine whether or not a permit modification will be required. | 401 Permit | All Sections | Design-Build Team, NCDOT
|  | Hydraulics Unit | If multiple pipes or barrels are required, they shall be designed to mimic natural stream cross section as closely as possible including pipes or barrels at flood plain elevation, floodplain benches, and/or sills may be required where appropriate. Widening the stream channel should be avoided. Stream channel widening at the inlet or outlet end of structures typically decrease water velocity causing sediment deposition that requires increased maintenance and disrupts aquatic life passage. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | Hydraulics Unit | An erosion and sedimentation control plan will be provided during the final design stage. Best management practices to minimize sedimentation and erosion impacts during construction shall be adhered to, in accordance with the most recent version of North Carolina Sediment and Erosion Control Planning and Design Manual and the most recent version of NCS000250. | 2023 ROD | All Sections | Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | If concrete is used during construction, a dry work area shall be maintained to prevent direct contact between curing concrete and stream water. Water that inadvertently contacts uncured concrete shall not be discharged to surface waters due to the potential for elevated pH and possible aquatic life and fish kills. Concrete shall be handled in accordance with the NPDES Construction General Permit NCG010000. | 401 Permit | All Sections | Construction, Design-Build Team
|  | Hydraulics Unit | As part of the Highway Stormwater Program, NCDOT will develop and implement numerous programs on a statewide basis to protect and promote stormwater quality impacted by NCDOT discharges. Programs will be developed to ensure compliance with the National Pollutant Discharge Elimination System (NPDES) permit. NCDOT will incorporate measures to control nonpoint source water quality impacts as described in Best Management Practices for Protection of Surface Waters (NCDOT 1997) and in NCDOT Stormwater Best Management Practices (NCDOT 2014d). | 2023 ROD | All Sections | Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | Hydraulics Unit | Heavy equipment should be operated from the bank rather than in stream channels in order to minimize sedimentation and reduce the likelihood of introducing other pollutants into streams. This equipment shall be inspected daily and maintained to prevent contamination of surface waters from leaking fuels, lubricants, hydraulic fluids, or other toxic materials. | 401 Permit | All Sections | Construction, Design-Build Team
|  | Hydraulics Unit | Riprap shall not be placed in the active thalweg channel or placed in the streambed in a manner that precludes aquatic life passage. Bioengineering boulders or structures should be properly designed, sized and installed. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Hydraulics Unit | Plans and specifications for the construction, expansion, or alternation of a public water system must be approved by the Division of Water Resources/Public Water Supply Section prior to the award of a contract or the initiation of construction as per 15A NCAC 18C. 0300 et. seq., Plans and specifications should be submitted to 1634 Mail Service Center Raleigh, North Carolina 27699-1634. All public water supply systems must comply with state and federal drinking water monitoring requirements. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | Hydraulics Unit | If existing water lines will be relocated during construction, plans for the water line relocation must be submitted to the Division of Water Resources/Public Water Supply Section at 1634 Mail Service Center Raleigh, North Carolina 27699-1634. | 2023 ROD | All Sections | Design-Build Team
NCDOT- Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | The recommended lane changes that improve operations at the Acton Circle and Smokey Park Highway intersection will be included in final design. | Green Sheet | Section A | NCDOT
NCDOT- Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | Traffic Management Unit: Congestion Management | NCDOT has secured a preliminary safety, operational, and engineering acceptability determination by the FHWA-Headquarters office. An Interstate Access Report (IAR) was submitted to the Federal Highway Administration (FHWA) on September 21, 2021. Final approval will be given after the ROD is signed given the selected alternative is consistent with the IAR. | Green Sheet | All Sections | NCDOT
|  | ECAP | Riparian vegetation (native trees and shrubs) shall be preserved to the maximum extent possible. Riparian vegetation must be reestablished within the construction limits of the project by the end of the growing season following completion of construction. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | ECAP | NCDOT will manage invasive plant species on the Department’s right-of-way, as appropriate. |  | All Sections | Design-Build Team, NCDOT
|  | ECAP | If Temporary access roads or detours are constructed, the site shall be graded to its preconstruction contours and elevations. Disturbed areas shall be seeded or mulched to stabilize the soil and appropriate native woody species shall be planted. When using temporary structures, the area shall be cleared but not grubbed. Clearing the area with chainsaws, movers, bush-hogs, or other mechanized equipment and leaving the stumps and root mat intact allows the area to re-vegetate naturally and minimizes soil disturbance. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Solid Waste | During construction, every feasible effort will be made to minimize the generation of waste, to recycle materials for which viable markets exist, and to use recycled products and materials in the development of the project where suitable. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Solid Waste | Any wastes generated by this project that cannot be beneficially reused or recycled must also be disposed of at a solid waste management facility approved to manage the respective waste type. The Section strongly recommends that any contractors are required to provide proof of proper disposal for all waste generated as part of the project. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Solid Waste | Any hazardous waste generated from the demolition, contraction, operation, maintenance, and/or remediation (e.g. excavated soil) from the proposed project must be managed in accordance with the North Carolina Hazardous Waste Rules. The demolition, construction, operation, maintenance and remediation activities conducted will most likely generate a solid waste, and a determination must be made whether it is a hazardous waste. If a project site generates more than 220 pounds of hazardous waste in a calendar month, the HWS must be notified, and the site must comply with the small amount quantity generator (SQG) requirements. If a project site generates more than 2200 pounds of hazardous waste in a calendar month, the HWS must be notified and the facility must comply with the large quantity generator (LQG) requirements. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Solid Waste | Notification of the proper regional office is requested if “orphan” underground storage tanks (USTS) are discovered during any excavation operation. | 2023 ROD | All Sections | Construction, Design-Build Team
NCDOT- Geotechnical Engineering Unit | Geotechnical Engineering Unit: Hazardous Materials | Geotechnical Engineering Unit: Hazardous Materials | A work plan based on final designs will be developed for the landfill site along Riverside Drive to address any contaminated material that may be encountered during construction. Commitments during construction are included in the Preliminary Site Assessment Report (GEL 2019). | Green Sheet | Section D | Design-Build Team
NCDOT- Geotechnical Engineering Unit | Geotechnical Engineering Unit: Hazardous Materials | Geotechnical Engineering Unit: Hazardous Materials | As part of the work plan, an environmental professional will be present during construction to screen for potentially hazardous conditions and to assess excavated materials for proper handling. | Green Sheet | All Sections | Design-Build Team, NCDOT
|  | Geotechnical Engineering Unit: Hazardous Materials | The Asheville Regional Office (ARO) UST Section recommends removal of any abandoned or out-of-use petroleum USTs or Petroleum ASTs within the project area. The UST Section should be contacted regarding use of any proposed or on-site petroleum USTs or ASTs. We may be reached at (828) 296-4500. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Hazardous Materials | Any petroleum USTs or ASTs must be installed and maintained in accordance with applicable local, state, and federal regulations. For additional information on petroleum ASTs it is advisable that the North Carolina Department of Insurance at (919)661-5880 ext. 239, USEPA (404) 562- 8761, local fire department and Local Building Inspectors be contacted. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | Geotechnical Engineering Unit: Hazardous Materials | Any petroleum spills must be contained, and the area of impact must be properly restored. Petroleum spills of significant quantity must be reported to the North Carolina Department of Environmental Quality(NCDEQ) – Division of Waste Management (DWM) UST Section in the ARO. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Hazardous Materials | Any soils excavated during demolition or construction that show evidence of petroleum contamination, such as stained soil, odors, or free product must be reported immediately to the local Fire Marshall to determine whether explosive or inhalation hazards exist. Also, notify the UST Section of the ARO. Petroleum contaminated soils must be handled in accordance with all applicable regulations. | 2023 ROD | All Sections | Construction, Design-Build Team
|  | Geotechnical Engineering Unit: Hazardous Materials | Generators are required to determine their generator status and both SQGs & LQGs are required to obtain a site EPA Identification number for the generation of hazardous waste. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | Geotechnical Engineering Unit: Hazardous Materials | Abandonment of any wells, if required must be in accordance with Title 15A. Subchapter 2C.0100. | 2023 ROD | All Sections | Design-Build Team, NCDOT
|  | NLEB Avoidance and Minimization Measures - Lighting | When installing new or replacing existing permanent lights, use downward-facing, full cut-off lens lights (with same intensity or less for replacement lighting); or for those transportation agencies using the BUG system developed by the Illuminating Engineering Society, be as close to 0 for all three ratings with a priority of "uplight" of 0 and "backlight" as low as practicable. |  | All Sections | Construction, Design-Build Team
|  | NLEB Avoidance and Minimization Measures - Tree Removal | Ensure tree removal is limited to that specified in project plans and ensure that contractors understand clearing limits and how they are marked in the field (e.g., install bright colored flagging/fencing prior to any tree clearing to ensure contractors stay within clearing limits). |  | All Sections | Construction, Design-Build Team
|  | NLEB Avoidance and Minimization Measures - General | Ensure all operators, employees, and contractors working in areas of known or presumed bat habitat are aware of all FHWA/FRA/FTA (Transportation Agencies) environmental commitments, including all applicable AMMs. |  | All Sections | Construction, Design-Build Team
|  | NLEB Avoidance and Minimization Measures - Hibernacula | For projects located within karst areas, on-site personnel will use best management practices, secondary containment measures, or other standard spill prevention and countermeasures to avoid impacts to possible hibernacula. Where practicable, a 300 foot buffer will be employed to separate fueling areas and other major containment risk activities from caves, sinkholes, losing streams, and springs in karst topography. |  | All Sections | Construction, Design-Build Team
|  | NLEB Avoidance and Minimization Measures - Tree Removal | Modify all phases/aspects of the project (e.g., temporary work areas, alignments) to avoid tree removal. |  | All Sections | Construction, Design-Build Team
|  | NLEB Avoidance and Minimization Measures - Lighting | Direct temporary lighting away from suitable habitat during the active season. |  | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | The NCDOT Division Environmental Officer or Environmental Assistant will conduct a pre-construction meeting with all appropriate staff to ensure that the project supervisor and essential staff understand the potential issues with stream and pipe alignment at the permitted site. NCDWR staff shall be invited to the pre-construction meeting. [15A NCAC 02H.0506(b)(2) and (b)(3)] | Green Sheet, 401 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | Compensatory mitigation for 1. 11 acres of wetland is required. We understand that you have chosen to perform compensatory mitigation for impacts to streams and wetlands through the North Carolina Division of Mitigation Service (DMS) (formerly NCEEP), and that the DMS has agreed to implement the mitigation for the project. The DMS has indicated in letters dated August 15, 2023, that they will assume responsibility for satisfying the federal Clean Water Act compensatory mitigation requirements for the above-referenced project, in accordance with the DMS Mitigation Banking Instrument signed July 28, 2010. [15A NCAC 02H .0506 (c)] | Green Sheet, 401 Permit | All Sections | NCDOT , NCDMS
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | The Permittee shall comply with all applicable measures for Appalachian Elktoe detailed under the Project Commitments in the Record of Decision dated May 2023. [15A NCAC 02B .0211(1)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | Bridge deck drains shall not discharge directly into the stream. Stormwater shall be directed across the bridge and pre-treated through site-appropriate means (grassed swales, pre-formed scour holes, vegetated buffers, etc.) before entering the stream. To meet the requirements ofNCDOT's NPDES permit NCS000250, please refer to the most recent version of the North Carolina Department of Transportation Stormwater Best Management Practices Toolbox manual for approved measures. [15A NCAC 02H .0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | As a condition of this 401 Water Quality Certification, the bridge demolition and construction must be accomplished in strict compliance with the most recent version ofNCDOT's Best Management Practices for Construction and Maintenance Activities. [15A NCAC02H .0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | If multiple pipes or barrels are required, they shall be designed to mimic natural stream cross section as closely as possible including pipes or barrels at flood plain elevation and/or sills where appropriate. Widening the stream channel should be avoided. Stream channel widening at the inlet or outlet end of structures typically decreases water velocity causing sediment deposition that requires increased maintenance and disrupts aquatic life passage. [15A NCAC 02H.0506(b)(2)] | Green Sheet, 401 Permit | All Sections | Design-Build Team, NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from 401 Water Quality Certification | Special Conditions from 401 Water Quality Certification | When final design plans are completed for 1-2513 Sections B, C, and D, a modification to the 401 Water Quality Certification shall be submitted to the NC Division of Water Resources. Final designs shall reflect all appropriate avoidance, minimization, and mitigation for impacts to wetlands, streams, and other surface waters. No construction activities that impact any wetlands, streams, or surface waters located in 1-2513 Sections B, C, and D shall begin until after the permittee applies for, and receives a written modification of the 401 Water Quality Certification from the NC Division ofWater Resources. | Green Sheet, 401 Permit | Section B, Section C, Section D | Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | During the construction of the project, no staging of equipment of any kind is permitted in waters of the U.S. or protected riparian buffers. [15 A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The dimension, pattern, and profile of the stream above and below the crossing shall not be modified. Disturbed floodplains and streams shall be restored to natural geomorphic conditions. [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The use of rip-rap above Normal High Water Mark shall be minimized. Any rip-rap placed for stream stabilization shall be placed in stream channels in such a manner that it does not impede aquatic life passage [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The Permittee shall ensure that the final design drawings adhere to the permit and to the permit drawings submitted for approval. [15A NCAC 02H .0507 (c ) and 15A NCAC 02H .0506 (b)(2) and (c )(2)] | 401 Permit | All Sections | NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All work in or adjacent to stream waters shall be conducted in a dry work area. Approved BMP measures from the most current version of NCDOT Construction and Maintenance Activities manual such as sandbags, rock berms, cofferdams and other diversion structures shall be used to prevent excavation in flowing water. [15A NCAC 02H.0506(b)(3) and (c )(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All mechanized equipment operated near surface waters must be regularly inspected and maintained to prevent contamination of stream waters from fuels, lubricants, hydraulic fluids, or other toxic materials. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | No rock, sand or other materials shall be dredged from the stream channel except where authorized by this certification. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Discharging hydroseed mixtures and washing out hydro seeders and other equipment in or adjacent to surface waters in iprohibited. [15A NCAC 02H.0506(b)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The permittee and its authorized agents shall conduct its activities in a manner consistent with State water quality standards (including any requirements resulting from compliance with 303(d) of the Clean Water Act) and any other appropiate requirements of State and Federal law. if the NCDWR determines that such standards or laws are not being met (including the failure to sustain an designated or achieved use) or the State or federal law is being violated, ot that further conditions are necessary to assure compliance, the NCDWR may reevaluate and modify this certification [15A NCAC 02B.0200] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | All fill slopes located in jurisdictional wetlalnds shall be placed at slopes no flatter than 3:1, unless otherwise authorized by this certification. [15A NCAC 02H.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | A copy of this Water Quality Certification shall be maintained on the constructioin site at all times. In addition, the Water Quality Certification and all subsequent modifications, if any, shall be maintained with the on-site project manager. [15A NCAC 02H.0507(c ) and a5A NCAC 02H .0506 (b)(2) and (C )(2) | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The outside buffer, wetland or water boundary located within the construction corridor approved by this authorization shall be clearly marked by highly visible fencing prior to any land disturbing activities. Impacts to areas within the fencing are prohibited unless otherwise authorized by this certification. [15A NCAC 02H.0501 and .0502] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The issuance of this certification does not exempt the Permittee from complying with any and all statutes, rules, regulations, or ordinances that may be imposed by other government agencies (i.e. locan, state, and federal) having jurisdiction, including but not limited to applicable buffer rules, stormwater management rules, soil erosion and sedimentation control requirements, etc. | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | The Permittee shall report any violations of this vertification to the Division of Water Resources within 24 hours of discovery. [15A NCAC 02B.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Upon completion of the project (including any impacts at associated borrow or waste sites), the Permittee shall complete and return the enclosed "Certification of Completion Form" to notify the NCDWR when all work included in the 401 Certification has eben completed. [15A NCAC 02H.0502(f)] | 401 Permit | All Sections | Construction, Design-Build Team, NCDOT
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Native riparian vegetaion must be reestablished in the riparian areas within the construction limits of the project by the end of the growing season following completion of construction. [15A NCAC 02B.0506(b)(2)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | There shall be no excavation from, or waste disposal into, jurisdictional wetlands or waters associated with this permit without appropiate modification. Should waste or borrow sites, or access roads to waste or borrow sites, be located inwetlands or streams, compensatory mitigation will be required since that is a direct impact from road construction activities. [15A NCAC 02H.0506(b)(3) and (c)(3)] | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Erosion and sediment control practices must be in full compliance with all specifications governing the proper design, installation and operation and maintenance of such Best Management Practices in order to protect surface waters standarts [15A NCAC 02H.0506(b)(3) and (c)(3)]: a. The erosion and sediment control measures for the project must be designed, installed, operated, and maintained in accordance with the most recent version of the North Carolina Sediment and Erosion Control Planning and Design Manual. B. The design, installation, operation, and maintenance of the sediment and erosion control measures must be such that they equal, or exeed, the requirements specified in the most recent version of the North Carolina Sediment and Erosion Control Manual. The devices shall be maintained on all construction sites, borrow sites, and waste pile (spoil) projects, including contractor-owned or leased borrow pits associated with the project. C. For borrow pit sires, the erosion and sediment control measures must be designed, installed, operated, and maintained in accordance with the most recent version of the North Carolina Surface Mining Manual. D. The reclamation measures and implementation must comply with the reclamation in accordance with the requirements of the Sedimentation pollution Control Act. | 401 Permit | All Sections | Construction, Design-Build Team
401 Permit: General Conditions | 401 Permit: General Conditions | General Conditions from 401 Water Quality Certification | Sediment and erosion control measures shall not be placed in wetlands or waters unless otherwise approved by this Certification. [15A NCAC 02H.0506(b)(3) and ©(3)] | 401 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | 1) The entire 7 mile project is identified as STIP I-2513. This permit only authorizes work on Sections I-2513 AA, AB, and AC of STIP I-2513, also known as “Phase 1” for permitting purposes. Construction on the remaining sections/phases of the I-2513 project (i.e., Sections I-2513 B, I-2513 C, and I-2513 D) shall not commence until: (a) final design for those sections/phases has been completed and submitted to the U.S. Army Corps of Engineers (Corps); (b) the Permittee has minimized impacts to waters and wetlands to the maximum extent practicable for those sections/phases and the Corps concurs with this assessment through standard Merger 4B and 4C meetings; (c) any modification(s) to the permit plans for those sections/phases have been approved by the Corps in writing; (d) NCDOT submits final versions of the Bridge Construction and Demolition Plan, River User Safety Plan, and Strategic Communication Plan that adequately address the Corps’ Public Interest Review Factors (to include recreation, safety, navigation, and flood hazards); and (e) a final compensatory mitigation plan for those sections/phases has been submitted by the Permittee and approved by the Corps. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team, NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | All work authorized by this permit shall be performed in strict compliance with the following: The description of work in the revised application dated August 17, 2023. All information submitted in response to the Corps’ requests for additional information. All final environmental commitments that NCDOT has agreed to, to include (but not limited to) the Biological Opinion (BO) and the Amended BO and Conference Opinion (special condition #14 of this permit), and the Section 106 Memorandum of Agreement (special condition #15 of this permit). The attached permit plans titled (1) “I-2513AA/AB”, Permit Drawings Sheets 1- 26, and (2) “I-2513AC”, Permit Drawings Sheets 1-36. The Permittee shall ensure that the construction design plans for this project do not deviate from the approved permit plans referenced above. Any modification to the approved permit plans must be approved by the U.S. Army Corps of Engineers prior to any active construction in waters or wetlands. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team, NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Unauthorized Dredge and/or Fill: Except as authorized by this permit or any U.S. Army Corps of Engineers approved modification to this permit, no excavation, fill, or mechanized land-clearing activities shall take place at any time in the construction or maintenance of this project, within waters or wetlands, nor shall any activities take place that cause the degradation of waters or wetlands. There shall be no excavation from, waste disposal into, or degradation of, jurisdictional wetlands or waters associated with this permit without appropriate modification of this permit, including appropriate compensatory mitigation. This prohibition applies to all borrow and waste activities connected with this project. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Maintain Flows and Circulation Patterns of Waters: Except as specified in the approved permit plans referenced above, no excavation, fill or mechanized land- clearing activities shall take place at any time in the construction or maintenance of this project in such a manner as to impair normal flows and circulation patterns within, into, or out of waters or wetlands, or to reduce the reach of waters or wetlands. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Work Limits | Permit Distribution: The Permittee shall require its contractors and/or agents to comply with the terms and conditions of this permit in the construction and maintenance of this project, and shall provide each of its contractors and/or agents associated with the construction or maintenance of this project with a copy of this permit. A copy of this permit, including all conditions, drawings and attachments shall be available at the project site during the construction and maintenance of this project. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Pre-Construction Meeting: The Permittee shall schedule a pre-construction meeting between their representatives, the contractor, and the U.S. Army Corps of Engineers (Corps), Wilmington District, NCDOT Regulatory Project Manager for Division 13, prior to conducting any work in jurisdictional waters of the U.S. to ensure that there is a mutual understanding of all terms and conditions contained in this Department of the Army permit. To schedule this preconstruction meeting, the Permittee shall poll, at least two weeks ahead of any proposed meeting date, the representatives from the Corps and the North Carolina Division of Water Resources as to their availability; this poll shall include multiple potential dates and times for the preconstruction meeting. If other special conditions of this permit require other agency representatives (e.g., U.S. Fish and Wildlife Service, North Carolina Wildlife Resources Commission, etc.) to be invited to the preconstruction meeting, NCDOT shall include those agency representatives in the poll and shall schedule the meeting when all required agency representatives can attend the meeting. To determine if other agency representatives must be included in the poll for the preconstruction meeting, NCDOT shall review all other special conditions of the permit, to include all referenced documents, letters, correspondence, etc. The Permittee shall provide the Corps and all other required agency representatives with a copy of the final permit plans (if different than the approved permit plans referenced above) at least two weeks prior to the preconstruction meeting along with a description of any changes that have been made to the project’s design,construction methodology or construction timeframe. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Notification of Construction Commencement and Completion: The Permittee shall advise the U.S. Army Corps of Engineers in writing at least two (2) weeks prior to beginning the work authorized by this permit and again upon completion of the work authorized by this permit. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Reporting Address: All reports, documentation, and correspondence required by the conditions of this permit shall be submitted to the following: U.S. Army Corps of Engineers, Wilmington District Asheville Regulatory Field Office, Attn: Lori Beckwith, 151 Patton Ave., Room 208, Asheville, NC 28801-5006, or by email to loretta.a.beckwith@usace.army.mil . The Permittee shall reference the following permit number on all submittals: SAW-2004-9986803, STIP Project No. I-2513. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Reporting Violations: Violation of these permit conditions or violation of Section 404 of the Clean Water Act shall be reported to the U.S. Army Corps of Engineers by email to loretta.a.beckwith@usace.army.mil and by telephone at 828-230-0483, or 828-271- 7980 (Asheville Office general number), within 24 hours of the Permittee’s discovery ofthe violation. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Notifications | Permit Revocation: The Permittee, upon receipt of a notice of revocation of this permit or upon its expiration before completion of the work will, without expense to the United States and in such time and manner as the Secretary of the Army or his authorized representative may direct, restore the water or wetland to its pre-project condition. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Clean Fill: The Permittee shall use only clean fill material for this project. The fill material shall be free from items such as trash, construction debris, metal and plastic products, and concrete block with exposed reinforcement bars. Soils used for fill shall not be contaminated with any toxic substance in concentrations governed by Section 307 of the Clean Water Act. Unless otherwise authorized by this permit, all fill material placed in waters or wetlands shall be generated from an upland source. | Green Sheet, 404 Permit | All Sections | Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Water Contamination: All mechanized equipment shall be regularly inspected and maintained to prevent contamination of waters and wetlands from fuels, lubricants, hydraulic fluids, or other toxic materials. In the event of a spill of petroleum products or any other hazardous waste, the Permittee shall immediately report it to the North Carolina Division of Water Resources at (919) 733-3300 or (800) 858-0368 and provisions of the North Carolina Oil Pollution and Hazardous Substances Control Act shall be followed. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Endangered Species Act: The Permittee shall implement all necessary measures to ensure the authorized activity does not kill, injure, capture, harass, or otherwise harm any federally-listed threatened or endangered species. While accomplishing the authorized work, if the Permittee discovers or observes an injured or dead threatened or endangered species, the Permittee shall immediately notify the U.S. Army Corps of Engineers, Wilmington District, Asheville Field Office, Attn: Lori Beckwith (Corps Project Manager for NCDOT Division 13) at loretta.a.beckwith@usace.army.mil or by telephone at 828-230-0483, or 828-271-7980 (Asheville Office general number), so that the required Federal coordination can occur. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | Endangered Species Act consultation: This Department of the Army permit does not authorize you to take a federally listed species. In order to legally take a federally listed species, you must have separate authorization under the Endangered Species Act (ESA) (e.g., an ESA Section 10 permit, or a Biological Opinion (BO) under ESA Section 7, with “incidental take” provisions with which you must comply). The U.S. Fish and Wildlife Service’s (USFWS’s) BO for this project titled, “Biological Opinion I-26 Connector from I-40 to US 19/23/70 North of Asheville Buncombe County, Asheville, North Carolina FWS Log # 02-252”, dated June 19, 2020, was amended on December 14, 2023 by a document titled, “Biological Opinion and Conference Opinion Addendum to the June 19, 2020 Biological Opinion for I-26 Connector from I-40 to US 19/23/70 North of Asheville, Buncombe County, North Carolina Service Log #02-252 NCDOT STIP I-2513”; these documents contain mandatory terms and conditions to implement the reasonable and prudent measures that are associated with incidental take for the species specified in these documents. Your authorization under this permit is conditional upon your compliance with all of the mandatory terms and conditions associated with incidental take of these documents. Failure to comply with the terms and conditions associated with incidental take detailed in these documents, where a take of a federally listed species occurs, would constitute an unauthorized take, and it would also constitute non-compliance with your permit. The USFWS is the appropriate authority to determine compliance with the terms and conditions of these documents/its Opinion(s), and with the ESA. These documents are attached to the permit for this project. | Green Sheet, 404 Permit | All Sections | Design-Build Team, BSG
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Related Laws | National Historic Preservation Act: NCDOT shall abide by all stipulations identified in the executed Memorandum of Agreement titled, “MEMORANDUM OF AGREEMENT AMONG THE FEDERAL HIGHWAY ADMINISTRATION, the NORTH CAROLINA DEPARTMENT OFTRANSPORTATION, and the NORTH CAROLINA STATE HISTORIC PRESERVATION OFFICE PURSUANT TO 36 CFR 800.6 regarding the I-26 CONNECTOR BUNCOMBE COUNTY, NORTH CAROLINA NCDOT TIP No. I-2513 FA No. MANHF-26-1(53). This MOA is attached to the permit for this project. | Green Sheet, 404 Permit | All Sections | NCDOT
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Prohibitions on Concrete: The Permittee shall take all measures necessary to prevent live or fresh concrete, including bags of uncured concrete, from coming into contact with any water in or entering into waters of the United States. Water inside coffer dams or casings that has been in contact with concrete shall only be returned to waters of the United States when it no longer poses a threat to aquatic organisms (concrete is set and cured). | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Aquatic Life Movement: No activity may substantially disrupt the necessary life cycle movements of those species of aquatic life indigenous to the waterbody, including those species that normally migrate through the area. All discharges of dredged or fill material within waters of the United States shall be designed and constructed to maintain low flows to sustain the movement of aquatic species. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Unless otherwise requested in the application and depicted on the approved permit plans, culverts greater than 48 inches in diameter shall be buried at least one foot below the bed of the stream. Culverts 48 inches in diameter and less shall be buried or placed on the stream bed as practicable and appropriate to maintain aquatic passage, and every effort shall be made to maintain existing channel slope. The bottom of the culvert shall be placed at a depth below the natural stream bottom to provide for passage during drought or low flow conditions. Culverts shall be designed and constructed in a manner that minimizes destabilization and head cutting. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Aquatic Life/Culverts | Measures shall be included in the construction/installation of culverts that will promote the safe passage of fish and other aquatic organisms. The dimension, pattern, and profile of the stream above and below a pipe or culvert shall not be modified by widening the stream channel or by reducing the depth of the stream in connection with the construction activity. The width, height, and gradient of a proposed opening shall be such as to pass the average historical low flow and spring flow without adversely altering flow velocity. Spring flow should be determined from gauge data, if available. Inthe absence of such data, bankfull flow can be used as a comparable level. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | During the clearing phase of the project, heavy equipment shall not be operated in surface waters or stream channels. Temporary stream crossings will be used to access the opposite sides of stream channels. All temporary diversion channels and stream crossings will be constructed of non-erodible materials. Grubbing of riparian vegetation will not occur until immediately before construction begins on a given segment of stream channel. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | No fill or excavation impacts for the purposes of sedimentation and erosion control shall occur within jurisdictional waters, including wetlands, unless the impacts are included on the approved plan drawings and specifically authorized by this permit. This includes, but is not limited to, sediment control fences and other barriers intended to catch sediment losses. | Green Sheet, 404 Permit | All Sections | Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall use appropriate sediment and erosion control practices which equal or exceed those outlined in the most recent version of the “North Carolina Sediment and Erosion Control Planning and Design Manual” to ensure compliance with the appropriate turbidity water quality standard. Erosion and sediment control practices shall be in full compliance with all specifications governing the proper design, installation and operation and maintenance of such Best Management Practices in order to ensure compliance with the appropriate turbidity water quality standards. This shall include, but is not limited to, the immediate installation of silt fencing or similar appropriate devices around all areas subject to soil disturbance or the movement of earthen fill, and the immediate stabilization of all disturbed areas. Additionally, the project shall remain in full compliance with all aspects of the Sedimentation Pollution Control Act of 1973 (North Carolina General Statutes Chapter 113A, Article 4). Adequate sedimentation and erosion control measures shall be implemented prior to any ground disturbing activities to minimize impacts to downstream aquatic resources. These measures shall be inspected and maintained regularly, especially following rainfall events. All fill material shall be adequately stabilized at the earliest practicable date to prevent sediment from entering into adjacent waters or wetlands. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall implement all reasonable and practicable measures to ensure that equipment, structures, work, and operations associated with this project do not adversely affect upstream and/or downstream reaches. Adverse effects include, but are not limited to, channel instability, flooding, and/or stream bank erosion. The Permittee shall routinely monitor for these effects, cease all work when detected, take initial corrective measures to correct actively eroding areas, and notify this office immediately. Permanent corrective measures may require additional authorization by the U.S. Army Corps of Engineers. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | The Permittee shall ensure that all excavation and/or construction areas in regulated waters, to inlcude wetlands, are temporarily dewatered during work. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Sediment and Erosion Control | Temporary Fills: Within thirty (30) days of the date of completing the authorized work, the Permittee shall remove all temporary fills in waters of the United States and restore the affected areas to pre-construction contours and elevations. The affected areas shall be re-vegetated with native, non-invasive vegetation as necessary to minimize erosion and ensure site stability. | Green Sheet, 404 Permit | All Sections | NCDOT, Construction, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Borrow and Waste | To ensure that all borrow and waste activities occur on high ground and do not result in the degradation of adjacent waters and wetlands, except as authorized by this permit, the Permittee shall require its contractors and/or agents to identify all areas to be used as borrow and/or waste sites associated with this project. The Permittee shall provide the U.S. Army Corps of Engineers with appropriate maps indicating the locations of proposed borrow and/or waste sites as soon as such information is available. The Permittee shall submit to the Corps site-specific information needed to ensure that borrow and/or waste sites comply with all applicable Federal requirements, to include compliance with the Endangered Species Act and the National Historic Preservation Act, such as surveys or correspondence with agencies (e.g., the U.S. Fish and Wildlife Service, the North Carolina Historic Preservation Office, etc.). The required information shall also include the location of all aquatic features, if any, out to a distance of 400 feet beyond the nearest boundary of the site. The Permittee shall not approve any borrow and/or waste sites before receiving written confirmation from the Corps that the proposed site meets all Federal requirements, whether or not waters of the U.S.,including wetlands, are located in the proposed borrow and/or waste site. All delineations of aquatic sites on borrow and/or waste sites shall be verified by the U.S. Army Corps of Engineers and shown on the approved reclamation plans. The Permittee shall ensure that all borrow and/or waste sites comply with Special Condition #3 of this permit. Additionally, the Permittee shall produce and maintain documentation of all borrow and waste sites associated with this project. This documentation will include data regarding soils, vegetation, hydrology, any delineation(s) of aquatic sites, and any jurisdictional determinations made by the Corps to clearly demonstrate compliance with Special Condition #3. All information will be available to the U.S. Army Corps of Engineers upon request. The Permittee shall require its contractors to complete and execute reclamation plans for each borrow and/or waste site and provide written documentation that the reclamation plans have been implemented and all work is completed. This documentation will be provided to the U.S. Army Corps of Engineers within 30 days of the completion of the reclamation work. | Green Sheet, 404 Permit | All Sections | NCDOT, Design-Build Team
NCDOT- Division Construction/Environmental Analysis Unit: Biological Surveys | Special Conditions from the Individual 404 Permit | Special Conditions from the Individual 404 Permit: Compensatory Mitigation | In order to compensate for impacts associated with this permit, mitigation shall be provided in accordance with the provisions outlined on the most recent version of the attached Compensatory Mitigation Responsibility Transfer Form. The requirements of this form, including any special conditions listed on this form, are hereby incorporatedas special conditions of this permit. | Green Sheet, 404 Permit | All Sections | NCDOT, NCDMS
| Conservation Measures to Benefit Protected Species (Causeways- French Broad River, hominy Creek, and Smith Mill Creek) | Conservation Measures to Benefit Protected Species (Causeways- French Broad River, hominy Creek, and Smith Mill Creek) | Causeways will not restrict more than 50% of the existing channel width of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with U.S. Army Corps of Engineers and Service prior to permitting. The updated 2.3.4.2 Causeways – French Broad River, Hominy Creek, and Smith Mill Creek states: • Causeways will not restrict more than 50% of the river or stream flow of the French Broad River, Hominy Creek, and Smith Mill Creek. Potential additional restrictions of the channel may be necessary for short durations, and these additional restrictions will be coordinated with USACE and USFWS prior to permitting. | 2023 Addendum BO | All Sections | Construction, Design-Build Team, BSG,
| Conservation Measures to Benefit Bats (Timing of Construction) | Conservation Measures to Benefit Bats (Timing of Construction) | Original Measure: NCDOT will monitor bat activity at the [Hill Street] culvert before, during, and after construction. Acoustic monitoring and/or emergence surveys will be conducted between March and November. Update: Based on recent data, the Service, North Carolina Wildlife Resources Commission (NCWRC), and NCDOT decided the best approach to monitoring the culvert would be through a combination of daytime visual surveys within the culvert and acoustic surveys. Visual surveys will be conducted two times per year during the active season (pre- and post-volancy) before, during, and after construction. If visual surveys discover large numbers of roosting bats, counts will switch to emergence surveys. Acoustic monitoring should occur throughout the active season (March 1 – November 15) at the culvert before, during, and post construction with detectors placed at the inlet and outlet. NCDOT will coordinate these monitoring efforts, including the preferred points of ingress and egress, ahead of time with the Service and NCWRC. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: NCDOT will conduct acoustic monitoring (or emergence counts, as appropriate) for MYGR at some locations immediately before, during and up to two years after construction. This monitoring may help determine changes in bat activity due to construction. Update: The above measure is no longer necessary, as described above. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: To help determine whether MYGR avoid active construction zones [including bridges and the Hill Street culvert roost] at night, NCDOT will investigate the use of night-vision video recordings, or other methods, in an attempt to monitor bat activity at locations where they may be most susceptible to disturbance. Update: The use of night vision recording at active construction zones (including bridges and the Hill Street culvert) is no longer necessary. The original commitment was to see if MYGR avoid active construction zones at night. This was investigated via the night vision work conducted by NCDOT at the I-26 bridge over the French Broad River (NCDOT project I-4400/I-4700) and additional work on this is not needed. It was also determined that there weren't other locations like the (I-4400/I-4700) I-26 bridge that lend themselves to successfully doing this type of work. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Conservation Measures to Benefit Bats (Monitoring for MYGR Return and Activity) | Original Measure: (As stated in T&C 10) NCDOT will conduct additional monitoring/research to include telemetry, coordinated monitoring of roosts, monitoring of new panels, basin-wide acoustics to be conducted at key points during and after construction. The details of additional monitoring will be decided by a committee to include USFWS, NCWRC and NCDOT. Information gathered will be used to increase our knowledge of impacts to bats to help inform future consultation, to learn more about gray bats in the project area, to better conserve the species, and to track movements of [MYGR] bats and hopefully determine where bats go if they abandon the culvert roost and/or the area. Update: Only the coordinated monitoring of roosts and roost panel monitoring aspects of this measure remain valid. As stated above, information gained on MYGR in the French Broad River basin over the past several years obviates the need to pursue additional monitoring as described in the original measure. Coordinated monitoring in the form of emergence surveys will be conducted at primary bridge roosts. Survey methods will be coordinated with the Service, NCWRC and NCDOT. Surveys will occur two times per summer and will take place in 2024 and 2025 (pre-construction), then four times every other year during project construction, then two years after construction. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Tree Clearing Minimization) | Conservation Measures to benefit Bats (Tree Clearing Minimization) | The wooded buffer along Hominy Creek between the existing right-of-way and hominy Creek will remain intact. Two locations will have stone rip rap installed at the outlets of two pipes (-RPD- Sta. 23+25.27). Some trees may be trimmed or removed to create an entrance point for the rip rap installation, however, the clearing for the two rip rap installations will be minimal and temporary, and vegetation will return. These two locations are adjacent to a maintained clearing for overhead electric transmission lines. An additional two areas involve clearing within the existing right-of-way to install ditches. The wooded area between the existing right-of-way and Hominy Creek will remain unaffected, which is expected to block lighting from the roadway. Clearing at this location is depicted via pink dashed lines in Appendix B, Figures 12 and 13. | 2023 Addendum BO | Section A, Section C | Design-Build Team, Construction
| Conservation Measures to Benefit Bats (Bat Telemetry Study) | Conservation Measures to Benefit Bats (Bat Telemetry Study) | NCDOT, in coordination with FHWA, shall manage a contract funding a research institution to conduct a 2-year-minimum telemetry study focused on the subject bat species within a 30-mile radius of the I-26 Connector project, with the goal of finding roosting locations and gaining information about commuting and foraging areas and habitat use. The research will include work to capture focal species (MYSO, MYSE, PESU, MYLU) to transmitter/track. Work may involve using acoustics to identify areas of high focal species activity and netting those locations, searching bridges and culverts, and netting nearby known occupied areas as well as Hominy Creek. Additionally, bats could be captured at nearby hibernacula in early spring to track where they go in the summer. Active ground telemetry, aerial telemetry, and fixed tower telemetry may be utilized. The structure and details of the study design and research decisions will be decided by a committee to include the Service, NCWRC, NCDOT, and the contracted researcher(s). | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Structure Surveys) | Conservation Measures to Benefit Bats (Structure Surveys) | Structure Surveys: a)NCDOT shall survey bridges and culverts that meet the criteria detailed in the Standard Operating Procedures: NCDOT Preliminary Bat Habitat Assessments (Structures, Caves, and Mines) (NCDOT 2015), within 2 years of construction for each phase of the project. This measure applies to structures that are proposed for modification or replacement. CM 2.3.3.3 Pre-Demolition Check for Bats in the 2020 BO remains valid. b) NCDOT shall conduct a 2023/2024 winter survey within the 15 originally surveyed culverts most suitable for winter roosting by PESUs and five smaller culverts that have features of high thermal stability that could support cold weather PESU roosting (e.g., concrete with longer lengths). NCDOT will involve the Service in deciding which five smaller culverts to survey. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Roost Panel Monitoring) | Conservation Measures to Benefit Bats (Roost Panel Monitoring) | NCDOT’s monitoring plan of the Modern Bat Modular Roost Panels as described in the Terms and Conditions outlined in the 2020 BO shall include the Pratt-Whitney roost panels placed on the Biltmore Farms bridge (E. Frederick Law Olmsted Way) over the French Broad River. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Bat Conservation Funding) | Conservation Measures to Benefit Bats (Bat Conservation Funding) | NCDOT shall contribute $150,000 to the NCWRC’s North Carolina Non-Game and Aquatics Project Fund (NCNGAPF) to support conservation and recovery efforts for MYSO, MYSE, PESU, and MYLU. This fund and its dispensation will be managed by the Service and NCWRC. At the time of the Addendum BO (Dec 2023), the NCNGAPF has not yet been set up to receive bat payments at NCWRC, it is expected in Jan 2025. This is in addition to the $350,000 first agreed to for gray bat (see above commitment) | 2023 Addendum BO | All Sections | BSG
| Conservation Measures to Benefit Bats (Lighting) | Conservation Measures to Benefit Bats (Lighting) | Lighting a) Smokey Park Highway Interchange: • Lighting at Ragsdale Creek shall not change from baseline condition. The current lighting will remain and the project will not result in changes or increases to the amount of light reaching Ragsdale Creek. • All new low level and high mast lighting installed by NCDOT for I-2513 A, B, C, and D sections shall be 3,000K color temperature, with the exception of the new ramp along Smokey Park Highway. b) I-26/I-40 Interchange Ramp East of Sand Hill Road: • The lighting fixtures installed at this location shall be 3,000K. This is a reduction from the existing lighting of 4000K. • At Trent Branch, high mast poles shall be reduced from existing conditions. At least four high mast poles shall be removed at this location. Replacement lighting shall be on single arm poles to the west of Trent Branch. This updated lighting configuration is designed to reduce lighting on Trent Branch. c) I-26/I-40 Interchange North of Pond Road: • Lighting adjacent to Hominy Creek shall be decreased from existing conditions. The existing lighting at this location is 400-watt high pressure sodium (HPS) with dropped glass lenses. Such fixtures typically produce 50,000 lumens of light each. The light-emitting diode (LED) replacement fixtures will produce less than 35,000 each. The LED fixtures have directional optics which enable light to be directed toward the road, as opposed to the HPS in dropped glass lens fixtures which result in more scattered light. | 2023 Addendum BO | All Sections | Design-Build Team
| Conservation Measures | Reasonable and Prudent Measures for Bats and Appalachian Elktoe | NCDOT shall ensure that the contractor(s) understands and follows the measures listed in the "Conservation Measures", "Reasonable and Prudent Measures" and "Terms and Conditions" sections of this Opinion | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Reasonable and Prudent Measures for Bats and Appalachian Elktoe | NCDOT shall monitor and document any take numbers and the surrogate measures of take and report those to the Service | 2023 Addendum BO | All Sections | BSG, Construction
| Conservation Measures | Terms and Conditions | Ensure that the procedures listed in the “Conservation Measures”, “Reasonable and Prudent Measures”, and “Terms and Conditions” sections of this Opinion are being implemented and that all project plans are being implemented in a manner that ensures the conditions of this Opinion are met. | 2023 Addendum BO | All Sections | Design-Build Team, NCDOT
| Conservation Measures | Terms and Conditions | NCDOT shall ensure that the Service and NCWRC are fully involved and in agreement with the design of the telemetry study. The study design process and subsequent data sharing shall be inclusive of and transparent to the involved agencies. Language will be included in any agreement requiring group consensus on any changes or contract and funding extensions, data sharing, and about following WNS decontamination protocols when working in western NC. Prior to funding approval, the study shall be approved by the Service and NCWRC. | 2023 Addendum BO | All Sections | BSG
| Conservation Measures | Terms and Conditions | Ensure that the telemetry study project description includes a specified minimum level of effort, e.g. minimum number of nights of netting, and/or number and size of culverts/bridges to check, and/or number of acoustic stations | 2023 Addendum BO | All Sections | BSG
| Conservation Measures | Terms and Conditions | NCDOT shall provide oversight and monitoring to ensure that construction contractors abide by all design plans. | 2023 Addendum BO | All Sections | NCDOT, REU
| Conservation Measures | Terms and Conditions | NCDOT shall monitor the surrogate measures of take to ensure that any exceedances are detected in a timely manner | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Terms and Conditions | NCDOT shall immediately notify the Service’s Asheville Field Office should live or deceased MYSO, MYSE, PESU, or MYLU be discovered during project work. | 2023 Addendum BO | All Sections | BSG, NCDOT
| Conservation Measures | Conservation Recommendations | Tree Clearing: Avoid tree clearing activities during the most sensitive bat seasons, notably the pup season of May 15 - July 31. During this time, pups are non-volant and unable to fly away from clearing activities. | 2023 Addendum BO | All Sections | Design-Build Team, Construction, BSG
| Conservation Measures | Conservation Recommendations | Habitat Protection: Continue pursuit of property acquisition adjacent to the Hill Street culvert. | 2023 Addendum BO | Section B (Design-Build) | BSG
| Conservation Measures | Conservation Recommendations | Lighting: Implement additional reductions in high mast poles throughout the action area, especially near waterbodies and riparian areas. | 2023 Addendum BO | All Sections | Design-Build Team
| Conservation Measures | Conservation Recommendations | Canton Bridge: Investigate the light that is illuminating one side of the Pigeon River where bats historically traveled and emerged from the bridge, but are now avoiding. The goal of this is to remove or modify the light in a way that removes illumination from the river and riparian corridor. | 2023 Addendum BO | N/A | Design-Build Team, BSG
| Conservation Measures | Conservation Recommendations | Riparian Planting: Replant disturbed riparian areas with native, fast-growing trees and shrubs that would serve to stabilize the stream bank, filter runoff and reduce erosion and sedimentation, block light pollution, and generally improve the quality of the habitat for bats and aquatic species. Examples of potential native tree species to plant include: sycamore, tulip poplar, black cherry and river birch. Planting with established (e.g. containerized) young trees can increase the survival rate of plantings and contribute to faster improvement of riparian habitat. | 2023 Addendum BO | All Sections | Design-Build Team, Construction
| Conservation Measures | Conservation Recommendations | Noise Considerations for Bats: If suitable roost trees are present near high-decibel activity (81 – 162 dBA) and would experience noise above background levels (41 – 70 dBA), avoid conducting those high-decibel activities during the bat maternity season (May 15 – August 15). Alternatively, activity could avoid the pup season (May 15 - July 31). To minimize noise levels, incorporate sound-dampening devices such as noise shrouds for pile driving. | 2023 Addendum BO | All Sections | Design-Build Team, Construction
| Conservation Measures | Monitoring and Reporting Requirements | Yearly monitoring summaries will be cumulative. That is, take the first year’s report and add data from year two. In year three, add data to the report that has years 1 and 2. Update the methods, results, and discussion each year as needed. In this way, the subsequent reports add to and supersede the older reports and provide updated context. The last report will serve as the final report | 2023 Addendum BO | All Sections | BSG
| Conservation Measures | Monitoring and Reporting Requirements | Include annual updates on the amount of tree clearing throughout the construction project in each year's report | 2023 Addendum BO | All Sections | BSG, Construction, Design-Build Team
| Conservation Measures | Reinitiation Notice | This concludes formal consultation on the action(s) outlined in the consultation request dated July 24, 2023. As provided in 50 CFR §402.16, reinitiation of formal consultation is required where discretionary Federal agency involvement or control over the action has been retained (or is authorized by law) and if: (1) the amount or extent of incidental take is exceeded; (2) new information reveals effects of the agency action that may affect listed species or critical habitat in a manner or to an extent not considered in this opinion; (3) the agency action is subsequently modified in a manner that causes an effect to the listed species or critical habitat not considered in this opinion; or (4) a new species is listed or critical habitat designated that may be affected by the action. In instances where the amount or extent of incidental take is exceeded, any operations cuasing such take must cease pending reinitiation. | 2023 Addendum BO | All Sections | BSG
|  |  | In addition to the amount of take described in the 2020 Opinion, the following is now included: As explained in the modified BO (USFWS log 02-252, 5/12/2025), the amount of take is expected to increase by 1 individual given the 12,000 square foot additional area of impact. Because impact area (i.e. square footage) serves as a surrogate measure of take for the purposes of this analysis for Appalachian elktoe, the amount of incidental take will be exceeded if the impact area is exceeded. | 2025 Addendum BO | All Sections | BSG
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | This work shall be conducted in accordance with the requirements of the modified 401 WQC | 2025 Permit Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | The permittee shall ensure that any equipment that is placed on the floodplain overnight, or at any other time, is moved to higher ground (above potential flooding) when either of the folllowing situations is forecasted or anticipated: (1) the water level will rise to a point where the equipment could be flooded (even during work days), and/or (2) the water level is expected to rise overnight, or over a non-work period of time, to a point where the equipment could be flooded | 2025 Permit Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | This modification is applicable only to the additional proposed activities. All of the authorized activities and conditions of the certification associated with the original Water Quality Certification dated October 30, 2023, still apply except where superseded by this certification. | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | Heavy equipment necessary for geotechnical borin gin the French Broad River may be operated within the river channel; however, its usage shall be minimized. In accordance with you rapplication, drill rigs shall follow the planned path as depicted in the French Broad River Path figure included in the application; drill rigs shall be mounted to large-diameter rubber-tire all terrain carriers with low-pressure tires to minimize contact pressures with the riverbed; drilling shall be performed during low water levels within the river (approximately 2 feet); and drill rigs shall be moved to the adjacent floodplain during the night. [15A NCAC 02H.0506(b)(3)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | The turbidity standard of 50 NTUs (Nephelometric Turbidity Units) shall not be exceeded as described in 15 A NCAC 02B .0200. Appropiate sediment and erosion control practices must be used to meet this standard. [15A NCAC 02B .0211 (21)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team
| Geotechnical borings for Sections B & D | Geotechnical borings for Sections B & D | In accordance with your application; NCDOT shall protect recreational river user safeth in the project area through the ofllowing protocol: move drill rigs to the floodplain for storage during overnight hours; utilize orange and white mooring buoys in teh water immediately around the drill rigs as a safety area that river users will need to avoid; position workers in the water in waders adjacent to drilling equipment to communicate river users; and maintain a River User Page as a resource for recreational users. [15A NCAC 02H .0506 (b)(1) and (2); 15A NCAC 02H .0507 (c)] | 401 Water Quality Certification 2025 Modification | Section B & D | Construction, Design-Build Team