# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: | #### Field Scoping Meeting Date: August 12, 2013 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR 1338 | County: SURRY |
| Project Description: Replace Bridge No. 850203 over Fisher River |  |
| Tier: Sub-regional |  |
| #### Municipality: None |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 | gjohnston@ncdot.gov |
| Hydraulics Engineer | Mark Shown |  |  |
| Hydraulics | Rusty Lassiter |  |  |
| Hydraulics | Matt York |  |  |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | Virginia Mabry |  |  |
| Bridge Management | Paul Garrett | 919-707-6457 | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 707-984-1070 | Marla.chambers@ncwildlife.org |
| Div. 11 | David Wayne |  |  |

Existing Features

| Feature Bridged: 850203 Fisher River |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 19.1 (Ft.) |  |  | Approach Roadway width: 18 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 81 (Ft.) |  |  | Deck Width (Out To Out): 24 (Ft.) |  |  |  |  |
| Water Depth: 2 (Ft.) |  |  | Height Bed-To-Crown: 14 (Ft.) |  |  |  |  |
| Built date: 1968 |  |  | Posted: SV 22 |  |  | TTST: 29 |  |
| Superstructure Type: ST M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: TM |  |  |  | 1 @ 50'-3; 1 @ 30'-3 |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 57 ; DP: 0 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 55 (mph) or Statutory 55mph |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: SR 1338 (Hidden Valley Road) - SR 1407 (Ladonia Church Road) - NC 89 - SR 1338 (Ramey Creek Road) |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 6 ( Miles ) per Div |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Local |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? 202 |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? Surry 202 programmed to be let with 17BP funds. |  |  |  |  |  |  |  |
| Sequencing priority in construction? complete 203 then constr. 202 consecutively |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict yes overhead power diagonal crossing |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict yes |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict yes |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog Turtle, Schweinitz's sunflower, Small Whorled pogonia |  |  |  |  |  |  |
| Trout County : Yes Hatchery supported |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: NO | Which If Yes-Duration : |  |  |  | Duration: |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification:, WS II; HQW; TR |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: Yadin/Pee Dee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No; |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes (MOA ) limited |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? none |  |  | Is Protection Needed? STD |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? STD |  |  |  |
| Appreciable Amount Of Large Debris? Moderate |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | None in water. |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 100’ | Min. Number Of Spans: 2 |  |  |  | Span Arrangement: 60’, 40’ |  |
| Waive setback: Left side (east) only with vertical abutment | Cap: 4’ |  |  |  |  | Skewed: slightly to help |
| Hold downstream(south) (face) of bridge . Vertical abutment 5’ from end of bridge left side looking downstream; hold low chord. |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - Clear roadway width: Temp. Signals: Alignment: |  |  | New Alignment: Alignment: |  |  |  |  | On-site detour CRW: one lane w/ signals; or two lanes CRW; Alignment: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 590/BIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 27’ OTO |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 10‘ with 3‘ shoulders including no paved shoulders: |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2.5” inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 45 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 120 days of closure. Amt: $ 500_ per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by DBT |  |  | R/W: by DBT |  |  |  | R/W monuments: cap/pin. |  |  |  |
| Salvageable materials: ALL STEEL (GUARDRAIL (POST, BLOCKS, WHEEL GUARD,AND RAIL), ALL STEEL I-BEAMS, BEARING PLATES, AND DIAPHRAGMS, AND ANY STEEL PLANK FLOOR THAT CAN BE SALVAGED. PLACE SPEC. IN CONTRACT TO CAREFULLY REMOVE ALL STEEL PLANK FLOOR WITHOUT DAMAGING FLOORING OR I-BEAMS), NEW TIMBER CAPS, AND NEW POST Contact Person/number: Gary Robbins / (336) 835-4941 Deliver to NCDOT ELKIN BRIDGE YARD |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: NO |  |  |  |  |  |  |  |  |  |  |
| Comments: Remove concrete footers, relocated drives as necessary. Hold downstream (South) face of bridge and widen to the north. |  |  |  |  |  |  |  |  |  |  |