# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.59 | #### Field Scoping Meeting Date: August 14, 2013 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1502 | County: YADKIN |
| Project Description: Replace Bridge No. 980109 over NORTH DEEP CREEK |  |
| Tier: Sub-regional |  |
| #### Municipality: None |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 | gjohnston@ncdot.gov |
| Hydraulics Engineer | Marc Shown |  |  |
| Hydraulics |  |  |  |
| DENR-DWQ | Amy Euliss | 336-771-4959 | amy.euliss@ncdenr.gov |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | Virginia Mabry | 919 707-6604 |  |
| Bridge Management | Paul Garrett | 919-707-6457 | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 707-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 980109 NORTH DEEP CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 24 (Ft.) |  |  | Approach Roadway width: 18 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 120 (Ft.) |  |  | Deck Width (Out To Out): 28.1 (Ft.) |  |  |  |  |
| Water Depth: 3 (Ft.) |  |  | Height Bed-To-Crown: 23 (Ft.) |  |  |  |  |
| Built date: 1963 |  |  | Posted: SV 25 |  |  | TTST: 32 |  |
| Superstructure Type: ST M-BM |  |  |  | End Bent Material Type: ST |  |  |  |
| Interior Bent Material Type: ST |  |  |  | 3@40 |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 2 ; DP: 0 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 55 (mph) or Statutory 55mph Advisory is 30/35 mph each side |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: SR 1503 (Steelman Road) - SR 1134 (Dobbins Mill Road) |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 2 ( Miles ) |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Local |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict Yes |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict Yes |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict Yes |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: None |  |  |  |  |  |  |
| Trout County : No |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No | Which If Yes-Duration : |  |  |  | Duration: |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C |  |  |  |  | 303d: No |  |
| Coast Guard Permit? No |  | Drainage Basin: Yadin/Pee Dee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries; No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: NO |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes (MOA ) limited |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? Std |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? localized around the bridge, needs some stabilization |  |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | None in water |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 135’ | Min. Number Of Spans: 3 |  |  |  | Span Arrangement: 40’-65’-30’ |  |
| Waive setback: No | Cap: 4’ |  |  |  |  | Skewed: slight skew would fit better |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - Clear roadway width: Temp. Signals: Alignment: |  |  | New Alignment: Alignment: |  |  |  |  | On-site detour CRW: one lane w/ signals; or two lanes CRW; Alignment: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 2400 /BIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: Maj-Collector |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 30’ OTO widen symmetrically |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 11‘ with 6‘ shoulders including 2' paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: tapered 8:1. |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2.5 inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 50 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 120 days of closure. Amt: $ _500_ per day |  |  |  |  |  |  |  |  |  |  |
| CEI: DBT |  |  | R/W: by NCDOT |  |  |  | R/W monuments: pin & cap. |  |  |  |
| Salvageable materials: ALL STEEL I-BEAMS, BEARING PLATES, AND DIAPHRAGMS. ROCK ON FACE OF ABUTMENT 1 AND 2 MAY BE REUSED ON NEW PROJECT. Contact Person/number: Gary Robbins Deliver to NCDOT Elkin Bridge Yard |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: None seen |  |  |  |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |