# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.87 | #### Field Scoping Meeting Date: August 12, 2013 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1727 (Linville Road) | County: SURRY |
| Project Description: Replace Bridge No. 850094 over ARARAT RIVER |  |
| Tier: Sub-regional |  |
| #### Municipality: Mount Airy |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 | gjohnston@ncdot.gov |
| Hydraulics Engineer | Marc & Rusty |  |  |
| Hydraulics |  |  |  |
| DENR-DWQ | Amy Euliss | 336-771-4959 | amy.euliss@ncdenr.gov |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | V Mabry |  |  |
| Bridge Management | Paul Garrett | 919-707-6457 | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 707-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 850094 ARARAT RIVER |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 24 (Ft.) |  |  | Approach Roadway width: 20 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 180 (Ft.) |  |  | Deck Width (Out To Out): 28.3 (Ft.) |  |  |  |  |
| Water Depth: 2 (Ft.) |  |  | Height Bed-To-Crown: 14 (Ft.) |  |  |  |  |
| Built date: 1963 |  |  | Posted: SV 33 |  |  | TTST: 37 |  |
| Superstructure Type: ST-M-BM |  |  |  | End Bent Material Type: RC |  |  |  |
| Interior Bent Material Type: RC |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 15.8 ; DP: 0 |  | School Busing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 35 mph posted |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: NC 103 (E. Pine St) – NC 104 (Riverside Dr.) |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 2.4 ( Miles ) |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing due to truck traffic |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? Not on detour route: B-5839 #94 requested to be removed from TIP, 11/25/13 |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict No Check surveys |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict No “ “ |  |  |  |  |  |  |  |
| Telephone In Conflict No “ ” |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict No “ “ |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict Old conduit - abandoned |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: Yes, Comments: NES to flag/gps upstream right side wetland |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog Turtle, Schweinitz's sunflower, Small Whorled pogonia |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No | Which If Yes-Duration : |  |  |  | Duration: |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: Yadin/Pee Dee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: Mt. Airy Pedestrian Plan recently adopted, Arrat River Greenway is planned; Mt. Airy requested width for future sidewalk on one side only 5.5’ (North side) and 4’ offset both sides for bike accommodations and standard 2-bar metal rail both sides. Provide accommodation for a future 12” DIP waterline to be attached to the bridge. |  |  |  |  |  |  |
| Comments: within Mount Airy City Limits – TPMU coordinating |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes MOA Detailed |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? Low |  |  | Is Protection Needed? Standard |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? fill up holes upstream Rt w/riprap |  |  |  |
| Appreciable Amount Of Large Debris? Moderate |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge |  | If Bridge: girder |  |  |  |  |
| Length Of Structure: 190’ | Min. Number Of Spans: 3 |  |  |  | Span Arrangement: 105’, 85’ |  |
| Waive offset: No | Cap: 4’ |  |  |  |  | Skewed: 90 degrees |
| Note: concrete overlay due to quarry truck traffic Upstream right wash out hole on west side, fill with riprap, do not need to span |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: |  |  | New Alignment: |  |  |  |  | On-site detour |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 2700 SIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 38 ft 1 in. OTO with concrete overlay 2-bar rail on both side and 5’6” sidewalk on north side. On the North side provide accommodations for the future DIP 12 in water line. |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 11‘ with 6‘ shoulders including 4' paved shoulders for bikes |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: tapered 8:1. |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2.5 inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: Raised |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 7 %; 3% Duals & 4% TTST |  |  |  |  | Reasonable Safe Speed: 35 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 120 days of closure. Amt: $ _500___ per day next to quarry. |  |  |  |  |  |  |  |  |  |  |
| CEI: by DBT |  |  | R/W: by DBT |  |  |  | R/W monuments: pin & cap. |  |  |  |
| Salvageable materials: ALL STEEL (ALL STEEL I-BEAMS, BEARING PLATES, AND DIAPHRAGMS. EXISTING ROCK ON FACE OF ABUTMENT 1 AND 2 MAY BE REUSED ON NEW PROJECT. The DBT will not be responsible for the removal of the concrete on the existing beams. Every caution should be taken to not damage the beams during demo. These beams will need to be salvaged and delivered with concrete attached Contact Person/number: Gary Robbins Deliver to NCDOT Elkin Bridge Yard |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: None |  |  |  |  |  |  |  |  |  |  |
| Comments: TPMU to prepare Municipal Agreement USGS gaging station upstream away from bridge. |  |  |  |  |  |  |  |  |  |  |