# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.69 | #### Field Scoping Meeting Date: August 12, 2013 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1300 | County: ALLEGHANY |
| Project Description: Replace Bridge No. 20046 over Prathers Creek |  |
| Tier: Sub-regional |  |
| #### Municipality: None |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 | gjohnston@ncdot.gov |
| Hydraulics Engineer |  |  |  |
| Hydraulics |  |  |  |
| DENR-DWQ |  |  |  |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU |  |  |  |
| Bridge Management | Paul Garrett | 919-707-6457 | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 707-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 20046 Prathers Creek |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 19.3 (Ft.) |  |  | Approach Roadway width: 17 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 41 (Ft.) |  |  | Deck Width (Out To Out): 20.3 (Ft.) |  |  |  |  |
| Water Depth: (Ft.) |  |  | Height Bed-To-Crown: (Ft.) |  |  |  |  |
| Built date: 1962 |  |  | Posted: SV 12 |  |  | TTST: 16 |  |
| Superstructure Type: ST M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: NONE |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 21.1 ; DP: 9.59 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: Statutory 55 mph |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: Flint Hill Road (SR 1301) - US 221 - NC 113 |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 5 ( Miles ) per Div |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? local |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict None observed |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 0 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: NE quad there is a wet pipe at station 11+75 south of the bridge. This pipe may have to be lengthened to accommodate the wider road should the project limits have to be extended to that point. In that case, this project will not qualify for NWP #3. That means Nationwide Permit #14 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog Turtle |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No | Which If Yes-Duration : |  |  |  | Duration: |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: B, Tr ; + |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: New |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NHP |  |  | Archaeology Survey required; NSR |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |
| Comments: Hatchery supported trout |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? No (MOA ) |  | State Stormwater Permit? No |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  | Is Protection Needed? Std |  |  |  |  |
| Are Banks Stable? Yes |  | Is Protection Needed? Std |  |  |  |  |
| Appreciable Amount Of Large Debris? Moderate |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge | If Bridge: CS |  |  |  | If girder; why? |  |
| Length Of Structure: 55’ |  |  | Min. Number Of Spans: 1 |  | Span Arrangement: 1 |  |
| Waive offset: Yes per Randy Henegar 5/13/14 |  |  | Cap: 4’ |  |  | Skewed: Yes |
| w/Vertical abutments |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - Clear roadway width: Temp. Signals: Alignment: |  |  | New Alignment: Alignment: |  |  |  |  | On-site detour CRW: one lane w/ signals; or two lanes CRW; Alignment: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 160 /BIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 24’ OTO |  |  |  |  |  |  |  |  |  | Min. CDW: |
| Roadway lane width 9‘ with 2‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: Raised / Snow-plowable / None |  |  |  |  | Pavement Marking on Asphalt: Paint, no centerline |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 30 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 90 days of closure. Amt: $ _500___ per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by DBT |  |  | R/W: by DBT |  |  |  | R/W monuments: pin/cap |  |  |  |
| Salvageable materials: ALL STEEL (ALL STEEL I-BEAMS, BEARING PLATES, AND DIAPHRAGMS) Deliver to NCDOT Warrensville Bridge Maintenance Yard Contact person: Chad Cox (336)-384-2562 |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |