# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.60 | #### Field Scoping Meeting Date: August14, 2013 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1300 | County: WILKES |
| Project Description: Replace Bridge No. 960106 over N.PRONG LEWIS FORK CREEK |  |
| Tier: Sub-regional |  |
| #### Municipality: None |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 | gjohnston@ncdot.gov |
| Hydraulics Engineer | Marc & Rusty |  |  |
| Hydraulics |  |  |  |
| DENR-DWQ | Amy Euliss | 336-771-4959 | amy.euliss@ncdenr.gov |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | V. Mabry |  |  |
| Bridge Management | Paul Garrett | 919-707-6457 | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 707-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 960106 N.PRONG LEWIS FORK CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 24 (Ft.) |  |  | Approach Roadway width: 18 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 120 (Ft.) |  |  | Deck Width (Out To Out): 24.4 (Ft.) |  |  |  |  |
| Water Depth: 2 (Ft.) |  |  | Height Bed-To-Crown: 16 (Ft.) |  |  |  |  |
| Built date: 1961 |  |  | Posted: SV 13 |  |  | TTST: 16 |  |
| Superstructure Type: ST M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: TM |  |  |  | 1 @ 40'-4; 1 @ 40'; 1 @ 40'-4 |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 22.3 ; DP: 12 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: (mph) or Statutory 55 mph |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: downstream |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 25 ( Miles ) |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Local |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? N/A |  |  |  |  |  |  |  |
| Sequencing priority in construction? Highest priority in Wilkes, blown out crutch bent |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict YES |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict YES aerial and underground |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict YES |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: None Comments: Remove concrete footers under interior bents. The water is washing around them during storm flows and shredding the banks. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? None T&E species listed in County: Bog turtle |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No | Which If Yes-Duration : |  |  |  | Duration: |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C |  |  |  |  | 303d: No |  |
| Coast Guard Permit? No |  | Drainage Basin: Yadin/Pee Dee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NHP |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: Wilkes County Bike Route No. 10, a variance to the standard 4’ offset on the bridge was coordinated with NCDOT Bike and Ped and accepted. |  |  |  |  |  |  |
| Comments: PCN if trib in SW quadrant is impacted for NWP 14, not the NWP 3 |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Yes when existing abut- |  |  |  |
| Appreciable Amount Of Large Debris? Yes ment is pulled, |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 135’ | Min. Number Of Spans: 3 |  |  |  | Span Arrangement: 25’, 70’, 40’ |  |
| Waive offset: No | Cap: 4’ |  |  |  |  | Skewed: approx. 60 deg. |
| Bank stabilization when pull old abutment Streams impacts may make this a NWP 14 Remove existing footings Replace existing 66” CMP with 78” CSP Drainge Pipe with conrete headwalls buried one foot with 48 hour weekend road closure – coordination with public required |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: Clear roadway width: 12’ off old bridge Temp. Signals: Yes Alignment: downstream (south) |  |  |  |  | New Alignment: |  |  | On-site detour |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 460 /BIR |  | NHS: No | Tier: Sub-regional |  | Func. Class: L-Rural |  |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 27’ OTO with 2-bar rail |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 10‘ with 4‘ shoulders including 2’ paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and:Yes |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2.5 inches: |  |  |  | Existing Roadway: paved |  |  |  |  |  |  |
| Pavement markers: None |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  | Reasonable Safe Speed: 45 mph per SIR |  |  |  |  |  |  |
| Liquidated damages: will be imposed after 180 days of construction. Amt: $ _500___ per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by DBT |  |  | R/W: by DBT |  |  |  | R/W monuments: pin cap. |  |  |  |
| Salvageable materials: ALL STEEL (GUARDRAIL (POST, BLOCKS, WHEEL GUARD,AND RAIL), ALL STEEL I-BEAMS, BEARING PLATES, AND DIAPHRAGMS, AND ANY STEEL PLANK FLOOR THAT CAN BE SALVAGED/MEANING RE-USED/PLACE SPEC. IN CONTRACT TO CAREFULLY REMOVE ALL STEEL PLANK FLOOR WITHOUT DAMAGING FLOORING OR I-BEAMS), NEW TIMBER CAPS, AND NEW POST/BRACING AT ABUTMENTS, PEIRS, AND CRUTCH BENTS. Deliver to NCDOT North Wilkesboro Bridge Maintenance Yard Contact person: Rick Minton (336)-903-9198 |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: Right (east) side remove existing remnant footing |  |  |  |  |  |  |  |  |  |  |
| Comments: Remove concrete footings/pull existing abutment Stage old bridge removal and realign new bridge (south) Impact stream next to drive (SW of bridge) – may require PCN. DEO to discuss with Corps Resurface to tie-ins. |  |  |  |  |  |  |  |  |  |  |