# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.90 |  |  | #### Field Scoping Meeting Date: August 13, 2013 |  |  |
| --- | --- | --- | --- | --- | --- |
| Division: 11 |  |  | #### Location: On-site |  |  |
| Route (US/NC/SR): SR1324 |  |  | County: ASHE |  |  |
| Project Description: Replace Bridge No. 40060 over BIG HORSE CREEK |  |  |  |  |  |
| Tier: Sub-regional |  |  |  |  |  |
| #### Municipality: None |  |  |  |  |  |
| Attendees |  |  |  |  |
|  | Name | Phone No. |  | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 |  | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 |  | hslaughter@ncdot.gov |
| Assist. Division Bridge Manager | Greg Johnston | 336-903-9203 |  | gjohnston@ncdot.gov |
| Hydraulics Engineer | Marc Shown |  |  |  |
| Hydraulics | Rusty Lassiter |  |  |  |
| Hydraulics | Matt York |  |  |  |
| DENR-DWQ | Amy Euliss | 336-771-4959 |  | amy.euliss@ncdenr.gov |
| TPMU | Pam Williams | 919-707-6608 |  | prwilliams@ncdot.gov |
| TPMU | Virginia Mabry |  |  |  |
| Bridge Management | Paul Garrett | 919-707-6457 |  | rgarrett@ncdot.gov |
| NCWRC | Marla Chambers |  |  | Not on site |

Existing Features

| Feature Bridged: 40060 BIG HORSE CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 29 (Ft.) |  |  | Approach Roadway width: 19 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 121 (Ft.) |  |  | Deck Width (Out To Out): 30.5 (Ft.) |  |  |  |  |
| Water Depth: 3 (Ft.) |  |  | Height Bed-To-Crown: 17 (Ft.) |  |  |  |  |
| Built date: 1973 |  |  | Posted: SV 21 |  |  | TTST: 28 |  |
| Superstructure Type: PC CHNL-BM |  |  |  | End Bent Material Type: ST |  |  |  |
| Interior Bent Material Type: ST |  |  |  | 1 @ 30'-3; 2 @ 30'; 1 @ 30'-3 |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 52.5 ; DP: 2.5 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 55mph |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route SR 1352 – NC 88 – NC 194 – SR 1353 per email 2/25/14 |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 8 ( Miles ) per BIR |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Sequencing priority in construction? Replace #61 (high priority) 1st then #60 (high priority) – same detour |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict Yes |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict Yes |  |  |  |  |  |  |  |
| Cable Lines In Conflict Yes |  |  |  |  |  |  |  |
| Fiber Optic In Conflict Yes |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: None Comments: There is a spring popping up under the eastern portion of the bridge. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog Turtle, Carolina northern flying squirrel, BlueRidge Goldenrod, Heller's blazing star, Roan mountain bluet, Spreading avens, Swamp pink, Virginia Spiraea, rock gnome lichen |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: Yes | Which species :Brown |  |  |  | Duration: Oct. 15 to April 15 |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C, ORW, Tr |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: New |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No; Adjacent to NC Bike Route; |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Stab.Bank in vicinity of pier upstream left |  |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: 1 |  |  |  | Where: @ waters’ edge |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 105’ | Min. Number Of Spans: 2 |  |  |  | Span Arrangement: 35’, 70’ |  |
| Waive offset: No | Cap: 4’ |  |  |  |  | Skewed: No |
| (proposed bridge 15’ shorter than existing) move end bent 20’ from end on bridge, intersection side. |  |  |  |  |  |  |
| Retain conc footing on interior both sides Remove bank downstream right to create floodplain if needed. Hold grade at intersection |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - Clear roadway width: Temp. Signals: Alignment: |  |  | New Alignment: Alignment: |  |  |  |  | On-site detour CRW: one lane w/ signals; or two lanes CRW; Alignment: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 860 /BIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 33’ OTO IA-350 TL-2 at NW corner of bridge to reduce impacts to access just off bridge per Division |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 10‘ with 3‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2.5 inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: III |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 25 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 150 days of closure. Amt: $ 600 per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by DBT |  |  | R/W: by DBT |  |  |  | R/W monuments: pin/cap. |  |  |  |
| Salvageable materials: ALL STEEL (GUARDRAIL (POST, BLOCKS, WHEEL GUARD, AND RAIL). ALL CONCRETE CHANNEL LEG BEAMS IN SPANS 1 - 3. ALL STEEL I-BEAMS IN SPAN 4. ALL STEEL H-PILE POST. Deliver to NCDOT Warrensville Bridge Maintenance Yard Contact person: Chad Cox (336)-384-2562 |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: remove remnant abutments to footings |  |  |  |  |  |  |  |  |  |  |
| Comments: - Connect guardrail from end of Bridge to Y-Line SR 1353 guardrail - Retain concrete footings on interior bents |  |  |  |  |  |  |  |  |  |  |