# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.12.R.46 |  |  | #### Field Scoping Meeting Date: Sept. 18, 2013 |  |  |
| --- | --- | --- | --- | --- | --- |
| Division: 12 |  |  | #### Location: On-site |  |  |
| Route (US/NC/SR): SR1338 |  |  | County: ALEXANDER |  |  |
| Project Description: Replace Bridge No. 010071 over GRASSY CREEK |  |  |  |  |  |
| Tier: Subregional |  |  |  |  |  |
| #### Municipality: None |  |  |  |  |  |
| Attendees |  |  |  |  |
|  | Name | Phone No. |  | E-mail |
| Division Bridge Manager | Steve Rackley | 704-480-9034 |  | srackley@ncdot.gov |
| Division Environmental Spec. | Tricia Beam | 704-480-5400 |  | pdbeam@ncdot.gov |
| Hydraulics Engineer | Randy Henegar | 919-707-6726 |  | rhenegar@ncdot.gov |
| Hydraulics Engineer | Walter Hunt |  |  |  |
| TPMU | Pam Williams | 919-707-6608 |  | prwilliams@ncdot.gov |
| USACE | Tasha L. McCormick | NP |  | Tasha.L.McCormick@usace.army.mil |
| DENR-DWR | Alan Johnson | NP |  | alan.johnson@ncdenr.gov |
| NCWRC | Marla Chambers Called in all info | NP |  | marla.chambers@ncwildlife.org |
| USFWS | Jay Mays | NP |  | jason_mays@fws.gov |
| Division Bridge Maintenance | Ryan Barbee | 704-480-9029 |  | rbarbee@ncdot.gov |

NP=not present

Existing Features

| Feature Bridged: 010071 over GRASSY CREEK |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 19.8 (Ft.) |  |  | Approach Roadway width: 17 (Ft.) |  |  |  |  |  |
| (Bridge / Culvert) Length: 41 (Ft.) |  |  | Deck Width (Out To Out): 20 (Ft.) |  |  |  |  |  |
| Water Depth: 1' (Ft.) |  |  | Height Bed-To-Crown: 12' (Ft.) |  |  |  |  |  |
| Built date: 1963 |  |  | Posted: SV 99 |  |  | TTST: 99 |  |  |
| Superstructure Type: ST M-BM |  |  |  | End Bent Material Type: TM |  |  |  |  |
| Interior Bent Material Type: NONE |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |
| Sufficiency Rating: 21.2 ; DP: 0 |  | School Bussing crossings per day: |  |  |  |  |  |  |
| Posted Speed Limit Vicinity: (mph) or Statutory 55mph |  |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: SR 1331-NC 16 |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 2.84 ( Miles ) per BIR |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing with road names |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Sequencing priority in construction? None |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No – low impact |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict northside and diagonal on west end |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict northside |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog Turtle, Bald Eagle, Dwarf-flowered heartleaf |  |  |  |  |  |  |
| Trout County : No |  |  |  | TVA County: No |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No | Which species : |  |  |  | Duration: |  |
| Permits Required: Yes, NWP 3 & 14 (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C |  |  |  |  | 303d: No per DWR |  |
| Coast Guard Permit? No |  | Drainage Basin: Catawba |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No ; |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NHP |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? Yes (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? Low |  |  | Is Protection Needed? STD |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? STD |  |  |  |
| Appreciable Amount Of Large Debris? Low |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: N/A |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 70’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |  |
| Waive setback: No | Cap: 4’ |  |  |  |  | Skewed: |
| Drainage ditches along roadway only & not jurisdictional |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - |  |  | New Alignment: |  |  |  |  | On-site detour |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 260 /SIR |  | NHS: No | Tier: Subregional |  |  | Func. Class: Local |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 30’ OTO |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 10 ‘ with 3‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2 ½” inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  | Method of Clearing: II Modified |  |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 50 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 90 days of closure. Amt: $ __300__ per day |  |  |  |  |  |  |  |  |  |  |
| CEI: DOT |  |  | R/W: by DBT |  |  |  |  | R/W monuments: Conc. |  |  |
| Salvageable materials: Bridge Beams, Guardrail, post and blocks Contact Person/number: All items to be delivered to Eric Schenz (704-876-4036): Deliver to: NCDOT Bridge Maintenance – Statesville, 190 Prison Camp Road, Statesville NC 28625 NCDOT will be responsible for unloading salvaged items. |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |  |
| Comments: Drive northwest goes to chicken houses and paved drive on NE to house. Provide full 2.5” full surface course 150’ each side or to extent of construction limits |  |  |  |  |  |  |  |  |  |  |