# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process Poste

| WBS No.: 17BP.14.R.108 |  |  | #### Field Scoping Meeting Date: Sept. 11, 2013 |  |  |
| --- | --- | --- | --- | --- | --- |
| Division: 14 |  |  | #### Location: On-site |  |  |
| Route (US/NC/SR): SR1740 |  |  | County: JACKSON |  |  |
| Project Description: Replace Bridge No. 490103 over MOSES CREEK |  |  |  |  |  |
| Tier: Sub-regional |  |  |  |  |  |
| #### Municipality: None |  |  |  |  |  |
| Attendees |  |  |  |  |
|  | Name | Phone No. |  | E-mail |
| Division Bridge Mgr | Josh Deyton | 828 586-2141 |  | jbdeyton@ncdot.gov |
| Div. Environmental Off. | Mark Davis | 828 586-2141 |  | markdavis@ncdot.gov |
| Div. 14 BMU | Mark Hill | 828-488-2131 |  | Mehill3@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 |  | Mshown@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 |  | rlassiter@ncdot.gov |
| Bridge Management | Paul Garrett | 919 835-8491 |  | pgarrett@ncdot.gov |
| TPMU | Christy Huff | 919-707-6606 |  | chuff@ncdot.gov |
| TPMU | Pam Williams | 919 707-6608 |  | prwilliams@ncdot.gov |
| L&S | Barry Hamrick | 828-586-0925 |  | bhamrick@ncdot.gov |
| NCDOT | Eileen Fuchs Pam Williams Josh Deyton Mark Davis 2/6/14 |  |  |  |
| USFS | Karen Compton Bryan Killian 2/6/14 |  |  | Not in attendance |
| DENR-DWQ | Amy Chapman |  |  | Not in attendance |
| WRC | Marla Chambers |  |  | Not in attendance |
| USACE | Lori Beckwith |  |  | Not in attendance |

Existing Features

| Feature Bridged: 490103 over MOSES CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 17.1 (Ft.) |  |  | Approach Roadway width: 10 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 21 (Ft.) |  |  | Deck Width (Out To Out): 18.1 (Ft.) |  |  |  |  |
| Water Depth: (Ft.) |  |  | Height Bed-To-Crown: 6 (Ft.) |  |  |  |  |
| Built date: 1963 |  |  | Posted: SV 23 |  |  | TTST: 37 |  |
| Superstructure Type: TM M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: NONE |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 14.1 ; DP: 0 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 35 (mph) |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: N/A |  |  |  |  |  |  |  |
| Approximate Length Of Detour? Not available |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? Bridge No. 101, B-5159, on same road SR 1740 is posted 10 Tons; Bridge No. 135 is upstream and is a DPOC |  |  |  |  |  |  |  |
| Sequencing priority in construction? None |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? Fire Department w/ water point |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? N/A |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict No Utilities |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 0 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: NCDOT to provide Comments: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog turtle, Carolina northern flying squirrel, Indiana bat, Appalachian Elktoe, Spruce-fir moss spider, small whorled pogonia, swamp pink, Rock gnome lichen |  |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: Yes |  |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |  |
| Moratoria: Yes | Which species :Rainbow/Brooke |  |  |  |  | Duration: Jan. 1 – April 15 Oct. 15 – April 15 |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |  |
| Water Quality Classification: TR |  |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: Little Tennessee |  |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |  |
| National Forest Yes ; USFS |  |  | Wildlife Refuge No ; |  |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries; No |  |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |  |
| Historic Archit. Survey required; No National Register or eligible properties |  |  |  |  | Archaeology Survey required; No National Register or eligible properties ; This project was coordinated with USFS and is considered an FS Exempt Undertaking |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: no |  |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |  |
| Comments: Within Nantahala National Forest property and Gamelands USFS to prepare Biological Evaluation. • The DBT/TPMU is to contact the USFS Ranger and meet with him to review the plans, then revise as discuss at meeting, then send to, NCDOT ROW, who will coordinate with USFS. • The electronic files should be sent to Grady Morris, NCDOT, as soon as ROW plans are ready • The TCE and ROW should be shown as usual and after review if the USFS Ranger wants to change to permanent easement, revise at that time. |  |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? No (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Std. |  |  |  |
| Appreciable Amount Of Large Debris? Mod |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 30’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |  |
| Waive offset: Yes | Cap: 4’ |  |  |  |  | Skewed: Yes |
| - Construct a vertical face using either (1) a cast-in-place abutment or (2) a deep end bent cap supported on piles; |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - |  |  | New Alignment: |  |  |  |  | On-site detour one lane gravel runaround with no no signals; CRW- 11’ Alignment: downstream |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 140 SIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 24’ OTO std rail. |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 9‘ with 2‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Blunted end pavement at end of guardrail; shop curve rail at driveway into hill is possible. |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2 ½” inches: |  |  |  |  | Existing Roadway: gravel |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: None |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  | Method of Clearing: II |  |  |  |
| Truck Percentage: : 0 %; |  |  |  |  | Reasonable Safe Speed: 25 mph per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 150 days of closure. Amt: $ 500 per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by NCDOT |  |  | R/W: DBT |  |  |  |  | R/W monuments: Pin/Cap. |  |  |
| Salvageable materials: No |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: None |  |  |  |  |  |  |  |  |  |  |
| Comments: - Pave to the end of guardrail and blunt end it, no pavement markings - coordinated with USFS no special rail type and guardrail for bridge. - Temp. gravel run around downstream; 11’ clear roadway; - Bridge 101 posted 10-Ton prior to 103, may need to shore up - NCDOT to provide updated geotech report when FSMs are provided. Sequencing Bridge No. 480103 is located within National Forest Service property and the Department has entered into a Category 5 Agreement accordingly. In such case, the Department will be required to coordinate with the US Forest Service based on the right-of-way/final design. The Design-Build Team shall anticipate that it will take minimum of 6 months from the acceptance of the right-of-way design to conclude the Category 5 agreement process. Therefore, the Design-Build Team is encouraged to schedule the design early in the contract. Environmental SOW Commitment If any blasting or cutting back of slope is required, the Design-Build Team shall immediately notify NCDOT Staff Archaeologist and/or Division Environmental Officer, as listed below, who will initiate the required State/Federal coordination. All questions regarding this site shall be addressed to Mr. Matthew Wilkerson, NCDOT Archaeology (919) 707-6089, or the Division Environmental Officer. |  |  |  |  |  |  |  |  |  |  |