# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.14.R.105 |  |  | #### Field Scoping Meeting Date: Sept. 11, 2013 |  |  |
| --- | --- | --- | --- | --- | --- |
| Division: 14 |  |  | #### Location: On-site |  |  |
| Route (US/NC/SR): SR1462 |  |  | County: JACKSON |  |  |
| Project Description: Replace Bridge No. 490164 over WOODFIN CREEK |  |  |  |  |  |
| Tier: Sub-regional |  |  |  |  |  |
| #### Municipality: None |  |  |  |  |  |
| Attendees |  |  |  |  |
|  | Name | Phone No. |  | E-mail |
| Division Bridge Mgr | Josh Deyton | 828 586-2141 |  | jbdeyton@ncdot.gov |
| Div. Environmental Off. | Mark Davis | 828 586-2141 |  | markdavis@ncdot.gov |
| Div. 14 BMU | Mark Hill | 828-488-2131 |  | Mehill3@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 |  | Mshown@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 |  | rlassiter@ncdot.gov |
| Bridge Management | Paul Garrett | 919 835-8491 |  | pgarrett@ncdot.gov |
| TPMU | Christy Huff | 919-707-6606 |  | chuff@ncdot.gov |
| TPMU | Pam Williams | 919 707-6608 |  | prwilliams@ncdot.gov |
| USFWS | Jason Mays |  |  | Not in attendance |
| DENR-DWQ | Amy Chapman |  |  | Not in attendance |
| WRC | Marla Chambers |  |  | Not in attendance |
| USACE | Lori Beckwith |  |  | Not in attendance |

Existing Features

| Feature Bridged: 490164 over WOODFIN CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 19.1 (Ft.) |  |  | Approach Roadway width: 18 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 21 (Ft.) |  |  | Deck Width (Out To Out): 20(Ft.) |  |  |  |  |
| Water Depth: (Ft.) |  |  | Height Bed-To-Crown: (Ft.) |  |  |  |  |
| Built date: 1957 |  |  | Posted: SV 24 |  |  | TTST: 37 |  |
| Superstructure Type: TM M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: NONE |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 9 ; DP: 1.5 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 25 posted (mph) or Statutory 55mph |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: N/A |  |  |  |  |  |  |  |
| Approximate Length Of Detour? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? N/A |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict AT&T underground cable goes aerial at bridge |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict At intersection |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: JD Stream downstream right side downhill road ditch |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog turtle, Carolina northern flying squirrel, Indiana bat, Appalachian Elktoe, Spruce-fir moss spider, small whorled pogonia, swamp pink, Rock gnome lichen |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: Yes |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: Yes | Which species : Rainbow |  |  |  | Duration: Jan. 1 – April 15 |  |
| Permits Required: (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: C - TR |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: Little Tennessee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest No |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries; No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NSR |  |  | Archaeology Survey required; NSR |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: 0.3 mile from NC-2/Mtns to Sea Route 107 |  |  |  |  |  |  |
| Comments: *Spring fed stream coming into creek |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? No (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? |  |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 55’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |  |
| Waive offset: No | Cap: 4’ |  |  |  |  | Skewed: |
| - Hold north side face of bridge |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - Clear roadway width: 11’ Temp. Signals: yes Stage Downstream |  |  | New Alignment: |  |  |  |  | On-site detour |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 330 SIR |  | NHS: No | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 27’ OTO - 42” Rail |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 9‘ with 3‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2 ½” inches: |  |  |  |  | Existing Roadway: paved |  |  |  |  |  |
| Pavement markers: None |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  | Method of Clearing: II |  |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  | Reasonable Safe Speed: 25 mph posted per SIR |  |  |  |  |  |
| Liquidated damages: will be imposed after 180 days of construction. Amt: $ 350 per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by NCDOT |  |  | R/W: DBT |  |  |  |  | R/W monuments: Pin/ Cap |  |  |
| Salvageable materials: No |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: None |  |  |  |  |  |  |  |  |  |  |
| Comments: Resurface intersection SR-1463 to furthest radius or existing asphalt limits. Hold north side face of bridge |  |  |  |  |  |  |  |  |  |  |