# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.14.R.106 |  |  | #### Field Scoping Meeting Date: Sept. 11, 2013 |  |  |
| --- | --- | --- | --- | --- | --- |
| Division: 14 |  |  | #### Location: On-site |  |  |
| Route (US/NC/SR): SR1747 |  |  | County: JACKSON |  |  |
| Project Description: Replace Bridge No. 490182 over JOHNS CREEK |  |  |  |  |  |
| Tier: Sub-regional |  |  |  |  |  |
| #### Municipality: None |  |  |  |  |  |
| Attendees |  |  |  |  |
|  | Name | Phone No. |  | E-mail |
| Division Bridge Mgr | Josh Deyton | 828 586-2141 |  | jbdeyton@ncdot.gov |
| Div. Environmental Off. | Mark Davis | 828 586-2141 |  | markdavis@ncdot.gov |
| Div. 14 BMU | Mark Hill | 828-488-2131 |  | Mehill3@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 |  | Mshown@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 |  | rlassiter@ncdot.gov |
| Bridge Management | Paul Garrett | 919 835-8491 |  | pgarrett@ncdot.gov |
| TPMU | Christy Huff |  |  |  |
| TPMU | Pam Williams | 919 707-6608 |  | prwilliams@ncdot.gov |
| NCDOT | Eileen Fuchs Pam Williams Josh Deyton Mark Davis 2/6/14 |  |  |  |
| USFS | Karen Compton 2/6/14 |  |  |  |
| USFWS | Jason Mays |  |  | Not in attendance |
| DENR-DWQ | Amy Chapman |  |  | Not in attendance |
| WRC | Marla Chambers |  |  | Not in attendance |
| USACE | Lori Beckwith |  |  | Not in attendance |

Existing Features

| Feature Bridged: 490182 over JOHNS CREEK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 19.1 (Ft.) |  |  | Approach Roadway width: 18 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 21 (Ft.) |  |  | Deck Width (Out To Out): 19.8 (Ft.) |  |  |  |  |
| Water Depth: (Ft.) |  |  | Height Bed-To-Crown: (Ft.) |  |  |  |  |
| Built date: 1961 |  |  | Posted: SV 25 |  |  | TTST: 39 |  |
| Superstructure Type: TM M-BM |  |  |  | End Bent Material Type: TM |  |  |  |
| Interior Bent Material Type: NONE |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |
| Sufficiency Rating: 9 ; DP: 0 |  | School Bussing crossings per day: |  |  |  |  |  |
| Posted Speed Limit Vicinity: 35 (mph) |  |  |  |  |  |  |  |
| Detour: Off-Site | Stage Construction: |  |  |  | On-site: |  |
| If Off-Site, Description Of Detour Route: N/A |  |  |  |  |  |  |  |
| Approximate Length Of Detour? Dead end road |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? Projects B-4472 and B-4612 are nearby on connecting SR 1737 |  |  |  |  |  |  |  |
| Sequencing priority in construction? |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? N/A |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? N/A |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict NONE; all are out of the way |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Utility attached to joist In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 0 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No Comments: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species Populations In Area? No T&E species listed in County: Bog turtle, Carolina northern flying squirrel, Indiana bat, Appalachian Elktoe, Spruce-fir moss spider, small whorled pogonia, swamp pink, Rock gnome lichen |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: Yes |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: Yes | Which species : Rainbow Trout |  |  |  | Duration: Jan. 1 – Apr. 15 |  |
| Permits Required: WSIII: TR (NCDOT will submit all permits prepared by DB Team) |  |  |  |  |  |  |
| Water Quality Classification: |  |  |  |  | 303d: |  |
| Coast Guard Permit? No |  | Drainage Basin: Little Tennessee |  |  |  | Riparian Buffer rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest Yes |  |  | Wildlife Refuge No ; |  |  |  |
| State, County, Or Local Park No; |  |  | Wild And Scenic River No; |  |  |  |
| Airport No; |  |  | Lake For Recreation Of Power Generation No |  |  |  |
| Water Supply Reservoir No; |  |  | Nutrient Sensitive Waters No |  |  |  |
| Public Use Boat Ramp No; |  |  | Cemeteries; Coward Cemetery driveway is at bridge, cemetery is not at bridge site |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Historic Archit. Survey required; NHP |  |  | Archaeology Survey required; coordination with USFS archaeological site on NW quad. See comment below: |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Any Church, Community Center, Or Other Public Facility Impacts? No |  |  |  |  |  |  |
| Project in on a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |
| Comments: Property around bridge is privately owned, but east of the bridge site is Nantahala National Forest; met with USFS on 2/6/14. |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And / Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type:

Hydraulics

| FEMA Approval? No (MOA ) |  |  | State Stormwater Permit? No |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? |  |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? |  |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |  |
| Length Of Structure: 35’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |  |
| Waive offset: Yes | Cap 4’ |  |  |  |  | Skewed: Yes: 60-degrees |
| - vertical abutments |  |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: - |  | New Alignment: |  | On-site detour gravel temporary onsite detour; 1-lane with 11-foot CRW with a stop sign on both sides; Alignment: DBT to determine best location. Design for stop conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Rule Checklist |  |  |  |  |  |  |  |  |  |  |
| ADT: 420 SIR |  | NHS: No |  | Tier: Sub-regional |  |  | Func. Class: L-Rural |  |  |  |
| Bridge Min. Clear Deck width Recommended by Div.: 27’ OTO |  |  |  |  |  |  |  |  |  |  |
| Roadway lane width 9‘ with 3‘ shoulders including no paved shoulders |  |  |  |  |  |  |  |  |  |  |
| Paved shoulders to be extended to end of construction limits and: N/A |  |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2 ½” inches: |  |  |  |  |  | Existing Roadway: paved |  |  |  |  |
| Pavement markers: None |  |  |  |  |  | Pavement Marking on Asphalt: Paint |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  |  |  | Method of Clearing: II |  |  |
| Truck Percentage: : 6 %; 3% Duals & 3% TTST |  |  |  |  |  | Reasonable Safe Speed: 20 mph per SIR |  |  |  |  |
| Liquidated damages: will be imposed after 150 days of closure. Amt: $ 600 per day |  |  |  |  |  |  |  |  |  |  |
| CEI: by NCDOT |  |  |  | R/W: DBT |  |  |  |  | R/W monuments: Pin/Caps. |  |
| Salvageable materials: No |  |  |  |  |  |  |  |  |  |  |
| Removal of remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |  |
| Comments: - Avoid impact on NW quadrant due to historic archaeology site. - Avoid impact to the National Forest Service property east of the bridge. Avoid any tree that reference USFS property on private property or if it impacted. Sequence and Schedule Restricts: There is a historic boundary located in the northwest quadrant of Bridge No. 480182 and any construction activities shall be avoided. No work at this site will be permitted prior to resolution of the historic issues. Therefore, the Design-Build Team shall prepare right-of-way plans early in this contract for this site to allow the Department to complete the assessment and the determination of any mitigation responsibilities in coordination with the State Historic Preservation Office. Any mitigation measures necessary as a result of this coordination will be paid for as Extra Work in accordance with Article 104-8(A) of the Standard Specifications. The National Forest Service lands are located east of Bridge No. 480182 and the Department has entered into a Category 5 Agreement accordingly. In such case, the Department will be required to coordinate with the US Forest Service based on the final design. The Design-Build Team shall anticipate that it will take roughly 6 months from the acceptance of the accepted right-of-way design to conclusion of the Category 5 agreement process. Therefore, the Design-Build Team is encouraged to schedule the design early in the contract. Environmental SOW: Property located on the northwest quadrant at Bridge No. 480182 has a historic boundary and shall be avoided (boundary provided in microstation format to be shown of plans as Historic Boundary). The Design-Build Team shall submit a set of preliminary roadway and right-of-way plans to Mr. Matt Wilkerson for review and to initiate any State/Federal coordination as applicable. |  |  |  |  |  |  |  |  |  |  |