# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.6.R.61 | #### Field Scoping Meeting Date: July 22, 2014 |
| --- | --- |
| Division: 6 | #### Location: On-site |
| Route (US/NC/SR): SR 1005 | County: COLUMBUS |
| Project Description: Bridge No. 230308 over SOULES SWAMP on SR 1005 (Peacock Rd.) |  |
| Tier: Subregional |  |
| #### Municipality: Chadbourn *Municipality Agreement |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Brice Bell | 910-486-1493 | bricebell@ncdot.gov |
| Division Environmental Off. | Jim Rerko | 910-437-0207 | jjrerko@ncdot.gov |
| Hydraulics Engineer | Jerry Lindsey | 919-707-6734 | jlindsey@ncdot.gov |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | Rachel Evans | 919-707-6609 | rcevans@ncdot.gov |
| TPMU | Jamie Lancaster | 919-707-6620 | jlancaster@ncdot.gov |
| Bridge Management | Paul Garrett | 919-707-6457 | pgarrett@ncdot.gov |
| Resident Engineer | W.R. Marsh |  |  |
| Assistant Resident Engineer | Terry Church |  |  |
| Div 6 Locating Engineer | John Kaukola |  |  |
| Division Maintenance Engineer | Ken Murphy |  |  |
| Division Bridge Engineer | Darren Pittman |  |  |
| Bridge Maintenance Supervisor | Barry Gelezinsky |  |  |
| NCDOT Div 6 | Kevin Worley |  |  |
| District Engineer | Drew Cox |  |  |
| USFWS* | Gary Jordan | 919-856-4520x32 | gary_jordan@fws.gov; |
| DENR-DWR | Mason Herndon | 910-308-4021 | Mason.herndon@ncdenr.gov |
| USACE* | Liz Hair | 910-251-4049 | sarah.e.hair@usace.army.mil |
| NCWRC* | Travis Wilson | 919-707-0370 | Travis.Wilson@ncwildlife.org; |

*invited but did not attend

**see sign-in sheet for more info

Existing Features

| Feature Bridged: 230308 over SOULES SWAMP on SR 1005 (Peacock Rd.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 24 (Ft.) |  |  | Roadway width: 18 (Ft.) |  |  |  |  |  |
| (Bridge / Culvert) Length: 37 (Ft.) |  |  | Deck Width (Out To Out): 25.33(Ft.) |  |  |  |  |  |
| Water Depth: 3(Ft.) |  |  | Height Bed-To-Crown: 10(Ft.) |  |  |  |  |  |
| Year Built: 1951 |  |  | Posted: SV 18 |  |  |  | TTST: 26 |  |
| Superstructure: ST M-BM |  | Abutment: TM |  |  |  | Pier Type: TM |  |  |
| Temp. Shored: Yes |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |
| PRI: 65 DP: 1.5 SR: 6.98 |  |  |  | School Bussing crossings per day: 2 trips/4 buses |  |  |  |  |
| Posted Speed Limit Vicinity: 55 (mph) |  |  |  | Existing Road Surface: Paved |  |  |  |  |
| Detour Off-Site | Stage Construction |  |  | New Alignment | On-site |  |  |  |
| If Off-Site, Description Of Detour Route: West route: Bus 74/76, NC 410, SR 1317 (East Institute Street), SR 1429 |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 6.0 ( Miles ) |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing (with St./Rd. names) |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No, pipe upstream on SR1429 |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? Length of Detour route would increase response times for fire, EMS and law enforcement |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? Yes but rail is not active |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict upstream, double circuit line, guy wire crosses 35’ north of bridge, |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict downstream |  |  |  |  |  |  |  |
| Sewer In Conflict downstream |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 12 Months if transmission line to be relocated. |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area No |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted No |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site Yes |  |  |  | Comments: NES located |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Endangered Species In County: American alligator, Atlantic sturgeon, Bald Eagle (BGPA), Red-cockaded woodpecker, Shortnose sturgeon, Waccamaw silverside, Wood stork, Cooley’s meadowrue & Rough-leaved loosestrife. |  |  |  |  |  |  |  |
| T&E species effect: Waccamaw silverside – No effect |  |  |  |  |  |  |  |
| Trout County : No |  |  | TVA County: No |  |  |  |  |
| CAMA County: No |  |  | Primary Nursery Area: No |  |  |  |  |
| Moratoria: No |  | Which species: |  |  |  | Duration : |  |
| Permits: Nationwide 14 |  |  |  |  |  |  |  |
| Water Quality Classification: C; Sw |  |  |  |  |  |  | 303d: No |
| Coast Guard Permit? No | Drainage Basin: Lumber |  |  |  | Riparian Buffer Rules: No |  |  |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |  |
| National Forest: No |  |  |  | Wildlife Refuge: No |  |  |  |
| State, County, Or Local Park: No |  |  |  | Wild And Scenic River: No |  |  |  |
| Airport: No |  |  |  | Recreation Of Power Generation: No |  |  |  |
| Water Supply Reservoir: No |  |  |  | Nutrient Sensitive Waters: No |  |  |  |
| Public Use Boat Ramp: No |  |  |  | Cemeteries: No |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |  |
| Architecture: No Survey Required |  |  |  | Archaeology: No Archaeological Sites |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? No |  |  |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And/Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type: @ End Bents @ Interior Note: *H piles or pipe piles allowed, no concrete piles

Hydraulics

| FEMA Approval? Limited DS |  |  | State Stormwater Permit? No |  |  |
| --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? No |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Standard end bent |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: N/A |  |
| Superstructure Type: Culvert |  | If Bridge: |  |  | If girder; why? |
| Length Of Structure: | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |
| Waive offset: | Cap: |  |  |  | Skewed: 90 |
| -culvert due to site constraints, avoid sewer line and transmission line relocation. -culvert 3@12x8 RCBC cast in place (no precast), sills (1’ sill in center barrel, 2’ minimum sill in exterior barrels), buried 1’ |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: |  |  |  |  | New Alignment: |  |  | On-site detour |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |  |
| ADT: 2500 SIR |  | NHS: No |  | Tier: Subregional |  |  |  | Func. Class: Minor Collector, Rural |  |
| Bridge Min. Clear Deck Width Recommended by Div.: |  |  |  |  |  |  |  |  |  |
| Roadway lane width 11‘ with 6‘ shoulders including 2’ paved shoulders (@ guardrail location only, use 4’ shoulders to minimize impacts to utilities) |  |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: end of construction limits and blunt end. |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 3” inches: |  |  |  |  | Existing Roadway: 18 |  |  |  |  |
| Pavement Marking: Thermoplastic |  |  |  |  | Pavement markers: Raised |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  | Method of Clearing: II modified |  |  |  |  |
| Truck Percentage: : 6% per BIR |  |  |  |  | Reasonable Safe Speed per SIR: 55 mph |  |  |  |  |
| Liquidated damages: will be imposed after 120 days of closure/construction. Amt: $ 500 per day |  |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  |  | R/W by? DBT |  |  |  | R/W monuments? concrete monuments |  |  |
| Salvageable materials: No |  |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? Construction from labor day to memorial day (no construction during summer months) |  |  |  |  |  |  |  |  |  |
| Comments: -Drainage District canal access to be maintained on both sides of roadway. -Strawberry festival 1st weekend of May- should not be of concern to detour traffic -Need to avoid impacts to sewer line and water line downstream of bridge and power transmission line upstream of bridge. -May need to consider asymmetrical widening due to gravity sewer line downstream side Division requests new pavement a minimum of 50 feet from ends of culvert |  |  |  |  |  |  |  |  |  |