# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.9.R.61 | #### Field Scoping Meeting Date: Nov 17 2014 |
| --- | --- |
| Division: 9 | #### Location: On-site |
| Route (US/NC/SR): SR1647 | County: STOKES |
| Project Description: Bridge No. 840224 over MILL CREEK (HAWKINS MILL CREEK) on SR1647 (Tom Shelton Rd.) |  |
| Tier: Sub-Regional |  |
| #### Municipality: N/A |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Program Manager | Matt Jones | 336-747-7800 | mwjones@ncdot.gov |
| Division Environmental Off. | Amy Euliss | 336-747-7800 | aeuliss@ncdot.gov |
| Division Environmental Off. | Stephanie Braquet | 336-747-7800 | scbraquet@ncdot.gov |
| Hydraulics Engineer | Galen Cail | 919-707-6711 | gcail@ncdot.gov |
| Hydraulics Engineer | Chris Lewis | 919-707-6714 | crlewis2@ncdot.gov |
| Hydraulics Tech | Amy Keeter | 919-707-6730 | amkeeter@ncdot.gov |
| Hydraulics Trainee | Courtney Carpenter | 919-707-4833 | cacarpenter@ncdot.gov |
| TPMU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| TPMU | Rachel Evans | 919 707-6609 | rcevan@ncdot.gov |
| TPMU | Jamie Lancaster | 919-707-6620 |  |
| Bridge Management | Paul Garrett | 919-707-6457 | pgarrett@ncdot.gov |
| USACE | John Thomas** | 919-554-4884 x.25 | john.t.thomas.jr@usace.army.mil |
| DENR-DWQ | Dave Wanucha** | 336-771-4951 | dave.wanucha@ncdenr.gov |
| USFWS | Jason Mays | 828-258-3939 x.226 | jason_mays@fws.gov |
| NCWRC | Marla Chambers | 704-984-1070 | marla.chambers@ncwildlife.org |
| L&S-Region III Locating Eng | Pat Tuttle | 336-969-9550 | ptuttle@ncdot.gov |
| Division 9 Locating Engineer | Mike Motsinger | 336-969-9550 | mmotsinger@ncdot.gov |

**Did not attend but sent comments

Existing Features

| Feature Bridged: 840224 over MILL CREEK (HAWKINS MILL CREEK) on SR1647 (Tom Shelton Rd.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 23.75 (Ft.) |  |  | Roadway width: 19 (Ft.) |  |  |  |  |  |
| (Bridge / Culvert) Length: 41 (Ft.) |  |  | Deck Width (Out To Out): 24.75 (Ft.) |  |  |  |  |  |
| Water Depth: 1 (Ft.) |  |  | Height Bed-To-Crown: 11 (Ft.) |  |  |  |  |  |
| Year Built: 1969 |  |  | Posted: SV 99 |  |  | TTST: 99 |  |  |
| Superstructure: PPCS (BMD-19) |  | Abutment: Ebs: PPC caps, steel posts&concr sills |  |  |  |  | Pier Type: |  |
| Temp. Shored: T |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |
| PRI: 51.4 DP: 0 SR: 30.3 |  |  |  | School Bussing crossings per day: division to provide |  |  |  |  |
| Posted Speed Limit Vicinity: 55 (mph) statutory |  |  |  |  |  |  |  |  |
| Detour Off-Site | Stage Construction |  |  | New Alignment | On-site |  |  |  |
| If Off-Site, Description Of Detour Route: SR 1649 (Steele Rd) – SR 1652 (Moir Farm Rd) – SR 1674 (Sheppard Mill/Delta Church Rd) |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 4.2 miles; original length 1.4 miles |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing with Street/Road names |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |
| Are future plans for upgrading this roadway either at or in the vicinity of this project? no |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? Yes, BD-5109AF (Bridge No. 840108 on SR 1674), should be completed by Fall 2015 |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? division to provide |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict yes, crosses rd at left end of bridge (lkg d/s) |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict yes |  |  |  |  |  |  |  |
| Telephone In Conflict yes |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area No |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted No |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site: no |  | Comments: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Endangered Species In County: Schweinitz’s sunflower, Small-anthered bittercress, James spinymussel, Northern long-eared bat; Habitat present for Bald Eagle |  |  |  |  |  |  |  |
| T&E species effect: No effect: Schweintz's sunflowers, James spinymussel, Bald Eagle; May effect not likely to adversely effect: Northern long-eared bat; DEO to survey (April-May): Small-anthered bittercress |  |  |  |  |  |  |  |
| Trout County: No |  | TVA County: No |  |  |  |  |  |
| CAMA County: No |  | Primary Nursery Area: No |  |  |  |  |  |
| Moratoria: No |  |  | Which species: |  |  | Duration : |  |
| Bats found on bridge: no, 10-27-14 tree clearing: possible |  |  |  |  |  |  |  |
| Tree Survey: no bat moratorium for tree clearing: commit to clearing trees in winter or tree bat survey will be required |  |  |  |  |  |  |  |
| Permits discussion: |  |  |  |  |  |  |  |
| Water Quality Classification: C |  |  |  |  |  |  | 303d: No |
| Coast Guard Permit? No | Drainage Basin: Roanoke |  |  |  | Riparian Buffer Rules: No |  |  |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |  |
| National Forest: No |  |  |  | Wildlife Refuge: No |  |  |  |
| State, County, Or Local Park: No |  |  |  | Wild And Scenic River: No |  |  |  |
| Airport: No |  |  |  | Recreation Of Power Generation: No |  |  |  |
| Water Supply Reservoir: No |  |  |  | Nutrient Sensitive Waters: No |  |  |  |
| Public Use Boat Ramp: No |  |  |  | Cemeteries: |  |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |  |
| Architecture: Survey Required |  |  |  | Archaeology: No Survey Required |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: no |  |  |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? no |  |  |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: no |  |  |  |  |  |  |  |
| Comments: -Within ½ mile Voluntary Agricultural District; No concerns per Stokes County VAD Coordinator. |  |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And/Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type: @ End Bents @ Interior

Hydraulics

| FEMA Approval? Limited Detailed Study (MOA ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? no |  |  | Is Protection Needed? Std end bent |  |  |
| Are Banks Stable? yes |  |  | Is Protection Needed? no |  |  |
| Appreciable Amount Of Large Debris? low |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: no |  |  |  | Where: |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |
| Length Of Structure: 60’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: 1@60’ |
| Waive offset: yes | Cap: 2’6” |  |  |  | Skewed: no |
| -keep concrete mud sills |  |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: Clear roadway width (CRW): Temp. Signals: Alignment: N, E, W, S |  |  |  |  | New Alignment: Alignment; N, E, W, S |  |  | On-site detour CRW: one lane w/ signals; or two lanes CRW; Alignment; |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |  |
| ADT:120 per SIR |  | NHS: 0 |  | Tier: Sub-Regional |  |  | Func. Class: Local |  |  |
| Bridge Min. Clear Deck Width Recommended by Div.: 30’ out to out |  |  |  |  |  |  |  |  |  |
| Roadway lane width 10’ with 3’ shoulders |  |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: n/a |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? yes |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2 ½ inches |  |  |  |  | Existing Roadway: 19 |  |  |  |  |
| Pavement Marking: Paint |  |  |  |  | Pavement markers: None |  |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  | Method of Clearing: III |  |  |  |  |
| Truck Percentage: 6 % per BIR |  |  |  |  | Reasonable Safe Speed per SIR: 40 mph |  |  |  |  |
| Liquidated damages: will be imposed after 100 days of closure/construction. Amt: $ 500 per day |  |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  |  | R/W by? DBT |  |  |  |  | R/W monuments? Conc. |  |
| Salvageable materials: NONE |  |  |  |  |  |  |  |  |  |
| Contact Person/number: |  |  |  |  |  |  |  |  |  |
| Deliver to: |  |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: none |  |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |