# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| TIP No.: B-5699 | WBS No.: 45653.1.1 | #### Field Scoping Meeting Date: 1/26/16 |
| --- | --- | --- |
| Division: 6 |  | #### Location: On-site |
| Route (US/NC/SR): NC 214 |  | County: COLUMBUS |
| Project Description: Bridge No. 230068 over Big Creek on NC 214 (Sam Potts Hwy.) |  |  |
| Tier: REGIONAL |  | Funding: HFB |
| #### Municipality: N/A |  |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Program Manager | Brice Bell | 910-486-1493 | bricebell@ncdot.gov |
| Division Environmental Officer | Jim Rerko | 910-437-0207 | jjrerko@ncdot.gov |
| Hydraulics Engineer | Jerry Lindsey | 919-707-6734 | jlindsey@ncdot.gov |
| Hydraulics Engineer | Jon Moore | 919-707-6738 | Jlmoore6@ncdot.gov |
| DENR-DWR | Mason Herndon | 910-308-4021 | Mason.herndon@ncdenr.gov |
| USACE | Liz Hair | 910-251-4049 | sarah.e.hair@usace.army.mil |
| PPU | Rachel Evans | 919-707-6609 | rcevans@ncdot.gov |
| District Engineer | Drew Cox | 910-642-3760 |  |
| Assistant Resident Engineer | Terry Church | 910-642-2489 |  |
| County Maintenance Engineer | Ken Clark | 910-862-3396 |  |
| Resident Engineer | Rusty Marsh | 910-642-2489 |  |
| Division Maintenance Engineer | Ken Murphy | 910-486-1493 |  |
| Division Bridge Maintenance Engineer | Darren Pittman | 910-829-6345 |  |
| Bridge Maintenance Supervisor | Gary Hilburn | 910-642-4388 |  |
| PPU | Pam Williams | 919-707-6608 |  |
| Assistant Resident Engineer | Donavan Hunt | 910-618-5690 |  |
| Assistant District Engineer | Michael Griffin | 910-728-5842 |  |
| Bridge Maintenance Supervisor | Daniel Leggett | 910-618-5542 |  |
| Division L&S | John Kaukola | 910-486-1338 |  |

Existing Features

| Feature Bridged: 230068 over Big Creek on NC 214 (Sam Potts Hwy.) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 35.83 (Ft.) |  |  |  |  |  | Roadway width: 33.50 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 74 (Ft.) |  |  |  |  |  | Deck Width (Out To Out): 38.00 (Ft.) |  |  |  |  |
| Water Depth: 2 (Ft.) |  |  |  |  |  | Height Bed-To-Crown: 10 (Ft.) |  |  |  |  |
| Year Built: 1922 |  |  |  | Posted: SV 99 |  |  |  |  | TTST: 99 |  |
| Superstructure: 5.00 |  |  |  | Abutment: 5.00 |  |  |  |  | Pier Type: |  |
| Temp. Shored: No |  |  |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |  |  |
| PRI: 54.15 |  | DP: 4.50 |  |  | SR: 84.52 |  | School Bussing crossings per day: No Response |  |  |  |
| Posted Speed Limit Vicinity: 55 (mph) |  |  |  |  |  |  |  |  |  |  |
| Detour | Off-Site |  | Stage Construction |  |  |  |  | New Alignment |  | On-site |
| If Off-Site, Description Of Detour Route: SR 1740 - US 74 - NC 211 |  |  |  |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 7 Miles |  |  |  |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing with Street/Road names |  |  |  |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Are future plans for upgrading this roadway either at or in the vicinity of this project? No |  |  |  |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? No Response |  |  |  |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict possible, upstream |  |  |  |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |  |  |  |
| Fiber Optic In Conflict Yes, downstream |  |  |  |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |  |  |  |
| Sewer In Conflict Yes, downstream, force main sewer on shoulder owned by town of Bolton, goes to Whiteville |  |  |  |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site: Yes | Comments: |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Endangered Species In County: American alligator, Bald eagle (BGPA), Red-cockaded woodpecker, Waccamaw silverside, Wood stork, Cooley's meadowrue, Rough-leaved loosestrife |  |  |  |  |  |
| T&E species effect: No Effect: American alligator, Bald eagle (BGPA), Red-cockaded woodpecker, Waccamaw silverside, Cooley's meadowrue, Rough-leaved loosestrife; Unresolved: Wood stork |  |  |  |  |  |
| Trout County: No |  |  | TVA County: No |  |  |
| CAMA County: No |  |  | Primary Nursery Area: No |  |  |
| Moratoria: No |  | Which species: |  |  | Duration: |
| Permits discussion: NW14; DSSW required due to being a trib to ES waters |  |  |  |  |  |
| Water Quality Classification: C; Sw:+ |  |  |  |  | 303d: No |
| Coast Guard Permit? No |  | Drainage Basin: Lumber |  |  | Riparian Buffer Rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |
| National Forest: No |  |  | Wildlife Refuge: No |  |  |
| State, County, Or Local Park: No |  |  | Wild And Scenic River: No |  |  |
| Airport: No |  |  | Recreation or Power Generation: No |  |  |
| Water Supply Reservoir: No |  |  | Nutrient Sensitive Waters: No |  |  |
| Public Use Boat Ramp: No |  |  | Cemeteries: No |  |  |
| VAD/Farmland Protection: No |  |  | Game Lands: Yes All 4 quadrants, Black Bear Sanctuary, NCWRC, applies to entire 662’ long bridge |  |  |
| Known Or Potential Historic Properties In The Area: No |  |  |  |  |  |
| Architecture: NSR |  |  |  | Archaeology: NSR |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? No |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |
| Comments: |  |  |  |  |  |

Geotechnical

Are There Any Historical and/or Vibration Sensitive Structures Near By? Comments:

Are There Any Known Landfills and/or Geo-environmental Hazard Sites at/or Within Close Proximity To The Project Site? Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells? Comments:

Possible Foundation Type: End Bents: Interior Bents:

Hydraulics

| FEMA Approval? Yes, Detailed Study (Br #68 is overflow structure for Big Creek) (MOA ) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  | Is Protection Needed? STD |  |  |
| Are Banks Stable? Yes |  | Is Protection Needed? STD |  |  |
| Appreciable Amount Of Large Debris? Moderate to heavy |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: Yes |  |  | Where: match upstream structure |  |
| Structure Type: Bridge | If Bridge: CS |  |  | If girder; why? |
| Length Of Structure: 107’ | Min. Number Of Spans: 3 |  |  | Span Arrangement: 1@36’, 1@35’, 1@36’ (match Bridge No. 230383) |
| Waive offset: Yes | EB Cap: 2'-6" |  |  | Skewed: 90 |
| *Bridge Nos. 230068 and 230077 are 1 bridge, 662’ long. In 1950, the 16 interior spans were converted to a pile supported roadway, bridge rail removed and earth fill material added to sides to resemble a typical roadway fill section. *Replacing with dual bridges and fill between. Match upstream structure lengths and pier placement. |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site | Stage Construction |  |  |  | New Alignment |  |  |  | On-site |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Clear roadway width: Temp. Signals: Alignment: N, E, W, S |  |  |  | Alignment: N, E, W, S |  |  |  | Clear roadway width: one lane w/ signals: or two lanes CRW: Alignment: N, E, W, S |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |  |
| ADT: 2000 |  | NHS: No |  | Tier: REGIONAL |  |  | Func. Class: Major Collector |  |  |
| Bridge Min. Clear Deck Width Recommended by Div.: 36’ OTO |  |  |  |  |  |  |  |  |  |
| Roadway lane width: 12’ with 6’ shoulders, including 2’ paved shoulders |  |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: end of construction limits and blunt ended |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 3" B mix |  |  |  |  |  | Existing Roadway: 30’ |  |  |  |
| Pavement Marking: Thermoplastic |  |  |  |  |  | Pavement Markers: Raised |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  | Method of Clearing: II except hand clearing in wetlands |  |  |  |
| Truck Percentage: 14 % per BIR *TBD |  |  |  |  |  | Reasonable Safe Speed per SIR: 55 mph |  |  |  |
| Liquidated damages: will be imposed after 300 days of closure/construction. Amt: $ 1,000 per day *combined with #77 |  |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  |  | R/W by? DBT |  |  |  |  | R/W monuments? Pin and cap |  |
| Salvageable materials: No |  |  |  |  |  |  |  |  |  |
| Contact Person/number: |  |  |  |  |  |  |  |  |  |
| Deliver to: |  |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? No priority. Bridge Nos. 230068 and 230077 shall be constructed concurrently |  |  |  |  |  |  |  |  |  |
| Comments: -Remove all of existing structure (Bridge #68/77 and the pile support roadway between) and undercut to remove existing fill and organic soils underneath the proposed embankments and existing embankments between Bridge # 68 &77. -West end of bridge has settled- undercut west approach. -Full depth pavement 50’ from each fill face -Maintain proposed typical between Bridge Nos. 68 and 77. Extend guardrail continuously between bridges. |  |  |  |  |  |  |  |  |  |