# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.118 | #### Field Scoping Meeting Date: June 15, 2016 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1209 | County: WATAUGA |
| Project Description: Bridge No. 940022 over Beaver Dam Creek on SR1209 (Rush Branch Road) |  |
| Tier: Sub-Regional |  |
| #### Municipality: No |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Off. | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Division Bridge Program Tech | Mark Johnson | 336-903-9208 | mgjohnson4@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 | rlassiter@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 | mshown@ncdot.gov |
| PPU | Christy Huff | 919-707-6606 | chuff@ncdot.gov |
| PPU | Eileen Fuchs | 919-707-6613 | eafuchs@ncdot.gov |
| Region III Locating Engr. | Pat Tuttle | 336-969-9550 | ptuttle@ncdot.gov |
| Division Locating Engr. | Larry Absher, Jr. | 336-903-9501 | lrabsher@ncdot.gov |
| Division 11 L&S | Landon Wagoner | 336-903-9501 | rlwagoner@ncdot.gov |
| NCWRC | Marla Chambers | 704-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 940022 over Beaver Dam Creek on SR1209 (Rush Branch Road) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 24.5 (Ft.) |  |  | Roadway width: 18 (Ft.) |  |  |  |  |  |
| (Bridge / Culvert) Length: 46 (Ft.) |  |  | Deck Width (Out To Out): 24.083(Ft.) |  |  |  |  |  |
| Water Depth: 1(Ft.) |  |  | Height Bed-To-Crown: 11(Ft.) |  |  |  |  |  |
| Year Built: 11 |  |  | Posted: SV 19 |  |  |  | TTST: 22 |  |
| Superstructure: Steel Plank Floor on I-beams |  | Abutment: Tim. Caps/tim. Post & sills |  |  |  | Pier Type: |  |  |
| Temp. Shored: |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |
| PRI: DP: SR: 33.56 |  |  |  | School Bussing crossings per day: N/A |  |  |  |  |
| Posted Speed Limit Vicinity: Stat. 55 (mph) |  |  |  |  |  |  |  |  |
| Detour Off-Site | Stage Construction |  |  | New Alignment | On-site |  |  |  |
| If Off-Site, Description Of Detour Route: N/A |  |  |  |  |  |  |  |
| Approximate Length Of Detour? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are future plans for upgrading this roadway either at or in the vicinity of this project? No |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? N/A |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? N/A |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? N/A |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict on the bridge |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 1 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area No |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted No |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site Yes, NE Quadrant; to be delineated by NES |  |  |  | Comments: Not near hibernaculum; therefore, NLEB is not an issue |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Endangered Species In County: Bog Turtle, Carolina northern flying squirrel, Northern long-eared bat, Virginia big-eared bat, Spruce-fir moss spider, BlueRidge goldenrod, Heller’s blazing star, Roan mountain bluet, Spreading avens |  |  |  |  |  |  |
| T&E species effect: No |  |  |  |  |  |  |
| Trout County : Yes |  |  |  | TVA County: Yes |  |  |
| CAMA County; No |  |  |  | Primary Nursery Area: No |  |  |
| Moratoria: Yes |  | Which species: Rainbow trout |  |  |  | Duration : Jan 1 – April 15 |
| Permits: NWP 3 or GP31 |  |  |  |  |  |  |
| Water Quality Classification: C; Tr |  |  | 303d: Yes; poor fish community |  |  |  |
| Coast Guard Permit? No | Drainage Basin: Watauga |  |  |  | Riparian Buffer Rules: No |  |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |
| National Forest; No |  |  |  | Wildlife Refuge ; No |  |  |
| State, County, Or Local Park ; No |  |  |  | Wild And Scenic River ; No |  |  |
| Airport; No |  |  |  | Recreation Of Power Generation No |  |  |
| Water Supply Reservoir; No |  |  |  | Nutrient Sensitive Waters; No |  |  |
| Public Use Boat Ramp; No |  |  |  | Cemeteries; No |  |  |
| Known Or Potential Historic Properties In The Area: |  |  |  |  |  |  |
| Architecture; No Historic Properties Present |  |  |  | Archaeology; Survey Required |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? Yes, school & school play ground |  |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |
| Comments: Bethel Elementary School and play ground |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And/Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type: @ End Bents @ Interior

Hydraulics

| FEMA Approval? No (MOA ) |  |  | State Stormwater Permit? No |  |  |
| --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  |  | Is Protection Needed? Standard end bent protection |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Standard end bent protection |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |
| Superstructure Type: Bridge |  | If Bridge: CS |  |  | If girder; why? |
| Length Of Structure: 70’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |
| Waive offset: No | Cap: 4’ |  |  |  | Skewed: match creek & depends upon alignment |

Replace the drainage pipe in the southwest quadrant.

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: |  |  | New Alignment: Alignment; West |  |  |  | On-site detour |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |
| ADT:130 / SIR | NHS: 0 |  | Tier: Sub-Regional |  |  | Func. Class: Local, Rural |  |  |
| Bridge Min. Clear Deck Width Recommended by Div.: 30’ out to out |  |  |  |  |  |  |  |  |
| Roadway lane width 10‘ with 6‘ shoulders including 4’ paved shoulders; 2 bar metal rail as requested by Division due to proximity to school. |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: end of construction limits and tapered 8:1 |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2-1/2” inches: |  |  |  |  | Existing Roadway: 18’ |  |  |  |
| Pavement Marking: Paint |  |  |  |  | Pavement markers: None |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  | Method of Clearing: III |  |  |  |
| Truck Percentage: : 6 % per BIR; |  |  |  |  | Reasonable Safe Speed per SIR: 25 mph |  |  |  |
| Liquidated damages: will be imposed after 150 days of closure/construction. Amt: $ _500_ per day |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  | R/W by? DBT |  |  |  |  | R/W monuments? Pin/cap. |  |
| Salvageable materials: Steel I-beams, bearing plates, diaphragms, steel guardrail, posts, post blocks and timber caps |  |  |  |  |  |  |  |  |
| Contact Person/number: David Scott (828) 268-6062 (DBT to deliver) |  |  |  |  |  |  |  |  |
| Deliver to: Boone Bridge Maintenance Facility at 1989 NC Hwy 194 North, Boone NC 28607 |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: No |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |  |
| Comments: -maintain access to the two agriculture fields on east & west sides. –Avoid/minimize impact to school property. - Retain concrete footers |  |  |  |  |  |  |  |  |