# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| WBS No.: 17BP.11.R.97 | #### Field Scoping Meeting Date: May 5, 2014 |
| --- | --- |
| Division: 11 | #### Location: On-site |
| Route (US/NC/SR): SR1340 | County: WATAUGA |
| Project Description: Bridge No. 940083 over NORTH FORK NEW RIVER on SR1340 (Meat Camp Road) |  |
| Tier: Sub-Regional |  |
| #### Municipality: No |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Hydraulics Engineer | Randy Henegar | 919-707-6726 | rhenegar@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 | mshown@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 | rlassiter@ncdot.gov |
| TPMU | Virginia Mabry | 919-707-6604 | vmabry@ncdot.gov |
| Bridge Management | Paul Garrett | 919-707-6457 | pgarrett@ncdot.gov |
| NCWRC | Marla Chambers | 704-984-1070 | Marla.chambers@ncwildlife.org |

Existing Features

| Feature Bridged: 940083 over NORTH FORK NEW RIVER on SR1340 (Meat Camp Road) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 15.70 (Ft.) |  |  | Roadway width: 16 (Ft.) |  |  |  |  |  |
| (Bridge / Culvert) Length: 19 (Ft.) |  |  | Deck Width (Out To Out): 17.80(Ft.) |  |  |  |  |  |
| Water Depth: 2(Ft.) |  |  | Height Bed-To-Crown: 7(Ft.) |  |  |  |  |  |
| Year Built: 1965 |  |  | Posted: SV 99 |  |  |  | TTST: 99 |  |
| Superstructure: TM M-BM ; |  | Abutment: TM |  |  |  | Pier Type: NONE |  |  |
| Temp. Shored: No |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |
| PRI: 55.3 DP: 0 SR: 15.9 |  |  |  | School Bussing crossings per day: N/A |  |  |  |  |
| Posted Speed Limit Vicinity: 55 mph (statutory) |  |  |  |  |  |  |  |  |
| Detour Off-Site | Stage Construction |  |  | New Alignment | On-site |  |  |  |
| If Off-Site, Description Of Detour Route: N/A |  |  |  |  |  |  |  |
| Approximate Length Of Detour? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? N/A |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? N/A |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? N/A |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? N/A |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? N/A |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? N/A |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict Yes Power |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |
| Telephone In Conflict Yes Overhead |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |
| Based On The Past History Near This Project Site, What Is The Estimated Time Required To Complete Utility Adjustments 3 Months |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area No |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted No |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site No |  |  |  | Comments: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Endangered Species In County: Bog turtle, Carolina northern flying squirrel, Virginia big eared bat, Spruce-fir moss spider, Blue Ridge goldenrod, Heller’s blazing star, Roan mountain bluet, Spreading avens, Rock gnome lichen, Northern long-eared bat |  |  |  |  |  |  |  |
| T&E species effect: No |  |  |  |  |  |  |  |
| Trout County : Yes |  |  | TVA County: Yes |  |  |  |  |
| CAMA County; No |  |  | Primary Nursery Area: No |  |  |  |  |
| Moratoria: Yes | Which species: Brown & Brook Trout |  |  |  |  | Duration : October 15 to April 15 |  |
| Permits: NWP #3, TVA |  |  |  |  |  |  |  |
| Water Quality Classification: C;Tr; ORW |  |  |  |  |  |  | 303d: No |
| Coast Guard Permit? No |  | Drainage Basin: New |  |  | Riparian Buffer Rules: No |  |  |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |  |
| National Forest: No |  |  |  | Wildlife Refuge: No |  |  |  |
| State, County, Or Local Park: adjacent to Elk Knob State Park boundary |  |  |  | Wild And Scenic River: No |  |  |  |
| Airport: No |  |  |  | Recreation Of Power Generation: No |  |  |  |
| Water Supply Reservoir: No |  |  |  | Nutrient Sensitive Waters: No |  |  |  |
| Public Use Boat Ramp: No |  |  |  | Cemeteries: NO |  |  |  |
| Known Or Potential Historic Properties In The Area: No |  |  |  |  |  |  |  |
| Architecture: No Survey Required |  |  |  | Archaeology: No survey required |  |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? None |  |  |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No |  |  |  |  |  |  |  |
| Comments: Paint 2-bar metal rail & guardrail. Coordinated with State Parks and EKSP there are no LWCF associated with this park. DBT to provide ROW plans early for coordination |  |  |  |  |  |  |  |

Geotechnical

Are There Any Historical And/Or Vibration Sensitive Structures Near By Comments:

Are There Any Known Landfills And / Or Geo-environmental Hazard Sites At Or Within Close Proximity To The Project Site Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells: Comments:

Possible Foundation Type: @ End Bents @ Interior

Hydraulics

| FEMA Approval? No |  |  | State Stormwater Permit? No |  |  |
| --- | --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? |  |  | Is Protection Needed? Standard |  |  |
| Are Banks Stable? Yes |  |  | Is Protection Needed? Standard |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: No |  |  |  | Where: |  |
| Superstructure Type: Bridge |  | If Bridge: Cored Slab |  |  | If girder; why? |
| Length Of Structure: 30’ | Min. Number Of Spans: 1 |  |  |  | Span Arrangement: |
| Waive offset: Yes, both sides | Cap: 4’ |  |  |  | Skewed: |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site Detour | Stage: |  |  | New Alignment: |  |  | On-site detour Clear roadway width (CRW):11’ Temp. Signals: Yes Alignment: South (upstream) 9’ lanes with 1’ offset each side Temporary 2 -60” pipes Onsite det. speed: 15mph |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DBE: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |
| ADT: 740 vpd (SIR/2011) |  |  | NHS: 0 | Tier: Sub-Regional |  |  |  | Func. Class: Local |
| Bridge Min. Clear Deck Width Recommended by Div.: Min. 30’ OTO with anodized 2 bar metal rail & guardrail |  |  |  |  |  |  |  |  |
| Roadway lane width _10_‘ with _3_‘ shoulders |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: N/A |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2-1/2” inches: |  |  |  |  |  | Existing Roadway: 16, no plans to upgrade |  |  |
| Pavement Marking: Paint – extend to existing markings |  |  |  |  |  | Pavement markers: None |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  | Method of Clearing: II modified |  |  |
| Truck Percentage: : 6 % per BIR; |  |  |  |  |  | Reasonable Safe Speed per SIR: 35 mph |  |  |
| Liquidated damages: will be imposed after 90 days of closure/construction. Amt: $ _500___ per day |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  | R/W by? DBT |  |  | R/W monuments? DBT to provide & install Pin/Cap |  |  |  |
| Salvageable materials: TIMBER JOISTS |  |  |  |  |  |  |  |  |
| Contact Person/number: David Scott (828) 268-6062 (DBT to deliver) |  |  |  |  |  |  |  |  |
| Deliver to: Boone Bridge Maintenance Facility at 1989 NC Hwy 194 North, Boone NC 28607 |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: None |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? No |  |  |  |  |  |  |  |  |
| Comments: Extend pavement markings to existing markings from each end of the existing bridge. Pave a minimum of 50’ with full depth paving (no milling). |  |  |  |  |  |  |  |  |