## Data Sheets
| TIP NO | 020142
| WBS | 17BP.11.R.133
| County | Alleghany
| Bridge Number | 142
| Description | Replace Bridge No. 142 over Potato Cr on SR 1319 (Piney Post Office Rd)
Stream | Basin | New
| Classification | C Tr +
| SIN | 10-5
| Type | Potato Cr: Perennial
| Size | Potato Cr: 10-20 ft
Existing Structure | Type
Size
Suff. Rating
Proposed Structure | Type
Size (width-out to out)
Stream | USACE Impacts (Y/N) | Y
| Non 404 Impacts (Y/N) | N
Wetlands | USACE Impacts (Y/N) | Y
| Non 404 Impacts (Y/N) | N
| CAMA Impacts (Y/N) | N
NC DWQ Buffers | Impacts (Y/N) | N
Buffer Application Required (>40 ft) (Y/N) |  | N
NC DWQ StormWater Permit Required (Y/N) | Permit Required (Y/N) | N
T&E | Habitat (Y/N) | To Be Done By Division
| Species Present | To Be Done By Division
| Bio Conclusion | To Be Done By Division
Moratorium | Type
Dates
Trout Waters | Native/Hatchery
Trout Species Present
| Trout Conditions (Y/N) | Tr water per DWR; WRC has not verified or provided input regarding any potential moratorium
WRC Reviewer
CAMA | AECs | N
Essential Fish | Habitat (Y/N) | N
Nav. | Opening | N/A
USCG | Permit | N
Historic | Properties
Archaeological | Resources
Tribal | Lands
4(f) | Resources
6(f) [LWCF] | Resources
Wild and | Scenic River | N
Forest Service | Lands
TVA | Area
FEMA | Buyout
FEMA | Flood Study
USTs | Haz Mats
Relocatees
Location | LAT | 36.5504
| LONG | -81.2639
Project Comments |  | 3 Wetlands (WA, WB, WC) within study area
Completed by:
Lead Engineer
Environmental Officer

## ARRA (II) Bridge Project 2010 (hidden)
ARRA (II) Design-Build Bridge Project 2010 | [10 empty] | Potential Pipe or Culvert | [9 empty] | NCDOT Material Request Status
Possible Low Impact Bridge Replacement Candidates | [20 empty] | % Comp | % Comp | % No | % Comp | % Comp | % Yes | % Comp | % Yes | % Comp | % Comp | % Comp
2011-2013 Division Managed DB & DBB Projects | [12 empty] | Total Number of Division Selected Candidate Structures: | [7 empty] | #DIV/0! | #DIV/0! | 28.1% | #DIV/0! | #DIV/0! | 23.33% | #DIV/0! | 5.714% | #DIV/0! | #DIV/0! | #DIV/0!
Div | County | Str # | Route | Across | Year Blt. | Div./ Let List /POC | TIP or Priority | Convent. Est Cost | Division Est Cost | Str Lngth (ft) | Exist Span Lengths (ft.) | Let Date | Any Preliminary Engineering Work or Notes of Interest | Str Def. | Func Obs. | SR | SV | TTST | Additional Notes: | USGS Quad Map | Geotech Subsurf. Invest. | Hydro | Hydro? | L&S | Historical recv'd | Hist. Surv.? | Archaeological | Arch. Surv.? | PCE Permit Append G | Photogram | ROW Abstract
1 | Chowan | 200019 | SR 1316 | Canal | 1964 | Div. | 1 | 475000 | 404685 | 30 | 1@30' | n/a | No Preliminary Engineering Work Done. | SD | N | 29 | 33 | 41 | 200013 on possible detour replaced in 2008 - B-4073. Hydro potential culvert. Historical noted on 04/09: "this may amount to no more than a site visit--I'm having trouble getting the information I need to make a call because HPO records are incomplete for this area." | EDENHSI | 2010-04-13 | 2010-02-17 | No | 2010-03-31 | 2010-04-09 | Yes | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Currituck | 260006 | SR 1228 | Shingle Landing Creek | 1962 | Div. | 2 | 575000 | 818892 | 60 | 2@30' | n/a | No Preliminary Engineering Work Done. | SD | N | 30.7 | 25 | 28 | 260014 on possible detour - not currently programmed. Hydraulic does not recommend could be a problem getting original FEMA model. | MOYOCKI | 2010-04-13 | 2010-02-17 | No | 2010-03-31 | 2010-04-09 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Gates | 360020 | SR 1308 | Duke Swamp | 1958 | Div. | 3 | 525000 | 717747 | 53 | 1@17'6 ; 1@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | N | N | 55.1 | 7 | 7 | Short detour into Va? 360022,23,24 on detour - none currently programmed | WHALVLI | 2010-04-15 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-05 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Martin | 570156 | SR 1117 | Ready Branch | 1966 | Div. | 4 | 525000 | 818892 | 60 | 2@30' | n/a | No Preliminary Engineering Work Done. | SD | N | 41.3 | 29 | 29 | 570006 = B-4576 Mar 2010 MOE project - on detour. | WLMSTNI | 2010-04-05 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-05 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Bertie | 70046 | SR 1500 | Roouist Creek | 1964 | Div. | 5 | 725000 | 823475 | 69 | 1@17'6 ; 2@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. FYI = B-4915 Post Year. | SD | N | 11.1 | 21 | 31 | 070049,50,66 on possible detour - not currently programmed. | WINDSSI | 2010-03-15 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-01 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Hertford | 450020 | SR 1167 | Old Field Swamp | 1950 | Div. | 6 | 575000 | 737320 | 69 | 1@17'6 ; 2@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 30.9 | 21 | 29 | No bridges on shortest detour. Historical note from 04/12 e-mail: This particular project has a National Register property in the APE; a site visit to ascertain the effect of the project on the property is necessary. Will schedule a visit asap. | MURFBOI | 2010-04-05 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-26 | Yes | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Northampton | 650046 | SR 1360 | Branch of Kirby's Creek | 1952 | Div. | 7 | 550000 | 649188 | 52 | 1@17'6 ; 1@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 27.3 | 15 | 19 | 650044 on detour - not currently programmed. | CONWAYI | 2010-03-29 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Bertie | 70083 | SR 1349 | Branch White Oak Swamp | 1971 | Div. | 8 | 500000 | 808735 | 52 | 1@17'6 ; 1@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 29.1 | 6 | 0 | C070056 and 070053 [B-5141 CFY2016] on shortest detour. Archaeology: The APE includes a small cemetery immediately to the east of White Oak Road. This cemetery appears to be within the APE and may include unmarked graves that extend beyond the small fenceline that can be seen in aerial photos. Further investigation may be required to adequately delineate the cemetery in relation to proposed changes to the existing ditchlines. | WINDSNI | 2010-03-18 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-01 | No | 2010-03-26 | Yes | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Bertie | 70145 | SR 1343 | Branch White Oak | 1961 | Div. | 9 | 425000 | 370300 | 35 | 1@35' | n/a | No Preliminary Engineering Work Done. | N | FO | 34.8 | 14 | 18 | Just around the corner from 070083 - no bridges on shortest detour. Hydro potential culvert. | WINDSNI | 2010-03-18 | 2010-02-16 | No | 2010-03-31 | 2010-04-01 | No | 2010-03-30 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Northampton | 650027 | SR 1108 | Creek | 1967 | Div. | 10 | 600000 | 809370 | 51 | 3@17' | n/a | No Preliminary Engineering Work Done. | SD | N | 30 | 10 | 17 | No bridges on shortest detour | RICHSQI | 2010-03-25 | 2010-02-18 |  | 2010-03-31 | 2010-04-06 | No | 2010-03-31 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Northampton | 650048 | SR 1126 | Gumberry Swamp | 1965 | Div. | 11 | 550000 | 607503 | 44 | 1@15' ; 1@14' ; 1@15' | n/a | No Preliminary Engineering Work Done. | SD | N | 30.2 | NP | NP | 650008, 63 on detour - not currently programmed. Archaeology: recommend further archaeological investigation (survey). A brief review of early 20th-century maps of Northampton County reveals that Barrows Mill was located immediately north of Bridge No. 48 at least 75-85 years ago and likely earlier. Without further field investigation it is nearly impossible to determined whether or not the proposed bridge replacement will impact archaeological elements associated with the mill or whether or not the remains of the mill complex are even present and NRHP-eligible. Additionally further archival research could be required. | BOOCRD | 2010-04-08 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-26 | Yes | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Hertford | 450139 | SR 1409 | Horse Swamp | 1961 | Div. | 12 | 625000 | 690450 | 52 | 1@17'6 ; 1@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 37.9 | 20 | 29 | 450036 on detour - not currently programmed. | AHOSKI | 2010-04-13 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-03-31 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Hertford | 450005 | SR 1346 | Buckhorn Creek | 1968 | Div. | 13 | 550000 | 715419 | 46 | 1@15'6 ; 1@15' ; 1@15'6 | n/a | No Preliminary Engineering Work Done. | N | N | 71.9 | 23 | 31 | C450024 on detour | RIVDALI | 2010-03-30 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-03-31 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
1 | Bertie | 70074 | SR 1518 | Creek | 1972 | Div. | 14 | 525000 | 790484 | 51 | 1@17'6 ; 1@16' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 39.8 | 23 | 38 | No bridges on shortest detour | WINDSSI | 2010-03-16 | 2010-02-16 | Yes | 2010-03-31 | 2010-04-01 | No | 2010-03-25 | No | 2010-05-05 | 2010-02-25 | 2010-03-31
2 | Pitt | 730079 | SR 1200 | Black Swamp | 1972 | Div. | 1 | 625000 | 1000000 | 54 | 1@17'8 ; 1@17' ; 1@18'10 | n/a | No Preliminary Engineering Work Done. | N | N | 36.9 | 19 | 28 | No bridges on shortest detour | FARMVLI | 2010-03-25 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-25 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730032 | SR 1750 | Indian Wells Creek | 1959 | Div. | 2 | 475000 | 1000000 | 53 | 1@17'10 ; 1@17'2 ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 39.9 | 26 | NP | 730013 - B-4604 on shortest detour MOE project | GARDVLI | 2010-03-25 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-25 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730101 | SR 1409 | Fork of Conetoe Creek | 1973 | Div. | 3 | 675000 | 1000000 | 86 | 1@30'3 ; 1@30'1 ; 1@25'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 44 | 25 | 28 | 730102,198,36 all on detour none are currently programmed. | CONETOI | 2010-03-29 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-13 | Yes | 2010-03-24 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730104 | SR 1409 | Conetoe Creek | 1968 | Div. | 4 | 525000 | 1000000 | 82 | 1@21' ; 1@40' ; 1@21' | n/a | Bridge Survey Report Complete. | SD | N | 28 | 4 | 0 | Near 730101; 730102 on detour. | CONETOI | 2010-03-29 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-25 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730176 | SR 1122 | Swift Creek | 1962 | Div. | 5 | 600000 | 1000000 | 70 | 1@10'9 ; 3@7'10 ; 1@8'10 ; 1@8'1.5 ; 1@9' ; 1@8'1 | n/a | No Preliminary Engineering Work Done. | SD | N | 47 | NP | NP | 730053 [B-4231 CFY 2008] on detour. Hydraulic does not recommend could be a problem getting original FEMA model. | AYDEN | 2010-03-23 | 2010-03-24 | No | 2010-03-31 | 2010-04-06 | No | 2010-03-25 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730012 | SR 1755 | Clayroot Creek | 1972 | Div. | 6 | 475000 | 1000000 | 52 | 1@18'3 ; 1@16'5 ; 1@17'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 38.3 | 19 | 27 | 730023 on detour not currently programmed | GARDVLI | 2010-03-29 | 2010-03-23 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-24 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730211 | SR 1753 | Buckleberry Creek | 1962 | Div. | 7 | 500000 | 1000000 | 47 | 1@16' ; 1@15'1 ; 1@15'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 22 | 25 | NP | C730022 on detour | FTBARNI | 2010-03-25 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-24 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730068 | SR 1217 | Pine Log Creek | 1970 | Div. | 8 | 550000 | 1000000 | 53 | 1@17'9 ; 1@17'1 ; 1@18' | n/a | No Preliminary Engineering Work Done. | N | N | 47.4 | 16 | 24 | 730065 [B-4233 BMU] on detour; Hydraulic does not recommend could be a problem getting original FEMA model. | FARMVLI | 2010-03-23 | 2010-03-24 | No | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730081 | SR 1200 | Little Contentnea Creek | 1961 | Div. | 9 | 550000 | 1000000 | 52 | 1@17'1 ; 1@17' ; 1@17'7 | n/a | No Preliminary Engineering Work Done. | N | N | 31.2 | 20 | 28 | No bridges on shortest detour. Hydraulic does not recommend could be a problem getting original FEMA model. | FALKLDI | 2010-03-25 | 2010-03-24 | No | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730144 | SR 1517 | Creek | 1953 | Div. | 10 | 425000 | 1000000 | 35 | 2@17'8 | n/a | No Preliminary Engineering Work Done. | N | N | 34.9 | 19 | 28 | No bridges on shortest detour | GRVLNEI | 2010-03-16 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-13 | Yes | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Pitt | 730162 | SR 1427 | Grindle Creek | 1961 | Div. | 11 | 425000 | 1000000 | 61 | 1@31' ; 1@30' | n/a | No Preliminary Engineering Work Done. | SD | N | 49.6 | 22 | 25 | 730089 [B-2603 - unfunded project] on detour | CONETOI | 2010-03-16 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Jones | 510060 | SR 1315 | Beaver Creek | 1974 | Div. | 12 | 775000 | 1000000 | 91 | 1@30'6 ; 1@30' ; 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 46 | 23 | 26 | 510010 [not currently programmed] on detour | DOVERI | 2010-03-10 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Jones | 510075 | SR 1319 | Mussel Shell Creek | 1975 | Div. | 13 | 525000 | 1000000 | 53 | 1@17'8 ; 1@17' ; 1@17'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 39 | 21 | 31 | 510013 [B-4168 CFY 2008] on detour | TRENTNI | 2010-03-10 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Lenoir | 530040 | SR 1111 | Southwest Creek | 1969 | Div. | 14 | 650000 | 1000000 | 82 | 1@20'4 ; 2@20'3 ; 1@20'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 48 | 23 | 36 | 530019 [not currently progammed] on detour. Archaeological: the bridge is immediately adjacent to Tulls Mill. A very brief review of historic maps of Lenoir County indicates that Tulls Mill is at least 100 years old and likely served as a local community focal point. An archaeological reconnaissance survey and possibly subsurface investigations would be required to insure that no NRHP-eligible resources related to Tulls Mill would be impacted by the project. Hydraulic does not recommend could be a problem getting original FEMA model. | DEERUNI | 2010-03-11 | 2010-03-24 | No | 2010-03-31 | 2010-04-13 | Yes | 2010-03-22 | Yes | 2010-05-06 | 2010-02-25 | 2010-03-30
2 | Lenoir | 530048 | SR 1326 | Bear Creek | 1968 | Div. | 15 | 575000 | 1000000 | 81 | 1@20'7 ; 1@20'3 ; 1@19'11 ; 1@20'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 42 | 20 | 23 | Unpaved detour? 530047 or 530049 will be on detour - neither programmed | LAGRANI | 2010-03-11 | 2010-03-24 | Yes | 2010-03-31 | 2010-04-06 | No | 2010-03-22 | No | 2010-05-06 | 2010-02-25 | 2010-03-30
3 | Sampson | 810144 | SR 1320 | Branch of Coharie | 1963 | Div. | 1 | 600000 | 468429.5 | 35 | 1@17'8 ; 1@17'6 | n/a | DPOC. | SD | N | 5 | 26 | NP | No bridges on shortest detour | BEARSK | 2010-03-18 | 2010-02-18 | No | 2010-03-31 | 2010-04-20 | No | 2010-04-14 | No |  | 2010-02-25 | 2010-03-29
3 | Duplin | 300211 | SR 1801 | Branch Muddy Creek | 1950 | Div. | 2 | 575000 | 736103.5 | 55 | 1@18'6 ; 1@18'2 ; 1@18'5 | n/a | DPOC. | SD | FO | 12 | 16 | 24 | No bridges on shortest detour. Hydro potential culvert but must dewater. | POTTHLI | 2010-03-18 | 2010-02-15 | No | 2010-03-31 | 2010-04-20 | No | 2010-04-21 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810214 | SR 1706 | Kill Creek | 1967 | Div. | 3 | 650000 | 1021181.6 | 76 | 1@25'6 ; 1@25' ; 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 31 | 34 | 810213 on detour - not currently programmed. Hydraulic does not recommend could be a problem getting original FEMA model. | NEWGRSI | 2010-03-19 | 2010-02-18 | No | 2010-03-31 | 2010-04-20 | No | 2010-04-14 | Yes |  | 2010-02-25 | 2010-03-29
3 | Duplin | 300154 | SR 1700 | Cabin Creek | 1951 | Div. | 4 | 550000 | 736103.5 | 55 | 1@18'3 ; 1@18'6 ; 1@18'5 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 16 | 23 | No bridges on shortest detour. Hydro potential pipe or culvert. | BEULVL | 2010-03-18 | 2010-02-15 | No | 2010-03-31 | 2010-04-20 | Yes | 2010-04-14 | No |  | 2010-02-25 | 2010-03-29
3 | Brunswick | 90077 | SR 1300 | Scippeo Creek | 1952 | Div. | 5 | 575000 | 816405.7 | 61 | 1@15'10 ; 2@15' ; 1@15'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 41 | 34 | 43 | 090027 on detour | FREELDI | 2010-04-08 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-21 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810143 | SR 1913 | Turkey Swamp | 1967 | Div. | 6 | 725000 | 1222730.6 | 91 | 1@30'6 ; 1@30' ; 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 31 | 22 | 26 | 810056 [B-4636 CFY 2019] on detour Several other none programmed bridges on possible detours | TURKEYI | 2010-03-17 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-21 | No |  | 2010-02-25 | 2010-03-29
3 | Duplin | 300067 | SR 1912 | Maxwell Creek | 1957 | Div. | 7 | 650000 | 923475.3 | 69 | 1@17'9 ; 1@16'11 ; 1@16'10 ; 1@17'10 | n/a | No Preliminary Engineering Work Done. | N | N | 50 | 19 | 27 | No bridges on shortest detour | WARSASI | 2010-03-16 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810231 | SR 1740 | Six Runs Creek | 1953 | Div. | 8 | 575000 | 698703.2 | 52 | 1@17'7 ; 1@17'1 ; 1@17'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 37.3 | 17 | 25 | 810233 on detour on this list | CLINTNI | 2010-03-18 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-14 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810060 | SR 1007 | Branch Black Creek | 1951 | Div. | 9 | 500000 | 481813.2 | 36 | 1@17'10 ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 25 | 18 | 23 | B-1382 CFY 2008 on detour along with other none programmed bridges | TOMAHKI | 2010-04-06 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | Yes | 2010-04-27 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810233 | SR 1742 | Six Run Creek | 1952 | Div. | 10 | 525000 | 481813.2 | 36 | 1@17'6 ; 1@18'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 26 | 25 | NP | 810231 on detour on this list | NEWGRSI | 2010-03-18 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | Yes | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810077 | SR 1208 | South River Overflow | 1952 | Div. | 11 | 650000 | 936859 | 70 | 1@17'10 ; 1@17'2 ; 1@16'8 ; 1@17'11 | n/a | No Preliminary Engineering Work Done. Needs to be done with 810078. | SD | N | 26 | 20 | 27 | Pair 810078 Detour into Bladen County 080058,93 on possible detour. Hydraulic does not recommend could be a problem getting original FEMA model. | GARLANI | 2010-04-06 | 2010-02-15 | No | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810078 | SR 1208 | South River | 1952 | Div. | 11 | 825000 | 1391904.8 | 104 | 1@17'11;1@16'10;1@17'1;1@17'2;1@17';1@17'8 | n/a | No Preliminary Engineering Work Done. Needs to be done with 810077. | SD | N | 36 | 20 | 26 | Pair 810077 Detour into Bladen County 080058, 93 on possible detour. Hydraulic does not recommend could be a problem getting original FEMA model. | GARLANI | 2010-04-06 | 2010-02-15 | No | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810101 | SR 1256 | Big Swamp Creek | 1962 | Div. | 12 | 600000 | 1164381.9 | 87 | 1@17'9 ; 1@17'1 ; 1@17' ; 1@16'10 ; 1@17'11 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 18 | 26 | 810011 on detour | ROSEBOI | 2010-04-12 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | Yes | 2010-04-21 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810034 | SR 1945 | Branch Six Runs Creek | 1950 | Div. | 13 | 575000 | 695952.4 | 52 | 1@17'6 ; 1@17' ; 1@17'7 | n/a | No Preliminary Engineering Work Done. | SD | N | 26 | 32 | 36 | No bridges on shortest detour | DELWAYI | 2010-03-16 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | Yes | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810105 | SR 1233 | Big Swamp Creek | 1950 | Div. | 14 | 675000 | 923475.3 | 69 | 1@17'6 ; 1@17'4 ; 1@16'8 ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 27 | 26 | 38 | 810122 on detour | SALMBGI | 2010-04-07 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Duplin | 300097 | SR 1305 | Goshen Creek | 1953 | Div. | 15 | 700000 | 1150998.2 | 86 | 1@18'3 ; 1@18'6 ; 1@18'5 | n/a | No Preliminary Engineering Work Done. | SD | N | 24 | 18 | 27 | Group with 300094 Several bridges on both detours - both detours long | WARSANI | 2010-03-15 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
3 | Duplin | 300069 | SR 1915 | Branch of Maxwell Creek | 1966 | Div. | 16 | 550000 | 709336.1 | 53 | 1@17'10 ; 1@17' ; 1@17'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 53 | 18 | 26 | 300063 on detour | ROSEHLI | 2010-03-16 | 2010-02-15 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-21 | No |  | 2010-02-25 | 2010-03-29
3 | Sampson | 810177 | SR 1703 | Great Coherie Creek | 1951 | Div. | 17 | 550000 | 1164381.9 | 87 | 1@17'11 ; 1@17' ; 1@16'10 ; 1@17' ; 1@18' | n/a | No Preliminary Engineering Work Done. | SD | N | 19 | 25 | 37 | No bridges on shortest detour. | NEWGRSI | 2010-03-19 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-20 | No | 2010-04-28 | No |  | 2010-02-25 | 2010-03-29
4 | Wilson | 970065 | SR 1163 | Swamp | 1961 | Div. | 1 | 650000 | 483717.6 | 36 | 2@17'9 | n/a | Division Managed Project / Just Begun. | N | FO | 37 | 15 | 22 | L&S file references B-5126. Adjacent to 970066. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Hydro not good candidate. | WILSONI | 2010-03-24 | 2010-02-18 | No | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Wilson | 970066 | SR 1163 | Swamp | 1961 | Div. | 2 | 725000 | 712139.8 | 53 | 1@17'9 ; 1@17' ; 1@17'9 | n/a | Division Managed Project / Just Begun. | N | FO | 44 | 17 | 25 | L&S file references B-4679 (DPOC). L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Hydro not good candidate. | WILSONI | 2010-03-24 | 2010-02-18 | No | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Nash | 630025 | SR 1145 | Little Sapony Creek | 1950 | Div. | 6 | 600000 | 709336.1 | 53 | 1@17'9 ; 1@17' ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 39 | 10 | 17 | L&S file references B-4938. 630187 on detour. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | SPGHOPI | 2010-03-15 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Johnston | 500039 | SR 1136 | Mill Creek Overflow | 1959 | Div. | 7 | 625000 | 850473.3 | 69 | 1@17'9 ; 1@16'9 ; 1@17' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. Needs to be done with 500041. | N | FO | 39 | 12 | 20 | L&S file references B-4936. Group with 500041 adjacent bridge. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Archaeology: is rather close to Bentonville Battleground. It is a State Historic Site, and has been designated as a National Landmark among other honors for it's associated military history and condition and proximity to the National Landmark site, Bentonville Battlefield. It was an expansive movement of engaged troops, and the boundaries can be considered loose. This would merit further investigation and an archaeological survey should the project move forward. | NEWGRNI | 2010-03-25 | 2010-02-19 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-03-30 | Yes | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Johnston | 500041 | SR 1136 | Mill Creek | 1953 | Div. | 8 | 650000 | 854123.4 | 69 | 1@17'9 ; 1@16'9 ; 1@17' ; 1@17'9 | n/a | No Preliminary Engineering Work Done. Needs to be done with 500039. | SD | N | 27 | 12 | 20 | L&S file references B-4936. Group with 500039 adjacent bridge. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Archaeology: is rather close to Bentonville Battleground. It is a State Historic Site, and has been designated as a National Landmark among other honors for it's associated military history and condition and proximity to the National Landmark site, Bentonville Battlefield.. It was an expansive movement of engaged troops, and the boundaries can be considered loose. This would merit further investigation and an archaeological survey should the project move forward. Hydro needs to be modeled with 500039. | NEWGRNI | 2010-03-25 | 2010-02-19 | Yes | 2010-03-31 | 2010-04-10 | No | 2010-03-30 | Yes | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Johnston | 500113 | SR 1309 | Big Branch | 1963 | Div. | 9 | 625000 | 522704.9 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 4 | 14 | 18 | L&S file references B-4557. B-4557 CFY 2016 PDEA has done significant preliminary data collection on project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Historical noted on 04/09: "A Study List Property, the Joseph B. Hardee House, is within the APE, will need to check this out for sure." | BENSON | 2010-03-25 | 2010-02-22 | Yes | 2010-03-31 | 2010-04-09 | Yes | 2010-04-14 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Nash | 630156 | SR 1433 | Basket Creek | 1956 | Div. | 10 | 650000 | 1222730.6 | 91 | 1@30'6 ; 1@30' ; 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 27 | 26 | 29 | L&S file references B-4939. 630135 and 630136 are on the shortest detour. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | NASHVLI | 2010-03-15 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Wayne | 950121 | SR 1702 | West Bear Creek | 1950 | Div. | 11 | 625000 | 695952.4 | 52 | 1@8'7 ; 1@8'10 ; 1@8'4 ; 1@8'8 ; 1@8'8 ; 1@8'5 | n/a | No Preliminary Engineering Work Done. | SD | N | 19 | NP | NP | 950010 on detour. Hydro not good candidate potential problem obtaining FEMA model. | JASONI | 2010-03-25 | 2010-02-17 | No | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Johnston | 500011 | SR 1200 | Mill Creek | 1970 | Div. | 12 | 925000 | 2061089.8 | 161 | 1@40'4 ; 2@40'1 ; 1@40'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 18 | 22 | B-4771 CFY 2019. Hydro not good candidate problem obtaining FEMA model.. | GRANTHI | 2010-03-25 | 2010-02-19 | No | 2010-03-31 | 2010-04-09 | No |  |  | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Johnston | 500222 | SR 2320 | Little Creek | 1952 | Div. | 13 | 625000 | 940562 | 70 | 1@17'9 ; 2@17' ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 36 | 16 | 24 | L&S file references B-4773. B-4773 CFY 2017 PDEA and Design have done substantial work on project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | KENLYWI | 2010-03-25 | 2010-02-22 | Yes | 2010-03-31 | 2010-04-10 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Edgecombe | 320059 | SR 1006 | Trib. Of Cokey Swamp | 1961 | Div. | 14 | 650000 | 695952.4 | 52 | 2@8'9 ; 2@8'4.5 ; 2@8'10.5 | n/a | No Preliminary Engineering Work Done. | SD | N | 26 | NP | NP | On Quad Map, it is on SR 1222, NOT SR 1006. No bridges on shortest detour | HARTSE | 2010-03-16 | 2010-02-16 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Nash | 630026 | SR 1145 | Sapony Creek | 1951 | Div. | 15 | 650000 | 1217916.7 | 91 | 1@18'1 ; 1@18'1 ; 1@18'2 ; 1@18'4 ; 1@18' | n/a | No Preliminary Engineering Work Done. | N | N | 41 | 13 | 21 | L&S file references B-5108. Several possible detours, with several bridges, none are currently programmed. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | SPGHOPI | 2010-03-15 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Wilson | 970109 | SR 1002 | Town Creek | 1940 | Div. | 16 | 875000 | 1174591.6 | 91 | 1@15'8 ; 1@15' ; 1@15'2 ; 1@14'10 ; 1@15' ; 1@15'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 36 | 13 | 17 | 970105 on one detour | ELMCYI | 2010-03-23 | 2010-02-16 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
4 | Wayne | 950025 | SR 1575 | Exum Mill Branch | 1971 | Div. | 17 | 675000 | 1463425.6 | 91 | 3@30'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 33 | 21 | 24 | No bridges on shortest detour. Hydro not good candidate potential problem obtaining FEMA model. | JASONI | 2010-03-25 | 2010-02-16 | No | 2010-03-31 | 2010-04-13 | No | 2010-04-26 | No | 2010-04-28 | 2010-02-25 | 2010-03-31
5 | Franklin | 340075 | SR 1600 | Trib. Of Tar River | 1954 | Div. | 1 | 775000 | 650000 | 91 | 2@25'4 ; 1@40'2 ; 1@25'2 | n/a | No Preliminary Engineering Work Done. Bridge 75 must be completed before Bridge 76 begins. | SD | N | 31 | 13 | 16 | Same route as 340076. Historical: "I'm going to need to eyeball these. The good news is, it should be quick work, and I can have it to you within a week." | LOUISBI | 2010-03-17 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-13 | Yes | 2010-04-08 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Franklin | 340076 | SR 1600 | Sycamore Creek | 1954 | Div. | 2 | 700000 | 500000 | 81 | 2@40'4 | n/a | Shelf Ready (Wetherill Engineering) | SD | FO | 28 | NP | NP | Same route as 340075 | LOUISBI | 2010-03-17 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-08 | No | ready to const | 2010-02-25 | 2010-03-31
5 | Vance | 900067 | SR 1120 | Bed Bud Creek | 1967 | Div. | 3 | 775000 | 680000 | 97 | 1@31'2 ; 1@34'10 ; 1@31'2 | n/a | No Preliminary Engineering Work Done. | SD | FO | 13 | 9 | 13 | No bridges on shortest detour. Historical: "I'm going to need to eyeball these. The good news is, it should be quick work, and I can have it to you within a week." | HENDERI | 2010-03-17 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-13 | Yes | 2010-04-08 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380020 | SR 1705 | Fork Creek | 1960 | Div. | 4 | 575000 | 350000 | 40 | 1@40'2 | n/a | No Preliminary Engineering Work Done. | SD | FO | 39 | 12 | 15 | No bridges on shortest detour | WILTONI | 2010-03-16 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Person | 720036 | SR 1123 | South Flat River | 1965 | Div. | 5 | 775000 | 850000 | 121 | 1@40'3 ; 1@40' ; 1@40'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 27 | 13 | 17 | 720033 on detour. Hydro not good candidate- potential problem obtaining FEMA model. Historical: "I'm going to need to eyeball these. The good news is, it should be quick work, and I can have it to you within a week." | TIMBLKI | 2010-03-17 | 2010-02-23 | No | 2010-03-31 | 2010-04-13 | Yes | 2010-04-08 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380042 | SR 1724 | Ledge Creek | 1956 | Div. | 6 | 750000 | 625000 | 81 | 2@40'2 | n/a | No Preliminary Engineering Work Done. | SD | FO | 33 | 15 | 19 | 380004 on detour | CREEDMI | 1993-12-10 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Vance | 900070 | SR 1326 | Flat Creek | 1970 | Div. | 7 | 675000 | 950000 | 91 | 1@30'4 ; 1@30' ; 1@30'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 29 | 21 | 24 | 900034 on detour | TOWNVLI | 2010-03-15 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-13 | No | 2010-04-08 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Person | 720093 | SR 1536 | Tar River | 1950 | Div. | 8 | 600000 | 265000 | 21 | 1@20'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 44 | 14 | 18 | Per Charlie Brown on 03/01: "We received request on B-5220 (the same bridge) to stake the r/w. The request was and was removed from our project database." 720098 on detour. Historical: "I'm going to need to eyeball these. The good news is, it should be quick work, and I can have it to you within a week." | TRISPGI | 1999-12-07 | 2010-02-23 | Yes | 2010-03-03 | 2010-04-13 | Yes | 2010-04-09 | No | B-5220 | 2010-02-25 | 2010-03-31
5 | Person | 720094 | SR 1565 | Creek | 1957 | Div. | 9 | 500000 | 285000 | 26 | 1@25'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 49 | 13 | 18 | No bridges on shortest detour. Historical: "I'm going to need to eyeball these. The good news is, it should be quick work, and I can have it to you within a week." | MORIAHI | 2010-03-16 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-13 | Yes | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380143 | SR 1442 | Johnston Creek | 1960 | Div. | 10 | 900000 | 950000 | 161 | 1@35'4 ; 1@45' ; 1@35' ; 1@45'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 42 | 12 | 16 | Detour into Virginia? | CLKVLSI | 2010-03-16 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Person | 720044 | SR 1111 | South Flat River | 1950 | Div. | 11 | 475000 | 265000 | 21 | 1@26' | n/a | No Preliminary Engineering Work Done. | SD | FO | 42 | 12 | 17 | No bridges on shortest detour. Hydro not good candidate- potential problem obtaining FEMA model. | HURDMLI | 1999-11-23 | 2010-02-23 | No | 2010-03-31 | 2010-04-13 | Yes | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380012 | SR 1609 | Tabb's Creek | 1955 | Div. | 12 | 650000 | 560000 | 71 | 1@30'5 ; 1@40'4 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21.1 | 14 | 18 | Detour crosses into Vance County. Hydro not good candidate- potential problem obtaining FEMA model. | OXFORDI | 2010-03-16 | 2010-02-26 | No | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380123 | SR 1407 | Creek | 1955 | Div. | 13 | 500000 | 285000 | 26 | 1@25'8 | n/a | No Preliminary Engineering Work Done. | SD | FO | 26 | 14 | 19 | No bridges on shortest detour. Hydro - potential pipe (2@ 142"x91" CSPA) or bottomless culvert. | NELSONI | 2010-03-09 | 2006-06-13 | No | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380090 | SR 1145 | Creek | 1960 | Div. | 14 | 600000 | 465000 | 49 | 1@14'9 ; 1@16'10 ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | N | FO | 49 | 12 | 19 | Detour crosses into Person County. | MORIAHI | 2010-03-16 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
5 | Granville | 380205 | SR 1428 | Little Blue Creek | 1957 | Div. | 15 | 550000 | 480000 | 53 | 1@17'9 ; 1@17' ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | N | FO | 44 | 12 | 20 | No bridges on shortest detour | SATTWHI | 2010-03-16 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-09 | No | 2010-05-07 | 2010-02-25 | 2010-03-31
6 | Columbus | 230207 | SR 1585 | Pine Log Swamp | 1956 | Div. | 1 | 575000 | 415000 | 35 | 2@17'8 | n/a | No Preliminary Engineering Work Done. | N | N | 50 | 19 | 27 | 230034,50 on detour | CHADI | 2010-04-13 | 2010-02-15 | Yes | 2010-03-31 | 2010-03-29 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Harnett | 420233 | SR 1544 | Black River Trib. | 1960 | Div. | 2 | 675000 | 610000 | 52 | 1@17.7' ; 2@8.3' ; 1@17.7' | n/a | No Preliminary Engineering Work Done. | SD | N | 21 | 22 | 32 | No bridges on shortest detour. Hydro-Dam just upstream where detail study starts, if detail study data needed then may be delay, use as last choice. | COATSI | 2010-03-24 | 2010-02-17 | MAYBE | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Robeson | 770275 | SR 1005 | Ten Mile Swamp | 1940 | Div. | 3 | 775000 | 1075000 | 83 | 1@21'5 ; 2@20' 1 @21'5 | n/a | No Preliminary Engineering Work Done. | SD | N | 25 | 26 | 30 | 770151,54 on detour | NELUMBI | 2010-04-07 | 2010-02-17 | Yes | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Columbus | 230301 | SR 1005 | Branch of Tom's Creek | 1951 | Div. | 4 | 625000 | 440000 | 37 | 2@18'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 28 | 17 | 24 | No bridges on shortest detour. Hydro-potential culvert, dewatering will drive up costs. | TABCYEI | 2010-04-15 | 2010-02-15 | No | 2010-03-31 | 2010-03-29 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Columbus | 230123 | SR 1005 | Beaverdam Swamp | 1956 | Div. | 5 | 675000 | 645000 | 55 | 1@18'6 ; 1@18' ; 1@18'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 27 | 16 | 23 | No bridges on shortest detour | TABCYEI | 2010-04-15 | 2010-02-15 | Yes | 2010-03-31 | 2010-03-30 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Columbus | 230046 | SR 1932 | Creek | 1951 | Div. | 6 | 550000 | 470000 | 38 | 2@18'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 27 | 16 | 23 | B-4482 unfunded project. Historical: The tax parcel cards for Columbus County show a house and accompanying farm buildings for the parcel adjacent to the bridge. Further investigation will be required before eligibility can be determined. | PIREWAI | 4/1510 | 2010-02-16 | Yes | 2010-03-31 | 2010-03-30 | Yes | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Harnett | 420195 | SR 1234 | Branch of Upper Little Riv | 1960 | Div. | 7 | 600000 | 430000 | 36 | 2@17'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 27 | 26 | NP | No bridges on shortest detour. Hydro-potential culvert site. | ANDCRK | 2010-03-22 | 2010-02-17 | No | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Bladen | 80172 | SR 1728 | Carver Creek | 1967 | Div. | 8 | 575000 | 430000 | 36 | 1@17'9 ; 1@18' | n/a | No Preliminary Engineering Work Done. | SD | N | 38 | 16 | 23 | No bridges on shortest detour | COUNCLI | 2010-03-03 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-01 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Harnett | 420151 | SR 1415 | Hector's Creek | 1965 | Div. | 9 | 675000 | 1085000 | 90 | 3@30' | n/a | No Preliminary Engineering Work Done. | SD | N | 32 | 22 | 25 | No bridges on shortest detour | FUQVARI | 2010-03-22 | 2010-02-17 | Yes | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Columbus | 230038 | SR 1141 | Branch Monte Swamp | 1954 | Div. | 10 | 950000 | 1450000 | 121 | 1@20'6 ; 1@20' ; 1@20'2 ; 1@20'1 ; 1@20'2 ; 1@20'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 26 | 24 | 37 | B-4476 unfunded project | NAKINAI | 2010-04-13 | 2010-02-16 | Yes | 2010-03-31 | 2010-03-29 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Columbus | 230161 | SR 1351 | Gapway Swamp | 1967 | Div. | 11 | 675000 | 1400000 | 121 | 1@30'6 ; 2@30' ; 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 35 | 23 | 26 | Detour into South Carolina? | TABCYWI | 2010-04-13 | 2010-02-16 | Yes | 2010-03-31 | 2010-03-30 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Robeson | 770320 | SR 1709 | Little Marsh Swamp | 1964 | Div. | 12 | 600000 | 385000 | 31 | 1@31'3 | n/a | No Preliminary Engineering Work Done. | N | FO | 44 | 23 | 30 | No bridges on shortest detour | PARKTNI | 2010-04-05 | 2010-02-17 | Yes | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
6 | Bladen | 80062 | SR 1704 | White Creek | 1969 | Div. | 13 | 625000 | 620000 | 53 | 1@17'8 ; 1@17'1 ; 1@18' | n/a | No Preliminary Engineering Work Done. | SD | N | 33 | 20 | 30 | 080061 on detour. Historical: There is a church with a cemetery within 300 feet of the bridge. I recommend a site survey to evaluate the eligibility of the property. | ELITNSI | 2010-03-03 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-01 | Yes | 2010-04-09 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
7 | Guilford | 400231 | SR 1005 | Stinking Quarter | 1954 | Div. | 1 | 675000 | 1217916.7 | 91 | 1@30'3 ; 1@30' ; 1@30'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 13 | 17 | 400269 on shortest detour | KIMEVL | 1993-05-12 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Guilford | 400112 | SR 2109 | Haw River | 1967 | Div. | 2 | 850000 | 2058656.4 | 138 | 1@46'3 ; 1@45' ; 1@46'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 43 | 25 | 31 | No bridges on shortest detour. Hydro- not good candidate- potential problem obtaining FEMA model-May be a problem getting model to match floodplain. | SUMFLD | 2010-03-12 | 2010-02-24 | No | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | Yes | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Rockingham | 780143 | SR 1321 | Beaver Island Creek | 1955 | Div. | 3 | 700000 | 1127087.4 | 106 | 1@35'4 ; 1@35'1 ; 1@35'4 | n/a | No Preliminary Engineering Work Done. | SD | FO | 42 | 13 | 17 | On Quad Map, it is on SR 1324, not SR 1321. 780145 and 780148 on detour. | AYERVL | 2010-03-24 | 2010-02-25 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Caswell | 160047 | SR 1301 | Hogan's Creek | 1957 | Div. | 4 | 800000 | 1625828.6 | 121 | 1@40'7 ; 1@40' ; 1@40'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 41 | 16 | 20 | Detour goes into Rockingham County | RUFFIN | 2010-03-31 | 2010-03-01 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Alamance | 134 | SR 2356 | Cane Creek | 1960 | Div. | 5 | 825000 | 1638630.4 | 121 | 1@30'3 ; 2@30' ; 1@30'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 37 | 16 | 21 | B-3603 possible old TIP project and 000135 on detour | SNOCMP | 2010-03-12 | 2010-03-02 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Alamance | 66 | SR 1910 | Quaker Creek | 1963 | Div. | 6 | 675000 | 1222730.6 | 91 | 1@30'6 ; 1@30' ; 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 29 | 41 | 44 | 000064 on detour | BURLNE | 2010-04-14 | 2010-03-02 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Guilford | 400030 | SR 1129 | Register's Creek | 1952 | Div. | 7 | 600000 | 395692 | 34 | 1@33'7 | n/a | No Preliminary Engineering Work Done. | N | FO | 40 | 15 | 19 | B-3843 and B-3846 on detour - may be old replacement projects I don't have any info on them. Hydro- not good candidate- potential problem obtaining FEMA model-May be a problem getting model to match floodplain. | HIGPTE | 2010-03-12 | 2010-03-10 | No | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Guilford | 400293 | SR 3314 | Little Alamance Creek | 1951 | Div. | 8 | 650000 | 548731.7 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 12 | 15 | Does not appear to be a good offsite detour. Hydro- not good candidate- potential problem obtaining FEMA model-May be a problem getting model to match floodplain. | MCLEAN | 2010-03-12 | 2010-03-01 | No | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Rockingham | 780086 | SR 2598 | Little Troublesome Crk | 1952 | Div. | 9 | 600000 | 675691.7 | 53 | 1@17'9 ; 1@17'1 ; 1@17'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 25 | NP | NP | 780087 on detour | REIDVL | 2010-03-31 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Orange | 670076 | SR 1113 | New Hope Creek | 1954 | Div. | 10 | 650000 | 739436.2 | 58 | 1@17'9 ; 1@40' | n/a | No Preliminary Engineering Work Done. | SD | FO | 29 | 16 | 20 | Several bridges on possible detours, none are programmed projects. | CHAPHLI | 2010-04-14 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Alamance | 32 | SR 1582 | Buttermilk Creek | 1955 | Div. | 11 | 625000 | 740600 | 70 | 1@17'10 ; 1@35'1 ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | 12 | 16 | 000031 on detour | LKBURL | 2010-04-01 | 2010-03-01 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Orange | 670135 | SR 1516 | North Fork Little River | 1956 | Div. | 12 | 625000 | 429442.2 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 30 | 13 | 17 | No bridges on shortest detour. Historical note from 04/08: a field survey will be required before Section 106 can be complete. | CALDWLI | 2010-04-05 | 2010-02-25 | Yes | 2010-03-31 | 2010-04-08 | Yes | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Orange | 670047 | SR 1520 | North Fork Little River | 1964 | Div. | 13 | 550000 | 532703 | 53 | 1@17'9 ; 1@17' ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | SD | FO | 28 | 10 | 17 | No bridges on shortest detour | CALDWLI | 2010-04-02 | 2010-02-26 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Rockingham | 780044 | SR 2336 | Jacob's Creek | 1955 | Div. | 14 | 575000 | 470281 | 35 | 1@34'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 37 | 11 | 14 | 780191 on possible detour | ELLIBO | 2010-03-25 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | No | 2010-04-30 | 2010-02-25 | 2010-03-25
7 | Caswell | 160053 | SR 1527 | Trib. of Dan River | 1953 | Div. | 15 | 750000 | 733670.1 | 69 | 1@17'10 ; 1@34' ; 1@17'2 | n/a | No Preliminary Engineering Work Done. | SD | FO | 25 | 16 | 21 | Off site detour into Virginia. Hydro- not good candidate, may require CLOMR, study may extend into Va. | RINGGD | 2010-03-31 | 2010-03-01 | No | 2010-03-31 | 2010-04-08 | No | 2010-04-06 | Yes | 2010-04-30 | 2010-02-25 | 2010-03-25
8 | Chatham | 180282 | SR 1362 | Rocky River | 1952 | Div. | 1 | 775000 | 740600 | 70 | 1@17'6 ; 1@35' ; 1@17'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 69 | NP | NP | Per Charlie on 02/26: "According to Greg Myrick, this is the water supply for Siler City. Looking at the pictures and considering that this is a water supply, I'm not sure this is a good candidate for this program. (See Pictures from 02/26 e-mail) | CRUCRD | 2010-04-15 | 2010-02-16 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Hoke | 460057 | SR 1406 | Puppy Creek | 1946 | Div. | 2 | 675000 | 952200 | 75 | 1@24'9 ; 1@ 25'1 ; 1@25'2 | n/a | No Preliminary Engineering Work Done. | N | FO | 41 | 22 | 32 | Hydro- not good candidate- potential problem obtaining FEMA model. | PARKTNI | 2010-04-05 | 2010-02-16 | No | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Hoke | 460054 | SR 1422 | Beaver Creek | 1968 | Div. | 3 | 600000 | 672888 | 53 | 1@17'10 ; 1@17'1 ; 1@17'8 | n/a | No Preliminary Engineering Work Done. | N | N | 53 | 16 | 24 |  | PARKTNI | 2010-04-05 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750149 | SR 2141 | Creek | 1952 | Div. | 5 | 600000 | 433780 | 41 | 2@20'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | 14 | 19 |  | GRACHA | 2010-04-15 | 2010-02-17 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Moore | 620184 | SR 1404 | William's Creek | 1955 | Div. | 6 | 575000 | 560740 | 53 | 1@17'8 ; 1@17' ; 1@17'10 | n/a | No Preliminary Engineering Work Done. | N | FO | 38 | 10 | 17 |  | SPIES | 2010-04-15 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750014 | SR 1163 | McGee's Creek | 1957 | Div. | 7 | 725000 | 861212 | 74 | 1@17'1 ; 1@39' ; 1@17'5 | n/a | No Preliminary Engineering Work Done. | SD | FO | 27 | 17 | 22 |  | FARMER | 2010-04-15 | 2010-02-18 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750194 | SR 2876 | Creek | 1960 | Div. | 8 | 650000 | 846400 | 80 | 1@18'1 ; 1@43'9 ; 1@18'1 | n/a | No Preliminary Engineering Work Done. | N | FO | 38 | 11 | 19 |  | BENNET | 2010-04-15 | 2010-02-19 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750419 | SR 2159 | Creek | 1962 | Div. | 9 | 575000 | 360778 | 31 | 1@30'8 | n/a | Hydro 2000. Geotechnical Report 2001. | SD | N | 34 | 11 | 15 | Hydro- not good candidate- potential problem obtaining FEMA model. | ASHEBO | 2001-07-09 | 2010-02-22 | No | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Moore | 620039 | SR 1838 | Little River | 1962 | Div. | 10 | 650000 | 616814 | 53 | 1@18'5 ; 1@16'10 ; 1@17'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 43 | 15 | 22 | Hydro- not good candidate- potential problem obtaining FEMA model. | CARTHA | 2010-04-15 | 2010-02-22 | No | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Hoke | 460026 | SR 1138 | Fork of Big Raft Swamp | 1964 | Div. | 11 | 625000 | 725576.4 | 54 | 1@17'11 ; 1@17'1 ; 1@17'11 | n/a | No Preliminary Engineering Work Done. | SD | N | 43 | 13 | 22 |  | RAEFO | 2010-04-05 | 2010-02-22 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750318 | SR 2640 | Creek | 1961 | Div. | 12 | 575000 | 356122.8 | 36 | 2@17'9 | n/a | No Preliminary Engineering Work Done. | N | FO | 39 | 9 | 16 |  | COLERI | 2010-04-15 | 2010-02-23 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Montgomery | 610130 | SR 1318 | Doomas Creek | 1958 | Div. | 13 | 625000 | 382784.4 | 36 | 1@35'8 | n/a | Hydro 2001 (1@25' 1@55' 1@25') | SD | FO | 41 | 12 | 16 |  | LOVEJO | 2010-04-15 | 2010-02-24 | Yes | 2010-03-31 | 2010-04-15 | Yes | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Chatham | 180412 | SR 2160 | Robeson Creek | 1957 | Div. | 14 | 625000 | 860154 | 65 | 1@17'3 ; 1@30' ; 1@17'3 | n/a | No Preliminary Engineering Work Done. | N | N | 49 | 11 | 19 |  | PITTBO | 2010-04-15 | 2010-02-25 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
8 | Randolph | 750215 | SR 2903 | Bachelor Creek | 1945 | Div. | 15 | 600000 | 362894 | 49 | 1@29'8 ; 1@19'8 | n/a | No Preliminary Engineering Work Done. | N | FO | 40 | 16 | 21 |  | ERECT | 2010-04-15 | 2010-02-25 | Yes | 2010-03-31 | 2010-04-15 | No | 2010-04-07 | No | 2010-05-05 | 2010-02-25 | 2010-03-26
9 | Davidson | 280447 | SR 1454 | Creek | 1958 | Div. | 1 | 475000 | 275080 | 26 | 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 30 | 16 | 22 | Hydro- not good candidate- potential problem obtaining FEMA model. | LEXINW | 2010-04-16 | 2010-03-08 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-08 | No |  | 2010-02-25
9 | Forsyth | 330002 | SR 1470 | Creek | 1958 | Div. | 2 | 600000 | 440286.7 | 41 | 1@40'7 | n/a | No Preliminary Engineering Work Done. | N | FO | 49 | 21 | 26 |  | VIENNA | 2010-03-24 | 2010-03-12 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-08 | No |  | 2010-02-25
9 | Rowan | 790011 | SR 1763 | Sill's Creek | 1953 | Div. | 3 | 600000 | 429442.2 | 41 | 1@36.7' | n/a | No Preliminary Engineering Work Done. | SD | FO | 25 | 16 | 21 |  | CLEVLD | 2010-03-17 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-09 | Yes | 2010-04-08 | No |  | 2010-02-25
9 | Davidson | 280079 | SR 1231 | Creek | 1950 | Div. | 4 | 575000 | 327980 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 31 | 12 | 16 | Hydro- not good candidate- potential problem obtaining FEMA model. | LEXINW | 2010-04-16 | 2010-03-09 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-08 | No |  | 2010-02-25
9 | Davidson | 280338 | SR 2265 | Flat Swamp Creek | 1963 | Div. | 5 | 500000 | 433780 | 41 | 1@40'10 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | 14 | 19 |  | DENTON | 2010-04-16 | 2010-03-16 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-08 | No |  | 2010-02-25
9 | Davie | 290077 | SR 1321 | Dutchman's Creek | 1977 | Div. | 6 | 600000 | 393576 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 35 | 13 | 16 |  | LONHIC | 2010-04-16 | 2010-03-10 | Yes | 2010-03-31 | 2010-04-09 | Yes | 2010-04-08 | No |  | 2010-02-25
9 | Forsyth | 330152 | SR 1137 | Silas Creek | 1961 | Div. | 7 | 650000 | 819632.6 | 61 | 2@30'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 19 | 6 | 0 | Hydro- not good candidate- potential problem obtaining FEMA model. | WNSALW | 2010-03-24 | 2010-03-11 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-08 | No |  | 2010-02-25
9 | Stokes | 840002 | SR 1103 | Run Creek | 1962 | Div. | 8 | 700000 | 861264.9 | 81 | 2@40'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 31 | 15 | 18 |  | PINNAC | 2010-03-24 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-09 | Yes | 2010-04-08 | No |  | 2010-02-25
9 | Rowan | 790122 | SR 1348 | Creek | 1966 | Div. | 9 | 550000 | 423094.2 | 31 | 1@31'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 24 | 38 | NP | Hydro- potential culvert. | CHINGR | 2010-04-16 | 2010-03-11 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Davidson | 280282 | SR 2533 | Cabin Creek | 1962 | Div. | 10 | 625000 | 539580 | 51 | 1@50'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 36 | 12 | 15 |  | HIGHRK | 2010-04-16 | 2010-03-16 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Forsyth | 330068 | SR 2014 | Branch of Belew's Crk | 1968 | Div. | 11 | 550000 | 345648.6 | 27 | 1@26'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 39 | 23 | 31 |  | BELECK | 2010-03-24 | 2010-03-12 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Rowan | 790200 | SR 2539 | Town Creek | 1964 | Div. | 12 | 725000 | 650987.4 | 42 | 1@41'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 48 | NP | NP | Hydro- not good candidate- potential problem obtaining FEMA model. | CHINGR | 2010-04-16 | 2010-03-11 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Davidson | 280134 | SR 1755 | Creek | 1961 | Div. | 13 | 625000 | 676062 | 71 | 1@40'6 ; 1@30' | n/a | No Preliminary Engineering Work Done. | SD | FO | 42 | 11 | 15 | Hydro- not good candidate- potential problem obtaining FEMA model. | HIGPTW | 2010-04-16 | 2010-03-16 | No | 2010-03-31 | 2010-04-09 | Yes | 2010-04-09 | No |  | 2010-02-25
9 | Davie | 290053 | SR 1406 | Frost Mill Creek | 1963 | Div. | 14 | 575000 | 491335.2 | 36 | 1@35'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 32 | 15 | 19 |  | MOCKVL | 2010-04-16 | 2010-03-09 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Davidson | 280277 | SR 2504 | Lick Creek | 1953 | Div. | 15 | 550000 | 446211.5 | 35 | 2@17'4 | n/a | No Preliminary Engineering Work Done. | SD | N | 46 | 19 | 27 |  | HIGHRK | 2010-04-16 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Forsyth | 330145 | SR 1625 | Shangrila Creek | 1965 | Div. | 16 | 525000 | 605916.6 | 46 | 1@24'3 ; 1@21'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 38 | 25 | 28 | Hydro- not good candidate- potential problem obtaining FEMA model. | RURHAL | 2010-03-12 | 2010-03-12 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Davidson | 280349 | SR 2099 | Plummer's Creek | 1952 | Div. | 17 | 600000 | 529211.6 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 30 | 17 | 20 |  | FAIRGR | 2010-04-16 | 2010-03-09 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Davie | 290060 | SR 1802 | Peeler Creek | 1965 | Div. | 18 | 500000 | 423094.2 | 31 | 1@31' | n/a | No Preliminary Engineering Work Done. | SD | N | 23 | NP | NP |  | COOLEE | 2010-04-16 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-09 | Yes | 2010-04-09 | No |  | 2010-02-25
9 | Rowan | 790203 | SR 1526 | Town Creek | 1961 | Div. | 19 | 650000 | 620517 | 46 | 1@23' ; 1@22'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 37 | 19 | 26 | Hydro- not good candidate- potential problem obtaining FEMA model. | ROWMIL | 2010-04-16 | 2010-03-11 | No | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
9 | Stokes | 840184 | SR 1175 | Creek | 1941 | Div. | 20 | 625000 | 550160 | 52 | 1@52'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 39 | NP | NP | Hydro- good Division DB project. | HANGRK | 2010-03-24 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-09 | No | 2010-04-09 | No |  | 2010-02-25
10 | Union | 890077 | SR 1751 | Rays Creek | 1956 | Div. | 2 | 725000 | 701136.6 | 47 | 1@46'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 50 | 32 | 35 | Per Charlie Brown on 02/26: "ARRA 890077 is a part of R-2559B&C (Monroe Bypass). We surveyed this project in 1997. Monroe Bypass stops right at the bridge. The survey is NAD83, NGVD29. With a couple of setups, we can convert it to NAD88. We also found out that Toll Authority flown this project recently, so there is new photography available." Several questions to this: "If this bridge is to be replaced as part of the Monroe Bypass, then the question becomes one of timing. What is the schedule for that project? How much money would NCDOT expend in replacing a bridge that would be replaced soon afterwards. But the other side of that is also a question of timing. What is the rating on this bridge and how badly does it need to be replaced?" | WINGAT | 2010-04-13 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-22 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-31
10 | Union | 890151 | SR 2139 | Richardson Creek | 1953 | Div. | 3 | 625000 | 524873.8 | 41 | 1@41' | n/a | No Preliminary Engineering Work Done. | SD | FO | 28 | 21 | 26 |  | MONROE | 2010-04-09 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-31
10 | Mecklenburg | 590128 | SR 2131 | Branch of Mcdowell Crk | 1963 | Div. | 4 | 575000 | 319939.2 | 24 | 1@23'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | NP | NP | Historical: will require a field survey to determine the National Register eligibility a study-listed site (MK147) located approximately 800 feet from the bridge. Please let our office know if you would like us to proceed with this project. | LKNORS | 2008-03-11 | 2010-02-23 | Yes | 2010-03-31 | 2010-03-22 | Yes | 2010-04-05 | No |  | 2010-02-25 | 2010-03-31
10 | Union | 890124 | SR 1941 | Flag Branch | 1968 | Div. | 5 | 475000 | 281639.6 | 22 | 1@22' | n/a | No Preliminary Engineering Work Done. | SD | FO | 36 | 22 | 29 |  | WINGAT | 2010-04-14 | 2010-02-22 | Yes | 2010-03-31 |  |  | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Union | 890168 | SR 1128 | Cane Creek | 1963 | Div. | 8 | 525000 | 553069.5 | 41 | 1@40'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 24 | 17 | 20 |  | UNITY | 2010-04-09 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-22 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Cabarrus | 120070 | SR 2416 | McAllister Creek | 1958 | Div. | 9 | 550000 | 295182 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | 15 | 20 | Hydro- good culvert site. | MTPLEA | 2010-04-12 | 2010-02-22 | No | 2010-03-31 | 2010-03-23 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Cabarrus | 120207 | SR 1143 | Branch of Andero | 1964 | Div. | 10 | 450000 | 476100 | 36 | 1@36'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 30 | 19 | 24 |  | CONCSE | 2010-04-07 | 2010-02-19 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Stanly | 830198 | SR 1228 | Running Creek | 1965 | Div. | 11 | 525000 | 324700.2 | 31 | 1@30'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 22 | 14 | 19 |  | LOCUST | 2005-08-25 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-22 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Union | 890451 | SR 1194 | Trib. Of Waxhaw Creek | 1964 | Div. | 12 | 475000 | 294441.4 | 22 | 1@21'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 29 | 21 | 30 |  | VANWYC | 2010-04-13 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-22 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Stanly | 830097 | SR 1957 | Little Long Creek | 1963 | Div. | 13 | 550000 | 479908.8 | 36 | 1@35'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 28 | 15 | 20 | Hydro-40'x4' crownspan | ALBEMA | 2009-07-15 | 2010-02-22 | Crownspan | 2010-03-31 | 2010-03-22 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Cabarrus | 120142 | SR 1113 | Muddy Creek | 1962 | Div. | 14 | 600000 | 433780 | 41 | 1@39'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 22 | 30 | 33 |  | MIDLND | 2010-04-08 | 2010-02-23 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
11 | Surry | 850088 | SR 1621 | Paul's Creek | 1951 | Div. | 1 | 900000 | 1000000 | 136 | 1@45'5 ; 1@45' ; 1@ 45'5 | n/a | B-4821. FSM Held. FEMA Permit according to FSM? Utilities in conflict. Rated as medium impact on FSM. | SD | FO | 10 | 16 | 19 | Hydro- not good candidate- potential problem obtaining FEMA model. TIP Project B-4821 | CANA | 2010-04-16 | 2010-03-01 | No | 2010-03-31 | 2010-04-14 | No | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Caldwell | 130045 | SR 1722 | Upper Little River | 1961 | Div. | 2 | 725000 | 500000 | 68 | 1@17' ; 1@35' ; 1@16'4 | n/a | No Preliminary Engineering Work Done. | SD | FO | 31 | 16 | 20 |  | KINGCK | 2010-03-30 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-31 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960238 | SR 2026 | Creek | 1950 | Div. | 3 | 625000 | 500000 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 23 | 12 | 17 | Hydro-potential for culvert. 1@14'x8' | THURMD | 2010-03-23 | 2010-03-15 | No | 2010-03-31 | 2010-04-14 | Yes | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960089 | SR 1151 | Naked Creek | 1965 | Div. | 4 | 600000 | 400000 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 26 | 18 | 22 |  | PURLEA | 2010-03-23 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-14 | No | 2010-03-31 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Surry | 850322 | SR 1622 | Stewarts Creek | 1962 | Div. | 5 | 825000 | 650000 | 96 | 1@25'6 ; 1@45' ; 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 17 | 16 | 19 | Hydro- not good candidate- potential problem obtaining FEMA model. | CANA | 2010-03-31 | 2010-03-02 | No | 2010-03-31 | 2010-04-14 | No | 2010-04-01 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960086 | SR 1150 | Creek | 1957 | Div. | 6 | 675000 | 500000 | 57 | 1@17'1 ; 1@40'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | NP | NP |  | PURLEA | 2004-04-01 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-31 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Watauga | 940142 | SR 1359 | Creek | 1974 | Div. | 7 | 525000 | 400000 | 26 | 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 20 | 21 | 28 | Hydro-potential for culvert. | TODD | 2010-03-17 | 2010-03-11 | No | 2010-03-31 | 2010-04-14 | Yes | 2010-04-01 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Yadkin | 980110 | SR 1503 | North Deep Creek | 1961 | Div. | 8 | 700000 | 550000 | 55 | 1@36'7 ; 1@18'8 | n/a | No Preliminary Engineering Work Done. | N | FO | 66 | 25 | 39 |  | YADKVL | 2010-03-26 | 2010-03-15 | Yes | 2010-03-31 | 2010-04-14 | No | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Watauga | 940132 | SR 1306 | Cove Creek | 1960 | Div. | 9 | 675000 | 400000 | 41 | 1@40'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 22 | 17 | 21 |  | SHERWD | 2010-03-17 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-04-01 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960222 | SR 2149 | Creek | 1963 | Div. | 10 | 525000 | 400000 | 26 | 1@26' | n/a | No Preliminary Engineering Work Done. | SD | FO | 17 | 11 | 15 | Hydro-potential for culvert. | THURMD | 2010-04-06 | 2010-03-15 | No | 2010-03-31 | 2010-04-14 | Yes | 2010-03-31 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960345 | SR 2425 | Creek | 1959 | Div. | 11 | 575000 | 400000 | 26 | 1@25'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 18 | 17 | 23 |  | GILREA | 2010-03-30 | 2010-03-15 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960021 | SR 2423 | Hunting Creek | 1965 | Div. | 12 | 800000 | 800000 | 82 | 1@40'3 ; 1@42'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 37 | 17 | 21 |  | OSBOVL | 2010-04-07 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960737 | SR 2425 | Cales Creek | 1958 | Div. | 13 | 550000 | 400000 | 26 | 1@25'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 29 | 20 | 27 |  | OSBOVL | 2010-03-30 | 2010-03-15 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Surry | 850309 | SR 1320 | Creek | 1958 | Div. | 14 | 525000 | 400000 | 26 | 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 39 | 15 | 20 | Hydro-potential for culvert. | ROARGP | 2010-03-31 | 2010-03-03 | No | 2010-03-31 | 2010-04-14 | No | 2010-04-01 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Caldwell | 130057 | SR 1732 | Middle Little River | 1962 | Div. | 15 | 675000 | 500000 | 51 | 1@50'6 | n/a | B-4721. FSM Held. Very few problems. Utilities in coflict. Rated as low impact on FSM. | N | FO | 36 | 15 | 18 |  | ELLNDL | 2010-03-30 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-14 | No | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Wilkes | 960042 | SR 2486 | Moravian Creek | 1959 | Div. | 16 | 650000 | 250000 | 41 | 1@40'6 | n/a | B-4847. FSM Held. FEMA Permit according to FSM? Utilities in conflict, rated as low impact on FSM. Long detour for one prop. Owner. | SD | FO | 25 | 15 | 19 | Per Charlie Brown on 02/26: "Low Impact Bridge# 960042 is also TIP B-4847 (( we flew it last year)) We have also did our Low Impact survey on it." | MORFAL | 2010-04-14 | 2010-03-11 | Yes | 2010-03-31 | 2010-04-14 | No | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
11 | Yadkin | 980149 | SR 1368 | North Deep Creek | 1960 | Div. | 17 | 675000 | 350000 | 46 | 1@45'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | 17 | 21 |  | YADKVL | 2010-03-26 | 2010-03-08 | Yes | 2010-03-31 | 2010-04-14 | Yes | 2010-03-29 | No | 2010-04-30 | 2010-02-25 | 2010-03-11
12 | Gaston | 350045 | SR 1136 | Blackwood Creek | 1957 | Div. | 1 | 700000 | 424892.8 | 32 | 1@32'5 | n/a | No Preliminary Engineering Work Done. | SD | FO | 11 | NP | NP | Hydro-not good candidate-Potential obtaining FEMA model | GASTOS | 2010-04-12 | 2010-02-16 | No | 2010-03-31 | 2010-03-17 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-19
12 | Iredell | 480334 | SR 2136 | Dutchman Creek | 1955 | Div. | 2 | 725000 | 1068580 | 100 | 1@20'1 ; 1@19'7 ; 1@20' ; 1@20'3 ; 1@19'10 | n/a | No Preliminary Engineering Work Done. | SD | FO | 19 | 40 | 40 |  | HARMON | 2010-04-16 | 2010-02-16 | Yes | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-19
12 | Cleveland | 220188 | SR 1637 | Maple Creek | 1954 | Div. | 3 | 625000 | 648606.9 | 61 | 2@30'8 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | 19 | 24 | Historical: In the APE of this project is an identified historic site (CL397). A field site visit is required to investigate this property. Please contact our office if you would like us to move forward on this project. | LAWNDA | 2010-04-13 | 2010-02-17 | Yes | 2010-03-31 | 2010-03-18 | Yes | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-10
12 | Catawba | 170045 | SR 1131 | Hop Creek | 1959 | Div. | 4 | 475000 | 317400 | 30 | 1@30'4 | n/a | No Preliminary Engineering Work Done. | SD | FO | 22 | 33 | 40 | Hydro- potential culvert. | HICKOR | 2010-04-16 | 2010-02-17 | No | 2010-03-31 | 2010-03-19 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-10
12 | Catawba | 170229 | SR 1809 | Creek | 1959 | Div. | 5 | 525000 | 257199.8 | 26 | 1@26' | n/a | No Preliminary Engineering Work Done. | SD | FO | 23 | 11 | 16 | Historical: will require a field survey to determine the eligibility of two houses that are greater than 50 years old in the project vicinity. Please let our office know if you would like us to proceed with this project. Hydro- crown span 1@40'x7' | NEWTON | 2003-04-01 | 2010-02-17 | Crownspan | 2010-03-31 | 2010-03-19 | Yes | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-10
12 | Cleveland | 220374 | SR 1316 | W. Fork of Beaverdam Crk | 1961 | Div. | 6 | 600000 | 865549.8 | 81 | 2@40'4 | n/a | No Preliminary Engineering Work Done. | SD | FO | 33 | 13 | 16 |  | BOSPRN | 2010-04-13 | 2010-02-17 | Yes | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-10
12 | Iredell | 480077 | SR 1338 | Third Creek | 1967 | Div. | 7 | 700000 | 462134.4 | 39 | 1@38'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 34 | 14 | 18 | Hydro-not good candidate-Potential obtaining FEMA model | STVLW | 2010-04-16 | 2010-02-18 | No | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-19
12 | Alexander | 10087 | SR 1337 | Kirby Creek | 1977 | Div. | 8 | 675000 | 1041230.7 | 81 | 1@25'3 ; 1@30' ; 1@25'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 34 | 25 | 37 | Hydro-potential culvert site. | MORFAL | 2010-04-05 | 2010-02-18 | No | 2010-03-31 | 2010-03-19 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-10
12 | Lincoln | 540115 | SR 1129 | Indian Creek | 1952 | Div. | 9 | 675000 | 729702.6 | 66 | 1@40' ; 1@26' | n/a | No Preliminary Engineering Work Done. | SD | FO | 36 | 24 | 30 | Historical: will require a field survey to determine the eligibility of a large agriculture complex that is greater than 50 years old in the project vicinity. Please let our office know if you would like us to proceed with this project. | BANOAK | 2010-04-09 | 2010-02-18 | Yes | 2010-03-31 | 2010-03-19 | Yes | 2010-04-05 | No |  | 2010-02-25 | 2010-03-19
12 | Catawba | 170043 | SR 1131 | Hop Creek | 1950 | Div. | 10 | 500000 | 497260 | 47 | 1@46'8 | n/a | No Preliminary Engineering Work Done. | SD | FO | 36 | 16 | 19 |  | HICKOR | 2010-04-16 | 2010-02-18 | Yes | 2010-03-31 | 2010-03-19 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-10
12 | Cleveland | 220189 | SR 1639 | Maple Creek | 1954 | Div. | 11 | 525000 | 331259.8 | 31 | 1@31'2 | n/a | No Preliminary Engineering Work Done. | N | FO | 38 | 13 | 18 |  | LAWNDA | 2010-04-14 | 2010-02-19 | Yes | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-10
12 | Catawba | 170014 | SR 1486 | Creek | 1952 | Div. | 12 | 500000 | 285660 | 27 | 1@27' | n/a | No Preliminary Engineering Work Done. | SD | FO | 47 | NP | NP |  | MILLVL | 2010-04-16 | 2010-02-19 | Yes | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-19
12 | Iredell | 480107 | SR 1503 | Buffalo Shoals Creek | 1952 | Div. | 13 | 750000 | 1127087.4 | 106 | 1@35'3 ; 1@35' ; 1@35'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 23 | 32 | 32 | Hydro-could invovle 2 stream models. | STONPT | 2010-04-16 | 2010-02-19 | Yes | 2010-03-31 | 2010-03-18 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-19
12 | Iredell | 480079 | SR 1337 | Back Creek | 1964 | Div. | 14 | 575000 | 1005100 | 76 | 1@25'3 ; 1@25' ; 1@25'3 | n/a | No Preliminary Engineering Work Done. | SD | N | 49 | 15 | 18 | Historical: will require a field survey to determine to effects to the National Register Listed Property known as The Davidson House (ID 19). Please let our office know if you would like us to proceed with this project. | STVLW | 2010-04-16 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-18 | Yes | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-19
12 | Iredell | 480039 | SR 1138 | Rocky River | 1953 | Div. | 15 | 625000 | 1028376 | 81 | 1@20'3 ; 1@20' ; 1@20'5 ; 1@19'10 | n/a | No Preliminary Engineering Work Done. | SD | FO | 50 | NP | NP |  | MOORVL | 2010-04-16 | 2010-02-22 | Yes | 2010-03-31 | 2010-03-17 | No | 2010-04-05 | No | 2010-05-05 | 2010-02-25 | 2010-03-19
13 | Buncombe | 100030 | SR 1381 | Newfound Creek | 1945 | Div. | 3 | 575000 | 329619.9 | 31 | 1@30'6 | n/a | B-4730. | N | FO | 48 | 14 | 18 | Historical: will need addition field survey before Section 106 is complete. Hydro- not a good candidate-potential problem obtaining FEMA model. | LEICES | 2010-03-17 | 2010-02-02 | No | 2010-03-31 | 2010-03-23 | Yes | 2010-03-19 | Yes | 2010-05-06 | 2010-02-25 | 2010-03-04
13 | Burke | 110174 | SR 1901 | Little Rvier | 1963 | Div. | 4 | 650000 | 384688.8 | 36 | 2@17'10.5 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | NP | NP | Hydro- potential culvert. | CASAR | 2010-04-07 | 2010-02-03 | No | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-04
13 | Madison | 560024 | SR 1530 | Paint Fork Creek | 1970 | Div. | 5 | 675000 | 755412 | 56 | 1@18'3 ; 1@19'10 ; 1@18'2 | n/a | No Preliminary Engineering Work Done. | SD | N | 44 | 12 | 20 | Historical: will need addition field survey before Section 106 is complete. Hydro-could be a problem- bridge at stream branch and may have to model both streams- potential culvert. | BARNVL | 2010-03-17 | 2010-02-03 | No | 2010-03-31 | 2010-03-23 | Yes | 2010-03-19 | Yes | 2010-05-06 | 2010-02-25 | 2010-03-04
13 | McDowell | 580064 | SR 1760 | Creek | 1958 | Div. | 6 | 600000 | 334592.5 | 25 | 1@25'1 | n/a | No Preliminary Engineering Work Done. | SD | FO | 39 | 15 | 21 | Historical: will need addition field survey before Section 106 is complete. | MARIOE | 2010-04-02 | 2010-02-04 | Yes | 2010-03-31 | 2010-03-23 | Yes | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-09
13 | Rutherford | 800385 | SR 1709 | Creek | 1964 | Div. | 7 | 775000 | 1047208.4 | 98 | 1@22'7 ; 1@39'6 ; 1@35'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | NP | NP |  | SUNSHI | 2010-04-06 | 2010-02-04 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-05
13 | Mitchell | 600026 | NC 226 | Big Rock Creek | 1949 | Div. | 8 | 1075000 | 1000000 | 161 | 1@40'4 ; 2@40' ; 1@40'4 | n/a | These 2 projects need to be superstructure rehab only. Deck and beams are in bad shape but the substructure is in great shape. With minor cap mods, could be replaced with cored slab units and be no permit jobs. | SD | N | 39 | 31 | 36 | Historical: will need addition field survey before Section 106 is complete. | BAKEVL | 2010-03-23 | 2010-02-04 | Yes | 2010-03-31 | 2010-03-23 | Yes | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-24
13 | Mitchell | 600028 | NC 226 | Big Rock Creek | 1949 | Div. | 9 | 1100000 | 1000000 | 141 | 1@35'4 ; 2@35' ; 1@35'4 | n/a | These 2 projects need to be superstructure rehab only. Deck and beams are in bad shape but the substructure is in great shape. With minor cap mods, could be replaced with cored slab units and be no permit jobs. | SD | FO | 27 | 21 | 28 |  | BAKEVL | 2010-03-19 | 2010-02-04 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-23
13 | Rutherford | 800025 | SR 2129 | Creek | 1968 | Div. | 10 | 675000 | 1025202 | 76 | 1@25'9 ; 1@24'6 ; 1@25'9 | n/a | No Preliminary Engineering Work Done. | SD | N | 21 | 19 | 26 |  | FORECY | 2010-04-12 | 2010-02-05 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-18
13 | Madison | 560251 | SR 1506 | Creek | 1962 | Div. | 11 | 600000 | 287088.3 | 27 | 1@26'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 41 | 15 | 21 | hydro-Good culvert site. | SAMGAP | 2010-03-17 | 2010-02-05 | No | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-10
13 | Madison | 560516 | SR 1196 | Walnut Creek | 1965 | Div. | 12 | 675000 | 713621 | 71 | 2@35'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 46 | 38 | 42 |  | MARSHA | 2010-03-16 | 2010-02-18 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-10
13 | Burke | 110352 | SR 1874 | East Prong Hunting Crk | 1969 | Div. | 13 | 825000 | 1262723 | 77 | 1@25'10 ; 1@24'4 ; 1@25'10 | n/a | No Preliminary Engineering Work Done. | SD | N | 41 | 31 | 31 | Hydro-not good candidate-Potential obtaining FEMA model | MORGAS | 2010-04-05 | 2010-02-08 | No | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-09
13 | Burke | 110353 | SR 1874 | East Prong Hunting Crk | 1971 | Div. | 14 | 825000 | 1262356.5 | 77 | 1@25'8 ; 1@25' ; 1@25'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 41 | 30 | 30 | Hydro-not good candidate-Potential obtaining FEMA model | MORGAS | 2010-04-05 | 2010-02-08 | No | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-09
13 | McDowell | 580019 | SR 1143 | Cove Creek | 1969 | Div. | 15 | 625000 | 967593.9 | 91 | 1@25'3 ; 1@40' ; 1@25'3 | n/a | No Preliminary Engineering Work Done. | N | FO | 37 | 12 | 16 | Hydro-multiple streams converge-use as last resort. | SUGAHL | 2010-04-02 | 2010-02-09 | MAYBE | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-05
13 | Rutherford | 800204 | SR 1733 | Creek | 1952 | Div. | 16 | 575000 | 384688.8 | 36 | 1@35'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 39 | 13 | 17 |  | BENNKB | 2010-04-02 | 2010-02-10 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-09
13 | Rutherford | 800090 | SR 1762 | Sandy Run Creek | 1952 | Div. | 17 | 675000 | 1017161.2 | 87 | 1@25'9 ; 1@40'2 ; 1@20'7 | n/a | No Preliminary Engineering Work Done. | SD | FO | 19 | 39 | NP |  | BOSPRN | 2010-04-07 | 2010-02-10 | Yes | 2010-03-31 | 2010-03-23 | No | 2010-03-19 | No | 2010-05-06 | 2010-02-25 | 2010-03-18
14 | Swain | 860118 | SR 1133 | Brush Creek | 1961 | Div. | 1 | 575000 | 295000 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 10 | 12 | 17 |  | ALARKA | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | Yes | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
14 | Graham | 370029 | SR 1206 | Franks Creek | 1962 | Div. | 2 | 650000 | 330000 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 46 | 12 | 16 |  | ROBBVL | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | Yes | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Polk | 740085 | SR 1336 | Creek | 1962 | Div. | 3 | 675000 | 275000 | 26 | 1@26' | n/a | No Preliminary Engineering Work Done. | N | FO | 48 | 12 | 17 | Hydro- good pipe site 1@96" w/headwall | FINVLW | 2010-04-12 | 2010-03-29 | No | 2010-03-31 | 2010-03-25 | Yes | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Henderson | 440128 | SR 1713 | Hungry Creek | 1962 | Div. | 4 | 600000 | 280000 | 26 | 1@25'8 | n/a | No Preliminary Engineering Work Done. | SD | N | 37 | 13 | 18 | Removed per Joshua Deyton on 03/30/10 (See 03/30 e-mail) To be done as part of the Division Bridge Managed Program | CLIFMT | 2010-04-12 | 2010-03-29 | Yes |  | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Jackson | 490008 | SR 1120 | Cedar Creek | 1961 | Div. | 5 | 775000 | 433780 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 33 | 14 | 18 | Hydro- No effective model inhouse-should not be a problem to obtain. | BIGRID | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
14 | Macon | 550099 | SR 1128 | Jones Creek | 1961 | Div. | 6 | 1075000 | 325000 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 45 | 14 | 18 |  | PRENTI | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Clay | 210007 | SR 1300 | Fires Creek | 1960 | Div. | 7 | 1100000 | 710000 | 61 | 2@30'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 7 | 14 | 19 |  | HAYEVL | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Macon | 550050 | SR 1632 | Little Tennessee River | 1960 | Div. | 8 | 675000 | 598000 | 71 | 1@16' ; 1@39'3 ; 1@15'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 45 | 40 | 44 |  | PRENTI | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
14 | Graham | 370023 | SR 1212 | Sweetwater Creek | 1963 | Div. | 9 | 600000 | 400000 | 36 | 1@35'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 38 | 16 | 20 |  | ROBBVL | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
14 | Transylvania | 870072 | SR 1143 | Creek | 1959 | Div. | 10 | 675000 | 214000 | 20 | 1@20'3 | n/a | No Preliminary Engineering Work Done. | SD | FO | 15 | NP | NP | Removed per Joshua Deyton on 03/30/10 (See 03/30 e-mail) To be done as part of the Division Bridge Managed Program. Hydro- potential culvert site. | REID | 2010-04-09 | 2010-03-29 | No |  | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Macon | 550052 | SR 1114 | Coweeta Creek | 1961 | Div. | 11 | 825000 | 328000 | 31 | 1@30'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 47 | 14 | 18 |  | PRENTI | 2010-04-02 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Cherokee | 190235 | SR 1623 | Vengeance Creek | 1967 | Div. | 12 | 825000 | 245000 | 23 | 1@22'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 49 | 21 | 28 | Hydro-potential culvert site. | MARBLE | 2010-04-12 | 2010-03-29 | No | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | No | 2010-05-03 | 2010-02-25 | 2010-03-31
14 | Jackson | 490144 | SR 1397 | Nations Creek | 1961 | Div. | 13 | 625000 | 222000 | 21 | 1@46'8 | n/a | No Preliminary Engineering Work Done. | SD | FO | 22 | NP | NP |  | WHITTR | 2010-04-02 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | Yes | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
14 | Macon | 550076 | SR 1370 | Burningtown Creek | 1951 | Div. | 14 | 575000 | 328000 | 60 | 1@19'7 ; 1@39'11 | n/a | No Preliminary Engineering Work Done. | SD | FO | 20 | 16 | 20 |  | ALARKA | 2010-04-12 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | No | 2010-03-23 | Yes |  | 2010-02-25 | 2010-03-31
14 | Haywood | 430213 | SR 1508 | Liner Creek | 1957 | Div. | 15 | 675000 | 300000 | 26 | 1@25'6 | n/a | No Preliminary Engineering Work Done. | SD | FO | 8 | 39 | NP |  | CLYDE | 2010-03-16 | 2010-03-29 | Yes | 2010-03-31 | 2010-03-25 | Yes | 2010-03-23 | No |  | 2010-02-25 | 2010-03-31
[8 empty] | 134200000 | 145109675
| Let List Candidates | [17 empty] | \
2 | Beaufort | 60140 | SR 1626 | Albemarle Canal | 1962 | Let List | B-4428 |  | 875000 | 116 | 1@20.8' ; 1@19.7' ; 1@17.5' ; 19.7' ; 20.8' | 2010-05-18 | 404/401/CAMA Permits (IN) NO Moratorium SSP (IN) | SD | FO | 23 | NP | NP | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
4 | Johnston | 500084 | SR 1330 | Black Creek | 1951 | Let List | B-4559 |  | 1150000 | 172 | 1@17'9 ; 8@17' ; 1@17'9 | 2010-04-20 | NO Permits required Moratorium 2/15 - 6/15 MOA PENDING | SD | FO | 7 | 21 | 27 | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
5 | Person | 720043 | SR 1112 | South Flat River | 1955 | Let List | B-4600 |  | 800000 | 41 | 1@41'5 | 2010-08-01 | 404/401 Permits (IN) NO Moratorium MOA (IN) | SD | FO | 11 | 14 | 17 | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Chatham | 180056 | NC 42 | Buckhorn Creek | 1951 | Let List | B-4459 |  | 1600000 | 121 | 2@20' ; 2@20'3 ; 2@20'3 | 2010-06-15 | 404/401 Permits (IN) NO Moratorium MOE (IN) | SD | FO | 12 | NP | NP | MOE project per Bill Goodwin. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Moore | 620011 | SR 1864 | The Little River | 1961 | Let List | B-4584 |  | 1050000 | 121 | 1@40'4 ; 1@40' ; 1@40'4 | 2010-06-15 | 404/401 Permits (IN) SSP (IN) NO Moratorium MOA (IN) | SD | N | 24.3 | 16 | 19 | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Randolph | 750073 | SR 1518 | Lake Lucas | 1946 | Let List | B-4610 |  | 1600000 | 226 | 1@38' ; 4@37'6 ; 1@38' | 2010-06-15 | 404/401 Permits (IN) NO Moratorium. | SD | FO | 42 | 13 | 16 | MOE project per Bill Goodwin. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Scotland | 820075 | US 74B | Big Shoe Heel Creek | 1924 | Let List | B-4641 |  | 1950000 | 168 | 1@41'8 ; 1@42'4 ; 1@42'8 ; 1@41'2 | 2010-06-15 | 404/401 Permits (IN) NO Moratorium MOA (IN) | SD | N | 38 | NP | NP | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
12 | Gaston | 350173 | SR 1820 | Sailors Branch Creek | 1966 | Let List | B-4117 |  | 525000 | 41 | 1@35'3 ; 1@35' ; 1@35'3 | 2010-05-18 | 404/401 Permits (IN) NO Moratorium | SD | FO | 37 | 11 | 14 | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
12 | Gaston | 350049 | SR 1103 | Crowder's Creek | 1949 | Let List | B-4517 |  | 1500000 | 161 | 1@20'3 ; 1@20' ; 1@20'5 ; 1@19'10 | 2010-05-18 | 404/401 Permits (IN) NO Moratorium | SD | FO | 18 | 12 | 12 | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
13 | Buncombe | 100134 | NC 151 | Stony Fork Creek | 1926 | Let List | B-4034 |  | 1300000 | 42 | 1@41'11 | 2010-04-20 | 404/401 Permits (IN) TVA (IN) FEMA PENDING T-Moratorium 10/15 - 4/15 | N | FO | 48 | NP | NP | L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
13 | McDowell | 580037 | NC 226 | Hopper Creek | 1950 | Let List | B-4190 |  | 1300000 | 76 | 1@25'3 ; 1@25' ; 1@25'3 | 2010-06-15 | 404 Permit PENDING 401 Permit (IN) NO Moratorium MOA PENDING | SD | FO | 12 | NP | NP | MOE project per Bill Goodwin. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
| POC Candidates | [17 empty] | \
5 | Warren | 920107 | SR 1224 | Smith Creek | 1952 | POC | B-4308 |  | 425000 | 46 | 1@15'9 ; 1@14'9 ; 1@15'10 | 2010-05-19 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 32 | 9 | 15 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
5 | Franklin | 340076 | SR 1600 | Sycamore Creek | 1954 | POC | MA05002B |  | 651547 | 81 | 2@40'4 | n/a | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 28 | NP | NP | Per Charlie Brown on 03/01: "We staked the r/w on this back in 10/2008 for Bridge Management. We had no involvement other staking the r/w and it was done under Project MA-0002-EB." Per Mike Summers, need to be sure to build Structure 75 first, prior to this one. |  | 2010-03-17 | [8 empty] | 2010-02-25
6 | Robeson | 770041 | SR 2115 | Lee Pond | 1957 | POC | B-3898 |  | 400000 | 36 | 1@17'10 ; 1@17'8 | 2010-06-15 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | N | 11 | 12 | 20 | Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
6 | Robeson | 770143 | SR 1146 | Ashpole Swamp | 1957 | POC | B-4249 |  | 375000 | 36 | 2@18' | 2010-06-15 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | N | 27 | 24 | 40 | Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
6 | Robeson | 770035 | SR 1750 | Big Marsh Swamp | 1955 | POC | B-4250 |  | 550000 | 68 | 1@17'3 ; 1@16'6 ; 1@17'3 ; 1@18' | 2010-05-19 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 16 | 16 | 23 | Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
6 | Robeson | 770094 | SR 2237 | Old Field Swamp | 1956 | POC | B-4251 |  | 475000 | 73 | 1@18'5 ; 2@18'2 ; 1@18'5 | 2011-04-21 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 39 | 15 | 22 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
8 | Chatham | 180095 | SR 1520 | Brooks Creek | 1951 | POC | B-4064 |  | 1100000 | 36 | 2@17'9 | 2010-09-21 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | N | 30 | 20 | 29 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
10 | Cabarrus | 120090 | SR 2408 | Black Run Creek | 1957 | POC | B-4051 |  | 325000 | 25 | 1@24'8 | 2010-04-20 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 62 | 21 | 28 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
10 | Stanly | 830209 | SR 1136 | Island Creek | 1959 | POC | B-4278 |  | 1050000 | 41 | 1@40'8 | 2010-05-18 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 21 | 10 | 13 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
10 | Mecklenburg | 590134 | SR 2025 | McIntyre Creek | 1958 | POC | B-4579 |  | 300000 | 31 | 1@17' ; 1@13' | 2010-07-20 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 19 | NP | NP | Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
10 | Stanly | 830057 | SR 1934 | Hardy Creek | 1961 | POC | B-4644 |  | 650000 | 76 | 1@35'4 ; 1@40'4 | 2010-05-19 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 27 | 12 | 15 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
10 | Union | 890251 | SR 1508 | S. Fork Crooked Crk | 1957 | POC | B-4651 |  | 450000 | 61 | 2@30'6 | 2010-08-17 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 17 | 14 | 18 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
11 | Ashe | 40229 | SR 1169 | W. Fork Pine Swamp Crk | 1960 | POC | B-3802 |  | 725000 | 41 | 1@20'3 ; 1@20'4 | 2010-08-17 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 15 | 16 | 21 | Per Bill Goodwin on 02/17: "one BMU project B-3802 is in fact a BPOC." L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers noted ROW fund authorization not complete. | [10 empty] | 2010-02-25
11 | Surry | 850029 | SR 1322 | Mill Creek | 1951 | POC | B-4284 |  | 400000 | 36 | 1@36'4 | 2010-09-21 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 40 | 11 | 15 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
11 | Wilkes | 960104 | SR 1353 | N. Prong Lewis Fork Crk | 1958 | POC | B-4323 |  | 850000 | 77 | 1@76'6 | 2010-05-16 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 22 | 8 | 12 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
12 | Cleveland | 220139 | SR 1314 | Beaverdam Creek | 1958 | POC | B-1135 |  | 295000 | 41 | 2@20'5 | 2010-11-16 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 21 | NP | NP | Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
12 | Cleveland | 220129 | SR 1184 | Grog Creek | 1949 | POC | B-4075 |  | 725000 | 61 | 2@30'4 | 2010-07-20 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 53 | 17 | 22 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
12 | Lincoln | 540183 | SR 1346 | Uppard Creek | 1965 | POC | B-4573 |  | 625000 | 106 | 1@35'3 ; 1@35' ; 1@35'3 | 2010-05-16 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | N | 54 | 15 | 19 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
13 | Rutherford | 800217 | SR 1520 | Creek | 1952 | POC | B-4262 |  | 650000 | 32 | 1@32' | 2010-09-21 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 42 | 12 | 16 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Per Mike Summers, no env. Document in hand, no ROW. | [10 empty] | 2010-02-25
14 | Haywood | 430009 | SR 1100 | Crawford Creek | 1949 | POC | B-3657 |  | 800000 | 40 | 1@39'8 | 2010-08-17 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | N | 34 | 12 | 15 | Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
14 | Henderson | 440056 | SR 1006 | N. Branch Hungry Crk | 1973 | POC | B-4145 |  | 650000 | 58 | 1@16'7.5 ; 1@24'9 ; 1@16'7.5 | 2010-05-16 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | N | 59 | 19 | 28 | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
14 | Polk | 740024 | SR 1520 | Hooper Creek | 1955 | POC | B-4241 |  | 475000 | 36 | 1@18'4 ; 1@17'6 | 2010-08-17 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 10 | NP | NP | Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). Mike Summers notes ROW fund authorization not complete. | [10 empty] | 2010-02-25
| Deleted Bridge Candidates | [17 empty] | \
1 | Bertie | 70085 | SR 1108 | Indian Creek | 1951 | POC | B-3811 |  | 720000 | 35 | 2@17'6 | 2010-06-15 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 33 | 12 | 20 | Per Sterling Baker on 02/25: "Division took this over late last year as a Division Managed Project. We are finalizing plans and working on utilities and right of way and acquiring permits." | [10 empty] | 2010-02-25
1 | Washington | 930029 | SR 1163 | Maul Creek | 1971 | POC | B-4314 |  | 550000 | 57 | 1@40' ; 1@17' | 2010-06-15 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | N | 51 | 12 | 19 | Per Sterling Baker on 02/25: "Division took this over late last year as a Division Managed Project. We are finalizing plans and working on utilities and right of way and acquiring permits." | [10 empty] | 2010-02-25
1 | Bertie | 70044 | SR 1100 | Roquist Creek | 1952 | Let List | B-4435 |  | 825000 | 103 | 1@17'6 ; 4@17' ; 1@17'6 | 2010-02-16 | 404/401/CAMA Permits (IN) Moratorium 2/15 - 6/15 MOA (IN) SSP (IN) | SD | N | 22 | 12 | 20 | Per Sterling Baker on 02/25: "This project let last week ." L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
2 | Greene | 390046 | SR 1091 | Wheat Swamp Crk | 1964 | Let List | B-4125 |  | 825000 | 90 | 3@30' | 2010-02-16 | 404/401 Permits (IN) NO Moratorium | SD | FO | 23 | 25 | 38 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
2 | Pitt | 730009 | NC 903 | Swift Creek | 1958 | POC | B-4232 |  | 525000 | 52 | 1@17'5 ; 1@17' ; 1@17'8 | 2011-01-18 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 37 | 12 | 21 | Removed per Mike Summers on 02/17. Utility nightmare. Not a low impact. Major Embark Communication Company on one end. Bill Goodwin noted that this is a BMU project. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
4 | Edgecombe | 320028 | NC 42 | Tar River | 1952 | Div. | 1 |  | 11450000 | 606 | 3@35'; 1@65'6; 1@65'6; 5@35' | n/a | Tri Managed? Maintenance nightnmare. Top priority, but it is not necessarily a "low-impact" type of bridge. Would sacrifice all the other bridges, minus the other Division Managed projects, for this bridge. | N | N | 46 | 29 | 31 | Removed on 02/17/10 per Lacy Love. | [10 empty] | 2010-02-25
4 | Halifax | 410133 | SR 1304 | Butterwood Creek | 1956 | Div. | 3 |  | 438117.8 | 41 | 1@40'6 | n/a | Division Managed Project / Just Begun. | SD | FO | 25 | 11 | 14 | Removed on 03/23/10 per Freddie Bunn (see 03/31 e-mail from James Dodson). 410136 on one detour. | LITTONI | 2010-03-15 | 2010-02-18 |  |  | 2010-04-09 | No | 2010-04-26 | No |  | 2010-02-25 | 2010-03-31
4 | Edgecombe | 320063 | SR 1003 | Trib. Of Town Creek | 1957 | Div. | 4 |  | 709336.1 | 53 | 1@18'1 ; 1@17' ; 1@17'9 | n/a | Division Managed Project / Just Begun. | SD | N | 14 | 19 | 25 | Removed on 03/23/10 per Freddie Bunn (see 03/31 e-mail from James Dodson). L&S file references B-4743 (DPOC). L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | PINETPI | 2010-03-16 | 2010-02-17 |  |  | 2010-04-09 | No | 2010-04-15 | Yes |  | 2010-02-25 | 2010-03-31
4 | Halifax | 410071 | SR 1804 | Keehukee Swamp | 1952 | Div. | 5 |  | 723354.6 | 53 | 2@17'6 ; 1@17'9 | n/a | Division Managed Project / Just Begun. | SD | N | 15 | NP | NP | Removed on 03/23/10 per Freddie Bunn (see 03/31 e-mail from James Dodson). 410072 [B-4135 CFY 2008] on detour. Historical noted on 04/09: "There's incomplete information from HPO on this one." | NORFLEI | 2010-03-15 | 2010-02-18 |  |  | 2010-04-09 | Yes | 2010-04-26 | No |  | 2010-02-25 | 2010-03-31
4 | Wayne | 950037 | SR 1537 | Nahunta Swamp | 1951 | Let List | B-4672 |  | 725000 | 87 | 1@17'9 ; 1@17'2 ; 1@16'10 ; 1@17'2 ; 1@17'8 | 2010-02-16 | 404/401 Permits PENDING Moratorium 2/15 - 6/15 MOA (IN) | SD | FO | 14 | 16 | 21 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
4 | Wilson | 970122 | SR 1507 | Whitoak Swamp | 1953 | Let List | B-4680 |  | 650000 | 87 | 1@18' ; 2@17' ; 1@18' | 2010-02-16 | 404 Permit PENDING 401 Permit (IN) NO Moratorium MOA (IN) | SD | N | 26 | 11 | 18 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
5 | Wake | 910359 | SR 1163 | Beaver Creek | 1979 | POC | B-4991 |  | 1300000 | 41 | 2@20'3 | 2010-02-16 | Preliminary Engineering work is done. Waiting on ROW and permits. | N | FO | 35 | 13 | 17 | Removed per conversation with Mike Summers on 03/24/10. Bill Goodwin noted that this is a BMU project. Mike Summers notes design is complete, waiting for agreement from town of apex. Sent to schedule for June Let. Will have to go to Randy Garris. Beyond Mike's Limit. FEMA problem. Coordination with Wester Wake Freeway. Not a good ARRA project candidate. | [10 empty] | 2010-02-25
5 | Franklin | 340038 | SR 1239 | Lynch Creek | 1956 | POC | MA05012B |  | 665506 | 81 | 2@40'4 | 2010-04-27 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | N | 29 | 12 | 15 | Removed per conversation with Mike Summers on 03/24/10. | [10 empty] | 2010-02-25
6 | Robeson | 770088 | SR 2230 | Hog Swamp | 1955 | Div. | 14 |  | 805000 | 69 | 1@17'8 ; 1@17'1 ; 1@17'5 ; 1@17'1 | n/a | Division Pilot. Proposed Division Managed Project. | SD | N | 13 | 19 | 28 | Per 03/08 phone call with Ken Murphy, remove from candidate list as this is a Division Pilot Project. (see 03/15 e-mail) 770081 on detour |  |  |  |  | 2010-03-31 | 2010-03-31 | No | 2010-04-09 | No |  | 2010-02-25 | 2010-03-26
6 | Robeson | 770030 | SR 1005 | Cold Camp Creek | 1983 | Div. | 15 |  | 1120000 | 121 | 1@18' ; 4@17' ; 1@16'8 ; 1@18' | n/a | Division Pilot. Proposed Division Managed Project. | SD | FO | 23 | 16 | 23 | Per 03/08 phone call with Ken Murphy, remove from candidate list as this is a Division Pilot Project. (see 03/15 e-mail) B-4617 CFY 2018 no work started yet. |  |  |  |  | 2010-03-31 |  |  | 2010-04-09 | No |  | 2010-02-25
8 | Randolph | 750068 | SR 1564 | Creek | 1950 | Div. | 4 |  | 395692 | 34 | 1@17'2 ; 1@17'1 | n/a | No Preliminary Engineering Work Done. | SD | FO | 18 | 21 | 30 | Removed per Tim Welch on 03/29. (see 03/29 e-mail from Eric Williams) This will be handled as a Division Bridge Project. | GLENOL |  | 2010-02-17 |  |  |  |  | 2010-04-07 | No | B-POC | 2010-02-25 | 2010-03-26
8 | Montgomery | 610028 | NC109 | Rock Creek | 1921 | Let List | B-4204 |  | 1950000 | 46 | 1@45'6 | 2010-03-16 | 404/401 Permits (IN) NO Moratorium SSP (IN) | SD | FO | 25 | 32 | 35 | Removed because Let on 03/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Moore | 620176 | SR 1105 | Aberdeen Creek | 1956 | Let List | B-4583 |  | 875000 | 108 | 1@18'3 ; 1@18'1 ; 1@17'11 ; 1@35' ; 1@18'5 | 2010-03-16 | 404/401 Permits (IN) NO Moratorium Municipal Agreeement (IN) MOA (IN) | SD | FO | 26 | 12 | 20 | Removed because Let on 03/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
8 | Scotland | 820028 | SR 1433 | Juniper Creek | 1951 | Let List | B-4642 |  | 875000 | 69 | 1@17'10 ; 2@17' ; 1@17'2 | 2010-02-16 | 404/401 Permits (IN) NO Moratorium MOA (IN) | SD | FO | 19 | 16 | 23 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
9 | Rowan | 790026 | SR 1003 | Third Creek | 1947 | Let List | B-4627 |  | 1500000 | 226 | 1@45'3 ; 3@45' ; 1@45'3 | 2010-02-16 | 404/401 Permits (IN) NO Moratorium MOA (IN) | SD | N | 39 | 31 | 34 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
10 | Cabarrus | 120170 | SR 1161 | Fuda Creek | 1957 | Div. | 1 |  | 448644.9 | 33 | 1@32'6 | n/a | No Preliminary Engineering Work Done. | N | FO | 50 | 22 | 28 | Hydro- not good candidate- potential problem obtaining FEMA model. S149Removed per Garland Haywood due to FEMA involvement on 03/19/10 (see Pam Williams 03/19 e-mail) Historical: will require a field survey. A house next to the bridge was identified on the HPO survey map. We will need to determine its eligibility for Nati | CONCSE | 2010-04-13 | 2010-02-19 |  |  | 2010-03-23 | No | 2010-04-05 | No |  | 2010-02-25 | 2010-03-31
10 | Cabarrus | 120173 | SR 1169 | McKees Creek | 1961 | Div. | 6 |  | 544393.9 | 41 | 1@40'6 | n/a | No Preliminary Engineering Work Done. | SD | N | 20 | 26 | 36 | Removed per Garland Haywood due to FEMA involvement on 03/19/10 (see Pam Williams 03/19 e-mail) Historical: will require a field survey. A house next to the bridge was identified on the HPO survey map. We will need to determine its eligibility for National Register listing. Hydro- not good candidate- potential problem obtaining FEMA model. | HARSBG | 2010-04-12 | 2010-02-22 |  |  | 2010-03-23 | Yes | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Mecklenburg | 590130 | SR 2130 | Branch of Mcdowell Crk | 1962 | Div. | 7 |  | 276455.4 | 26 | 1@11' ; 1@14.5' | n/a | No Preliminary Engineering Work Done. | SD | FO | 21 | 11 | 16 | Removed per Garland Haywood due to FEMA involvement on 03/19/10 (see Pam Williams 03/19 e-mail) Per hydro looks like it may be ok, need to check. Hydro-not a good candidate. | LKNORS | 2010-02-24 | 2010-02-22 |  |  | 2010-03-22 | No | 2010-04-07 | No |  | 2010-02-25 | 2010-03-31
10 | Union | 890201 | SR 1149 | Twelve Mile Creek | 1935 | Div. | 9 |  | 240166 | 20 | 1@19'10 | n/a | No Preliminary Engineering Work Done. | SD | FO | 44 | NP | NP | Removed on 02/17/10 per Dan Holderman. | [10 empty] | 2010-02-25
10 | Anson | 30314 | SR 1127 | South Fork Jones Crk | 1928 | Let List | B-3404 |  | 1050000 | 162 | 1@35'8 | 2010-03-16 | 404/401 Permits (IN) NO Moratorium MOA (IN) | SD | N | 22 | 20 | 24 | Removed because Let on 03/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
10 | Stanly | 830099 | SR 1968 | Long Creek | 1957 | Let List | B-3909 |  | 1350000 | 83 | 1@39'6 | 2010-02-16 | 404/401 Permits (IN) No Moratorium MOA (IN) (ARRA Funding) 1511 (IN) | N | FO | 49 | 18 | 24 | Removed because Let on 02/16/10. | [10 empty] | 2010-02-25
11 | Avery | 50044 | US 19E | North Toe River | 1970 | Let List | B-3608 |  | 1100000 | 126 | 1@40'3 ; 1@45' ; 1@40'3 | 2010-02-16 | No permits required No Moratorium RR Agreement (IN) Municipal Agreement (IN) | SD | N | 28 | 24 | 28 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
11 | Watauga | 940334 | SR 1351 | South Fork New River | 1965 | Let List | B-3928 |  | 1950000 | 142 | 1@20'10 ; 3@30' ; 1@30'10 | 2010-08-01 | 404/401 Permits (IN) FEMA (IN) No Moratorium SSP (IN) | N | FO | 54 | 20 | 27 | Removed per Bill Goodwin on 02/17: "And I think B-3928 should probably be removed. This project has 2 historic sites, and a park, and has had significant public interest. I think we have everything worked out, but I'm not sure we want to run it through this process given the project history." This is a Todd Community Bridge. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
12 | Cleveland | 220144 | SR 1327 | Sandy Run Creek | 1952 | Let List | B-4468 |  | 925000 | 121 | 1@25'3 ; 1@25' ; 1@25'3 | 2010-03-16 | No permits required No Moratorium MOA (IN) | SD | FO | 40 | 13 | 16 | Removed because Let on 03/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
13 | Buncombe | 100550 | SR 1383 | South Turkey Creek | 1961 | Div. | 1 |  | 370300 | 35 | 1@34'6 | n/a | Division Pilot. Proposed Division Managed Project. | SD | FO | 19 | NP | NP | Removed on 03/03/10 per Edward Green. (see 03/15 e-mail) |  |  |  |  | 2010-03-31 | [5 empty] | 2010-02-25 | 2010-03-04
13 | Buncombe | 100015 | SR 1608 | Turkey Creek | 1952 | Div. | 2 |  | 493980.2 | 46 | 1@46' | n/a | Division Pilot. Proposed Division Managed Project. | SD | FO | 43 | 15 | 18 | Removed on 03/03/10 per Edward Green. (see 03/15 e-mail) |  |  |  |  | 2010-03-31 | [5 empty] | 2010-02-25 | 2010-03-10
14 | Graham | 370070 | SR 1134 | Cheoah River | 1956 | Let List | B-3335 |  | 1200000 | 161 | 2@20'6 ; 2@20' ; 2@20' ; 2@20'6 | 2010-06-15 | 404/401 Permits PENDING TVA (IN) NO Moratorium MOA (IN) | SD | FO | 20 | 13 | 23 | Removed per Bill Goodwing on 02/17: "I also recommend that B-3335 be removed - we are having issues with both the Forest Service [right of entry] and Fish and Wildlife [Endangered species] on this one and I'm not sure we will have it all worked out by the current let date." USFS conflict, not a good candidate. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
14 | Graham | 370068 | SR 1232 | Panther Creek | 1963 | POC | B-3457 |  | 400000 | 62 | 1@16'7 ; 1@45'7 | 2010-09-21 | Preliminary Engineering work is done. Waiting on ROW and permits. | SD | FO | 15 | 10 | 13 | Removed per Mike Summers on 02/17, NO ROW done. Forest service is not going to grant ROW unless we come back with a one lane bridge. It accessess the Bridal Trails. All in National Forest. No Design has been completed. Bill Goodwin noted that this is a BMU project. | [10 empty] | 2010-02-25
14 | Graham | 370117 | SR 1123 | West Buffalo Creek | 1961 | Let List | B-4123 |  | 575000 | 41 | 1@40'6 | 2010-02-16 | 404/401 Permits (IN) T-Moratorium 10/15-4/15 TVA (IN) MOA (IN) | N | FO | 44 | 14 | 17 | Removed because Let on 02/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
14 | Jackson | 490123 | SR 1437 | Scotts Creek | 1960 | Let List | B-4163 |  | 1350000 | 50 | 1@50'6 | 2010-03-16 | 404/401 Permits PENDING TVA Permit (IN) T-Moratorium 10/15 - 4/15 MOA (IN) | SD | FO | 40 | 14 | 14 | Removed because Let on 03/16/10. L&S agree to provide the shell mapping and DTM (reference Keith Johnson 02/23 e-mail). | [10 empty] | 2010-02-25
Div. | From the Division (Green on the Map)
Let List | From the Let List (Red on the Map)
POC | From the Bridge Purchase Order Contract (Blue on the Map)
Note on C225: Most recent inspection report did not work, need to get most current once Cary Clemmons fixes.