# NORTH CAROLINA DEPARTMENT OF TRANSPORTATION

# FIELD SCOPING MEETING WORKSHEET

Design Build Process

| TIP No.: | WBS No.: 17BP.11.R.134 | #### Field Scoping Meeting Date: 10/19/16 |
| --- | --- | --- |
| Division: 11 |  | #### Location: On-site |
| Route (US/NC/SR): SR1349 |  | County: AVERY |
| Project Description: Bridge No. 050001 over Linville River on SR1349 (Ruffin Street) |  |  |
| Tier: SUBREGIONAL |  | Funding: State |
| #### Municipality: Linville (Linville is unincoporated therefore no Municipal agreement required) |  |  |

| Attendees |  |  |  |
| --- | --- | --- | --- |
|  | Name | Phone No. | E-mail |
| Division Bridge Program Manager | Jami Guynn | 336-903-9220 | jcguynn@ncdot.gov |
| Division Environmental Officer | Heath Slaughter | 336-903-9202 | hslaughter@ncdot.gov |
| Division L&S | Pat Tuttle | 336-969-9550 | ptuttle@ncdot.gov |
| Division L&S | Larry Absher | 828-381-1469 336-903-9501 (o) | lrabsher@ncdot.gov |
| Division L&S | Landon Wagoner | 336-903-9501 | rlwagoner@ncdot.gov |
| Hydraulics Engineer | Marc Shown | 919-707-6751 | mshown@ncdot.gov |
| Hydraulics Engineer | Rusty Lassiter | 919-707-6732 | rlassiter@ncdot.gov |
| PPU | Rachel Evans | 919-707-6609 | rcevans@ncdot.gov |
| PPU | Pam Williams | 919-707-6608 | prwilliams@ncdot.gov |
| USFWS | Andrew Henderson | 828-258-3939 ext 227 | Andrew_henderson@fws.gov |

Existing Features

| Feature Bridged: 050001 over Linville River on SR1349 (Ruffin Street) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ex. Bridge Clear Deck Width: 17.833 (Ft.) |  |  |  |  |  | Roadway width: 15.83 (Ft.) |  |  |  |  |
| (Bridge / Culvert) Length: 72 (Ft.) |  |  |  |  |  | Deck Width (Out To Out): 18 (Ft.) |  |  |  |  |
| Water Depth: 3 (Ft.) |  |  |  |  |  | Height Bed-To-Crown: 11 (Ft.) |  |  |  |  |
| Year Built: 1955 |  |  |  | Posted: SV 99 |  |  |  |  | TTST: 99 |  |
| Superstructure: 4 |  |  |  | Abutment: 5 |  |  |  |  | Pier Type: |  |
| Temp. Shored: Yes |  |  |  |  |  |  |  |  |  |  |
| Historic High Water (Elev. To The Existing Structure ): (Ft) |  |  |  |  |  |  |  |  |  |  |
| PRI: 51.74 |  | DP: 1.00 |  |  | SR: 27.69 |  | School Bussing crossings per day: 1 bus, 3 trips, no concern for road closure |  |  |  |
| Posted Speed Limit Vicinity: 25 (mph) posted |  |  |  |  |  |  |  |  |  |  |
| Detour | Off-Site |  | Stage Construction |  |  |  |  | New Alignment |  | On-site |
| If Off-Site, Description Of Detour Route: US 221 - NC 105 - SR 1351 |  |  |  |  |  |  |  |  |  |  |
| Approximate Length Of Detour? 1.1 Miles |  |  |  |  |  |  |  |  |  |  |
| Improvements Needed To Road(s) On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Div. Traffic Eng. Recommend Off-site detour signing? Trailblazing with Street/Road names; message boards on US 221 and NC 105 to provide access to Old Hampton Store on SR 1349, just north of bridge |  |  |  |  |  |  |  |  |  |  |
| Improvements Needed To Bridges On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Are future plans for upgrading this roadway either at or in the vicinity of this project? No |  |  |  |  |  |  |  |  |  |  |
| Are Bridges On Detour Currently Programmed? No |  |  |  |  |  |  |  |  |  |  |
| Are There EMS Or Business Access Issues? Moderate impact to homeowners due to other routes entering this area |  |  |  |  |  |  |  |  |  |  |
| Are There Any Railroad Crossings On Detour? No |  |  |  |  |  |  |  |  |  |  |
| Should Work Zone Pedestrian Access Be Maintained During Construction? No |  |  |  |  |  |  |  |  |  |  |
| Overhead Utility Lines In Conflict Yes, power downstream |  |  |  |  |  |  |  |  |  |  |
| Power Transmission Lines In Conflict |  |  |  |  |  |  |  |  |  |  |
| Telephone In Conflict Yes, upstream |  |  |  |  |  |  |  |  |  |  |
| Cable Lines In Conflict |  |  |  |  |  |  |  |  |  |  |
| Fiber Optic In Conflict |  |  |  |  |  |  |  |  |  |  |
| Water In Conflict |  |  |  |  |  |  |  |  |  |  |
| Sewer In Conflict |  |  |  |  |  |  |  |  |  |  |
| Natural Gas In Conflict |  |  |  |  |  |  |  |  |  |  |
| Other In Conflict |  |  |  |  |  |  |  |  |  |  |
| Is There Any Future Utility Construction Anticipated In The Project Area: No |  |  |  |  |  |  |  |  |  |  |
| Is A FEMA Buy-Out Property Being Impacted: No |  |  |  |  |  |  |  |  |  |  |

Environmental

| Wetlands At Site: No |  | Comments: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Endangered Species In County: Bog turtle, Carolina northern flying squirrel, Northern long-eared bat, Virginia big-eared bat, Spruce-fir moss spider, BlueRidge goldenrod, Heller's blazing star, Roan mountain bluet, Spreading avens, Rock gnome lichen |  |  |  |  |  |  |  |
| T&E species effect: May affect, but the activity is excepted under the Biological Opinion on NLEB Final 4d Rule: Northern long-eared bat; Gray Bat per USFWS review 10/19/16 no indications of any species of bat use, nor any bats present on the existing structure |  |  |  |  |  |  |  |
| Trout County: Yes |  |  |  | TVA County: Yes |  |  |  |
| CAMA County: No |  |  |  | Primary Nursery Area: No |  |  |  |
| Moratoria: Yes | Which species: Brown Trout |  |  |  |  | Duration: October 15 to April 15 |  |
| Permits discussion: |  |  |  |  |  |  |  |
| Water Quality Classification: C; Tr *Adhere to DSSW* |  |  |  |  |  |  | 303d: No |
| Coast Guard Permit? No |  |  | Drainage Basin: Catawba |  |  |  | Riparian Buffer Rules: No |
| Is The Project Site In Or Near Any Of The Following: |  |  |  |  |  |  |  |
| National Forest: No |  |  |  | Wildlife Refuge: No |  |  |  |
| State, County, Or Local Park: No |  |  |  | Wild And Scenic River: No |  |  |  |
| Airport: No |  |  |  | Recreation or Power Generation: No |  |  |  |
| Water Supply Reservoir: No |  |  |  | Nutrient Sensitive Waters: No |  |  |  |
| Public Use Boat Ramp: No |  |  |  | Cemeteries: No |  |  |  |
| VAD/Farmland Protection: No |  |  |  | Game Lands: No |  |  |  |
| Known Or Potential Historic Properties In The Area: No; note, bridge 0.3 miles from Linville Historic District |  |  |  |  |  |  |  |
| Architecture: NHPA |  |  |  |  | Archaeology: NSR |  |  |
| Is The Bridge Structure Itself, Or Any Part Thereof, Considered Historic: No |  |  |  |  |  |  |  |
| Impacts to a Church, Community Center, Or Other Public Facility? Yes, Old Hampton Store and Linville United Methodist Church, just north of bridge on SR 1349 and Peoples Church, just northeast of bridge on SR 1352 |  |  |  |  |  |  |  |
| Is this a Statewide Bicycle Route or a Local Non-Marked Bicycle Route: No but Blue Ridge Plan Route Segment #14 on US 221 and NC 105 brings bicycling traffic through area |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |

Geotechnical

Are There Any Historical and/or Vibration Sensitive Structures Near By? Comments:

Are There Any Known Landfills and/or Geo-environmental Hazard Sites at/or Within Close Proximity To The Project Site? Comments:

Are Any Impacts Anticipated To Natural Springs Or Artesian Wells? Comments:

Possible Foundation Type: End Bents: Interior Bents:

Hydraulics

| FEMA Approval? Redelineated (MOA ) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Is There Unusual Scour Potential? No |  | Is Protection Needed? STD |  |  |
| Are Banks Stable? Yes |  | Is Protection Needed? STD |  |  |
| Appreciable Amount Of Large Debris? No |  |  |  |  |
| Placement Of Bents In The Water Be Allowed: Yes |  |  | Where: Not in main channel |  |
| Structure Type: Bridge | If Bridge: CS |  |  | If girder; why? |
| Length Of Structure: 90' | Min. Number Of Spans: 2 |  |  | Span Arrangement: 2 @ 45' |
| Waive offset: yes, south end only | EB Cap: 4'-0" |  |  | Skewed: No |
| -vertical abutment south end -hold downstream face (west) of existing bridge and widen upstream (east) -Oregon rail , use anodized rail (regardless of historic) |  |  |  |  |

Items To Be Discussed / Resolved At FSM By Attendees

| Off-Site | Stage Construction |  |  |  | New Alignment |  |  |  | On-site |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental Document Prepared by DEO: Low Impact Data Spreadsheet Minimum Criteria Checklist |  |  |  |  |  |  |  |  |  |
| ADT: 430 per SIR |  | NHS: No |  | Tier: SUBREGIONAL |  |  | Func. Class: Local |  |  |
| Bridge Min. Clear Deck Width Recommended by Div.: 33’ out to out |  |  |  |  |  |  |  |  |  |
| Roadway lane width: 10’ with 3’ shoulders, including 0’ paved shoulders |  |  |  |  |  |  |  |  |  |
| Extension of Paved shoulders: N/A |  |  |  |  |  |  |  |  |  |
| Pave to face of guardrail and taper 8:1 to travel lane/paved shoulder? Yes |  |  |  |  |  |  |  |  |  |
| Min. Pavement Surface Course: 2½" |  |  |  |  |  | Existing Roadway: 18’ |  |  |  |
| Pavement Marking: Paint |  |  |  |  |  | Pavement Markers: None |  |  |  |
| Will Railroad Involvement Be Required: No |  |  |  |  |  | Method of Clearing: II modified |  |  |  |
| Truck Percentage: 6 % per BIR |  |  |  |  |  | Reasonable Safe Speed per SIR: 25 mph |  |  |  |
| Liquidated damages: will be imposed after 150 days of closure/construction. Amt: $500 per day |  |  |  |  |  |  |  |  |  |
| CEI by? NCDOT |  |  | R/W by? DBT |  |  |  |  | R/W monuments? Pin & Cap |  |
| Salvageable materials: ALL STEEL I-BEAMS (14) 21" I-BEAMS |  |  |  |  |  |  |  |  |  |
| Contact Person/number: DAVID SCOTT 828-268-6062 - OFFICE 828-964-1354 - CELL |  |  |  |  |  |  |  |  |  |
| Deliver to: BOONE BRIDGE MAINTENANCE YARD - 1989 NC 194N, BOONE NC 28607 |  |  |  |  |  |  |  |  |  |
| Removal of previous structure remnant abutments/piers: No |  |  |  |  |  |  |  |  |  |
| Sequencing priority in construction? No priority. No Sunday construction or construction 1 hr before or 1 hr after funerals (DBT to coordinate with pastor/church) |  |  |  |  |  |  |  |  |  |
| Comments: -Remove both vertical abutments and existing bridge bents (pull) -pave to back radius of SR 1342 -mill and tie into intersection with US 221 -dike and pump lagoon fed by small tributary in north east quadrant dry prior to construction |  |  |  |  |  |  |  |  |  |