TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 192000 | FY 2024: 192000
TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 48000 | FY 2024: 48000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON-SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 3200000 | FY 2025: 3200000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON-SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 2959000 | FY 2024: 2959000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON-SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 800000 | FY 2025: 800000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON-SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 740000 | FY 2024: 740000
TL-0055 | Public Transportation (Transit) | Locally Selected | GREENSBORO TRANSIT AUTHORITY | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | BGANY | CONSTRUCTION | 1600000 | FY 2025: 1600000
TL-0055 | Public Transportation (Transit) | Locally Selected | GREENSBORO TRANSIT AUTHORITY | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 613000 | FY 2025: 613000
TL-0055 | Public Transportation (Transit) | Locally Selected | GREENSBORO TRANSIT AUTHORITY | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339 | CONSTRUCTION | 850000 | FY 2025: 850000
TL-0056 | Public Transportation (Transit) | Locally Selected | CATS | BALLANTYNE I-485 SERVICE. PURCHASE TWO BATTERY ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1750000 | FY 2026: 1750000
TL-0056 | Public Transportation (Transit) | Locally Selected | CATS | BALLANTYNE I-485 SERVICE. PURCHASE TWO BATTERY ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 438000 | FY 2026: 438000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 58000 | FY 2025: 58000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 14000 | FY 2025: 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 14000 | FY 2025: 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2025: 4000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 350000 | FY 2025: 350000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 88000 | FY 2025: 88000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 86000 | FY 2025: 86000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 22000 | FY 2025: 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 22000 | FY 2025: 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2025: 5000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 324000 | FY 2025: 324000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 81000 | FY 2025: 81000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 271000 | FY 2024: 271000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 68000 | FY 2024: 68000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | OPERATIONS | 271000 | FY 2025: 271000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | OPERATIONS | 678000 | FY 2025: 678000
TL-0060 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | IMPLEMENT A CASHLESS FARE SYSTEM ACROSS THE FIXED ROUTE AND PARATRANSIT FLEET. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 125000 | FY 2024: 125000
TL-0060 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | IMPLEMENT A CASHLESS FARE SYSTEM ACROSS THE FIXED ROUTE AND PARATRANSIT FLEET. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 31000 | FY 2024: 31000
TL-0061 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | PURCHASE LAND TO CONSTRUCT A WEST FAYETTEVILLE HUB. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | CRPDA | RIGHT-OF-WAY | 800000 | FY 2024: 800000
TL-0061 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | PURCHASE LAND TO CONSTRUCT A WEST FAYETTEVILLE HUB. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 200000 | FY 2024: 200000
TL-0062 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | IMPROVE BUS STOPS AT VARIOUS LOCATIONS IN DOWNTOWN CHAPEL HILL. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 361000 | FY 2025: 361000
TL-0062 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | IMPROVE BUS STOPS AT VARIOUS LOCATIONS IN DOWNTOWN CHAPEL HILL. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 90000 | FY 2025: 90000
TL-6110 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5310 | ADMINISTRATIVE | 262000 | FY 2024: 30000; FY 2025: 30000
TM-0002 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/CAPITAL AND 5311(F) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 3950000
TM-0004 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 150000
TM-0010 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 142000
TM-0012 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 129000
TM-0014 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 75000
TM-0015 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 145000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | OPERATIONS | 1073000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 1073000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 45000
TM-0022 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 18000
TM-0023 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/CAPITAL PURCHASE SERVICE) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | ADMINISTRATIVE | 1022000 | FY 2024: 500000
TM-0024 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5312 | OPERATIONS | 250000
TM-0024 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 63000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5310 OPERATING PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 2106000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5310 OPERATING PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | OPERATIONS | 2106000
TM-0026 | Public Transportation (Transit) | Locally Selected | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 427000
TM-0026 | Public Transportation (Transit) | Locally Selected | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 183000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | ADMINISTRATIVE | 2204000 | FY 2024: 320000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | ADMINISTRATIVE | 10868000 | FY 2024: 320000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 32358000 | FY 2024: 2600000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | OPERATIONS | 100000 | FY 2024: 100000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 2124000 | FY 2024: 660000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | OPERATIONS | 2124000 | FY 2024: 660000
TM-0029 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 3361000
TM-0030 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | ADTAP | ADMINISTRATIVE | 177000
TM-0031 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | RTAP | ADMINISTRATIVE | 1628000 | FY 2024: 650000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | OPERATIONS | 12607000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | OPERATIONS | 16834000
TM-0033 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit
TM-0033 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 494000
TM-0035 | Public Transportation (Transit) | Operations and Maintenance | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 3621000 | FY 2024: 712000; FY 2025: 730000; FY 2026: 740000
TM-0036 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5310 STATE ADMINISTRATIVE FUNDS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | ADMINISTRATIVE | 567000
TM-0038 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | ADMINISTRATIVE | 86000 | FY 2024: 86000
TM-0038 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | FEDT | ADMINISTRATIVE | 1415000 | FY 2024: 15000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1000000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 1000000
TM-0040 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE TRANSIT AREA | FIRST MILE-LAST MILE PROJECT WILL PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH A NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | ARP | PLANNING | 750000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | DP | CONSTRUCTION | 15000000 | FY 2024: 15000000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CONSTRUCTION | 70718000 | FY 2024: 70718000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | CMAQ | CAPITAL | 2040000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CAPITAL | 668000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | CMAQ | ACQUISITION | 871000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | S | ACQUISITION | 1393000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | ACQUISITION | 475000
TM-0043 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | ACQUISITION | 883000
TM-0043 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | ACQUISITION | 846000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 44000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 175000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | LINK TRANSIT | PREVENTATIVE MAINTENANCE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 714000 | FY 2024: 102000; FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | LINK TRANSIT | PREVENTATIVE MAINTENANCE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 2870000 | FY 2024: 410000; FY 2025: 410000; FY 2026: 410000; FY 2027: 410000; FY 2028: 410000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | GASTONIA TRANSIT | CAPITAL ROLLING STOCK |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 200000 | FY 2025: 200000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | GASTONIA TRANSIT | CAPITAL ROLLING STOCK |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 800000 | FY 2025: 800000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 1650000 | FY 2024: 550000; FY 2025: 275000; FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | 5317 | OPERATIONS | 1650000 | FY 2024: 550000; FY 2025: 275000; FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | INTEGRATED MOBILITY DIVISION | MACON COUNTY AREAS OF PERSISTENT POVERTY (AoPP) Grant |  | MACON | 14 | Southwestern RPO |  | Public Transit |  | DP | CAPITAL | 470000 | FY 2024: 470000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | INTEGRATED MOBILITY DIVISION | MACON COUNTY AREAS OF PERSISTENT POVERTY (AoPP) Grant |  | MACON | 14 | Southwestern RPO |  | Public Transit |  | L | CAPITAL | 55000 | FY 2024: 55000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ROLLING STOCK-SHOP SERVICE VEHICLE (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 817000 | FY 2024: 12000; FY 2025: 805000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ROLLING STOCK-SHOP SERVICE VEHICLE (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 48000 | FY 2024: 48000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES AND ROUTINE CAPITAL |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 971000 | FY 2024: 458000; FY 2025: 513000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES AND ROUTINE CAPITAL |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 971000 | FY 2024: 458000; FY 2025: 513000
TM-0053 |  |  | GTA | OPERATING MICROSTRANSIT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 2735000 | FY 2024: 547000; FY 2025: 547000; FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0053 |  |  | GTA | OPERATING MICROSTRANSIT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 2735000 | FY 2024: 547000; FY 2025: 547000; FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | HAYWOOD COUNTY | HATWOOD COUNTY OPERATING ASSISTANCE. |  | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | L | OTHER | 492000 | FY 2024: 84000; FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | HAYWOOD COUNTY | HATWOOD COUNTY OPERATING ASSISTANCE. |  | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | 5307 | OTHER | 492000 | FY 2024: 84000; FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0055 |  |  | WINSTON-SALEM TRANSIT | WINSTON-SALEM TRANSIT, LOW-NO EMISSIONS PROGRAM FOR THE PURCHASE OF FIVE (5) HYBRID-ELECTRIC BUSES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 788000 | FY 2024: 788000
TM-0055 |  |  | WINSTON-SALEM TRANSIT | WINSTON-SALEM TRANSIT, LOW-NO EMISSIONS PROGRAM FOR THE PURCHASE OF FIVE (5) HYBRID-ELECTRIC BUSES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5339(b) | CAPITAL | 4445000 | FY 2024: 4445000
TM-0056 |  |  | CHARLOTTE AREA TRANSIT SYSTEM | CAPITAL COST FOR CONTRACTING RELATED TO DEMAND RESPONSE VENDOR TRIPS, PREVENTATIVE MAINTENANCE EXPENSES AND SECURITY RELATED SOFTWARE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CAPITAL | 249000 | FY 2024: 249000
TM-0056 |  |  | CHARLOTTE AREA TRANSIT SYSTEM | CAPITAL COST FOR CONTRACTING RELATED TO DEMAND RESPONSE VENDOR TRIPS, PREVENTATIVE MAINTENANCE EXPENSES AND SECURITY RELATED SOFTWARE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | 5307 | CAPITAL | 994000 | FY 2024: 994000
TM-0058 |  |  | GASTONIA TRANSIT | PURCHASE AN EV ADA VAN. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CONSTRUCTION | 23000 | FY 2025: 23000
TM-0058 |  |  | GASTONIA TRANSIT | PURCHASE AN EV ADA VAN. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 94000 | FY 2025: 94000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | JARC OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 766000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | JARC OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 3037 | OPERATIONS | 766000
TM-5163 | Public Transportation (Transit) | Locally Selected | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ |  | BUNCOMBE, HAYWOOD | 13, 14 | French Broad River MPO |  | Public Transit |  | L | ADMINISTRATIVE | 85000
TM-5301 | Public Transportation (Transit) | Operations and Maintenance | SUB REGIONAL | STATE ADMINISTRATION - JOB ACCESS NON-URBAN |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5316 | ADMINISTRATIVE | 5592000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 550000 | FY 2024: 55000; FY 2025: 55000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5316 | OPERATIONS | 550000 | FY 2024: 55000; FY 2025: 55000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | ON SYSTEM (RCATS) | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Exempt |  | CRPANY | CAPITAL | 587000 | FY 2024: 587000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | ON SYSTEM (RCATS) | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Exempt |  | L(M) | CAPITAL | 146000 | FY 2024: 146000
TN-5102 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | OPERATING ASSISTANCE - NEW FREEDOM - URBAN |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 504000
TN-5102 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | OPERATING ASSISTANCE - NEW FREEDOM - URBAN |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5317 | OPERATIONS | 1260000
TN-5112 | Public Transportation (Transit) | Operations and Maintenance | SUB REGIONAL | STATE ADMINISTRATION - NEW FREEDOM - 5317 |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5317 | ADMINISTRATIVE | 4270000
TN-6116 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 4070000 | FY 2024: 725000; FY 2025: 800000; FY 2026: 868000
TN-6125 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5317 NEW FREEDOM |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | FEP | OPERATIONS | 3963000 | FY 2024: 450000; FY 2025: 460000; FY 2026: 470000; FY 2027: 480000
TN-6125 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5317 NEW FREEDOM |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 793000 | FY 2024: 90000; FY 2025: 92000; FY 2026: 94000; FY 2027: 96000
TN-6126 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY TRANSIT | ORANGE COUNTY MOBILITY ON DEMAND - PURCHASE 2 ADA ACCESSIBLE MINI-VANS. EXPAND MICRO-TRANSIT ZONES. |  | ORANGE | 7 | Central Pines RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 150000 | FY 2024: 150000
TN-6126 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY TRANSIT | ORANGE COUNTY MOBILITY ON DEMAND - PURCHASE 2 ADA ACCESSIBLE MINI-VANS. EXPAND MICRO-TRANSIT ZONES. |  | ORANGE | 7 | Central Pines RPO |  | Exempt |  | L | IMPLEMENTATION | 38000 | FY 2024: 38000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | RUTHERFORDTON | PURCHASE FOUR ELECTRIC VEHICLES. |  | RUTHERFORD | 13 | Foothills RPO |  | Exempt |  | CRP550 | CAPITAL | 233000 | FY 2025: 233000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | RUTHERFORDTON | PURCHASE FOUR ELECTRIC VEHICLES. |  | RUTHERFORD | 13 | Foothills RPO |  | Exempt |  | L(M) | CAPITAL | 58000 | FY 2025: 58000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 22000 | FY 2025: 22000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 6000 | FY 2025: 6000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 301000 | FY 2026: 301000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | CONSTRUCTION | 75000 | FY 2026: 75000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRPANY | ENGINEERING | 144000 | FY 2025: 144000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | T(M) | ENGINEERING | 36000 | FY 2025: 36000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRPANY | CAPITAL | 3858000 | FY 2025: 3858000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | T(M) | CAPITAL | 965000 | FY 2025: 965000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CAPITAL | 2040000 | FY 2025: 2040000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CAPITAL | 158000 | FY 2025: 158000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | CAPITAL | 510000 | FY 2025: 510000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | PITTSBORO | OPERATING ASSISTANCE FOR NEW TRANSIT SERVICE IN THE TOWN OF PITTSBORO. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | OPERATIONS | 140000 | FY 2025: 140000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | PITTSBORO | OPERATING ASSISTANCE FOR NEW TRANSIT SERVICE IN THE TOWN OF PITTSBORO. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | OPERATIONS | 35000 | FY 2025: 35000
TO-0002 | Public Transportation (Transit) | Miscellaneous/Other | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 274000
TO-0002 | Public Transportation (Transit) | Miscellaneous/Other | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1094000
TO-0003 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5312 | ADMINISTRATIVE | 120000
TO-0003 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5307 | ADMINISTRATIVE | 30000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | CONSTRUCTION | 1000000 | FY 2025: 500000; FY 2026: 500000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | CONSTRUCTION | 2810000 | FY 2025: 1810000; FY 2026: 1000000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 600000 | FY 2024: 600000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 176000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | ADMINISTRATIVE | 1800000 | FY 2024: 1800000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | ADMINISTRATIVE | 704000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  |  |  | 484000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  |  | OPERATIONS | 1452000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 7289000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 3600000
TO-4075 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 9600000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 2651000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2003000
TO-4719 | Public Transportation (Transit) | Miscellaneous/Other | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 5546000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 4058000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4397000
TO-4726 | Public Transportation (Transit) | Miscellaneous/Other | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 10520000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 11511000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 24565000 | FY 2024: 2025000; FY 2025: 2030000
TO-4751 | Public Transportation (Transit) | Miscellaneous/Other | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 48457000 | FY 2024: 2025000; FY 2025: 2030000
TO-4779 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF WILSON | OPERATING ASSISTANCE |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 2704000
TO-4779 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF WILSON | OPERATING ASSISTANCE |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 706000
TO-4779 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF WILSON | OPERATING ASSISTANCE |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 12144000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE. |  | RANDOLPH, DAVIDSON, GUILFORD | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE. |  | RANDOLPH, DAVIDSON, GUILFORD | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 5588000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE. |  | RANDOLPH, DAVIDSON, GUILFORD | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 27588000 | FY 2024: 5400000; FY 2025: 2600000; FY 2026: 2200000; FY 2027: 2200000; FY 2028: 2200000
TO-4790 | Public Transportation (Transit) | Miscellaneous/Other | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE. |  | RANDOLPH, DAVIDSON, GUILFORD | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 38618000 | FY 2024: 5400000; FY 2025: 2600000; FY 2026: 2200000; FY 2027: 2200000; FY 2028: 2200000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | SMAP | OPERATIONS | 2084000 | FY 2024: 105000; FY 2025: 101000; FY 2026: 97000; FY 2027: 93000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 3783000 | FY 2024: 399000; FY 2025: 413000; FY 2026: 427000; FY 2027: 441000
TO-4923 | Public Transportation (Transit) | Miscellaneous/Other | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 8199000 | FY 2024: 504000; FY 2025: 514000; FY 2026: 524000; FY 2027: 534000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 15143000 | FY 2024: 1647000; FY 2025: 1647000; FY 2026: 1647000; FY 2027: 1647000; FY 2028: 1647000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 33330000 | FY 2024: 3890000; FY 2025: 3890000; FY 2026: 3890000; FY 2027: 3890000; FY 2028: 3890000
TO-4971 | Public Transportation (Transit) | Miscellaneous/Other | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 18187000 | FY 2024: 2243000; FY 2025: 2243000; FY 2026: 2243000; FY 2027: 2243000; FY 2028: 2243000
TO-5024 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE. |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | L | OPERATIONS | 2430000 | FY 2024: 275000; FY 2025: 350000; FY 2026: 275000
TO-5024 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE. |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 2430000 | FY 2024: 275000; FY 2025: 350000; FY 2026: 275000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 7004000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 8478000 | FY 2024: 146000
TO-5126 | Public Transportation (Transit) | Miscellaneous/Other | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 12574000 | FY 2024: 582000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | TAR RIVER TRANSIT | OPERATING ASSISTANCE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 3341000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | TAR RIVER TRANSIT | OPERATING ASSISTANCE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2250000
TO-5127 | Public Transportation (Transit) | Miscellaneous/Other | TAR RIVER TRANSIT | OPERATING ASSISTANCE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 6607000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 40308000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 85480000 | FY 2024: 14580000; FY 2025: 14437000; FY 2026: 18036000
TO-5128 | Public Transportation (Transit) | Miscellaneous/Other | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 58500000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 3226000 | FY 2024: 230000; FY 2025: 240000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 20513000 | FY 2024: 3956000; FY 2025: 4054000; FY 2026: 4156000
TO-5129 | Public Transportation (Transit) | Miscellaneous/Other | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 300000
TO-5130 | Public Transportation (Transit) | Miscellaneous/Other | GODURHAM | OPERATING ASSISTANCE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 39184000
TO-5131 | Public Transportation (Transit) | Miscellaneous/Other | GOTRIANGLE | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 27619000
TO-5131 | Public Transportation (Transit) | Miscellaneous/Other | GOTRIANGLE | OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 31999000 | FY 2024: 5087000; FY 2025: 6657000; FY 2026: 6838000
TO-5132 | Public Transportation (Transit) | Miscellaneous/Other | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 7530000
TO-5133 | Public Transportation (Transit) | Miscellaneous/Other | CHAPEL HILL TRANSIT | OPERATING ASSISTANCE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 50081000
TO-5134 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 3846000 | FY 2024: 320000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TO-5134 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4646000 | FY 2024: 320000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TO-5134C | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 7272000 | FY 2024: 800000; FY 2025: 818000; FY 2026: 818000; FY 2027: 818000; FY 2028: 818000
TO-5134C | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 7972000 | FY 2024: 800000; FY 2025: 818000; FY 2026: 818000; FY 2027: 818000; FY 2028: 818000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 430000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1920000 | FY 2024: 160000; FY 2025: 160000; FY 2026: 160000; FY 2027: 160000
TO-5135 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3420000 | FY 2024: 285000; FY 2025: 285000; FY 2026: 285000; FY 2027: 285000
TO-5136 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | ALAMANCE, GUILFORD | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 11817000
TO-5137 | Public Transportation (Transit) | Miscellaneous/Other | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING ASSISTANCE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 200670000 | FY 2024: 12552000; FY 2025: 12552000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 4072000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 11112000
TO-5138 | Public Transportation (Transit) | Miscellaneous/Other | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 19684000
TO-5139 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING - FREE FARE |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | CMAQ | OPERATIONS | 408000 | FY 2024: 34000; FY 2025: 34000; FY 2026: 34000; FY 2027: 34000
TO-5139 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING - FREE FARE |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 96000 | FY 2024: 8000; FY 2025: 8000; FY 2026: 8000; FY 2027: 8000
TO-5142 | Public Transportation (Transit) | Miscellaneous/Other | GASTONIA TRANSIT | OPERATING ASSISTANCE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 3470000
TO-5142 | Public Transportation (Transit) | Miscellaneous/Other | GASTONIA TRANSIT | OPERATING ASSISTANCE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 5909000
TO-5142 | Public Transportation (Transit) | Miscellaneous/Other | GASTONIA TRANSIT | OPERATING ASSISTANCE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 8289000
TO-5144 | Public Transportation (Transit) | Miscellaneous/Other | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4630000
TO-5144 | Public Transportation (Transit) | Miscellaneous/Other | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 4630000
TO-5149 | Public Transportation (Transit) | Miscellaneous/Other | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) |  | IREDELL | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1174000
TO-5149 | Public Transportation (Transit) | Miscellaneous/Other | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) |  | IREDELL | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1440000
TO-5201 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING ASSISTANCE |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | CMAQ | OPERATIONS | 1311000
TO-5201 | Public Transportation (Transit) | Miscellaneous/Other | CITY OF SALISBURY | OPERATING ASSISTANCE |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 3164000
TO-5204 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1121000
TO-5204 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1121000
TO-5206 | Public Transportation (Transit) | Miscellaneous/Other | DURHAM | 5307 OPERATING FUNDS NC 2019-060-01-P11 |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5307 | OPERATIONS | 311000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | SMAP | OPERATIONS | 4676000 | FY 2024: 668000; FY 2025: 668000; FY 2026: 668000; FY 2027: 668000; FY 2028: 668000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | L | OPERATIONS | 4387000 | FY 2024: 518000; FY 2025: 456000; FY 2026: 456000; FY 2027: 456000; FY 2028: 456000
TO-5209 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | Public Transit |  | 5307 | OPERATIONS | 4387000 | FY 2024: 518000; FY 2025: 456000; FY 2026: 456000; FY 2027: 456000; FY 2028: 456000
TO-5214 | Public Transportation (Transit) | Miscellaneous/Other | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 6277000 | FY 2024: 805000; FY 2025: 805000; FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5214 | Public Transportation (Transit) | Miscellaneous/Other | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 7603000 | FY 2024: 805000; FY 2025: 805000; FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5215 | Public Transportation (Transit) | Miscellaneous/Other | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT |  | DAVIDSON | 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 270000
TO-5215 | Public Transportation (Transit) | Miscellaneous/Other | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT |  | DAVIDSON | 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 270000
TO-5216 | Public Transportation (Transit) | Miscellaneous/Other | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO |  | GUILFORD | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 525000 | FY 2024: 60000; FY 2025: 65000; FY 2026: 70000; FY 2027: 75000
TO-5216 | Public Transportation (Transit) | Miscellaneous/Other | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO |  | GUILFORD | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 980000 | FY 2024: 120000; FY 2025: 130000; FY 2026: 140000; FY 2027: 150000
TO-5220 | Public Transportation (Transit) | Miscellaneous/Other | BURLINGTON -GRAHAM | 5307 OPERATING FUNDS NC-2019-060-01-P10 |  | ORANGE | 7 | Burlington-Graham MPO | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY 2020 GRANTS | Public Transit |  | 5307 | OPERATIONS | 282000
TO-5221 | Public Transportation (Transit) | Miscellaneous/Other | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT |  | GUILFORD | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | L | OPERATIONS | 280000 | FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-5221 | Public Transportation (Transit) | Miscellaneous/Other | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT |  | GUILFORD | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | 5307 | OPERATIONS | 280000 | FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-6061 | Public Transportation (Transit) | Miscellaneous/Other | GASTONIA TRANSIT | OPERATING EXPENSES |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 4166000 | FY 2025: 2080000
TO-6061 | Public Transportation (Transit) | Miscellaneous/Other | GASTONIA TRANSIT | OPERATING EXPENSES |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 4166000 | FY 2025: 2080000
TO-6101 | Public Transportation (Transit) | Miscellaneous/Other | APPALCART | OPERATING ASSISTANCE |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 15464000
TO-6101 | Public Transportation (Transit) | Miscellaneous/Other | APPALCART | OPERATING ASSISTANCE |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 17748000
TO-6102 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 344000
TO-6102 | Public Transportation (Transit) | Miscellaneous/Other | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 866000
TO-6103 | Public Transportation (Transit) | Miscellaneous/Other | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE |  | FRANKLIN, GRANVILLE, VANCE, WARREN | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 486000
TO-6103 | Public Transportation (Transit) | Miscellaneous/Other | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE |  | FRANKLIN, GRANVILLE, VANCE, WARREN | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1228000
TO-6104 | Public Transportation (Transit) | Miscellaneous/Other | APPALCART | OPERATING ASSISTANCE |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 9212000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 461000 | FY 2024: 237000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 237000 | FY 2024: 237000
TO-6106 | Public Transportation (Transit) | Miscellaneous/Other | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 448000
TO-6107 | Public Transportation (Transit) | Miscellaneous/Other | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 168000
TO-6107 | Public Transportation (Transit) | Miscellaneous/Other | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 436000
TO-6135 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | OPERATIONS | 947000
TO-6139 | Public Transportation (Transit) | Miscellaneous/Other | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING. |  | GUILFORD | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | L | OPERATIONS | 883000 | FY 2024: 50000; FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
TO-6139 | Public Transportation (Transit) | Miscellaneous/Other | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING. |  | GUILFORD | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | Public Transit |  | 5310 | OPERATIONS | 881000 | FY 2024: 50000; FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
TO-6142 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING |  | STATEWIDE | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 9389000
TO-6142 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING |  | STATEWIDE | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 9389000
TO-6150 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 5347000 | FY 2024: 439000; FY 2025: 546000; FY 2026: 546000; FY 2027: 546000; FY 2028: 546000
TO-6150 | Public Transportation (Transit) | Miscellaneous/Other | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 5440000 | FY 2024: 439000; FY 2025: 546000; FY 2026: 546000; FY 2027: 546000; FY 2028: 546000
TO-6151 | Public Transportation (Transit) | Miscellaneous/Other | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING |  | GUILFORD | 7 | Burlington-Graham MPO |  | Public Transit |  | L | OPERATIONS | 2016000
TO-6151 | Public Transportation (Transit) | Miscellaneous/Other | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING |  | GUILFORD | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | OPERATIONS | 2016000
TO-6154 | Public Transportation (Transit) | Miscellaneous/Other | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 1091000
TO-6154 | Public Transportation (Transit) | Miscellaneous/Other | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5307 | OPERATIONS | 1340000
TO-6155 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | 5311 OPERATING AND 5311 OPERATING F |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 57825000 | FY 2024: 6435000; FY 2025: 6445000; FY 2026: 6455000; FY 2027: 6465000
TO-6155 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | 5311 OPERATING AND 5311 OPERATING F |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | OPERATIONS | 115650000 | FY 2024: 12870000; FY 2025: 12890000; FY 2026: 12910000; FY 2027: 12930000
TO-6156 | Public Transportation (Transit) | Miscellaneous/Other | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) |  | UNION | 10 | Charlotte Regional TPO | ADDING FUNDS FOR FFY20-21 | Public Transit |  | L | OPERATIONS | 783000
TO-6156 | Public Transportation (Transit) | Miscellaneous/Other | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) |  | UNION | 10 | Charlotte Regional TPO | ADDING FUNDS FOR FFY20-21 | Public Transit |  | 5307 | OPERATIONS | 783000
TO-6157 | Public Transportation (Transit) | Miscellaneous/Other | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 |  | HOKE | 8 | Fayetteville Area MPO |  | Public Transit |  | L | OPERATIONS | 466000
TO-6157 | Public Transportation (Transit) | Miscellaneous/Other | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 |  | HOKE | 8 | Fayetteville Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 466000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | IREDELL COUNTY | OPERATION FOR FY20-21 |  | IREDELL | 12 | Charlotte Regional TPO | ADDING FUNDS FOR FFY2020 | Public Transit |  | L | OPERATIONS | 1186000
TO-6158 | Public Transportation (Transit) | Miscellaneous/Other | IREDELL COUNTY | OPERATION FOR FY20-21 |  | IREDELL | 12 | Charlotte Regional TPO | ADDING FUNDS FOR FFY2020 | Public Transit |  | 5307 | OPERATIONS | 1186000
TO-6159 | Public Transportation (Transit) | Miscellaneous/Other | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADDING CURRENT YEAR TO THE STIP | Public Transit |  | L | OPERATIONS | 1537000
TO-6159 | Public Transportation (Transit) | Miscellaneous/Other | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADDING CURRENT YEAR TO THE STIP | Public Transit |  | 5307 | OPERATIONS | 1537000
TO-6162 | Public Transportation (Transit) | Miscellaneous/Other | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 11365000 | FY 2024: 1700000; FY 2025: 1700000
TO-6162 | Public Transportation (Transit) | Miscellaneous/Other | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 11365000 | FY 2024: 1700000; FY 2025: 1700000
TO-6165 | Public Transportation (Transit) | Miscellaneous/Other | DAVIDSON COUNTY | OPERATING ASSISTANCE |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 163344000
TO-6165 | Public Transportation (Transit) | Miscellaneous/Other | DAVIDSON COUNTY | OPERATING ASSISTANCE |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 163344000
TO-6166 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 33.93 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO |  | Region A, C
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 1500000 | FY 2031: 1500000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7649000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 14344000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2126000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 3988000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40224000
TO-6166A | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 75425000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 9.19 | WAKE | 5 | Capital Area MPO |  | Region C |  | 5309 | ENGINEERING | 8134000 | FY 2024: 8134000
TO-6166B | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 9.19 | WAKE | 5 | Capital Area MPO |  | Region C |  | L | CONSTRUCTION | 45168000
TO-6166C | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5.93 | WAKE | 5 | Capital Area MPO |  | Region C |  | L | ENGINEERING | 1500000
TO-6166C | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5.93 | WAKE | 5 | Capital Area MPO |  | Region C |  | 5309 | CONSTRUCTION | 8134000 | FY 2024: 8134000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 1500000 | FY 2031: 1500000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7649000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 14344000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2126000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 3988000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40224000
TO-6166D | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Region A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 75426000
TO-6168 | Public Transportation (Transit) | Miscellaneous/Other | GORALEIGH | TOWN OF WAKE FOREST REVERSE CIRCULATOR OPERATING ASSISTANCE |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 2283000 | FY 2024: 387000; FY 2025: 394000; FY 2026: 404000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | L | OPERATIONS | 5890000 | FY 2024: 820000; FY 2025: 820000; FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | L | OPERATIONS | 792000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | 5307 | OPERATIONS | 1349000
TO-6170 | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | Public Transit |  | 5307 | OPERATIONS | 6008000 | FY 2024: 820000; FY 2025: 820000; FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6812A | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | ADA SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | OPERATIONS | 322000 | FY 2024: 46000; FY 2025: 46000; FY 2026: 46000; FY 2027: 46000; FY 2028: 46000
TO-6812A | Public Transportation (Transit) | Miscellaneous/Other | LINK TRANSIT | ADA SERVICE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | OPERATIONS | 1260000 | FY 2024: 180000; FY 2025: 180000; FY 2026: 180000; FY 2027: 180000; FY 2028: 180000
TO-6813 | Public Transportation (Transit) | Locally Selected | KINGS MOUNTAIN | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 823000 | FY 2024: 823000
TO-6813 | Public Transportation (Transit) | Locally Selected | KINGS MOUNTAIN | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L | CONSTRUCTION | 206000 | FY 2024: 206000
TP-4732A | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 586000
TP-4732A | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 586000
TP-4732A | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 7257000
TP-4732B | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 586000
TP-4732B | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 586000
TP-4732B | Public Transportation (Transit) | Planning | GOTRIANGLE | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 7257000
TP-4901 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 630000
TP-4901 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FSPR | CAPITAL | 7139000
TP-4908 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | PLANNING | 91000 | FY 2024: 10000; FY 2025: 10000; FY 2026: 10000; FY 2027: 10000
TP-4908 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | PLANNING | 91000 | FY 2024: 10000; FY 2025: 10000; FY 2026: 10000; FY 2027: 10000
TP-4908 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | PLANNING | 911000 | FY 2024: 76000; FY 2025: 78000; FY 2026: 78000; FY 2027: 80000
TP-5100A | Public Transportation (Transit) | Planning | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 368000
TP-5100A | Public Transportation (Transit) | Planning | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 376000
TP-5100A | Public Transportation (Transit) | Planning | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 4831000
TP-5100B | Public Transportation (Transit) | Planning | GORALEIGH | PLANNING ASSISTANCE - 5307 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 400000
TP-5100B | Public Transportation (Transit) | Planning | GORALEIGH | PLANNING ASSISTANCE - 5307 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 946000
TP-5100B | Public Transportation (Transit) | Planning | GORALEIGH | PLANNING ASSISTANCE - 5307 |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 8086000
TP-5101 | Public Transportation (Transit) | Planning | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | PLANNING | 225000 | FY 2024: 27000; FY 2025: 27000; FY 2026: 27000; FY 2027: 27000; FY 2028: 27000
TP-5101 | Public Transportation (Transit) | Planning | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 225000 | FY 2024: 27000; FY 2025: 27000; FY 2026: 27000; FY 2027: 27000; FY 2028: 27000
TP-5101 | Public Transportation (Transit) | Planning | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 1811000 | FY 2024: 217000; FY 2025: 217000; FY 2026: 217000; FY 2027: 217000; FY 2028: 217000
TP-5102 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | PLANNING | 53000 | FY 2024: 6000; FY 2025: 6000; FY 2026: 6000; FY 2027: 6000
TP-5102 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | PLANNING | 53000 | FY 2024: 6000; FY 2025: 6000; FY 2026: 6000; FY 2027: 6000
TP-5102 | Public Transportation (Transit) | Planning | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5303 | PLANNING | 499000 | FY 2024: 31000; FY 2025: 32000; FY 2026: 32000; FY 2027: 32000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 48000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 56000
TP-5103 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 815000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 353000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 353000
TP-5103B | Public Transportation (Transit) | Operations and Maintenance | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3866000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 |  | GUILFORD | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 32000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 |  | GUILFORD | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 32000
TP-5104 | Public Transportation (Transit) | Capital (Non-STI) | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 |  | GUILFORD | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 552000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 94000 | FY 2024: 10000; FY 2025: 10000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 94000 | FY 2024: 10000; FY 2025: 10000
TP-5105 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 1393000 | FY 2024: 83000; FY 2025: 83000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | S | PLANNING | 34000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | L | PLANNING | 34000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | 5303 | PLANNING | 264000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | S | CAPITAL | 16000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | L | CAPITAL | 16000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | 5303 | CAPITAL | 377000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | S | ADMINISTRATIVE | 17000 | FY 2024: 8000; FY 2025: 9000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | L | ADMINISTRATIVE | 17000 | FY 2024: 8000; FY 2025: 9000
TP-5106 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | Public Transit |  | 5303 | ADMINISTRATIVE | 127000 | FY 2024: 60000; FY 2025: 67000
TP-5107 | Public Transportation (Transit) | Planning | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 24000
TP-5107 | Public Transportation (Transit) | Planning | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 24000
TP-5107 | Public Transportation (Transit) | Planning | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 413000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5303 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 112000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5303 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 112000
TP-5108 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5303 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 1736000
TP-5109 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5307 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 384000
TP-5109 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5307 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 384000
TP-5109 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | PLANNING ASSISTANCE - 5307 |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 5494000
TP-5110 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 38000
TP-5110 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 152000
TP-5110 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 20000
TP-5110 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 20000
TP-5110 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 260000
TP-5111 | Public Transportation (Transit) | Planning | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 112000
TP-5111 | Public Transportation (Transit) | Planning | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 112000
TP-5111 | Public Transportation (Transit) | Planning | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 4184000
TP-5112 | Public Transportation (Transit) | Planning | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 14000
TP-5112 | Public Transportation (Transit) | Planning | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 466000 | FY 2024: 54000; FY 2025: 56000
TP-5112 | Public Transportation (Transit) | Planning | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 2461000 | FY 2024: 270000; FY 2025: 280000
TP-5112 | Public Transportation (Transit) | Planning | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | PLANNING | 48000
TP-5113 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | PLANNING ASSISTANCE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 14000
TP-5113 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | PLANNING ASSISTANCE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 14000
TP-5113 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | PLANNING ASSISTANCE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 680000
TP-5114 | Public Transportation (Transit) | Planning | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 430000 | FY 2024: 43000; FY 2025: 43000
TP-5114 | Public Transportation (Transit) | Planning | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 430000 | FY 2024: 43000; FY 2025: 43000
TP-5114 | Public Transportation (Transit) | Planning | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 5206000 | FY 2024: 347000; FY 2025: 347000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 24000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 24000
TP-5116 | Public Transportation (Transit) | Capital (Non-STI) | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 324000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 64000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 64000
TP-5118 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | CAPITAL | 632000
TP-5122 | Public Transportation (Transit) | Planning | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 14000
TP-5122 | Public Transportation (Transit) | Planning | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | PLANNING | 56000
TP-5150 | Public Transportation (Transit) | Planning | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | PLANNING | 8000
TP-5150 | Public Transportation (Transit) | Planning | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | PLANNING | 36000 | FY 2024: 4000
TP-5150 | Public Transportation (Transit) | Planning | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5303 | PLANNING | 270000 | FY 2024: 30000
TP-5153 | Public Transportation (Transit) | Planning | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | PLANNING | 180000
TP-5153 | Public Transportation (Transit) | Planning | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5307 | PLANNING | 726000
TP-5154 | Public Transportation (Transit) | Planning | STATEWIDE | 5304 PLANNING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | PLANNING | 954000 | FY 2024: 108000; FY 2025: 110000; FY 2026: 112000; FY 2027: 114000
TP-5154 | Public Transportation (Transit) | Planning | STATEWIDE | 5304 PLANNING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5303 | PLANNING | 4770000 | FY 2024: 540000; FY 2025: 550000; FY 2026: 560000; FY 2027: 570000
TP-5156 | Public Transportation (Transit) | Capital (Non-STI) | CATS | ADD A LIGHT RAIL STATION ON THE LYNX BLUE LINE NEAR IVERSON WAY IN SOUTH CHARLOTTE |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION. | Public Transit |  | L | CAPITAL | 7582000
TP-5159 | Public Transportation (Transit) | Planning | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | PLANNING | 331000 | FY 2024: 51000
TP-5159 | Public Transportation (Transit) | Planning | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5303 | PLANNING | 1325000 | FY 2024: 203000
TP-5160 | Public Transportation (Transit) | Capital (Non-STI) | GO RALEIGH | CONSTRUCT BUS RAPID TRANSIT ON NEW BERN CORRIDOR. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  |  |  | 4316000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | PLANNING | 4605000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | 5309 | PLANNING | 5950000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | FUZ | PLANNING | 1195000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 1757000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | FUZ | RIGHT-OF-WAY | 302000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | 5309 | RIGHT-OF-WAY | 1027000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 13650000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 25358000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | FUZ | CONSTRUCTION | 5163000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | 5309 | CONSTRUCTION | 24336000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | ARP | CAPITAL | 5404000
TP-5160A | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | 5309 | CAPITAL | 3687000
TP-5160B | Public Transportation (Transit) | Capital (Non-STI) | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR, BETTERMENT FUNDING | 3.54 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 814000
TP-5161 | Public Transportation (Transit) | Planning | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | PLANNING | 1000
TP-5161 | Public Transportation (Transit) | Planning | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | PLANNING | 4000
TP-5162 | Public Transportation (Transit) | Planning | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | PLANNING | 19000
TP-5162 | Public Transportation (Transit) | Planning | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | PLANNING | 76000
TQ-6186 | Public Transportation (Transit) | Capital (Non-STI) | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 138000
TQ-6186 | Public Transportation (Transit) | Capital (Non-STI) | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5310 | CAPITAL | 555000
TQ-6187 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | 5310 OTHER PROJECTS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 344000
TQ-6187 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | 5310 OTHER PROJECTS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5310 | OPERATIONS | 344000
TQ-6507 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | Public Transit |  | L | OPERATIONS | 1087000 | FY 2024: 150000; FY 2025: 150000
TQ-6507 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | Public Transit |  | 5310 | OPERATIONS | 1428000 | FY 2024: 150000; FY 2025: 150000
TQ-6513 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1028000 | FY 2024: 88000; FY 2025: 128000; FY 2026: 132000
TQ-6513 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 1028000 | FY 2024: 88000; FY 2025: 128000; FY 2026: 132000
TQ-6514 | Public Transportation (Transit) | Operations and Maintenance | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 248000
TQ-6514 | Public Transportation (Transit) | Operations and Maintenance | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 1000000
TQ-6597 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | OPERATIONS | 1395000
TQ-6597 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | OPERATIONS | 1395000
TQ-6702 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 926000 | FY 2024: 146000; FY 2025: 89000
TQ-6702 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5310 | OPERATIONS | 3695000 | FY 2024: 582000; FY 2025: 355000
TQ-6782 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 1221000 | FY 2024: 90000; FY 2025: 90000; FY 2026: 90000; FY 2027: 90000
TQ-6782 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5310 | OPERATIONS | 4867000 | FY 2024: 358000; FY 2025: 358000; FY 2026: 358000; FY 2027: 358000
TQ-6783 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 680000 | FY 2024: 80000; FY 2025: 80000; FY 2026: 80000; FY 2027: 80000; FY 2028: 80000
TQ-6783 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5310 | CAPITAL | 2720000 | FY 2024: 320000; FY 2025: 320000; FY 2026: 320000; FY 2027: 320000; FY 2028: 320000
TQ-6953 | Public Transportation (Transit) | Operations and Maintenance | CAPITAL AREA TRANSIT | 5310 OPERATING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2086000
TQ-6953 | Public Transportation (Transit) | Operations and Maintenance | CAPITAL AREA TRANSIT | 5310 OPERATING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 2086000
TQ-6954 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5310 OPERATING PROJECTS FOR RURAL AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | L | OPERATIONS | 2832000 | FY 2024: 695000
TQ-6954 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5310 OPERATING PROJECTS FOR RURAL AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5310 | OPERATIONS | 6103000 | FY 2024: 2005000
TQ-6957 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | OPERATIONS | 2347000
TQ-6957 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | OPERATIONS | 4218000
TQ-7000 | Public Transportation (Transit) | Operations and Maintenance | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 PROGRAM ADMINISTRATION |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 342000 | FY 2024: 41000; FY 2025: 41000; FY 2026: 41000; FY 2027: 41000; FY 2028: 41000
TQ-7005 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT IS FOR ADMINISTRATIVE SUPPORT REQUIRED TO EFFECTVELY MANAGE THE SECTION 5310 PROGRAM AND ANNUAL FUNDING ALLOCATION FROM FTA. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 280000 | FY 2024: 25000; FY 2025: 37000; FY 2026: 38000
TQ-7006 | Public Transportation (Transit) | Operations and Maintenance | CAPITAL AREA TRANSIT | 5310 ADMIN. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 295000
TQ-7009 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | ADMINISTRATIVE OVERSIGHT FOR 5310 |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | ADMINISTRATIVE | 692000
TQ-7010 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT. 5310 ADMINISTRATIVE OVERSIGHT. |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5310 | CAPITAL | 163000
TQ-8019 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 134000 | FY 2024: 15000; FY 2025: 22000; FY 2026: 22000
TQ-8019 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 543000 | FY 2024: 60000; FY 2025: 87000; FY 2026: 90000
TQ-9001 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 97000 | FY 2024: 20000; FY 2025: 29000; FY 2026: 30000
TQ-9001 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5310 | CAPITAL | 815000 | FY 2024: 79000; FY 2025: 114000; FY 2026: 117000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | S | CAPITAL | 240000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | L | CAPITAL | 1879000 | FY 2024: 101000; FY 2025: 104000
TQ-9033 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | Public Transit |  | 5310 | CAPITAL | 8193000 | FY 2024: 810000; FY 2025: 834000
TQ9037 | Public Transportation (Transit) | Operations and Maintenance | CAPITAL AREA TRANSIT | 5310 ADMINISTRATION |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | ADMINISTRATIVE | 295000
TQ-9037 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | 5310 CAPITAL AND ADMIN |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 648000
TQ-9037 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | 5310 CAPITAL AND ADMIN |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 2591000
TQ-9038 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5310 CAPITAL PROJECTS FOR RURAL AREAS AND SMALL URBAN AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5310 | CAPITAL | 2850000
TQ-9039 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE. |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 402000 | FY 2024: 100000; FY 2025: 100000
TQ-9039 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE. |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5310 | CAPITAL | 1609000 | FY 2024: 400000; FY 2025: 400000
TS-4758 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | CAPITAL | 141000 | FY 2024: 17000; FY 2025: 17000; FY 2026: 17000; FY 2027: 17000; FY 2028: 17000
TS-4758 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5307 | CAPITAL | 554000 | FY 2024: 66000; FY 2025: 66000; FY 2026: 66000; FY 2027: 66000; FY 2028: 66000
TS-4900Z | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | STATEWIDE RTAP |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | RTAP | ADMINISTRATIVE | 480000
TS-5101 | Public Transportation (Transit) | Capital (Non-STI) | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 21000
TS-5101 | Public Transportation (Transit) | Capital (Non-STI) | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 29000
TS-5102 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 12000
TS-5102 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 103000
TS-5103 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 16000
TS-5103 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 310000
TS-5104 | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 214000
TS-5104 | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1218000
TS-5107 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1224000 | FY 2024: 122000; FY 2025: 122000
TS-5107 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 7276000 | FY 2024: 490000; FY 2025: 490000
TS-5108 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 32000
TS-5108 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 543000
TS-5109 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 48000
TS-5109 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 339000
TS-5112 | Public Transportation (Transit) | Capital (Non-STI) | GREENVILLE AREA TRANSIT | SAFETY & SECURITY |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 177000
TS-5113 | Public Transportation (Transit) | Capital (Non-STI) | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DAVIDSON, GUILFORD, RANDOLPH | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 16000
TS-5113 | Public Transportation (Transit) | Capital (Non-STI) | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DAVIDSON, GUILFORD, RANDOLPH | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 204000
TS-5114 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | ONSLOW | 3 | Jacksonville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 254000 | FY 2024: 21000; FY 2025: 21000
TS-5115 | Public Transportation (Transit) | Capital (Non-STI) | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | GUILFORD, ALAMANCE, FORSYTH | 7, 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 39000
TS-5116 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 303000
TS-5119 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 14000
TS-5119 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 390000
TS-5120 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | SMAP | CAPITAL | 7000
TS-5120 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 81000 | FY 2024: 17000; FY 2025: 8000
TS-5120 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 535000 | FY 2024: 69000; FY 2025: 33000
TS-5129 | Public Transportation (Transit) | Capital (Non-STI) | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 8000
TS-5129 | Public Transportation (Transit) | Capital (Non-STI) | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 79000
TS-5133 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | SAFETY & SECURITY MIN. 1% SET ASIDE |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 56000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | ADMINISTRATIVE | 812000 | FY 2024: 69000; FY 2025: 69000; FY 2026: 70000; FY 2027: 70000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | FED | ADMINISTRATIVE | 4224000 | FY 2024: 345000; FY 2025: 345000; FY 2026: 346000; FY 2027: 346000
TS-7001 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | ADMINISTRATIVE | 70000 | FY 2027: 70000
TS-7002 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 88000 | FY 2024: 14000; FY 2025: 14000
TS-7002 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | CAPITAL | 356000 | FY 2024: 58000; FY 2025: 58000
TT-4907 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 262000 | FY 2024: 20000; FY 2025: 20000; FY 2026: 20000; FY 2027: 20000
TT-4907 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 2171000 | FY 2024: 80000; FY 2025: 80000; FY 2026: 80000; FY 2027: 80000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 17000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 17000
TT-5204 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 182000
TT-5206 | Public Transportation (Transit) | Capital (Non-STI) | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 14000
TT-5206 | Public Transportation (Transit) | Capital (Non-STI) | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 70000
TT-5207 | Public Transportation (Transit) | Operations and Maintenance | GTA | TRANSIT SAFETY INNOVATIONS |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO |  |  | 5312 | OPERATIONS | 68000
TT-5207 | Public Transportation (Transit) | Operations and Maintenance | GTA | TRANSIT SAFETY INNOVATIONS |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO |  |  | L | OPERATIONS | 18000
TU-0001 | Public Transportation (Transit) | Planning | CATS | LYNX SILVER LINE LIGHT RAIL PROJECT | 28.84 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | PLANNING | 48647000
TU-0001 | Public Transportation (Transit) | Planning | CATS | LYNX SILVER LINE LIGHT RAIL PROJECT | 28.84 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | PLANNING | 1353000
TU-0002 | Public Transportation (Transit) | Planning | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | PLANNING | 26000
TU-0002 | Public Transportation (Transit) | Planning | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5305 | PLANNING | 234000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | PLANNING | 32000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | 5312 | PLANNING | 110000
TU-0003 | Public Transportation (Transit) | Planning | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | 5303 | PLANNING | 80000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. |  | WAKE, LEE, VANCE | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | S | PLANNING | 100000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. |  | WAKE, LEE, VANCE | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | FED | PLANNING | 900000
TU-0004 | Public Transportation (Transit) | Planning | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. |  | WAKE, LEE, VANCE | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | Public Transit |  | L | PLANNING | 505000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | PLANNING | 1081000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | PLANNING | 1081000
TU-0005 | Public Transportation (Transit) | Planning | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5303 | PLANNING | 8647000
TU-0006 | Public Transportation (Transit) | Planning | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | CMAQ | PLANNING | 650000
TU-0006 | Public Transportation (Transit) | Planning | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 90000
TU-0007 | Public Transportation (Transit) | Planning | GORALEIGH | MAJOR INVESTMENT STUDY/ALTERNATIVES ANALYSIS FOR BUS RAPID TRANSIT EXTENSION TO RESEARCH TRIANGLE PARK AND CLAYTON. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 430000
TU-0008 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | PLANNING | 118000
TU-0008 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | PLANNING | 470000
TU-0009 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | RTAP | PLANNING | 765000
TU-0010 | Public Transportation (Transit) | Planning | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | L | PLANNING | 120000
TU-0010 | Public Transportation (Transit) | Planning | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | 5307 | PLANNING | 480000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | PLANNING | 227000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5303 | PLANNING | 2834000 | FY 2024: 1700000
TU-0011 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5303 | ADMINISTRATIVE | 370000
TU-0012 | Public Transportation (Transit) | Planning | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | PLANNING | 20000
TU-0012 | Public Transportation (Transit) | Planning | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5303 | PLANNING | 80000
TU-0013 | Public Transportation (Transit) | Planning | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | PLANNING | 2700000 | FY 2024: 2340000
TU-0013 | Public Transportation (Transit) | Planning | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | 5339(b) | PLANNING | 10800000 | FY 2024: 9360000
TU-0014 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | PLANNING | 127000
TU-0014 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | PLANNING | 507000
TU-0015 | Public Transportation (Transit) | Planning | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO THE DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | RTAP | PLANNING | 73000
TU-0016 | Public Transportation (Transit) | Planning | INTEGRATED MOBILITY DIVISION | THIS PLANNING PROJECT WILL FUND THE PLANNING OF MOBILITY HUBS IN SEVEN COMMUNITIES ALONG THE S-LINE PASSENGER RAIL CORRIDOR. PARTICIPATING COMMUNITIES INCLUDE SANFORD, APEX, WAKE FOREST, YOUNGSVILLE, HENDERSON, FRANLINTON, AND NORLINA. PLANNING ACTIVTIES INCLUDE FEASIBILLITY AND SITE ASSESSMENTS FOR ALL PARTNER COMMUNITIES, AND NATIONAL ENVIRONMENT POLICY ACT (NEPA) COMPLIANCE AND PRELIMINARY ENGINEERING FOR THREE COMMUNITIES. |  | FRANKLIN, LEE, VANCE, WARREN, WAKE | 5, 8 | STATEWIDE PROJECT | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | DP | PLANNING | 3400000 | FY 2024: 1000000
TU-0016 | Public Transportation (Transit) | Planning | INTEGRATED MOBILITY DIVISION | THIS PLANNING PROJECT WILL FUND THE PLANNING OF MOBILITY HUBS IN SEVEN COMMUNITIES ALONG THE S-LINE PASSENGER RAIL CORRIDOR. PARTICIPATING COMMUNITIES INCLUDE SANFORD, APEX, WAKE FOREST, YOUNGSVILLE, HENDERSON, FRANLINTON, AND NORLINA. PLANNING ACTIVTIES INCLUDE FEASIBILLITY AND SITE ASSESSMENTS FOR ALL PARTNER COMMUNITIES, AND NATIONAL ENVIRONMENT POLICY ACT (NEPA) COMPLIANCE AND PRELIMINARY ENGINEERING FOR THREE COMMUNITIES. |  | FRANKLIN, LEE, VANCE, WARREN, WAKE | 5, 8 | STATEWIDE PROJECT | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | L | PLANNING | 1030000 | FY 2024: 250000; FY 2025: 45000; FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TU-0016 | Public Transportation (Transit) | Planning | INTEGRATED MOBILITY DIVISION | THIS PLANNING PROJECT WILL FUND THE PLANNING OF MOBILITY HUBS IN SEVEN COMMUNITIES ALONG THE S-LINE PASSENGER RAIL CORRIDOR. PARTICIPATING COMMUNITIES INCLUDE SANFORD, APEX, WAKE FOREST, YOUNGSVILLE, HENDERSON, FRANLINTON, AND NORLINA. PLANNING ACTIVTIES INCLUDE FEASIBILLITY AND SITE ASSESSMENTS FOR ALL PARTNER COMMUNITIES, AND NATIONAL ENVIRONMENT POLICY ACT (NEPA) COMPLIANCE AND PRELIMINARY ENGINEERING FOR THREE COMMUNITIES. |  | FRANKLIN, LEE, VANCE, WARREN, WAKE | 5, 8 | STATEWIDE PROJECT | DP FUNDING REPRESENTS RAISE GRANT FUNDS | Public Transit |  | 5307 | PLANNING | 740000 | FY 2025: 185000; FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TU-0017 | Public Transportation (Transit) | Planning | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ACTA PLANNING AND FEASIBILITY STUDY (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | PLANNING | 30000 | FY 2024: 30000
TU-0017 | Public Transportation (Transit) | Planning | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ACTA PLANNING AND FEASIBILITY STUDY (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | PLANNING | 120000 | FY 2024: 120000
TV-4903 | Public Transportation (Transit) | Operations and Maintenance | SUB REGIONAL | 5310 STATE ADMIN |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | ADMINISTRATIVE | 450000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 1208000 | FY 2024: 73000; FY 2025: 75000; FY 2026: 77000; FY 2027: 80000 | 167000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1208000 | FY 2024: 73000; FY 2025: 75000; FY 2026: 77000; FY 2027: 80000 | 167000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FMOD | CAPITAL | 2700000
TW-4901 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 7979000 | FY 2024: 584000; FY 2025: 601000; FY 2026: 619000; FY 2027: 638000 | 1333000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 355000 | FY 2024: 30000; FY 2025: 30000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 355000 | FY 2024: 30000; FY 2025: 30000
TW-5102A | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 3364000 | FY 2024: 240000; FY 2025: 240000
TW-5102B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 410000
TW-5102B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FMOD | CONSTRUCTION | 2845000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 2372000 | FY 2024: 242000; FY 2025: 249000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2372000 | FY 2024: 242000; FY 2025: 249000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 18977000 | FY 2024: 1933000; FY 2025: 1991000
TW-5104B | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 15989000
U-0071 | Highway | Transition | NEW ROUTE | EAST END CONNECTOR, NC 147 (DURHAM FREEWAY) TO NORTH OF NC 98 IN DURHAM. FOUR-LANE DIVIDED FREEWAY WITH AUXILIARY LANES, PART ON NEW LOCATION. | 2.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 219683000
U-0209 | Highway | Pre-STI (Historic) | US 74 (INDEPENDENCE BOULEVARD) | BROOKSHIRE FREEWAY TO IDLEWILD ROAD IN CHARLOTTE. ADD ADDITIONAL LANES AND CONSTRUCT INTERCHANGES WITH SHARON AMITY ROAD AND IDLEWILD ROAD AND SAFETY IMPROVEMENTS. | 1.4 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024 |  |  |  |  | 334267000
U-0209B | Highway | Pre-STI (Historic) | US 74 (INDEPENDENCE BOULEVARD) | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE ROW | 10968000
U-0209B | Highway | Pre-STI (Historic) | US 74 (INDEPENDENCE BOULEVARD) | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE CON | 1025000 | FY 2024: 205000
U-0209BA | Highway | Pre-STI (Historic) | US 74 (INDEPENDENCE BOULEVARD) | SEPARATE ITS CONTRACT FOR U-209 B |  | MECKLENBURG | 10 | Charlotte Regional TPO | WORK TO BE CONSTRUCTED BY PROJECT U-6103 | Pre-STI (Transition)
U-2307 | Highway | STI (Prioritization) | HICKORY | EAST SIDE THOROUGHFARE (MCDONALD PARKWAY), US 70-321 TO NC 127. MULTI-LANES, PART ON NEW LOCATION. | 6.6 | CATAWBA | 12 | Greater Hickory MPO | STBG-DA FUNDS (W/ STATE MATCH) AS A RESULT OF FUNDING SWAP WITH EB-5911. |  |  |  |  | 58010000
U-2307AA | Highway | Pre-STI (Historic) | HICKORY | US 70-321 TO NORTH OF I-40. |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2307AB | Highway | Pre-STI (Historic) | HICKORY | NORTH OF I-40 TO SR 1453 (SPRINGS ROAD) |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2307AD | Highway | Pre-STI (Historic) | HICKORY | NORTH OF I-40 TO NORTH OF SR 1692 (TATE BOULEVARD) |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2307AE | Highway | Pre-STI (Historic) | HICKORY | NORTH OF SR 1692 (TATE BOULEVARD) TO SR 1453 (SPRINGS ROAD) |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 12374000 | FY 2027: 12374000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 9684000 | FY 2029: 9684000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 10760000 | FY 2030: 10760000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 8608000 | FY 2026: 8608000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 12374000 | FY 2028: 12374000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | UTILITIES | 15700000 | FY 2026: 7850000; FY 2027: 7850000
U-2307B | Highway | STI (Prioritization) | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | CONSTRUCTION | 64701000 | FY 2029: 5754000; FY 2030: 18944000; FY 2031: 16548000; FY 2032: 12619000; FY 2033: 10836000
U-2307C | Highway | Pre-STI (Historic) | HICKORY | HICKORY EAST SIDE THOROUGHFARE TO 15TH AVE SE |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2412 | Highway | STI (Prioritization) | SR 1486 (GREENSBORO ROAD) / SR 4121 (HIGH POINT RO | PROPOSED US 311 BYPASS IN HIGH POINT TO SR 1424 (HILLTOP ROAD) IN GREENSBORO. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 7.8 | GUILFORD | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | [5 empty] | 127674000
U-2412A | Highway | STI (Prioritization) | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 3.61 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 27681000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1851000
U-2412A | Highway | STI (Prioritization) | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 3.61 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 36780000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 4904000
U-2412A | Highway | STI (Prioritization) | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 3.61 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | CONSTRUCTION | 16138000
U-2412B | Highway | Pre-STI (Historic) | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | SR 4228 (VICKREY CHAPEL ROAD) TO SR 1424 (HILLTOP ROAD) | 4.35 | GUILFORD | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
U-2507 | Highway | Pre-STI (Historic) | SR 2467 (MALLARD CREEK ROAD) | SR 2480 (SUGAR CREEK ROAD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) IN CHARLOTTE. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 4.1 | MECKLENBURG | 10 | Charlotte Regional TPO | [5 empty] | 63399000
U-2507A | Highway | Transition | SR 2467 (MALLARD CREEK ROAD) | SR 2480 (SUGAR CREEK ROAD) TO SR 2665 (HARRIS BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 2.37 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Pre-STI (Transition)
U-2507AA | Highway | Transition | NEW ROUTE | SR 2467 (MALLARD CREEK ROAD) TO IBM DRIVE. CONSTRUCT NEW CONNECTOR ROAD AND MULTI-USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO | IMPROVEMENTS CONSTRUCTED UNDER U-2507A | Pre-STI (Transition)
U-2507B | Highway | Pre-STI (Historic) | SR 2467 (MALLARD CREEK ROAD) | SR 2665 (W.T. HARRIS BOULEVARD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) | 1.945 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE
U-2509 | Highway | STI (Prioritization) | US 74 (INDEPENDENCE BOULEVARD) | WEST OF IDLEWILD ROAD TO I-485. UPGRADE ROADWAY TO EXPRESSWAY WITH EXPRESS LANES AND CONSTRUCT IMPROVEMENTS ON PARALLEL ROUTES. | 6.62 | MECKLENBURG | 10 | Charlotte Regional TPO
U-2509AA | Highway | STI (Prioritization) | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 64401000 | FY 2025: 7806000; FY 2026: 18735000; FY 2027: 18735000; FY 2028: 12880000; FY 2029: 6245000
U-2509AA | Highway | STI (Prioritization) | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | UTILITIES | 1800000 | FY 2025: 900000; FY 2026: 900000
U-2509AA | Highway | STI (Prioritization) | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | Statewide Mobility |  | NHP | CONSTRUCTION | 40400000 | FY 2029: 404000; FY 2030: 17481000; FY 2031: 12792000; FY 2032: 7416000; FY 2033: 2307000
U-2509AB | Highway | STI (Prioritization) | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 66499000 | FY 2025: 8061000; FY 2026: 19345000; FY 2027: 19345000; FY 2028: 6448000; FY 2029: 13300000
U-2509AB | Highway | STI (Prioritization) | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | UTILITIES | 2700000 | FY 2025: 1350000; FY 2026: 1350000
U-2509AB | Highway | STI (Prioritization) | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | Statewide Mobility |  | NHP | CONSTRUCTION | 45306000 | FY 2029: 453000; FY 2030: 19161000; FY 2031: 14235000; FY 2032: 8405000; FY 2033: 3052000
U-2509AC | Highway | STI (Prioritization) | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 0.7 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C11 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 5800000 | FY 2025: 696000; FY 2026: 1682000; FY 2027: 1682000; FY 2028: 580000; FY 2029: 1160000
U-2509AC | Highway | STI (Prioritization) | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 0.7 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C11 | Statewide Mobility |  | NHP | UTILITIES | 3500000 | FY 2025: 1750000; FY 2026: 1750000
U-2509AC | Highway | STI (Prioritization) | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 0.7 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C11 | Statewide Mobility |  | NHP | CONSTRUCTION | 20000000 | FY 2029: 204000; FY 2030: 12444000; FY 2031: 6528000; FY 2032: 824000
U-2509AD | Highway | STI (Prioritization) | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 0.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 51601000 | FY 2025: 6255000; FY 2026: 15011000; FY 2027: 15011000; FY 2028: 5004000; FY 2029: 10320000
U-2509AD | Highway | STI (Prioritization) | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 0.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | UTILITIES | 1800000 | FY 2025: 900000; FY 2026: 900000
U-2509AD | Highway | STI (Prioritization) | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 0.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | Statewide Mobility |  | NHP | CONSTRUCTION | 26999000 | FY 2029: 270000; FY 2030: 12810000; FY 2031: 8630000; FY 2032: 4756000; FY 2033: 533000
U-2509B | Highway | STI (Prioritization) | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 0.95 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 26001000 | FY 2026: 3152000; FY 2027: 7564000; FY 2028: 7564000; FY 2029: 2521000; FY 2030: 5200000
U-2509B | Highway | STI (Prioritization) | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 0.95 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | UTILITIES | 0 | FY 2025: 0; FY 2026: 0
U-2509B | Highway | STI (Prioritization) | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 0.95 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M1 | Statewide Mobility |  | NHP | CONSTRUCTION | 25251000 | FY 2029: 7932000; FY 2030: 10198000; FY 2031: 5613000; FY 2032: 1508000
U-2509C | Highway | STI (Prioritization) | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 2.45 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M2 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 39200000
U-2509C | Highway | STI (Prioritization) | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 2.45 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M2 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 5600000
U-2509C | Highway | STI (Prioritization) | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 2.45 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT M2 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 70349000
U-2509D | Highway | STI (Prioritization) | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 3.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 92300000
U-2509D | Highway | STI (Prioritization) | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 3.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 10300000
U-2509D | Highway | STI (Prioritization) | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 3.23 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 202205000
U-2509E | Highway | STI (Prioritization) | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 3.39 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | RIGHT-OF-WAY | 43200000 | [10 empty] | 43200000
U-2509E | Highway | STI (Prioritization) | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 3.39 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | UTILITIES | 3500000 | [10 empty] | 3500000
U-2509E | Highway | STI (Prioritization) | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 3.39 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | Not Funded |  | T | CONSTRUCTION | 61200000 | [10 empty] | 61200000
U-2509EA | Highway | STI (Prioritization) | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 5568000 | FY 2025: 1392000; FY 2026: 2784000; FY 2027: 1392000
U-2509EA | Highway | STI (Prioritization) | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 3000000 | FY 2025: 750000; FY 2026: 1500000; FY 2027: 750000
U-2509EA | Highway | STI (Prioritization) | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 3768000 | FY 2028: 38000; FY 2029: 2818000; FY 2030: 912000
U-2509EA | Highway | STI (Prioritization) | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 2029000 | FY 2028: 986000; FY 2029: 912000; FY 2030: 131000
U-2509EB | Highway | STI (Prioritization) | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.63 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | RIGHT-OF-WAY | 1200000 | FY 2025: 300000; FY 2026: 600000; FY 2027: 300000
U-2509EB | Highway | STI (Prioritization) | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.63 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | UTILITIES | 190000 | FY 2025: 95000; FY 2026: 95000
U-2509EB | Highway | STI (Prioritization) | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.63 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENT C9 | Division 10 |  | T | CONSTRUCTION | 12000000 | FY 2028: 5880000; FY 2029: 5040000; FY 2030: 1080000
U-2519 | Highway | STI (Prioritization) | I-295 (FAYETTEVILLE OUTER LOOP) | I-95 SOUTH OF FAYETTEVILLE TO WEST OF NC 24/87 (BRAGG BOULEVARD). FREEWAY ON NEW LOCATION. | 22.5 | CUMBERLAND, ROBESON | 6 | Fayetteville Area MPO, Lumber River RPO | [5 empty] | 544102000
U-2519AA | Highway | STI (Prioritization) | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 1.88 | ROBESON, CUMBERLAND | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | NHP | GARVEE CON | 123812000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000
U-2519AA | Highway | STI (Prioritization) | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 1.88 | ROBESON, CUMBERLAND | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | NHP | CONSTRUCTION | 125600000 | FY 2024: 41868000
U-2519AA | Highway | STI (Prioritization) | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 1.88 | ROBESON, CUMBERLAND | 6 | Fayetteville Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | Region C |  | S(M) | CONSTRUCTION | 11030000
U-2519AB | Highway | STI (Prioritization) | I-295 | SOUTH OF SR 1118 (PARKTON ROAD) TO SOUTH OF SR 1003 (CAMDEN ROAD). | 4.88 | CUMBERLAND | 6 | Fayetteville Area MPO, Lumber River RPO | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA. | Region C
U-2519BA | Highway | STI (Prioritization) | I-295 | SOUTH OF SR 1003 (CAMDEN ROAD) TO SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD). | 3.96 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | NHP | CONSTRUCTION | 161113000 | FY 2024: 34451000; FY 2025: 26920000; FY 2026: 15908000
U-2519BB | Highway | STI (Prioritization) | I-295 | SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD) TO SOUTH OF US 401. | 0.79 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | NHP | CONSTRUCTION | 55880000 | FY 2024: 17323000; FY 2025: 12294000; FY 2026: 3352000
U-2519CA | Highway | STI (Prioritization) | I-295 | SOUTH OF US 401 TO SOUTH OF SR 1400 (CLIFFDALE ROAD). | 2.63 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. | Statewide Mobility
U-2519CB | Highway | Transition | I-295 | SOUTH OF SR 1400 (CLIFFDALE ROAD) TO EAST OF SR 1415 (YADKIN ROAD). | 4.69 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
U-2519DA | Highway | Pre-STI (Historic) | I-295 | EAST OF SR 1415 (YADKIN ROAD) TO WEST OF NC24/NC 87 (BRAGG BOULEVARD). |  | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
U-2519F | Highway | Pre-STI (Historic) | I-295 | FAYETTEVILLE OUTER LOOP ITS. | 34 | CUMBERLAND, ROBESON | 6 | Fayetteville Area MPO, Lumber River RPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 6000000 | FY 2025: 2952000; FY 2026: 3048000
U-2523 | Highway | STI (Prioritization) | NC 279 | NC 7 TO WEST OF NC 275 IN DALLAS. WIDEN TO MULTI-LANES. | 3.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  |  |  | 17423000
U-2523A | Highway | Pre-STI (Historic) | NC 279 | NC 7 (OZARK AVENUE) TO NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD). |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
U-2523B | Highway | STI (Prioritization) | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 1.94 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F |  | BGANY | RIGHT-OF-WAY | 12500000 | FY 2026: 5714000; FY 2027: 4286000; FY 2028: 1250000; FY 2029: 1250000
U-2523B | Highway | STI (Prioritization) | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 1.94 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F |  | BGANY | UTILITIES | 2300000 | FY 2026: 1150000; FY 2027: 1150000
U-2523B | Highway | STI (Prioritization) | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 1.94 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | Region F |  | BGANY | CONSTRUCTION | 20200000 | FY 2028: 1537000; FY 2029: 9042000; FY 2030: 6761000; FY 2031: 2860000
U-2524 | Highway | STI (Prioritization) | I-73 / I-840 / FUTURE I-840 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF I-85 TO LAWNDALE DRIVE IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 15 | GUILFORD | 7 | Greensboro Urban Area MPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 635532000
U-2524AA | Highway | Pre-STI (Historic) | SR 1546 (GUILFORD COLLEGE ROAD) | SOUTH OF SR 1541 (WENDOVER AVENUE) TO NORTH OF SR 1560 (SAPP ROAD) | 1.244 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AB | Highway | Pre-STI (Historic) | I-73 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF I-85 NEAR SR 1129 (GROOMETOWN ROAD) TO NORTH OF SR 4121 (HIGH POINT ROAD) | 4.207 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AC | Highway | Pre-STI (Historic) | I-73 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF SR 4121 (HIGH POINT ROAD) TO SOUTH OF I-40 | 3.471 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524AE | Highway | Pre-STI (Historic) | I-73 / US 421 | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED HIGH POINT ROAD RELOCATION | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION
U-2524BA | Highway | Pre-STI (Historic) | I-73 / I-840 | GREENSBORO WESTERN LOOP, SOUTH OF I-40 TO NORTH OF SR 2147 (WEST FRIENDLY AVENUE) | 2.429 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524BB | Highway | Pre-STI (Historic) | I-73 / I-840 | GREENSBORO WESTERN LOOP, NORTH OF SR 2147 (WEST FRIENDLY AVENUE) TO NORTH OF SR 2176 (BRYAN BOULEVARD) | 1.872 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2524BC | Highway | Transition | I-73 / I-840 | SR 2085 (BRYAN BOULEVARD) INTERCHANGE MODIFICATIONS, INCLUDING AUXILIARY LANES, ITS, AND INMAN ROAD BRIDGE REPLACEMENT. | 2 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE | Pre-STI (Transition)
U-2524C | Highway | Pre-STI (Historic) | FUTURE I-840 | GREENSBORO WESTERN LOOP, NORTH OF SR 2176 (BRYAN BOULEVARD) TO US 220 (BATTLEGROUND AVENUE) | 3.54 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024 | Pre-STI (Transition) |  | NHP | GARVEE CON | 54285000 | FY 2024: 10857000
U-2524D | Highway | STI (Prioritization) | FUTURE I-840 | GREENSBORO WESTERN LOOP, US 220 (BATTLEGROUND AVENUE) TO SR 2303 (LAWNDALE DRIVE) | 1.64 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
U-2524E | Highway | Pre-STI (Historic) | I-73 / I-840 | GREENSBORO WESTERN LOOP, ITS INSTALLATION |  | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2525 | Highway | STI (Prioritization) | I-785 / I-840; FUTURE I-785; FUTURE I-840 | GREENSBORO EASTERN LOOP, LAWNDALE DRIVE TO NORTH OF I-40 / I-85 IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 12.6 | GUILFORD | 7 | Greensboro Urban Area MPO | [5 empty] | 367708000
U-2525A | Highway | Pre-STI (Historic) | I-785 / I-840 | GREENSBORO EASTERN LOOP, SOUTH OF SR 3041 (CLAPP FARMS ROAD) TO US 70 RELOCATION | 1.809 | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-2525B | Highway | Transition | FUTURE I-785 / FUTURE I-840 | GREENSBORO EASTERN LOOP, US 70 RELOCATION TO US 29 NORTH OF GREENSBORO | 4.59 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
U-2525C | Highway | STI (Prioritization) | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 1.89 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | ENGINEERING | 8340000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 1112000
U-2525C | Highway | STI (Prioritization) | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 1.89 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | BUILD NC CON | 37710000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 5028000
U-2525C | Highway | STI (Prioritization) | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 1.89 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | CONSTRUCTION | 57121000
U-2525CA | Highway | STI (Prioritization) | US 70 WENDOVER AVENUE | US 70 (WENDOVER AVENUE) AT US 29 INTERCHANGE. REPLACE AND UPGRADE OVERHEAD SIGNS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  |  |  | T | ENGINEERING | 100000 | FY 2024: 100000
U-2525CA | Highway | STI (Prioritization) | US 70 WENDOVER AVENUE | US 70 (WENDOVER AVENUE) AT US 29 INTERCHANGE. REPLACE AND UPGRADE OVERHEAD SIGNS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  |  |  | T | CONSTRUCTION | 1550000 | FY 2025: 100000; FY 2026: 1450000
U-2525D | Highway | STI (Prioritization) | FUTURE I-840 | INTERCHANGE AT PROPOSED CONE BOULEVARD EXTENSION | 15.4 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 15000000 | [10 empty] | 15000000
U-2530 | Highway | STI (Prioritization) | NC 127 | WIDEN NC 127 TO MULTI-LANES, SR 1132 TO SR 1008. UPGRADE AND EXTEND SR 1213 (CURRENTLY NC 127), PROPOSED US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182. | 4.5 | CATAWBA | 12 | Greater Hickory MPO | [5 empty] | 12399000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 3.14 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 23900000 | FY 2025: 7284000; FY 2026: 10926000; FY 2027: 910000; FY 2028: 2390000; FY 2029: 2390000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 3.14 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | UTILITIES | 3800000 | FY 2025: 1900000; FY 2026: 1900000
U-2530A | Highway | STI (Prioritization) | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 3.14 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGANY | CONSTRUCTION | 25499000 | FY 2028: 7636000; FY 2029: 9401000; FY 2030: 6453000; FY 2031: 2009000
U-2530B | Highway | Pre-STI (Historic) | NC 127 | NORTH OF US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182 |  | CATAWBA | 12 | Greater Hickory MPO | COMPLETE
U-2561 | Highway | STI (Prioritization) | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. WIDEN TO MULTI-LANES. | 0.61 | NASH | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 6745000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 1.65 | NASH | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | RIGHT-OF-WAY | 3131000 | FY 2026: 527000; FY 2027: 1582000; FY 2028: 396000; FY 2029: 313000; FY 2030: 313000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 1.65 | NASH | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | UTILITIES | 2968000 | FY 2026: 1484000; FY 2027: 1484000
U-2561C | Highway | STI (Prioritization) | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 1.65 | NASH | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BGLT5 | CONSTRUCTION | 7601000 | FY 2028: 2339000; FY 2029: 4095000; FY 2030: 1167000
U-2567 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 1 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1500000
U-2567 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 1 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 21200000
U-2567 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 1 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-2567 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 1 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25200000
U-2579 | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTI-LANE FREEWAY ON NEW LOCATION. | 17.1 | FORSYTH | 9 | Winston-Salem Area TPO | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 588926000
U-2579 | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTI-LANE FREEWAY ON NEW LOCATION. | 17.1 | FORSYTH | 9 | Winston-Salem Area TPO | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  | T | RIGHT-OF-WAY | 175000 | FY 2025: 175000
U-2579AA | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO I-40 | 0.87 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | CONSTRUCTION | 144951000 | FY 2024: 40567000; FY 2025: 33028000; FY 2026: 24396000; FY 2027: 13161000
U-2579AB | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 3.27 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | NHP | GARVEE CON | 77220000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 15444000
U-2579AB | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 3.27 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | NHP | CONSTRUCTION | 213147000 | FY 2024: 42523000; FY 2025: 34648000; FY 2026: 31503000
U-2579AB | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 3.27 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | Region D |  | S(M) | CONSTRUCTION | 20000000 | FY 2024: 5000000; FY 2025: 5000000
U-2579B | Highway | Transition | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158 | 2.92 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026 | Pre-STI (Transition) |  | NHP | GARVEE CON | 68971000 | FY 2024: 9853000; FY 2025: 9853000; FY 2026: 9853000
U-2579BA | Highway | Transition | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158. STREAM RELOCATION. | 2.92 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | NHP | CONSTRUCTION | 9300000
U-2579BB | Highway | Transition | FUTURE I-74 | CONSTRUCT NOISE WALL | 2.92 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | UTILITIES | 234000
U-2579BB | Highway | Transition | FUTURE I-74 | CONSTRUCT NOISE WALL | 2.92 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | CONSTRUCTION | 2855000 | FY 2024: 1354000
U-2579C | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 1.41 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | NHP | GARVEE ROW | 6138000 | 558000 | 558000 | 558000 | 558000 | 558000 | 558000 | 558000
U-2579C | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 1.41 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 11662000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 1561000
U-2579C | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 1.41 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | NHP | CONSTRUCTION | 15560000
U-2579D | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | 3.2 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 42380000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000
U-2579E | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, SR 2211 (BAUX MOUNTAIN ROAD) TO NC 8 | 2.21 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 33462000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000
U-2579F | Highway | STI (Prioritization) | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, NC 8 TO WEST OF NC 66 (UNIVERSITY PARKWAY) | 2.44 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 26767000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
U-2579G | Highway | Pre-STI (Historic) | SR 2667 (HASTINGS HILL ROAD) | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, BRIDGE NO. 366 OVER US 421 / NC 150 / BUSINESS 40 |  | FORSYTH | 9 | Winston-Salem Area TPO | PROJECT COMPLETE
U-2581 | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 4.5 | GUILFORD | 7 | Greensboro Urban Area MPO | [5 empty] | 6281000
U-2581A | Highway | STI (Prioritization) | US 70 | SR 2851 (PENRY ROAD) TO SR 2828 (WILLOWLAKE ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | ENGINEERING | 1414000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | ENGINEERING | 195000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 26000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC ROW | 2618000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 11910000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 1588000
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 13000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0
U-2581BA | Highway | STI (Prioritization) | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | CONSTRUCTION | 3612000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2113000 | [10 empty] | 2113000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 626000 | [10 empty] | 626000
U-2581BB | Highway | STI (Prioritization) | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 8200000 | [10 empty] | 8200000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3040000 | [10 empty] | 3040000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 901000 | [10 empty] | 901000
U-2581BC | Highway | STI (Prioritization) | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 11800000 | [10 empty] | 11800000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  |  |  | 9483000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | ENGINEERING | 4230000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | ENGINEERING | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 8000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC ROW | 3510000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC CON | 16875000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 2250000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | CONSTRUCTION | 5985000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | CONSTRUCTION | 900000 | FY 2024: 400000
U-2714 | Highway | STI (Prioritization) | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | L | CONSTRUCTION | 1327000
U-2719 | Highway | STI (Prioritization) | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5.58 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  |  |  | 262047000
U-2719 | Highway | STI (Prioritization) | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5.58 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHP | GARVEE ROW | 34749000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2311000
U-2719 | Highway | STI (Prioritization) | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5.58 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 158558000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000
U-2729 | Highway | STI (Prioritization) | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 0.42 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 9 |  |  |  | 3710000
U-2729 | Highway | STI (Prioritization) | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 0.42 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | ENGINEERING | 702000 |  | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000
U-2729 | Highway | STI (Prioritization) | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 0.42 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC ROW | 441000 |  | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-2729 | Highway | STI (Prioritization) | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 0.42 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC CON | 9660000 |  | 644000 | 644000 | 644000 | 644000 | 644000 | 644000 | 644000 | 644000 | 644000 | 3864000
U-2729 | Highway | STI (Prioritization) | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 0.42 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | CONSTRUCTION | 3151000 | FY 2026: 3151000
U-2801 | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO ROBERTS ROAD IN ASHEVILLE. WIDEN TO MULTI-LANES. | 7.3 | BUNCOMBE | 13 | French Broad River MPO | [5 empty] | 22226000
U-2801AA | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 2.77 | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 92500000
U-2801AA | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 2.77 | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 10200000
U-2801AA | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 2.77 | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 39400000
U-2801AB | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 2.68 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | BGANY | RIGHT-OF-WAY | 56599000 | FY 2028: 12349000; FY 2029: 16465000; FY 2030: 16465000; FY 2031: 5660000; FY 2032: 5660000
U-2801AB | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 2.68 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | BGANY | UTILITIES | 7100000 | FY 2028: 3550000; FY 2029: 3550000
U-2801AB | Highway | STI (Prioritization) | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 2.68 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | BGANY | CONSTRUCTION | 53499000 | FY 2031: 12536000; FY 2032: 16115000; FY 2033: 13473000 | 11375000
U-2801B | Highway | Pre-STI (Historic) | US 25A (SWEETEN CREEK ROAD) | SR 3081 (ROCK HILL ROAD) TO SR 3079 (ROBERTS ROAD) | 1.473 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE
U-2810 | Highway | Pre-STI (Historic) | SR 1003 (CAMDEN ROAD) | NC 59 (HOPE MILLS ROAD) TO SR 1007 (OWEN DRIVE) IN FAYETTEVILLE. WIDEN ROADWAY TO MULTI-LANES, PART ON NEW LOCATION. | 4.2 | CUMBERLAND | 6 | Fayetteville Area MPO | [5 empty] | 53156000
U-2810A | Highway | Pre-STI (Historic) | SR 1003 (CAMDEN ROAD) | NC 59 (HOPE MILLS ROAD) TO NC 162 (HOPE MILLS BYPASS). | 1.243 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
U-2810B | Highway | Pre-STI (Historic) | SR 1003 (CAMDEN ROAD) | NC 162 (HOPE MILLS BYPASS TO EAST OF CSX RAILROAD. | 1.429 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
U-2810C | Highway | Transition | SR 1003 (CAMDEN ROAD) | EAST OF CSX RAILROAD TO SR 1007 (OWEN DRIVE). | 1.62 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
U-2817 | Highway | STI (Prioritization) | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  |  |  | 60010000
U-2817 | Highway | STI (Prioritization) | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BG5200 | RIGHT-OF-WAY | 22800000
U-2817 | Highway | STI (Prioritization) | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BG50200 | UTILITIES | 9000000 | FY 2025: 9000000
U-2817 | Highway | STI (Prioritization) | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BG5200 | UTILITIES | 3972000
U-2817 | Highway | STI (Prioritization) | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BG50200 | CONSTRUCTION | 104300000 | FY 2026: 5149000; FY 2027: 32005000; FY 2028: 27990000; FY 2029: 22498000; FY 2030: 16658000
U-2823 | Highway | STI (Prioritization) | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 4.07 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3775000
U-2823 | Highway | STI (Prioritization) | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 4.07 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 40599000
U-2823 | Highway | STI (Prioritization) | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 4.07 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1500000
U-2823 | Highway | STI (Prioritization) | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 4.07 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 107700000
U-2827 | Highway | STI (Prioritization) | US 158 / US 421 / NC 150 / BUSINESS 40 | I-40 TO WEST OF US 158 IN WINSTON-SALEM. PAVEMENT REHABILITATION, REPLACE BRIDGES 330178, 330269, 330278, 330286, 330288 330291, 330293, 330305, 330312 330313, 330336 AND VARIOUS SAFETY IMPROVEMENTS. | 8 | FORSYTH | 9 | Winston-Salem Area TPO | [5 empty] | 189167000
U-2827A | Highway | Pre-STI (Historic) | US 421 / BUSINESS 40 | WEST OF OLD VINEYARD ROAD TO EAST OF US 158 (STRATFORD ROAD) |  | FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE
U-2827B | Highway | STI (Prioritization) | US 158 / US 421 / NC 150 / BUSINESS 40 | WEST OF FOURTH STREET TO EAST OF CHURCH STREET | 1.2 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT | Region D
U-2827C | Highway | Pre-STI (Historic) | US 158 / US 421 / NC 150 / BUSINESS 40 | WEST OF US 311 (MARTIN LUTHER KING, JR. DRIVE) TO WEST OF US 158 |  | FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE
U-2901 | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD) IN APEX. WIDEN TO A MULTI-LANE CURB AND GUTTER FACILITY. | 2.8 | WAKE | 5 | Capital Area MPO | PROJECTS U-2901AA AND AB COMPLETE |  |  |  |  | 4860000
U-2901B | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 1.73 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 12900000 | FY 2028: 2814000; FY 2029: 3753000; FY 2030: 3753000; FY 2031: 1290000; FY 2032: 1290000
U-2901B | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 1.73 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 1700000 | FY 2028: 850000; FY 2029: 850000
U-2901B | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 1.73 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 20002000 | FY 2031: 5486000; FY 2032: 6961000; FY 2033: 4959000 | 2596000
U-2901BA | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 830000 | FY 2027: 272000; FY 2028: 362000; FY 2029: 30000; FY 2030: 83000; FY 2031: 83000
U-2901BA | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 140000 | FY 2027: 140000
U-2901BA | Highway | STI (Prioritization) | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 17000000 | FY 2029: 5831000; FY 2030: 6920000; FY 2031: 4249000
U-2925 | Highway | Pre-STI (Historic) | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE) TO SR 4325 (MARTIN LUTHER KING, JR. DRIVE) IN WINSTON-SALEM. MULTI-LANE FACILITY ON NEW LOCATION. | 1.81 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT COMPLETE | Pre-STI (Transition) |  |  |  | 93832000
U-2925C | Highway | Locally Selected | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 1.09 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 362000
U-2925C | Highway | Locally Selected | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 1.09 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | ENGINEERING | 91000
U-2925C | Highway | Locally Selected | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 1.09 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1086000 | FY 2024: 1086000
U-2925C | Highway | Locally Selected | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 1.09 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 272000 | FY 2024: 272000
U-3109 | Highway | STI (Prioritization) | NC 119 | NC 119 RELOCATION, I-85 TO SOUTH OF SR 1918 (MRS. WHITE ROAD) IN MEBANE. FOUR-TO-SIX-LANE FACILITY ON NEW LOCATION. | 4.2 | ALAMANCE | 7 | Burlington-Graham MPO | [5 empty] | 84313000
U-3109A | Highway | STI (Prioritization) | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 3.01 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | ENGINEERING | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 48000
U-3109A | Highway | STI (Prioritization) | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 3.01 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 18195000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000
U-3109A | Highway | STI (Prioritization) | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 3.01 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 24772000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 3309000
U-3109B | Highway | STI (Prioritization) | NC 119 | NC 119 RELOCATION, NORTH OF SR 1921 (MEBANE ROGERS ROAD) TO SOUTH OF SR 1918 (MRS. WHITE ROAD) | 1.49 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 5835000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 778000
U-3110 | Highway | Pre-STI (Historic) | NEW ROUTE | NEW ROUTE, US 70 TO NC 100 IN ELON. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 2.1 | ALAMANCE | 7 | Burlington-Graham MPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 27033000
U-3110A | Highway | Pre-STI (Historic) | NEW ROUTE | US 70 TO NORTH OF SR 1309 (WESTBROOK AVENUE) | 0.87 | ALAMANCE | 7 | Burlington-Graham MPO | COMPLETE
U-3110B | Highway | Pre-STI (Historic) | NEW ROUTE | IMPROVEMENTS ON SR 1311 (COOK ROAD), SR 1309 (WESTBROOK AVENUE) TO NC 100, PART ON NEW LOCATION | 0.9 | ALAMANCE | 7 | Burlington-Graham MPO | COMPLETE; GARVEE BOND FUNDING $10.5 MILLION; PAYBACK FY 2011 - FY 2022 | Pre-STI (Transition) |  | BG5200 | GARVEE CON | 3444000
U-3125 | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | I-40 TO I-795. UPGRADE ROADWAY TO INTERSTATE STANDARDS, PART ON NEW LOCATION. | 24.3 | WAYNE, DUPLIN, SAMPSON | 3, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO, Mid-Carolina RPO | [5 empty] | 1000000
U-3125A | Highway | STI (Prioritization) | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 5.31 | DUPLIN, SAMPSON | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 7183000 | [10 empty] | 7183000
U-3125A | Highway | STI (Prioritization) | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 5.31 | DUPLIN, SAMPSON | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | UTILITIES | 2238000 | [10 empty] | 2238000
U-3125A | Highway | STI (Prioritization) | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 5.31 | DUPLIN, SAMPSON | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | CONSTRUCTION | 103500000 | [10 empty] | 103500000
U-3125B | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 6.73 | WAYNE, DUPLIN | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 25266000 | [10 empty] | 25266000
U-3125B | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 6.73 | WAYNE, DUPLIN | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | UTILITIES | 10475000 | [10 empty] | 10475000
U-3125B | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 6.73 | WAYNE, DUPLIN | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | CONSTRUCTION | 73300000 | [10 empty] | 73300000
U-3125C | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 3.61 | WAYNE | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A |  | NHP | RIGHT-OF-WAY | 100000 | FY 2026: 100000
U-3125C | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 3.61 | WAYNE | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A |  | NHP | UTILITIES | 138000 | FY 2026: 138000
U-3125C | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 3.61 | WAYNE | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | Region A |  | NHP | CONSTRUCTION | 13300000 | FY 2028: 3378000; FY 2029: 6334000; FY 2030: 3588000
U-3125D | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 2.42 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | RIGHT-OF-WAY | 13530000 | FY 2028: 1412000; FY 2029: 5647000; FY 2030: 3765000; FY 2031: 1353000; FY 2032: 1353000
U-3125D | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 2.42 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | UTILITIES | 2172000 | FY 2028: 1086000; FY 2029: 1086000
U-3125D | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 2.42 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | CONSTRUCTION | 59400000 | FY 2031: 11140000; FY 2032: 18609000; FY 2033: 14921000 | 14730000
U-3125E | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 1.82 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 35788000 | [10 empty] | 35788000
U-3125E | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 1.82 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 1513000 | [10 empty] | 1513000
U-3125E | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 1.82 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 135500000 | [10 empty] | 135500000
U-3125F | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 3.48 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 20760000 | [10 empty] | 20760000
U-3125F | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 3.48 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 4729000 | [10 empty] | 4729000
U-3125F | Highway | STI (Prioritization) | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 3.48 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 62700000 | [10 empty] | 62700000
U-3301 | Highway | Pre-STI (Historic) | NC 63 (LEICESTER HIGHWAY) | SR 1615 (GILBERT ROAD) TO WEST OF SR 1004 (NEWFOUND ROAD) IN ASHEVILLE. WIDEN TO MULTI-LANES, SOME RELOCATION. | 4.32 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION - DESIGN BUILD PROJECT | Pre-STI (Transition) |  |  |  | 55129000
U-3308 | Highway | Transition | NC 55 (ALSTON AVENUE) | NC 147 (DURHAM FREEWAY) TO US 70 BUSINESS / NC 98 (HOLLOWAY STREET) IN DURHAM. WIDEN TO FOUR-LANE DIVIDED FACILITY FROM NC 147 TO MAIN STREET AND REPLACE NORFOLK SOUTHERN RAILROAD BRIDGES. MODERNIZE FROM MAIN STREET TO US 70 BUSINESS / NC 98 (HOLLOWAY ST | 0.9 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 41348000
U-3326 | Highway | Pre-STI (Historic) | US 29 BUSINESS/US 158 (FREEWAY DRIVE) | SOUTH SCALES STREET TO NC 14 IN REIDSVILLE. WIDEN TO MULTI-LANES. | 5.6 | ROCKINGHAM | 7 | Piedmont Triad RPO | [5 empty] | 101957000
U-3326A | Highway | Pre-STI (Historic) | US 29 BUSINESS (FREEWAY DRIVE) | SOUTH SCALES STREET TO SR 2686 (RICHARDSON DRIVE) | 1.86 | ROCKINGHAM | 7 | Piedmont Triad RPO | COMPLETE
U-3326B | Highway | Pre-STI (Historic) | US 29 BUSINESS / US 158 (FREEWAY DRIVE) | SR 2686 (RICHARDSON DRIVE) TO NC 14 | 3.98 | ROCKINGHAM | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION
U-3338 | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO | [5 empty] | 76486000
U-3338B | Highway | Transition | SR 1175 (KERR AVENUE) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY). | 1.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED. | Pre-STI (Transition)
U-3338C | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MARTIN LUTHER KING, JR. PARKWAY). | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BGANY | CONSTRUCTION | 26800000 | FY 2028: 1640000; FY 2029: 11276000; FY 2030: 8812000; FY 2031: 5072000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 3.09 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  |  |  | 1520000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 3.09 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | RIGHT-OF-WAY | 7901000 | FY 2024: 79000; FY 2025: 2231000; FY 2026: 2231000; FY 2027: 1859000; FY 2028: 1501000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 3.09 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | UTILITIES | 6300000 | FY 2026: 3150000; FY 2027: 3150000
U-3400 | Highway | STI (Prioritization) | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 3.09 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | T | CONSTRUCTION | 34555000 | FY 2029: 10699000; FY 2030: 12308000; FY 2031: 8576000; FY 2032: 2972000
U-3403 | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD) | NC 280 TO NC 112 (SARDIS ROAD). WIDEN TO MULTI-LANES. | 9.1 | BUNCOMBE, HENDERSON | 13, 14 | French Broad River MPO | [5 empty] | 16273000
U-3403A | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). |  | BUNCOMBE, HENDERSON | 13, 14 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9000000 | [10 empty] | 9000000
U-3403A | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). |  | BUNCOMBE, HENDERSON | 13, 14 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 17700000 | [10 empty] | 17700000
U-3403B | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 3.63 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 23800000 | [10 empty] | 23800000
U-3403B | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 3.63 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | UTILITIES | 3900000 | [10 empty] | 3900000
U-3403B | Highway | STI (Prioritization) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 3.63 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 59700000 | [10 empty] | 59700000
U-3403C | Highway | Pre-STI (Historic) | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NORTH OF BLUE RIDGE PARKWAY TO NC 112 (SARDIS ROAD) |  | BUNCOMBE | 13 | French Broad River MPO | COMPLETE
U-3415 | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | SR 1445 (DERITA ROAD) TO US 29/601 BYPASS. WIDEN TO MULTI-LANES. | 6.1 | CABARRUS | 10 | Cabarrus-Rowan MPO | [5 empty] | 2732000
U-3415A | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 2.96 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | T | RIGHT-OF-WAY | 12900000 | FY 2026: 543000; FY 2027: 3259000; FY 2028: 3259000; FY 2029: 3259000; FY 2030: 2580000
U-3415A | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 2.96 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | T | UTILITIES | 900000 | FY 2026: 450000; FY 2027: 450000
U-3415A | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 2.96 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | T | CONSTRUCTION | 27712000 | FY 2029: 277000; FY 2030: 11362000; FY 2031: 9145000; FY 2032: 4988000; FY 2033: 1940000
U-3415B | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9900000 | [10 empty] | 9900000
U-3415B | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | UTILITIES | 13200000 | [10 empty] | 13200000
U-3415B | Highway | STI (Prioritization) | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | T | CONSTRUCTION | 32900000 | [10 empty] | 32900000
U-3422 | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 3.61 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  |  |  | 2500000
U-3422 | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 3.61 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | BGANY | RIGHT-OF-WAY | 16175000
U-3422 | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 3.61 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | BGANY | UTILITIES | 5225000 | FY 2025: 2400000
U-3422A | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | FROM PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO JUST WEST OF SR 1112 (ROCKFISH ROAD). | 1.53 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. | Division 6 |  | T | CONSTRUCTION | 19971000 | FY 2025: 3195000; FY 2026: 7789000; FY 2027: 5991000; FY 2028: 2996000
U-3422A | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | FROM PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO JUST WEST OF SR 1112 (ROCKFISH ROAD). | 1.53 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. | Division 6 |  | O | CONSTRUCTION | 7629000 | FY 2025: 7629000
U-3422B | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | 1.99 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. | Division 6 |  | T | BUILD NC CON | 9015000 |  |  | 1202000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 3606000
U-3422B | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | 1.99 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. | Division 6 |  | T | CONSTRUCTION | 34139000 | FY 2026: 2051000; FY 2027: 11519000; FY 2028: 9873000; FY 2029: 6994000; FY 2030: 3702000
U-3422B | Highway | STI (Prioritization) | SR 1003 (CAMDEN ROAD) | FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | 1.99 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $7,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. | Division 6 |  | O | CONSTRUCTION | 13861000 | FY 2026: 13861000
U-3431 | Highway | STI (Prioritization) | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO HAVELOCK BYPASS. CONSTRUCT ROAD IMPROVEMENTS. | 3.05 | CRAVEN | 2 | Down East RPO |  | Division 2 |  |  |  | 1450000
U-3431 | Highway | STI (Prioritization) | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO HAVELOCK BYPASS. CONSTRUCT ROAD IMPROVEMENTS. | 3.05 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 17300000 | FY 2026: 865000; FY 2027: 10380000; FY 2028: 2595000; FY 2029: 1730000; FY 2030: 1730000
U-3431 | Highway | STI (Prioritization) | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO HAVELOCK BYPASS. CONSTRUCT ROAD IMPROVEMENTS. | 3.05 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | UTILITIES | 3000000 | FY 2026: 1500000; FY 2027: 1500000
U-3431 | Highway | STI (Prioritization) | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO HAVELOCK BYPASS. CONSTRUCT ROAD IMPROVEMENTS. | 3.05 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 45001000 | FY 2029: 2216000; FY 2030: 16681000; FY 2031: 13667000; FY 2032: 9315000; FY 2033: 3122000
U-3440 | Highway | Transition | NC 3 | WEST SIDE BYPASS TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | 2.58 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 48456000
U-3440 | Highway | Transition | NC 3 | WEST SIDE BYPASS TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | 2.58 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T | CONSTRUCTION | 2500000 | FY 2025: 2500000
U-3465 | Highway | Transition | SR 1121 (RAY ROAD) | NC 210 TO SR 1120 (OVERHILLS ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.48 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  |  |  | 40292000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 4.02 | UNION | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 18015000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 4.02 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | BGANY | RIGHT-OF-WAY | 40999000 | FY 2024: 410000; FY 2025: 11166000; FY 2026: 11576000; FY 2027: 9647000; FY 2028: 8200000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 4.02 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | BGANY | UTILITIES | 3000000 | FY 2024: 1500000; FY 2025: 1500000
U-3467 | Highway | STI (Prioritization) | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 4.02 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | BGANY | CONSTRUCTION | 44898000 | FY 2027: 13722000; FY 2028: 16078000; FY 2029: 9786000; FY 2030: 5312000
U-3609 | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | SR 1560 (ROYAL AVENUE) TO NORTH OF SR 1572 (SAULSTON ROAD) IN GOLDSBORO. WIDEN TO MULTI-LANES. | 3 | WAYNE | 4 | Goldsboro Urban Area MPO | [5 empty] | 5806000
U-3609A | Highway | Transition | US 13 (BERKELEY BOULEVARD) | SR 1560 (ROYAL AVENUE) TO SR 1003 (NEW HOPE ROAD). | 1 | WAYNE | 4 | Goldsboro Urban Area MPO | COMPLETED. | Pre-STI (Transition)
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | ENGINEERING | 2400000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | RIGHT-OF-WAY | 23324000 | FY 2025: 7000000
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | UTILITIES | 3750000
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | BUILD NC CON | 12870000 |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 5148000
U-3609B | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Region A |  | T | CONSTRUCTION | 19200000 | FY 2025: 0; FY 2026: 10440000; FY 2027: 7300000; FY 2028: 1460000
U-3609BA | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF HOOD SWAMP ROAD. | 0.19 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 2030000
U-3615 | Highway | STI (Prioritization) | SR 1820 (SKEET CLUB ROAD) | US 311 TO NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. WIDEN TO FOUR- AND FIVE-LANE DIVIDED FACILITY. | 5.7 | GUILFORD | 7 | High Point Urban Area MPO | [5 empty] | 57587000
U-3615A | Highway | STI (Prioritization) | SR 1820 (SKEET CLUB ROAD) | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | 3.2 | GUILFORD | 7 | High Point Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5700000 | [10 empty] | 5700000
U-3615A | Highway | STI (Prioritization) | SR 1820 (SKEET CLUB ROAD) | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | 3.2 | GUILFORD | 7 | High Point Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 15500000 | [10 empty] | 15500000
U-3615B | Highway | Transition | SR 1820 (SKEET CLUB ROAD) | EAST OF SR 1818 (JOHNSON STREET) TO WEST OF NC 68 (EASTCHESTER DRIVE). WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY. | 3.18 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
U-3618 | Highway | STI (Prioritization) | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 1.81 | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  |  |  | 1258000
U-3618 | Highway | STI (Prioritization) | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 1.81 | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | BGANY | RIGHT-OF-WAY | 7701000 |  | 77000 | 2109000 | 2385000 | 1590000 | 770000 | 770000
U-3618 | Highway | STI (Prioritization) | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 1.81 | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | BGANY | UTILITIES | 2700000 | FY 2025: 1350000; FY 2026: 1350000
U-3618 | Highway | STI (Prioritization) | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 1.81 | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | BGANY | CONSTRUCTION | 35800000 | FY 2028: 3255000; FY 2029: 13964000; FY 2030: 10931000; FY 2031: 7650000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.35 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  |  |  | 1924000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.35 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  | T | RIGHT-OF-WAY | 2276000 | FY 2024: 1138000
U-3628 | Highway | STI (Prioritization) | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.35 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | Region E |  | NHP | CONSTRUCTION | 6900000 | FY 2025: 2553000; FY 2026: 3519000; FY 2027: 828000
U-3633 | Highway | STI (Prioritization) | NC 273 (SOUTH MAIN STREET) | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | 1.1 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | Region F |  |  |  | 22983000
U-3633 | Highway | STI (Prioritization) | NC 273 (SOUTH MAIN STREET) | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | 1.1 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | Region F |  | T | BUILD NC CON | 6315000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 842000
U-4007 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS TO SR 1326 (DRUMMER KELLUM ROAD) IN JACKSONVILLE. ADD ADDITIONAL LANES AND CONSTRUCT ROUTES ON NEW LOCATION. | 1.4 | ONSLOW | 3 | Jacksonville Urban Area MPO | [5 empty] | 93309000
U-4007A | Highway | Pre-STI (Historic) | SR 1702 (WEST HUFF DRIVE) | SR 1308 (BELL FORK ROAD) TO EAST OF SR 1470 (WESTERN BOULEVARD). | 1.4 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED.
U-4007B | Highway | Pre-STI (Historic) | JACKSONVILLE PARKWAY | COUNTRY CLUB ROAD TO SR 1470 (WESTERN BOULEVARD). | 0 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED.
U-4007C | Highway | STI (Prioritization) | US 17 | WESTERN BOULEVARD TO FAIRWAY DRIVE. | 0 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 34775000 | [10 empty] | 34775000
U-4007C | Highway | STI (Prioritization) | US 17 | WESTERN BOULEVARD TO FAIRWAY DRIVE. | 0 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 26300000 | [10 empty] | 26300000
U-4007D | Highway | STI (Prioritization) | US 17 | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | 0 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 32345000 | [10 empty] | 32345000
U-4007D | Highway | STI (Prioritization) | US 17 | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | 0 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 16600000 | [10 empty] | 16600000
U-4007E | Highway | STI (Prioritization) | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 0.7 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | Statewide Mobility |  | BG50200 | RIGHT-OF-WAY | 8099000 | FY 2028: 1564000; FY 2029: 2681000; FY 2030: 2234000; FY 2031: 810000; FY 2032: 810000
U-4007E | Highway | STI (Prioritization) | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 0.7 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | Statewide Mobility |  | BG50200 | UTILITIES | 430000 | FY 2028: 430000
U-4007E | Highway | STI (Prioritization) | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 0.7 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | Statewide Mobility |  | BG50200 | CONSTRUCTION | 12601000 | FY 2031: 4636000; FY 2032: 5686000; FY 2033: 2279000
U-4015 | Highway | STI (Prioritization) | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 1.6 | GUILFORD | 7 | Greensboro Urban Area MPO | [5 empty] | 7113000
U-4015A | Highway | STI (Prioritization) | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO AIRPARK ROAD IN GREENSBORO. WIDEN TO MULTILANES | 1.17 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT OF WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 11500000 | FY 2025: 2076000; FY 2026: 6561000; FY 2027: 2863000
U-4015B | Highway | Pre-STI (Historic) | SR 1556 (GALLIMORE DAIRY ROAD) | AIRPARK ROAD TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. |  | GUILFORD | 7 | Greensboro Urban Area MPO | COMPLETE
U-4024 | Highway | STI (Prioritization) | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 0.89 | UNION | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E |  |  |  | 2045000
U-4024 | Highway | STI (Prioritization) | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 0.89 | UNION | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E |  | T | RIGHT-OF-WAY | 3300000 | FY 2028: 360000; FY 2029: 1440000; FY 2030: 840000; FY 2031: 330000; FY 2032: 330000
U-4024 | Highway | STI (Prioritization) | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 0.89 | UNION | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E |  | T | UTILITIES | 770000 | FY 2028: 770000
U-4024 | Highway | STI (Prioritization) | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 0.89 | UNION | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | Region E |  | T | CONSTRUCTION | 13700000 | FY 2031: 3699000; FY 2032: 6576000; FY 2033: 3425000
U-4403 | Highway | STI (Prioritization) | US 401 (RAMSEY STREET) | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO NORTH OF SLOCUMB ROAD. WIDEN TO MULTI-LANES. | 8.5 | CUMBERLAND | 6 | Fayetteville Area MPO | [5 empty] | 5900000
U-4403A | Highway | STI (Prioritization) | US 401 BUSINESS | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3121000 | [10 empty] | 3121000
U-4403A | Highway | STI (Prioritization) | US 401 BUSINESS | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 7400000 | [10 empty] | 7400000
U-4403B | Highway | STI (Prioritization) | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 2.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 10123000
U-4403B | Highway | STI (Prioritization) | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 2.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 12020000
U-4403B | Highway | STI (Prioritization) | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 2.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 33003000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC ROW | 21885000 |  |  | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 10213000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC UTL | 20595000 |  |  | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 9611000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | RIGHT-OF-WAY | 5117000 |  |  | 0 | 0 | 0 | 693000 | 2212000 | 2212000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | UTILITIES | 4720000 | FY 2026: 0; FY 2027: 4720000
U-4403C | Highway | STI (Prioritization) | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | CONSTRUCTION | 34699000 | FY 2029: 4094000; FY 2030: 12826000; FY 2031: 10723000; FY 2032: 7056000
U-4404 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 1500000
U-4404 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | T | RIGHT-OF-WAY | 4391000 | FY 2028: 44000; FY 2029: 1796000; FY 2030: 1673000; FY 2031: 439000; FY 2032: 439000
U-4404 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | T | UTILITIES | 1020000 | FY 2028: 510000; FY 2029: 510000
U-4404 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | T | CONSTRUCTION | 10400000 | FY 2030: 104000; FY 2031: 5409000; FY 2032: 4206000; FY 2033: 681000
U-4405 | Highway | STI (Prioritization) | US 401 (RAEFORD ROAD) | SR 3569 (OLD RAEFORD ROAD) TO EAST OF SR 3828 (ROBESON STREET) IN FAYETTEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 6 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT OF WAY IN PROGRESS. | Division 6 |  |  |  | 70096000
U-4405A | Highway | STI (Prioritization) | US 401 (RAEFORD ROAD) | OLD RAEFORD ROAD TO EAST OF BUNCE ROAD. | 2.22 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGANY | CONSTRUCTION | 35403000 | FY 2024: 7003000; FY 2025: 1370000
U-4405B | Highway | STI (Prioritization) | US 401 (RAEFORD ROAD) | EAST OF BUNCE ROAD TO EAST OF BRIGHTON ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.61 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | CONSTRUCTION | 52600000 | FY 2025: 14728000; FY 2026: 19988000; FY 2027: 13676000; FY 2028: 4208000
U-4405C | Highway | STI (Prioritization) | US 401 (RAEFORD ROAD) | EAST OF BRIGHTON ROAD TO EAST OF ROBESON STREET. | 2.38 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | CONSTRUCTION | 41401000 | FY 2026: 3864000; FY 2027: 14481000; FY 2028: 12451000; FY 2029: 8694000; FY 2030: 1911000
U-4407 | Highway | STI (Prioritization) | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 1.88 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  |  |  | 750000
U-4407 | Highway | STI (Prioritization) | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 1.88 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | T | RIGHT-OF-WAY | 3979000 | FY 2026: 764000; FY 2027: 1528000; FY 2028: 891000; FY 2029: 398000; FY 2030: 398000
U-4407 | Highway | STI (Prioritization) | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 1.88 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | T | UTILITIES | 2090000 | FY 2026: 1045000; FY 2027: 1045000
U-4407 | Highway | STI (Prioritization) | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 1.88 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | T | CONSTRUCTION | 17499000 | FY 2028: 3676000; FY 2029: 8359000; FY 2030: 5464000
U-4414 | Highway | STI (Prioritization) | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 4.66 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2363000
U-4414 | Highway | STI (Prioritization) | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 4.66 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1548000
U-4414 | Highway | STI (Prioritization) | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 4.66 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 919000
U-4414 | Highway | STI (Prioritization) | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 4.66 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 67101000
U-4424 | Highway | STI (Prioritization) | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 2.28 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 5072000
U-4424 | Highway | STI (Prioritization) | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 2.28 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | T | BUILD NC CON | 19050000 |  | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 7620000
U-4424 | Highway | STI (Prioritization) | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 2.28 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | T | CONSTRUCTION | 327000 | FY 2026: 327000
U-4434 | Highway | STI (Prioritization) | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 1.81 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 4163000
U-4434 | Highway | STI (Prioritization) | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 1.81 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | RIGHT-OF-WAY | 88701000 | FY 2027: 887000; FY 2028: 24917000; FY 2029: 25804000; FY 2030: 19353000; FY 2031: 17740000
U-4434 | Highway | STI (Prioritization) | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 1.81 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | UTILITIES | 3632000 | FY 2027: 1816000; FY 2028: 1816000
U-4434 | Highway | STI (Prioritization) | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 1.81 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | CONSTRUCTION | 128601000 | FY 2031: 22762000; FY 2032: 34226000; FY 2033: 29986000 | 41627000
U-4437 | Highway | STI (Prioritization) | NC 54 (HILLSBOROUGH STREET) | SR 1664 / SR 3074 (BLUE RIDGE ROAD) IN VICINITY OF NC RAILROAD (CSX CORPORATION AND NORFOLK SOUTHERN) IN RALEIGH. CONSTRUCT GRADE SEPARATIONS AND ACCESS ROAD BETWEEN NC 54 AND SR 1664 / SR 3074. | 3 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT | Division 5 |  |  |  | 69748000
U-4700 | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO SR 1933 (SOUTHWEST BOULEVARD). WIDEN TO SIX LANES. | 13.3 | CALDWELL, CATAWBA, BURKE | 11, 12, 13 | Greater Hickory MPO | INCLUDES B-4450. |  |  |  |  | 11864000
U-4700A | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | CATAWBA, CALDWELL, BURKE | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | GARVEE ROW | 57915000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 7722000
U-4700A | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | CATAWBA, CALDWELL, BURKE | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 15100000
U-4700A | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | CATAWBA, CALDWELL, BURKE | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | S(M) | RIGHT-OF-WAY | 15000000
U-4700A | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | CATAWBA, CALDWELL, BURKE | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | NHP | CONSTRUCTION | 275530000 | FY 2026: 2755000; FY 2027: 74385000; FY 2028: 74385000; FY 2029: 66120000; FY 2030: 57885000
U-4700A | Highway | STI (Prioritization) | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | CATAWBA, CALDWELL, BURKE | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | Statewide Mobility |  | L | CONSTRUCTION | 699000 | FY 2026: 7000; FY 2027: 188000; FY 2028: 194000; FY 2029: 171000; FY 2030: 139000
U-4700AA | Highway | Bridges | US 321 | INTERIM STRUCTURE IMPROVEMENTS ON US 321 SOUTHBOUND BRIDGE OVER LAKE HICKORY. | 0.5 | BURKE, CALDWELL | 11, 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHP | CONSTRUCTION | 2550000 | FY 2024: 150000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 35000000 | [10 empty] | 35000000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | UTILITIES | 4000000 | [10 empty] | 4000000
U-4700B | Highway | STI (Prioritization) | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | CONSTRUCTION | 57500000 | [10 empty] | 57500000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 5000000 | [10 empty] | 5000000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | UTILITIES | 2000000 | [10 empty] | 2000000
U-4700C | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 0 | CALDWELL | 11 | Greater Hickory MPO |  | Not Funded |  | NHP | CONSTRUCTION | 12000000 | [10 empty] | 12000000
U-4700CA | Highway | STI (Prioritization) | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | Region F |  | NHP | RIGHT-OF-WAY | 420000
U-4700CA | Highway | STI (Prioritization) | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | Region F |  | NHP | CONSTRUCTION | 6510000 | FY 2025: 72000; FY 2026: 3657000; FY 2027: 2781000
U-4700CA | Highway | STI (Prioritization) | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | Region F |  | NHP | CONSTRUCTION | 690000 | FY 2028: 690000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 400000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 100000
U-4700CB | Highway | STI (Prioritization) | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 11998000 | FY 2025: 120000; FY 2026: 5467000; FY 2027: 4602000; FY 2028: 1809000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 450000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 100000
U-4700CC | Highway | STI (Prioritization) | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 8300000 | FY 2025: 83000; FY 2026: 4050000; FY 2027: 3217000; FY 2028: 950000
U-4709 | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 1.05 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  |  |  | 1400000
U-4709 | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 1.05 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | RIGHT-OF-WAY | 9556000
U-4709 | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 1.05 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | UTILITIES | 1575000
U-4709 | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 1.05 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | CONSTRUCTION | 22250000 | FY 2025: 3786000; FY 2026: 8899000; FY 2027: 6658000; FY 2028: 2907000
U-4712 | Highway | STI (Prioritization) | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 2.09 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  |  |  | 680000
U-4712 | Highway | STI (Prioritization) | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 2.09 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | RIGHT-OF-WAY | 27100000 | FY 2027: 271000; FY 2028: 8401000; FY 2029: 10407000; FY 2030: 2601000; FY 2031: 5420000
U-4712 | Highway | STI (Prioritization) | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 2.09 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | UTILITIES | 4800000 | FY 2027: 2400000; FY 2028: 2400000
U-4712 | Highway | STI (Prioritization) | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 2.09 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | CONSTRUCTION | 25501000 | FY 2030: 5409000; FY 2031: 9838000; FY 2032: 6935000; FY 2033: 3319000
U-4713 | Highway | STI (Prioritization) | NEW ROUTE | SR 3457 (CAMPUS RIDGE ROAD) TO SR 3448 (PLEASANT PLAINS ROAD) IN MATTHEWS. CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 1.1 | MECKLENBURG | 10 | Charlotte Regional TPO | [5 empty] | 5399000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | ENGINEERING | 1155000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | BUILD NC ROW | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | RIGHT-OF-WAY | 2320000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | UTILITIES | 600000 | FY 2024: 600000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | UTILITIES | 500000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | BUILD NC CON | 5160000 |  | 688000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 1720000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | CONSTRUCTION | 7520000 | FY 2025: 0; FY 2026: 4487000; FY 2027: 3033000
U-4713A | Highway | STI (Prioritization) | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | L | CONSTRUCTION | 2000000 | FY 2025: 0; FY 2026: 1278000; FY 2027: 722000
U-4713B | Highway | Transition | CAMPUS RIDGE ROAD REALIGNMENT | SR 1009 (JOHN STREET) TO SR 3457 (CAMPUS RIDGE ROAD). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 1.1 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Pre-STI (Transition)
U-4714 | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | 6.5 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL. |  |  |  |  | 23619000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 1.01 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | RIGHT-OF-WAY | 9149000 | FY 2028: 92000; FY 2029: 5538000; FY 2030: 1689000; FY 2031: 915000; FY 2032: 915000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 1.01 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | UTILITIES | 1900000 | FY 2028: 950000; FY 2029: 950000
U-4714AA | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 1.01 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGANY | CONSTRUCTION | 14301000 | FY 2030: 6282000; FY 2031: 5779000; FY 2032: 2240000
U-4714AB | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | I-485. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | LET WITH I-5507 | Division 10
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGANY | RIGHT-OF-WAY | 498000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGDA | RIGHT-OF-WAY | 9026000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | S(M) | RIGHT-OF-WAY | 2256000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T | UTILITIES | 2200000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T | BUILD NC CON | 9015000 |  |  | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 4207000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | T(DA) | CONSTRUCTION | 11000000 | FY 2026: 0; FY 2027: 3800000; FY 2028: 5220000; FY 2029: 1980000
U-4714AC | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $7.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | S(M) | CONSTRUCTION | 1924000 | FY 2026: 152000; FY 2027: 999000; FY 2028: 588000; FY 2029: 185000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | BGANY | RIGHT-OF-WAY | 37750000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | BGDA | RIGHT-OF-WAY | 5000000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | O | RIGHT-OF-WAY | 2000000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | S(M) | RIGHT-OF-WAY | 1250000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | BGANY | UTILITIES | 4500000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | T | BUILD NC CON | 10935000 |  |  |  |  | 729000 | 729000 | 729000 | 729000 | 729000 | 729000 | 6561000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | T | BUILD NC CON | 19305000 |  |  | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 9009000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | T | CONSTRUCTION | 17000000 | FY 2028: 7685000; FY 2029: 6885000; FY 2030: 2430000
U-4714B | Highway | STI (Prioritization) | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $15.0M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | Division 10 |  | O | CONSTRUCTION | 3000000 | FY 2026: 30000; FY 2027: 1034000; FY 2028: 1041000; FY 2029: 618000; FY 2030: 277000
U-4715 | Highway | STI (Prioritization) | CITYWIDE | ASHEVILLE SIGNAL SYSTEM. |  | BUNCOMBE | 13 | French Broad River MPO | A PORTION OF THE SIGNALS ARE NOT ELIGIBLE FOR FEDERAL FUNDING DUE THE ROAD'S FUNCTIONAL CLASSIFICATION. THE RESULTING FUNDING SPLIT IS 74% FEDERAL AND 26% STATE |  |  |  |  | 16377000
U-4715AA | Highway | Pre-STI (Historic) | US 25 (HENDERSONVILLE ROAD) | SIGNAL IMPROVEMENTS |  | BUNCOMBE | 13 | French Broad River MPO | COMPLETE
U-4715AB | Highway | Pre-STI (Historic) | PATTON AVENUE AND COLLEGE STREET. | SIGNAL IMPROVEMENTS |  | BUNCOMBE | 13 | French Broad River MPO | COMPLETE
U-4715B | Highway | STI (Prioritization) | CITYWIDE | SIGNAL IMPROVEMENTS |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION | Division 13
U-4716 | Rail | Other | VARIOUS PIEDMONT CORRIDOR | VARIOUS ROUTES AND NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD IN DURHAM AND MORRISVILLE, SOUTH OF I-40 TO NORTH OF MCCRIMMON PARKWAY. CONSTRUCT A GRADE SEPARATION AT SR 1978 (HOPSON ROAD), EXTEND CHURCH STREET TO HOPSON ROAD, CLOSE CHURCH STREET C |  | DURHAM, WAKE | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO | [5 empty] | 31776000
U-4716A | Rail | Other | SR 1978 (HOPSON ROAD) | NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD. CONSTRUCT RAILROAD GRADE SEPARATION AND SHIFT RAIL LINE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PROJECT COMPLETE
U-4716B | Rail | Pre-STI (Historic) | SR 1980 (CHURCH STREET) | NORFOLK SOUTHERN RAILROAD / NC RAILROAD TO SR 1978 (HOPSON ROAD) REALIGN AND CLOSE CROSSING 734 748M OF THE NORFOLK SOUTHERN-NORTH CAROLINA RAILROAD |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PROJECT COMPLETE | Pre-STI (Transition)
U-4716C | Rail | Other | NORFOLK-SOUTHERN RAILROAD / NC RAILROAD | CLEGG TO NELSON. CONSTRUCT PASSING SIDING |  | DURHAM, WAKE | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROJECT COMPLETE
U-4716D | Highway | STI (Prioritization) | SR 1978 (HOPSON ROAD) | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | O | RIGHT-OF-WAY | 1126000 | [10 empty] | 1126000
U-4716D | Highway | STI (Prioritization) | SR 1978 (HOPSON ROAD) | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | O | CONSTRUCTION | 3160000 | [10 empty] | 3160000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  |  |  | 856000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 1785000 | FY 2024: 1785000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 448000 | FY 2024: 448000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 3854000 | FY 2025: 3854000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 120000 | FY 2025: 120000
U-4724 | Bike & Ped | Transition | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Pre-STI (Transition) |  | L | CONSTRUCTION | 1004000 | FY 2025: 1004000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  |  |  | 12842000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  | BGDA | RIGHT-OF-WAY | 1527000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  | L | RIGHT-OF-WAY | 382000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  | BGANY | CONSTRUCTION | 429000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  | BGDA | CONSTRUCTION | 8984000
U-4726 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5, 7, 8 |  | L | CONSTRUCTION | 2353000
U-4726DF | Bike & Ped | Locally Selected | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 29000 | FY 2024: 29000
U-4726DF | Bike & Ped | Locally Selected | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | BGDA | CONSTRUCTION | 96000 | FY 2024: 96000
U-4726DF | Bike & Ped | Locally Selected | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 24000 | FY 2024: 24000
U-4726DF | Bike & Ped | Locally Selected | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 7000 | FY 2024: 7000
U-4726HN | Bike & Ped | Locally Selected | SR 1321 (HILLANDALE ROAD) | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1572000 | FY 2024: 1572000
U-4726HN | Bike & Ped | Locally Selected | SR 1321 (HILLANDALE ROAD) | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 393000 | FY 2024: 393000
U-4726HO | Bike & Ped | Locally Selected | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 22000 | FY 2024: 22000
U-4726HO | Bike & Ped | Locally Selected | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 5000 | FY 2024: 5000
U-4726HO | Bike & Ped | Locally Selected | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 6305000 | FY 2025: 6305000
U-4726HO | Bike & Ped | Locally Selected | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 1576000 | FY 2025: 1576000
U-4726IK | Bike & Ped | Locally Selected | SR 1777 (HOMESTEAD ROAD) | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 1600000
U-4726IK | Bike & Ped | Locally Selected | SR 1777 (HOMESTEAD ROAD) | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 400000
U-4727 | Highway | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  |  |  | 15908000
U-4727 | Highway | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  | BGDA | PLANNING | 21022000 | 3206000 | 3846000 | 3241000 | 3403000 | 3574000 | 3752000
U-4727 | Highway | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | Division 5, 7, 8 |  | L | PLANNING | 4839000 | 801000 | 961000 | 714000 | 750000 | 787000 | 826000
U-4734 | Highway | STI (Prioritization) | NEW ROUTE | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | 1.52 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  |  |  | 13700000
U-4734 | Highway | STI (Prioritization) | NEW ROUTE | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | 1.52 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC CON | 11172000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000
U-4735 | Highway | Locally Selected | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 77938000 |  |  |  |  | 3688000 | 14850000 | 14850000 | 14850000 | 14850000 | 14850000
U-4739 | Highway | STI (Prioritization) | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). UPGRADE ROADWAY WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 2.87 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  |  |  | 622000
U-4739 | Highway | STI (Prioritization) | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). UPGRADE ROADWAY WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 2.87 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 18500000 | FY 2027: 2242000; FY 2028: 5382000; FY 2029: 5382000; FY 2030: 1794000; FY 2031: 3700000
U-4739 | Highway | STI (Prioritization) | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). UPGRADE ROADWAY WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 2.87 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | UTILITIES | 7400000 | FY 2027: 3700000; FY 2028: 3700000
U-4739 | Highway | STI (Prioritization) | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). UPGRADE ROADWAY WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 2.87 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 38900000 | FY 2030: 6030000; FY 2031: 12637000; FY 2032: 10736000; FY 2033: 7607000 | 1890000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 13675000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 630000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 158000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | CONSTRUCTION | 487000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1599000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 276000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 69000
U-4741 | Bike & Ped | Locally Selected | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 522000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 98000 | FY 2025: 98000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 25000 | FY 2025: 25000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 720000 | FY 2025: 720000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 180000 | FY 2025: 180000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 1598000 | FY 2027: 1598000
U-4741OK | Bike & Ped | Locally Selected | PIEDMONT REGIONAL GREENWAY | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 400000 | FY 2027: 400000
U-4742 | Highway | Locally Selected | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 7170000
U-4742 | Highway | Locally Selected | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 700000
U-4742 | Highway | Locally Selected | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 175000
U-4744 | Highway | Locally Selected | VARIOUS | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | BGDA | CONSTRUCTION | 204922000 | 0 | 6080000 | 19872000 | 17121000 | 18781000 | 15911000 | 20932000 | 21245000 | 21245000 | 21245000 | 42490000
U-4744 | Highway | Locally Selected | VARIOUS | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | L | CONSTRUCTION | 51229000 | 0 | 1520000 | 4968000 | 4280000 | 4695000 | 3978000 | 5233000 | 5311000 | 5311000 | 5311000 | 10622000
U-4751 | Highway | STI (Prioritization) | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  |  |  | 255562000
U-4751 | Highway | STI (Prioritization) | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | ENGINEERING | 14850000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 1980000
U-4751 | Highway | STI (Prioritization) | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | RIGHT-OF-WAY | 255000 | FY 2024: 255000
U-4751 | Highway | STI (Prioritization) | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | BUILD NC CON | 36135000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 4818000
U-4751 | Highway | STI (Prioritization) | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | CONSTRUCTION | 49615000 | FY 2024: 21125000
U-4751A | Highway | STI (Prioritization) | LENDIRE ROAD | LENDIRE ROAD, WEST OF US 17 BUSINESS (MARKET STREET) TO US 17 BUSINESS (MARKET STREET)/SR 1403 (MIDDLE SOUND LOOP ROAD). REALIGN ROADWAY. | 0.31 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
U-4753 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 0.87 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  |  |  | 920000
U-4753 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 0.87 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | T | RIGHT-OF-WAY | 2000000
U-4753 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 0.87 | WAYNE | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | T | CONSTRUCTION | 12300000 | FY 2026: 1779000; FY 2027: 5211000; FY 2028: 3572000; FY 2029: 1738000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 7518000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | HP | RIGHT-OF-WAY | 6776000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | RIGHT-OF-WAY | 4751000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | S(M) | RIGHT-OF-WAY | 1694000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | UTILITIES | 7200000
U-4758 | Highway | STI (Prioritization) | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | CONSTRUCTION | 48400000 | FY 2025: 2792000; FY 2026: 20468000; FY 2027: 14525000; FY 2028: 7670000; FY 2029: 2945000
U-4762 | Highway | STI (Prioritization) | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 1.26 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  |  |  | 2892000
U-4762 | Highway | STI (Prioritization) | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 1.26 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | ENGINEERING | 1995000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 266000
U-4762 | Highway | STI (Prioritization) | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 1.26 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 2895000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000
U-4762 | Highway | STI (Prioritization) | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 1.26 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 3360000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 448000
U-4850 | Highway | Locally Selected | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  |  |  | 7089000
U-4850 | Highway | Locally Selected | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  | BGDA | PLANNING | 15200000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000
U-4850 | Highway | Locally Selected | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | Division 4, 5, 6 |  | L | PLANNING | 3800000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  |  |  | 3372000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | RIGHT-OF-WAY | 8480000 | FY 2024: 4240000; FY 2025: 2120000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | S(M) | RIGHT-OF-WAY | 2120000 | FY 2024: 1060000; FY 2025: 530000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | UTILITIES | 12000000 | FY 2024: 6000000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | S(M) | UTILITIES | 3000000 | FY 2024: 1500000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | BGDA | CONSTRUCTION | 18641000 | FY 2026: 2137000; FY 2027: 7912000; FY 2028: 6218000; FY 2029: 2374000
U-4900 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | Exempt |  | S(M) | CONSTRUCTION | 4659000 | FY 2026: 525000; FY 2027: 1973000; FY 2028: 1554000; FY 2029: 607000
U-4902 | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | COLONIAL DRIVE TO SR 1402 (PORTERS NECK ROAD). ACCESS MANAGEMENT IMPROVEMENTS. | 8.6 | NEW HANOVER | 3 | Wilmington Urban Area MPO | [5 empty] | 54718000
U-4902A | Highway | Pre-STI (Historic) | US 17 BUSINESS (MARKET STREET) | SR 1272 (NEW CENTRE DRIVE) TO MARTIN LUTHER KING JR., BOULEVARD. | 0.089 | NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
U-4902B | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 1.4 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10050000 | FY 2024: 50000 | 10000000
U-4902B | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 1.4 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | UTILITIES | 2900000 | [10 empty] | 2900000
U-4902B | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 1.4 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 9700000 | [10 empty] | 9700000
U-4902C | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 2.19 | NEW HANOVER | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | RIGHT-OF-WAY | 46088000 | FY 2028: 4254000; FY 2029: 17017000; FY 2030: 15599000; FY 2031: 4609000; FY 2032: 4609000
U-4902C | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 2.19 | NEW HANOVER | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | UTILITIES | 10811000 | FY 2028: 5405000; FY 2029: 5406000
U-4902C | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 2.19 | NEW HANOVER | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | Statewide Mobility |  | T | CONSTRUCTION | 55101000 | FY 2030: 12725000; FY 2031: 17433000; FY 2032: 13905000; FY 2033: 9890000 | 1148000
U-4902D | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 1.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | ENGINEERING | 4290000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 572000
U-4902D | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 1.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | BUILD NC CON | 12795000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 1706000
U-4902D | Highway | STI (Prioritization) | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 1.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Statewide Mobility |  | T | CONSTRUCTION | 14814000 | FY 2024: 2700000
U-4906 | Highway | Transition | SR 1308 (GUM BRANCH ROAD) | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. MODERNIZE ROADWAY, PROVIDE PAVED SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 7.42 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  |  |  | 5278000
U-4906 | Highway | Transition | SR 1308 (GUM BRANCH ROAD) | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. MODERNIZE ROADWAY, PROVIDE PAVED SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 7.42 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 16095000 | FY 2024: 142000
U-4910 | Highway | Transition | SR 1445 (DERITA ROAD) | SR 2894 (CONCORD MILLS BOULEVARD) TO SR 1394 (POPLAR TENT ROAD) IN CONCORD. WIDEN TO 4-LANES DIVIDED. | 2.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | SEGMENTS A AND B LET TOGETHER |  |  |  |  | 23417000
U-4910A | Highway | Locally Selected | SR 1445 (DERITA ROAD) | SR 2894 (CONCORD MILLS BOULEVARD) TO AVIATION BOULEVARD. WIDEN TO 4-LANES DIVIDED. | 1 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 10
U-4910B | Highway | Pre-STI (Historic) | SR 1445 (DERITA ROAD) | AVIATION BOULEVARD TO SR 1394 (POPLAR TENT ROAD). WIDEN TO 4-LANES DIVIDED. | 1.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 908000 | FY 2024: 908000
U-4910B | Highway | Pre-STI (Historic) | SR 1445 (DERITA ROAD) | AVIATION BOULEVARD TO SR 1394 (POPLAR TENT ROAD). WIDEN TO 4-LANES DIVIDED. | 1.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 227000 | FY 2024: 227000
U-4913 | Highway | STI (Prioritization) | SR 3174 / 1501 (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY | 0.77 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO | [5 empty] | 1545000
U-4913A | Highway | STI (Prioritization) | SR 3174 (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 0.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | RIGHT-OF-WAY | 750000 | FY 2026: 750000
U-4913A | Highway | STI (Prioritization) | SR 3174 (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 0.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | UTILITIES | 250000 | FY 2026: 250000
U-4913A | Highway | STI (Prioritization) | SR 3174 (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 0.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | CONSTRUCTION | 4400000 | FY 2028: 44000; FY 2029: 3201000; FY 2030: 1155000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 0.77 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 14886000 | [10 empty] | 14886000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 0.77 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 636000 | [10 empty] | 636000
U-4913B | Highway | STI (Prioritization) | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 0.77 | UNION, MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 21500000 | [10 empty] | 21500000
U-4916 | Highway | Transition | SR 1165 (BECKFORD DRIVE) | HARRISON STREET TO NORTH PARK DRIVE IN HENDERSON. WIDEN TO THREE LANES WITH CURB AND GUTTER, STORM DRAINAGE, AND SIDEWALKS. | 0.49 | VANCE | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION BY CITY OF HENDERSON | Pre-STI (Transition) |  |  |  | 961000
U-4950 | Highway | Locally Selected | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | Division 10, 12 |  |  |  | 1500000
U-4950 | Highway | Locally Selected | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | Division 10, 12 |  | BGDA | PLANNING | 13122000 | 1634000 | 1664000 | 1100000 | 1100000 | 1100000 | 1100000
U-4950 | Highway | Locally Selected | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | Division 10, 12 |  | L | PLANNING | 3282000 | 409000 | 416000 | 275000 | 275000 | 275000 | 275000
U-4951 | Highway | Locally Selected | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  |  |  | 1560000
U-4951 | Highway | Locally Selected | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  | BGDA | PLANNING | 4477000 | FY 2024: 855000; FY 2025: 1147000; FY 2026: 825000; FY 2027: 825000; FY 2028: 825000
U-4951 | Highway | Locally Selected | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO | FORMERLY U-9999D - IN PROGRESS | Division 9 |  | L | PLANNING | 1112000 | FY 2024: 214000; FY 2025: 280000; FY 2026: 206000; FY 2027: 206000; FY 2028: 206000
U-5007 | Highway | STI (Prioritization) | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 3.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 600000
U-5007 | Highway | STI (Prioritization) | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 3.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 39201000
U-5007 | Highway | STI (Prioritization) | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 3.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 10700000
U-5007 | Highway | STI (Prioritization) | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 3.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 68001000
U-5008 | Highway | Transition | SR 2975 (SUGAR CREEK ROAD) | CONSTRUCT GRADE SEPARATION OVER NORTH CAROLINA RAILROAD/NORFOLK SOUTHERN RAILWAY CROSSING 715 352H AND THE CLOSURE OF CRAIGHEAD ROAD CROSSING 715 355D. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS |  |  |  |  | 38497000
U-5008A | Bike & Ped | Other | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | RIGHT-OF-WAY | 1000000
U-5008A | Bike & Ped | Other | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | UTILITIES | 25000
U-5008A | Bike & Ped | Other | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 0.59 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | DP | CONSTRUCTION | 1200000 | FY 2024: 930000
U-5015 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 1.79 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  |  |  | 10000
U-5015 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 1.79 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 14900000 | [10 empty] | 14900000
U-5015 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 1.79 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 2200000 | [10 empty] | 2200000
U-5015 | Highway | STI (Prioritization) | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 1.79 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 8300000 | [10 empty] | 8300000
U-5019 | Highway | STI (Prioritization) | ASHEVILLE EAST OF THE RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT INTERCONNECTED NETWORK OF PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. PROJECT INCLUDES: CLINGMAN FOREST AND TOWN BRANCH GREENWAYS, FRENCH BROAD RIVER WEST GREENWAY, WILMA DIKEMAN RIVERWAY AND FIVE POINTS ROUNDABOUT, LIVINGSTON S |  | BUNCOMBE | 13 | French Broad River MPO | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING |  |  |  |  | 10130000
U-5019A | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT NASTY BRANCH GREENWAY. | 0.71 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 3412000 | FY 2025: 1706000; FY 2026: 1706000
U-5019A | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT NASTY BRANCH GREENWAY. | 0.71 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 855000 | FY 2025: 855000
U-5019B | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | FRENCH BROAD RIVER WEST GREENWAY, FRENCH BROAD RIVER PARK TO HAYWOOD ROAD. | 0.9 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION | Division 13
U-5019C | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | WILMA DYKEMAN RIVERWAY - RADTIP AND FIVE POINTS ROUNDABOUT. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION | Division 13
U-5019D | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | LIVINGSTON STREET COMPLETE STREETS IMPROVEMENTS. | 0.64 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 1500000 | FY 2026: 1500000
U-5019E | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER. | 0.11 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 4250000 | FY 2027: 4250000
U-5019E | Highway | STI (Prioritization) | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER. | 0.11 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 1050000 | FY 2027: 1050000
U-5021 | Highway | Locally Selected | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 71646000 | 4162000 | 5402000 | 5402000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000
U-5022 | Highway | Locally Selected | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 93095000 | 4187000 | 4649000 | 7264000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000
U-5023 | Highway | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726. | Division 5, 7, 8 |  | BGDA | CONSTRUCTION | 48984000 | 2386000 | 3493000 | 2635000 | 3177000 | 3006000 | 2828000 | 6580000 | 6580000 | 6580000 | 6580000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  |  |  | 2826000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | RIGHT-OF-WAY | 34540000 | FY 2024: 1779000; FY 2025: 703000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | UTILITIES | 336000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 26505000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 3534000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | CONSTRUCTION | 60923000 | FY 2024: 11500000
U-5026 | Highway | STI (Prioritization) | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | L | CONSTRUCTION | 208000
U-5100 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | BUNCOMBE, HENDERSON, HAYWOOD | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | BGDA | CONSTRUCTION | 39344000 | 0 | 0 | 0 | 1660000 | 2570000 | 4742000 | 5062000 | 5062000 | 5062000 | 5062000 | 10124000
U-5100 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | BUNCOMBE, HENDERSON, HAYWOOD | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | CONSTRUCTION | 9839000 | 0 | 0 | 0 | 415000 | 643000 | 1185000 | 1266000 | 1266000 | 1266000 | 1266000 | 2532000
U-5101 | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) SR 1614 (SHAW MILL ROAD) SR 16 | NC 24 (BRAGG BOULEVARD) TO US 401 (RAMSEY STREET). WIDEN ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.6 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 1250000
U-5101A | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC ROW | 19305000 |  |  | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 9009000
U-5101A | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | BUILD NC UTL | 6435000 |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-5101A | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | RIGHT-OF-WAY | 2785000 | FY 2026: 0; FY 2027: 0; FY 2028: 0; FY 2029: 1010000; FY 2030: 1775000
U-5101A | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | UTILITIES | 2732000 | FY 2026: 2732000
U-5101A | Highway | STI (Prioritization) | SR 1437 (SHAW ROAD) | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026-2040 (FY 2026 / YR 6 SALE). | Division 6 |  | T | CONSTRUCTION | 36601000 | FY 2028: 366000; FY 2029: 12776000; FY 2030: 11876000; FY 2031: 8577000; FY 2032: 3006000
U-5101B | Highway | STI (Prioritization) | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 38500000 | [10 empty] | 38500000
U-5101B | Highway | STI (Prioritization) | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 21445000 | [10 empty] | 21445000
U-5101B | Highway | STI (Prioritization) | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 36300000 | [10 empty] | 36300000
U-5105 | Highway | Transition | NC 225 SR 1164 (ERKWOOD DRIVE) | NC 225/SR 1164 (ERKWOOD DRIVE)/SR 1779(SHEPHERD STREET) IN HENDERSONVILLE. IMPROVE INTERSECTION. | 0.5 | HENDERSON | 14 | French Broad River MPO | DIVISION PROJECT - UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 7210000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  |  |  | 2925000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BA | ENGINEERING | 960000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 1750000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 1750000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 9417000 | FY 2024: 1337000; FY 2025: 4657000; FY 2026: 2625000; FY 2027: 798000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 2935000 | FY 2026: 2935000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 332000 | FY 2024: 47000; FY 2025: 164000; FY 2026: 93000; FY 2027: 28000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | L | CONSTRUCTION | 2023000 | FY 2024: 488000; FY 2025: 940000; FY 2026: 488000; FY 2027: 107000
U-5108 | Highway | Transition | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | Pre-STI (Transition) |  | L | CONSTRUCTION | 2935000 | FY 2026: 2935000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGDA | RIGHT-OF-WAY | 541000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | RIGHT-OF-WAY | 135000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | CMAQ | CONSTRUCTION | 1600000 | FY 2024: 1600000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | HSIP | CONSTRUCTION | 883000 | FY 2024: 883000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 1881000 | FY 2024: 1881000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 1135000 | FY 2024: 1135000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 1657000 | FY 2024: 1657000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 284000 | FY 2024: 284000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 414000 | FY 2024: 414000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 400000 | FY 2024: 400000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L(M) | CONSTRUCTION | 470000 | FY 2024: 470000
U-5112 | Highway | Transition | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Pre-STI (Transition) |  | L | CONSTRUCTION | 1479000 | FY 2024: 1479000
U-5114 | Highway | Transition | HUNTERSVILLE | INTERSECTION OF US 21 AND GILEAD ROAD IN HUNTERSVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS, INCLUDING BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition) |  |  |  | 19322000
U-5118 | Highway | Locally Selected | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | Division 4, 5, 6 |  |  |  | 21170000
U-5118 | Highway | Locally Selected | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 3000000
U-5118 | Highway | Locally Selected | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 582000 | FY 2024: 582000
U-5118 | Highway | Locally Selected | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | Division 4, 5, 6 |  | L | CONSTRUCTION | 145000 | FY 2024: 145000
U-5118 | Highway | Locally Selected | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | Division 4, 5, 6 |  | L | CONSTRUCTION | 750000
U-5118FB | Highway | Locally Selected | NC 96 (ARENDELL AVENUE) | NORTH OF PEARCES ROAD TO DOGWOOD DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 850000 | FY 2025: 850000
U-5118FB | Highway | Locally Selected | NC 96 (ARENDELL AVENUE) | NORTH OF PEARCES ROAD TO DOGWOOD DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | L(M) | CONSTRUCTION | 213000 | FY 2025: 213000
U-5119A | Public Transportation (Transit) | Planning | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FED | ENGINEERING | 3376000
U-5119A | Public Transportation (Transit) | Planning | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ENGINEERING | 844000
U-5169 | Highway | STI (Prioritization) | I-74 / US 311 | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. RECONSTRUCT INTERCHANGE AND APPROACHES. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  |  |  | 32225000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  |  |  | 202000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGDA | RIGHT-OF-WAY | 193000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | L | RIGHT-OF-WAY | 48000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 2199000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 459000
U-5190 | Bike & Ped | Transition | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | Pre-STI (Transition) |  | L | CONSTRUCTION | 664000
U-5207 | Highway | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  |  |  | 2650000
U-5207 | Highway | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | BGDA | PLANNING | 2807000 | 100000 | 547000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 900000
U-5207 | Highway | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | L | PLANNING | 625000 | 25000 | 60000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 225000
U-5301 | Highway | STI (Prioritization) | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 3.2 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  |  |  | 1000000
U-5301 | Highway | STI (Prioritization) | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 3.2 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 100558000 | FY 2027: 19502000; FY 2028: 29253000; FY 2029: 29253000; FY 2030: 2438000; FY 2031: 20112000
U-5301 | Highway | STI (Prioritization) | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 3.2 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | T | UTILITIES | 4012000 | FY 2027: 2006000; FY 2028: 2006000
U-5301 | Highway | STI (Prioritization) | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 3.2 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 134599000 | FY 2030: 1346000; FY 2031: 38573000; FY 2032: 37378000; FY 2033: 32052000 | 25250000
U-5302 | Highway | STI (Prioritization) | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  |  |  | 3345000
U-5302 | Highway | STI (Prioritization) | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | ENGINEERING | 1801000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 121000
U-5302 | Highway | STI (Prioritization) | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC ROW | 4128000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 278000
U-5302 | Highway | STI (Prioritization) | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | RIGHT-OF-WAY | 5803000
U-5302 | Highway | STI (Prioritization) | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | CONSTRUCTION | 24700000 | FY 2026: 8398000; FY 2027: 8645000; FY 2028: 5928000; FY 2029: 1729000
U-5304 | Highway | STI (Prioritization) | US 15 / US 501 (FORDHAM BOULEVARD) | NC 86 (SOUTH COLUMBIA STREET) TO I-40 IN CHAPEL HILL. UPGRADE CORRIDOR. | 6 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH EB-5998 AND U-5774 |  |  |  |  | 10000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [10 empty] | 10000000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 1040000 | [10 empty] | 1040000
U-5304A | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 22001000 | [10 empty] | 22001000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 2.13 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 6000000 | [10 empty] | 6000000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 2.13 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 285000 | [10 empty] | 285000
U-5304B | Highway | STI (Prioritization) | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 2.13 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 22001000 | [10 empty] | 22001000
U-5304C | Highway | Pre-STI (Historic) | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | WORK COMPLETED UNDER U-5550.
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 1.92 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5000000 | [10 empty] | 5000000
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 1.92 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 344000 | [10 empty] | 344000
U-5304D | Highway | STI (Prioritization) | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 1.92 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 30001000 | [10 empty] | 30001000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 12000000 | [10 empty] | 12000000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 446000 | [10 empty] | 446000
U-5304E | Highway | STI (Prioritization) | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 25000000 | [10 empty] | 25000000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 1.75 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D |  | T | RIGHT-OF-WAY | 3700000 | FY 2028: 877000; FY 2029: 1316000; FY 2030: 767000; FY 2031: 370000; FY 2032: 370000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 1.75 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D |  | T | UTILITIES | 1700000 | FY 2028: 850000; FY 2029: 850000
U-5304F | Highway | STI (Prioritization) | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 1.75 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D |  | T | CONSTRUCTION | 49300000 | FY 2030: 5710000; FY 2031: 19666000; FY 2032: 13522000; FY 2033: 7123000 | 3279000
U-5306 | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | INTERSECTION AND SIDEWALK IMPROVEMENTS AT CONE BOULEVARD-BENJAMIN PARKWAY, WESTRIDGE ROAD, NEW GARDEN ROAD, AND BRASSFIELD ROAD INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | [5 empty] | 9926000
U-5306A | Highway | Transition | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH BENJAMIN PARKWAY / CONE BOULEVARD AND APPROACHES | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE | Pre-STI (Transition)
U-5306B | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH WESTRIDGE ROAD AND APPROACHES | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D
U-5306C | Highway | Transition | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH NEW GARDEN ROAD AND APPROACHES | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE | Pre-STI (Transition)
U-5306D | Highway | Pre-STI (Historic) | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH BRASSFIELD ROAD AND APPROACHES | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT COMPLETE
U-5307 | Highway | STI (Prioritization) | US 1 | I-540 IN RALEIGH TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | 10 | WAKE | 5 | Capital Area MPO | [5 empty] | 1000000
U-5307A | Highway | STI (Prioritization) | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 1.63 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | Statewide Mobility |  | T | RIGHT-OF-WAY | 94301000 | FY 2026: 943000; FY 2027: 36777000; FY 2028: 37721000; FY 2029: 9430000; FY 2030: 9430000
U-5307A | Highway | STI (Prioritization) | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 1.63 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | Statewide Mobility |  | T | UTILITIES | 12200000 | FY 2026: 6100000; FY 2027: 6100000
U-5307A | Highway | STI (Prioritization) | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 1.63 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | Statewide Mobility |  | T | CONSTRUCTION | 184699000 | FY 2026: 27582000; FY 2027: 48026000; FY 2028: 44199000; FY 2029: 36202000; FY 2030: 28690000
U-5307B | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 2.11 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | BUILD NC ROW | 24453000
U-5307B | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 2.11 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 55600000
U-5307B | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 2.11 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 6700000
U-5307B | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 2.11 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 92399000
U-5307C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 3.83 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 28199000
U-5307C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 3.83 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 5100000
U-5307C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 3.83 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 108799000
U-5307D | Highway | STI (Prioritization) | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 2.33 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 71999000
U-5307D | Highway | STI (Prioritization) | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 2.33 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 10100000
U-5307D | Highway | STI (Prioritization) | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 2.33 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 133300000
U-5308 | Highway | STI (Prioritization) | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | RANDOLPH | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 8 |  | T | ENGINEERING | 2703000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 183000
U-5308 | Highway | STI (Prioritization) | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | RANDOLPH | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 8 |  | T | BUILD NC ROW | 244000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 20000
U-5308 | Highway | STI (Prioritization) | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | RANDOLPH | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 8 |  | T | RIGHT-OF-WAY | 2215000
U-5308 | Highway | STI (Prioritization) | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | RANDOLPH | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 8 |  | T | UTILITIES | 3500000 | FY 2026: 3500000
U-5308 | Highway | STI (Prioritization) | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | RANDOLPH | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 8 |  | T | CONSTRUCTION | 26799000 | FY 2028: 4260000; FY 2029: 10088000; FY 2030: 7728000; FY 2031: 4723000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 2.64 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  |  |  | 6977000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 2.64 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | RIGHT-OF-WAY | 5100000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 2.64 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | UTILITIES | 1217000
U-5312 | Highway | STI (Prioritization) | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 2.64 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | NHP | CONSTRUCTION | 64501000 | FY 2024: 17195000; FY 2025: 19354000; FY 2026: 15791000; FY 2027: 11516000
U-5315 | Highway | Locally Selected | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. MULTI-LANE FACILITY ON NEW LOCATION, INCLUDING INTERCHANGE AT NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). | 1.83 | WAKE | 5 | Capital Area MPO | PART C CONSTRUCTION BY TOWN OF CARY |  |  |  |  | 19749000
U-5315A | Highway | Locally Selected | MORRISVILLE PARKWAY EXTENSION | WEST OF HIGHCROFT DRIVE TO EAST OF MILLS PARK DRIVE IN CARY. CONSTRUCT 2-LANE FACILITY ON 4-LANE RIGHT OF WAY. | 0.48 | WAKE | 5 | Capital Area MPO | PROJECT COMPLETE. | Division 5
U-5315B | Highway | Locally Selected | MORRISVILLE PARKWAY EXTENSION | NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). CONSTRUCT INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | PROJECT COMPLETE. | Division 5
U-5315C | Highway | STI (Prioritization) | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. WIDEN TO 4 LANES WITH LANDSCAPED MEDIAN. |  | WAKE | 5 | Capital Area MPO |  | Not Funded |  | L | CONSTRUCTION | 7900000 | [10 empty] | 7900000
U-5317 | Highway | STI (Prioritization) | NORTH JUDD PARKWAY | NC 55 (NORTH BROAD STREET) TO NC 42 (WEST ACADEMY STREET) IN FUQUAY-VARINA, WAKE COUNTY. MULTI-LANE FACILITY ON NEW LOCATION. | 1.72 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF FUQUAY-VARINA | Division 5 |  |  |  | 25112000
U-5501 | Highway | Locally Selected | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  |  |  | 1869000
U-5501 | Highway | Locally Selected | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  | BGDA | CONSTRUCTION | 4526000
U-5501 | Highway | Locally Selected | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | Division 5 |  | L | CONSTRUCTION | 3166000
U-5501A | Highway | Locally Selected | SR 1650 (REEDY CREEK ROAD) | SR 1652 (HARRISION AVENUE) TO SOUTH OF WATTS POND LANE IN CARY. WIDEN ROADWAY TO THREE LANES INSTALL ROUNDABOUTS AND PEDESTRIAN ENHANCEMENTS | 0.38 | WAKE | 5 | Capital Area MPO |  | Division 5
U-5508 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | Statewide Mobility |  |  |  | 1262000
U-5508 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | Statewide Mobility |  | BG50200 | RIGHT-OF-WAY | 799000 | FY 2028: 799000
U-5508 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | Statewide Mobility |  | BG50200 | UTILITIES | 190000 | FY 2028: 190000
U-5508 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | Statewide Mobility |  | BG50200 | CONSTRUCTION | 2700000 | FY 2030: 780000; FY 2031: 1920000
U-5516 | Highway | STI (Prioritization) | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 935000
U-5516 | Highway | STI (Prioritization) | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 2700000
U-5516 | Highway | STI (Prioritization) | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 2000000
U-5516 | Highway | STI (Prioritization) | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 830000
U-5516 | Highway | STI (Prioritization) | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 22000000
U-5518 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 1.26 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  |  |  | 12447000
U-5518 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 1.26 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 153208000 | FY 2028: 61283000; FY 2029: 61283000; FY 2030: 15321000; FY 2031: 15321000
U-5518 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 1.26 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | UTILITIES | 15714000 | FY 2028: 7857000; FY 2029: 7857000
U-5518 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 1.26 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | Statewide Mobility |  | NHP | CONSTRUCTION | 168497000 | FY 2028: 21254000; FY 2029: 44866000; FY 2030: 40820000; FY 2031: 34644000; FY 2032: 26913000
U-5525 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 313000
U-5525 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | PLANNING | 15873000 | 679000 | 1084000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 6111000
U-5525 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | PLANNING | 3967000 | 170000 | 265000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 1530000
U-5527 | Bike & Ped | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS. | Division 3 |  |  |  | 273000
U-5527 | Bike & Ped | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS. | Division 3 |  | TADA | CONSTRUCTION | 17206000 | 2821000 | 2650000 | 0 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 5220000
U-5528 | Bike & Ped | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  |  |  | 910000
U-5528 | Bike & Ped | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | Division 6, 8 |  | TADA | CONSTRUCTION | 23787000 | 3126000 | 3181000 | 0 | 738000 | 738000 | 738000 | 738000 | 738000 | 738000 | 738000 | 6642000
U-5529 | Highway | Locally Selected | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  |  |  | 280000
U-5529 | Highway | Locally Selected | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | CONSTRUCTION | 1864000
U-5529 | Highway | Locally Selected | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | CONSTRUCTION | 466000
U-5530 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  |  |  | 12955000
U-5530 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | BGDA | CONSTRUCTION | 2000000
U-5530 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | TADA | CONSTRUCTION | 800000
U-5530 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | L | CONSTRUCTION | 500000
U-5530 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | L | CONSTRUCTION | 200000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 2843000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | ENGINEERING | 80000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | ENGINEERING | 20000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | RIGHT-OF-WAY | 50000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 400000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 100000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 50000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 100000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 12000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 12000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 24000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | CONSTRUCTION | 50000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGANY | CONSTRUCTION | 400000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | CONSTRUCTION | 4500000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | CONSTRUCTION | 2800000 | FY 2024: 2800000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | CONSTRUCTION | 4000000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 512000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | CONSTRUCTION | 200000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 462000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 12000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 700000 | FY 2024: 700000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 50000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 1000000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 100000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 115000
U-5532 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 1253000
U-5532C | Bike & Ped | Locally Selected | RUDD STATION ROAD | CONSTRUCT SIDEWALK FROM SCOTT ROAD TO TOWNSEND ROAD. | 0.63 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 296000 | FY 2025: 296000
U-5532C | Bike & Ped | Locally Selected | RUDD STATION ROAD | CONSTRUCT SIDEWALK FROM SCOTT ROAD TO TOWNSEND ROAD. | 0.63 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 74000 | FY 2025: 74000
U-5532E | Bike & Ped | Locally Selected | VARIOUS | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 1949000
U-5532E | Bike & Ped | Locally Selected | VARIOUS | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 487000
U-5532F | Bike & Ped | Locally Selected | VARIOUS | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 1518000 | FY 2025: 1518000
U-5532F | Bike & Ped | Locally Selected | VARIOUS | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 380000 | FY 2025: 380000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | RIGHT-OF-WAY | 56000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 14000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | UTILITIES | 4000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | UTILITIES | 1000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TADA | CONSTRUCTION | 920000 | FY 2025: 920000
U-5532G | Bike & Ped | Locally Selected | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 230000 | FY 2025: 230000
U-5532H | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEPHINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 536000 | FY 2025: 536000
U-5532H | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEPHINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 134000 | FY 2025: 134000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | ENGINEERING | 65000 | FY 2024: 65000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 16000 | FY 2024: 16000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 320000 | FY 2025: 320000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 80000 | FY 2025: 80000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 934000 | FY 2025: 934000
U-5532I | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 234000 | FY 2025: 234000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  |  |  | 3126000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | RIGHT-OF-WAY | 220000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | UTILITIES | 336000 | FY 2024: 336000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | L | UTILITIES | 84000 | FY 2024: 84000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGANY | CONSTRUCTION | 492000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDACV | CONSTRUCTION | 168000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | BGDA | CONSTRUCTION | 12187000 | FY 2024: 4203000
U-5534 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO | IN PROGRESS | Division 3 |  | L(M) | CONSTRUCTION | 2413000 | FY 2024: 1051000
U-5534C | Highway | Locally Selected | GREENVILLE AVENUE | SR 1411 (WRIGHTSVILLE AVENUE) TO HINTON AVENUE IN WILMINGTON. REALIGN INTERSECTION AND CONSTRUCT BIKE LANES AND SIDEWALK ALONG GREENVILLE AVENUE. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 861000 | FY 2025: 861000
U-5534G | Highway | Locally Selected | HOOKER ROAD | SR 1411 (WRIGHTSVILLE AVENUE) TO MALLARD DRIVE / ROSE AVENUE INTERSECTION IN WILMINGTON. CONSTRUCT A 10 FOOT MULTI-USE PATH. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1916000 | FY 2025: 1916000
U-5534H | Highway | Locally Selected | HINTON AVENUE | PARK AVENUE TO GREENVILLE AVENUE IN WILMINGTON. CONSTRUCT A 10 FOOT MULTI-USE PATH. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 786000 | FY 2025: 786000
U-5535 | Bike & Ped | Locally Selected | VARIOUS | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | TADA | CONSTRUCTION | 778000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778000
U-5535 | Bike & Ped | Locally Selected | VARIOUS | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | CONSTRUCTION | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276000
U-5536 | Highway | STI (Prioritization) | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.88 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 644000
U-5536 | Highway | STI (Prioritization) | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.88 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 14792000
U-5536 | Highway | STI (Prioritization) | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.88 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 1300000
U-5536 | Highway | STI (Prioritization) | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.88 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 22000000 | FY 2025: 4840000; FY 2026: 9020000; FY 2027: 5940000; FY 2028: 2200000
U-5537 | Highway | Locally Selected | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 0.31 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  |  |  | 1286000
U-5537 | Highway | Locally Selected | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 0.31 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  | BGDA | CONSTRUCTION | 468000
U-5537 | Highway | Locally Selected | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 0.31 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | Division 5 |  | L | CONSTRUCTION | 117000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  |  |  | 120000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | RIGHT-OF-WAY | 500000 | FY 2024: 500000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | RIGHT-OF-WAY | 100000 | FY 2024: 100000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1750000 | FY 2025: 1750000
U-5539A | Highway | Locally Selected | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 438000 | FY 2025: 438000
U-5544 | Bike & Ped | Locally Selected | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | TADA | CONSTRUCTION | 10789000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2344000 | 2815000 | 5630000
U-5544 | Bike & Ped | Locally Selected | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Division 10, 12 |  | L | CONSTRUCTION | 2698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586000 | 704000 | 1408000
U-5545 | Bike & Ped | Locally Selected | VARIOUS | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | TADA | CONSTRUCTION | 4775000 | 0 | 0 | 167000 | 512000 | 512000 | 512000 | 512000 | 512000 | 512000 | 512000 | 1024000
U-5545 | Bike & Ped | Locally Selected | VARIOUS | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | L | CONSTRUCTION | 1194000 | 0 | 0 | 42000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 256000
U-5546 | Bike & Ped | Locally Selected | VARIOUS | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | CATAWBA, BURKE, CALDWELL, ALEXANDER | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | TADA | CONSTRUCTION | 2610000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 506000 | 506000 | 506000 | 1012000
U-5546 | Bike & Ped | Locally Selected | VARIOUS | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | CATAWBA, BURKE, CALDWELL, ALEXANDER | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | CONSTRUCTION | 655000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 127000 | 127000 | 127000 | 254000
U-5550 | Highway | STI (Prioritization) | US 15 / US 501 (FORDHAM BOULEVARD) | SR 1742 (EPHESUS CHURCH ROAD) IN CHAPEL HILL. INTERSECTION IMPROVEMENTS. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Statewide Mobility |  |  |  | 2170000
U-5604 | Highway | STI (Prioritization) | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 1.4 | MACON | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  |  |  | 9756000
U-5604 | Highway | STI (Prioritization) | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 1.4 | MACON | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  | T | ENGINEERING | 1830000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 244000
U-5604 | Highway | STI (Prioritization) | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 1.4 | MACON | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  | T | BUILD NC CON | 3195000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000
U-5604 | Highway | STI (Prioritization) | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 1.4 | MACON | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | Region G |  | T | BUILD NC CON | 3885000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 518000
U-5606 | Highway | STI (Prioritization) | SR 1598 (DICKINSON AVENUE) | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | 1.34 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  |  |  | 3554000
U-5606 | Highway | STI (Prioritization) | SR 1598 (DICKINSON AVENUE) | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | 1.34 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | BG50200 | CONSTRUCTION | 18365000 | FY 2024: 3093000
U-5608 | Highway | Locally Selected | NEW ROUTE | SR 1211 (KIMBALL ROAD) EXTENSION, NORTH CHAPEL STREET TO SR 1221 (BOSTIAN ROAD) IN LANDIS. CONSTRUCT TWO-LANE CONNECTOR ON NEW LOCATION. | 0.27 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  |  |  | 8025000
U-5614 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | Division 9, 10 |  | BGDA | CONSTRUCTION | 30214000 | 0 | 0 | 0 | 0 | 1745000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 8134000
U-5614 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | Division 9, 10 |  | L | CONSTRUCTION | 7555000 | 0 | 0 | 0 | 0 | 436000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 2034000
U-5615 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | CATAWBA, BURKE, CALDWELL, ALEXANDER | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | BGDA | CONSTRUCTION | 32033000 | 0 | 0 | 0 | 697000 | 3917000 | 3917000 | 3917000 | 3917000 | 3917000 | 3917000 | 7834000
U-5615 | Highway | Locally Selected | VARIOUS | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | CATAWBA, BURKE, CALDWELL, ALEXANDER | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | CONSTRUCTION | 8006000 | 0 | 0 | 0 | 174000 | 979000 | 979000 | 979000 | 979000 | 979000 | 979000 | 1958000
U-5616 | Highway | Locally Selected | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Division 13, 14 |  |  |  | 313000
U-5616 | Highway | Locally Selected | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | BGDA | PLANNING | 3618000 | 617000 | 250000 | 250000 | 250000 | 250000 | 250000
U-5616 | Highway | Locally Selected | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | L | PLANNING | 907000 | 154000 | 63000 | 63000 | 63000 | 63000 | 63000
U-5617 | Highway | Locally Selected | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 0.28 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  |  |  | 1196000
U-5617 | Highway | Locally Selected | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 0.28 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  | BGANY | CONSTRUCTION | 1687000
U-5617 | Highway | Locally Selected | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 0.28 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. | Division 9 |  | L | CONSTRUCTION | 422000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  |  |  | 900000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | HF | CONSTRUCTION | 375000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | BGDA | CONSTRUCTION | 5670000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | BGDA | CONSTRUCTION | 516000 | FY 2024: 516000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | L(M) | CONSTRUCTION | 221000 | FY 2024: 221000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | L(M) | CONSTRUCTION | 1418000
U-5618 | Highway | Locally Selected | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | Division 5 |  | L | CONSTRUCTION | 295000 | FY 2024: 295000
U-5702 | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 9.7 | NEW HANOVER | 3 | Wilmington Urban Area MPO | [5 empty] | 2770000
U-5702A | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 2.64 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 56100000 | FY 2029: 16157000; FY 2030: 21542000; FY 2031: 7181000; FY 2032: 5610000; FY 2033: 5610000
U-5702A | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 2.64 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 13900000 | FY 2029: 6950000; FY 2030: 6950000
U-5702A | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 2.64 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 24500000 | FY 2031: 6860000; FY 2032: 10290000; FY 2033: 7350000
U-5702B | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 4.23 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 14240000 | [10 empty] | 14240000
U-5702B | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 4.23 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 8592000 | [10 empty] | 8592000
U-5702B | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 4.23 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 33800000 | [10 empty] | 33800000
U-5703 | Highway | STI (Prioritization) | US 74 (ROOSEVELT BOULEVARD) | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF MONROE |  |  |  |  | 3961000
U-5703A | Highway | STI (Prioritization) | US 74 (ROOSEVELT BLVD) | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
U-5703B | Highway | STI (Prioritization) | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 0.14 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 3457000 | FY 2024: 1276000; FY 2025: 851000; FY 2026: 346000; FY 2027: 346000
U-5703B | Highway | STI (Prioritization) | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 0.14 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 325000
U-5703B | Highway | STI (Prioritization) | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 0.14 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 1491000 | FY 2026: 1116000; FY 2027: 375000
U-5703B | Highway | STI (Prioritization) | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 0.14 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | O | CONSTRUCTION | 250000 | FY 2026: 22000; FY 2027: 228000
U-5704 | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1100000
U-5704 | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 21182000
U-5704 | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3400000
U-5704 | Highway | STI (Prioritization) | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 14100000
U-5706 | Highway | STI (Prioritization) | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 8 |  |  |  | 1685000
U-5706 | Highway | STI (Prioritization) | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 8 |  | T | RIGHT-OF-WAY | 8600000 |  |  | 86000 | 2207000 | 2752000 | 1835000 | 860000 | 860000
U-5706 | Highway | STI (Prioritization) | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 8 |  | T | UTILITIES | 1800000 | FY 2026: 900000; FY 2027: 900000
U-5706 | Highway | STI (Prioritization) | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 8 |  | T | BUILD NC CON | 12870000 | FY 2029: 858000; FY 2030: 858000; FY 2031: 858000; FY 2032: 858000; FY 2033: 858000 | 8580000
U-5706 | Highway | STI (Prioritization) | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 8 |  | T | CONSTRUCTION | 18200000 | FY 2030: 2948000; FY 2031: 9276000; FY 2032: 5976000
U-5709 | Highway | STI (Prioritization) | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 1214000
U-5709 | Highway | STI (Prioritization) | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | RIGHT-OF-WAY | 3427000
U-5709 | Highway | STI (Prioritization) | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 1700000
U-5709 | Highway | STI (Prioritization) | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 13198000 | FY 2026: 132000; FY 2027: 5978000; FY 2028: 5294000; FY 2029: 1794000
U-5710 | Highway | STI (Prioritization) | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  |  |  | 8833000
U-5710 | Highway | STI (Prioritization) | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 16900000 | FY 2024: 6591000; FY 2025: 6760000; FY 2026: 1690000; FY 2027: 1690000
U-5710 | Highway | STI (Prioritization) | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 4000000 | FY 2024: 2000000
U-5710 | Highway | STI (Prioritization) | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 45001000 | FY 2026: 450000; FY 2027: 14294000; FY 2028: 14797000; FY 2029: 10697000; FY 2030: 4763000
U-5710A | Highway | STI (Prioritization) | NEW LOCATION | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 2575000
U-5710A | Highway | STI (Prioritization) | NEW LOCATION | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGANY | CONSTRUCTION | 8200000
U-5711 | Highway | STI (Prioritization) | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | 0.61 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 2376000
U-5711 | Highway | STI (Prioritization) | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | 0.61 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 8800000 | FY 2025: 88000; FY 2026: 5896000; FY 2027: 2816000
U-5713 | Highway | STI (Prioritization) | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 1.8 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  |  |  | 1700000
U-5713 | Highway | STI (Prioritization) | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 1.8 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | RIGHT-OF-WAY | 88668000 | FY 2024: 10876000; FY 2025: 2192000
U-5713 | Highway | STI (Prioritization) | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 1.8 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | UTILITIES | 1000000
U-5713 | Highway | STI (Prioritization) | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 1.8 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | Statewide Mobility |  | T | CONSTRUCTION | 152337000 | FY 2024: 23299000; FY 2025: 45660000; FY 2026: 14000000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  |  |  | 2150000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | RIGHT-OF-WAY | 42556000 | 6906000 | 5000000 |  |  | 3796000 | 5694000 | 4270000 | 1720000 | 1720000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | UTILITIES | 2900000 | FY 2028: 1450000; FY 2029: 1450000
U-5716 | Highway | STI (Prioritization) | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | Statewide Mobility |  | T | CONSTRUCTION | 49599000 | FY 2030: 2385000; FY 2031: 16951000; FY 2032: 14675000; FY 2033: 10457000 | 5131000
U-5717 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | Statewide Mobility |  |  |  | 11400000
U-5717 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | Statewide Mobility |  | NHP | CONSTRUCTION | 53300000 | FY 2028: 16523000; FY 2029: 19188000; FY 2030: 13325000; FY 2031: 4264000
U-5720 | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO EAST OF SR 2095 (PAGE ROAD EXTENSION). UPGRADE TO CONTROLLED-ACCESS FACILITY AND CONVERT SR 1811 AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | [5 empty] | 2000000
U-5720A | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 1.56 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 93000000
U-5720A | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 1.56 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2900000
U-5720A | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 1.56 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 67900000
U-5720B | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 145000000
U-5720B | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2900000
U-5720B | Highway | STI (Prioritization) | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 164200000
U-5720C | Highway | STI (Prioritization) | US 70 | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PROJECT DELETED - WORK TO BE ACCOMPLISHED UNDER U-5720B
U-5722 | Highway | STI (Prioritization) | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 3.4 | LEE | 8 | Central Pines RPO |  | Region E |  |  |  | 3500000
U-5722 | Highway | STI (Prioritization) | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 3.4 | LEE | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 24700000 | FY 2028: 3640000; FY 2029: 6240000; FY 2030: 6240000; FY 2031: 3640000; FY 2032: 4940000
U-5722 | Highway | STI (Prioritization) | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 3.4 | LEE | 8 | Central Pines RPO |  | Region E |  | T | UTILITIES | 7564000 | FY 2028: 3782000; FY 2029: 3782000
U-5722 | Highway | STI (Prioritization) | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 3.4 | LEE | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 15099000 | FY 2031: 2419000; FY 2032: 7091000; FY 2033: 4752000 | 837000
U-5723 | Highway | STI (Prioritization) | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | 1 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | Statewide Mobility |  |  |  | 3846000
U-5723 | Highway | STI (Prioritization) | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | 1 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | Statewide Mobility |  | T | CONSTRUCTION | 16500000 | FY 2028: 6765000; FY 2029: 6270000; FY 2030: 3465000
U-5724 | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 0.62 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  |  |  | 2670000
U-5724 | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 0.62 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | RIGHT-OF-WAY | 1322000 | FY 2025: 1322000
U-5724 | Highway | STI (Prioritization) | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 0.62 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 19839000 | FY 2024: 7164000; FY 2025: 4163000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 1.63 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  |  |  | 17376000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 1.63 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | ENGINEERING | 2130000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 284000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 1.63 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | BUILD NC CON | 14880000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 1984000
U-5725 | Highway | STI (Prioritization) | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 1.63 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | Division 4 |  | T | CONSTRUCTION | 12360000
U-5726 | Highway | STI (Prioritization) | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.58 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 750000
U-5726 | Highway | STI (Prioritization) | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.58 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | RIGHT-OF-WAY | 13901000 |  | 1043000 | 4170000 | 4170000 | 1738000 | 1390000 | 1390000
U-5726 | Highway | STI (Prioritization) | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.58 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | UTILITIES | 4300000 | FY 2025: 2150000; FY 2026: 2150000
U-5726 | Highway | STI (Prioritization) | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.58 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | CONSTRUCTION | 29100000 | FY 2028: 7857000; FY 2029: 12513000; FY 2030: 8730000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 0.8 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 3000000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 0.8 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | Region E |  | NHP | RIGHT-OF-WAY | 12300000 | FY 2024: 6150000; FY 2025: 3075000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 0.8 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | Region E |  | NHP | UTILITIES | 1500000
U-5727 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 0.8 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 18400000 | FY 2026: 5931000; FY 2027: 7749000; FY 2028: 4720000
U-5728 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 3201000
U-5728 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | RIGHT-OF-WAY | 590000 | FY 2024: 590000
U-5728 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | BG50200 | CONSTRUCTION | 6500000 | FY 2026: 65000; FY 2027: 4225000; FY 2028: 2210000
U-5729 | Highway | STI (Prioritization) | US 421 (CAROLINA BEACH ROAD) | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.6 | NEW HANOVER | 3 | Wilmington Urban Area MPO | [5 empty] | 14510000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.54 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 21200000 | FY 2028: 5300000; FY 2029: 10600000; FY 2030: 5300000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.54 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | T | UTILITIES | 6560000 | FY 2028: 3280000; FY 2029: 3280000
U-5729REG | Highway | STI (Prioritization) | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.54 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | T | CONSTRUCTION | 16160000 | FY 2030: 5818000; FY 2031: 6302000; FY 2032: 4040000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 5300000 | FY 2028: 1325000; FY 2029: 2650000; FY 2030: 1325000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | UTILITIES | 1640000 | FY 2028: 820000; FY 2029: 820000
U-5729SW | Highway | STI (Prioritization) | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 4040000 | FY 2030: 1454000; FY 2031: 1576000; FY 2032: 1010000
U-5730 | Highway | STI (Prioritization) | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 200000
U-5730 | Highway | STI (Prioritization) | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | UTILITIES | 125000
U-5730 | Highway | STI (Prioritization) | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | CONSTRUCTION | 1400000 | FY 2026: 462000; FY 2027: 938000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  |  |  | 1500000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 6099000 | FY 2027: 1514000; FY 2028: 2019000; FY 2029: 1346000; FY 2030: 610000; FY 2031: 610000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | UTILITIES | 590000 | FY 2027: 590000
U-5731 | Highway | STI (Prioritization) | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 6800000 | FY 2029: 361000; FY 2030: 2510000; FY 2031: 2085000; FY 2032: 1435000; FY 2033: 409000
U-5732 | Highway | STI (Prioritization) | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5.51 | PENDER | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 18604000
U-5732 | Highway | STI (Prioritization) | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5.51 | PENDER | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 19536000
U-5732 | Highway | STI (Prioritization) | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5.51 | PENDER | 3 | Wilmington Urban Area MPO |  | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 35900000
U-5732A | Highway | STI (Prioritization) | DAN OWEN DRIVE EXTENSION | SR 1570 (FACTORY ROAD) TO DAN OWEN DRIVE. |  | PENDER | 3 | Wilmington Urban Area MPO | COMPLETED. | Region B
U-5734 | Highway | STI (Prioritization) | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 0.99 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  |  |  | 1000000
U-5734 | Highway | STI (Prioritization) | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 0.99 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | RIGHT-OF-WAY | 14800000 | FY 2025: 148000; FY 2026: 6817000; FY 2027: 4875000; FY 2028: 1480000; FY 2029: 1480000
U-5734 | Highway | STI (Prioritization) | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 0.99 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
U-5734 | Highway | STI (Prioritization) | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 0.99 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | CONSTRUCTION | 15700000 | FY 2027: 1129000; FY 2028: 7731000; FY 2029: 5414000; FY 2030: 1426000
U-5735 | Highway | STI (Prioritization) | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1900000
U-5735 | Highway | STI (Prioritization) | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | RIGHT-OF-WAY | 28864000 | FY 2027: 2566000; FY 2028: 10263000; FY 2029: 10263000; FY 2030: 2886000; FY 2031: 2886000
U-5735 | Highway | STI (Prioritization) | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 8328000 | FY 2027: 4164000; FY 2028: 4164000
U-5735 | Highway | STI (Prioritization) | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 52699000 | FY 2031: 4690000; FY 2032: 17670000; FY 2033: 15008000 | 15331000
U-5735A | Highway | STI (Prioritization) | US 17 (WILMINGTON HIGHWAY) | ROADWAY IMPROVEMENTS TO DOUGLAS GATE ENTRANCE. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS. | Exempt |  | O | CONSTRUCTION | 1075000
U-5736 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | Region B |  |  |  | 7800000
U-5736 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | Region B |  | BG50200 | RIGHT-OF-WAY | 16099000 | FY 2028: 5724000; FY 2029: 5724000; FY 2030: 1431000; FY 2031: 1610000; FY 2032: 1610000
U-5736 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | Region B |  | BG50200 | UTILITIES | 3400000 | FY 2028: 1700000; FY 2029: 1700000
U-5736 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | Region B |  | BG50200 | CONSTRUCTION | 45800000 | FY 2030: 5158000; FY 2031: 16188000; FY 2032: 13442000; FY 2033: 9189000 | 1823000
U-5737 | Highway | STI (Prioritization) | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 2.64 | CHATHAM | 8 | Central Pines RPO |  | Region E |  |  |  | 1656000
U-5737 | Highway | STI (Prioritization) | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 2.64 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 10800000 | FY 2025: 1620000; FY 2026: 2484000; FY 2027: 2484000; FY 2028: 2052000; FY 2029: 2160000
U-5737 | Highway | STI (Prioritization) | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 2.64 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | T | UTILITIES | 3400000 | FY 2025: 680000; FY 2026: 1360000; FY 2027: 1360000
U-5737 | Highway | STI (Prioritization) | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 2.64 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 40300000 | FY 2029: 5993000; FY 2030: 13603000; FY 2031: 11055000; FY 2032: 7606000; FY 2033: 2043000
U-5738 | Highway | STI (Prioritization) | SR 2528 (JULIAN ROAD) | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.28 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  |  |  | 3900000
U-5738 | Highway | STI (Prioritization) | SR 2528 (JULIAN ROAD) | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.28 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | T | CONSTRUCTION | 14995000 | FY 2024: 4777000; FY 2025: 1368000
U-5739 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.16 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  |  |  | 5200000
U-5739 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.16 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | RIGHT-OF-WAY | 3500000 | FY 2028: 187000; FY 2029: 2240000; FY 2030: 373000; FY 2031: 350000; FY 2032: 350000
U-5739 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.16 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | UTILITIES | 3100000 | FY 2028: 1550000; FY 2029: 1550000
U-5739 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.16 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | Region B |  | T | CONSTRUCTION | 27699000 | FY 2030: 3618000; FY 2031: 11533000; FY 2032: 8645000; FY 2033: 3903000
U-5741 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 11.18 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2500000
U-5741 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 11.18 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7368000
U-5741 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 11.18 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3664000
U-5741 | Highway | STI (Prioritization) | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 11.18 | ONSLOW | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | Region B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 49601000
U-5742 | Highway | STI (Prioritization) | FAYETTEVILLE | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | 0 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region C |  |  |  | 9034000
U-5742 | Highway | STI (Prioritization) | FAYETTEVILLE | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | 0 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region C |  | T | BUILD NC CON | 735000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 2151000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | RIGHT-OF-WAY | 2006000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | UTILITIES | 900000
U-5743 | Highway | STI (Prioritization) | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 13600000 | FY 2025: 1496000; FY 2026: 6392000; FY 2027: 4352000; FY 2028: 1360000
U-5744 | Highway | STI (Prioritization) | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1700000
U-5744 | Highway | STI (Prioritization) | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 783000
U-5744 | Highway | STI (Prioritization) | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 138000
U-5744 | Highway | STI (Prioritization) | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 24700000
U-5745 | Highway | STI (Prioritization) | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  |  |  | 2749000
U-5745 | Highway | STI (Prioritization) | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | ENGINEERING | 624000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 78000
U-5745 | Highway | STI (Prioritization) | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC ROW | 435000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
U-5745 | Highway | STI (Prioritization) | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC CON | 1313000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 81000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 0.81 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 4276000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 0.81 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | RIGHT-OF-WAY | 3638000 | FY 2024: 700000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 0.81 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | UTILITIES | 610000
U-5746 | Highway | STI (Prioritization) | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 0.81 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 5699000 | FY 2025: 3005000; FY 2026: 2694000
U-5747 | Highway | STI (Prioritization) | NC 54; SR 1635 (MCCRIMMON PARKWAY) | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | 2 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) |  |  |  |  | 9396000
U-5747 | Highway | STI (Prioritization) | NC 54; SR 1635 (MCCRIMMON PARKWAY) | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | 2 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) |  |  | T | ENGINEERING | 3001000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 201000
U-5747A | Highway | STI (Prioritization) | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.07 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | Division 5 |  | T | RIGHT-OF-WAY | 5000000 | FY 2024: 1000000
U-5747A | Highway | STI (Prioritization) | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.07 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | Division 5 |  | T | UTILITIES | 500000
U-5747A | Highway | STI (Prioritization) | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.07 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | Division 5 |  | T | CONSTRUCTION | 28100000 | FY 2026: 8547000; FY 2027: 11265000; FY 2028: 5957000; FY 2029: 2331000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | BUILD NC ROW | 72000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 7000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | RIGHT-OF-WAY | 2000000 | FY 2024: 2000000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | UTILITIES | 620000 | FY 2024: 620000
U-5747B | Highway | STI (Prioritization) | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Region C |  | T | CONSTRUCTION | 31700000 | FY 2026: 9083000; FY 2027: 12069000; FY 2028: 6739000; FY 2029: 3809000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 2133000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  | T | ENGINEERING | 1921000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  | T | BUILD NC ROW | 1996000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  | T | RIGHT-OF-WAY | 4844000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  | T | UTILITIES | 212000
U-5748 | Highway | STI (Prioritization) | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 22500000 | FY 2024: 1492000; FY 2025: 9573000; FY 2026: 7309000; FY 2027: 4126000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  |  |  | 12093000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | ENGINEERING | 1620000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | BUILD NC ROW | 3468000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | UTILITIES | 1700000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | BUILD NC CON | 10290000 |  |  | 686000 | 686000 | 686000 | 686000 | 686000 | 686000 | 686000 | 686000 | 4802000
U-5750 | Highway | STI (Prioritization) | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $8 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 21400000 | FY 2026: 1114000; FY 2027: 9702000; FY 2028: 6762000; FY 2029: 3822000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 3 | WAKE | 5 | Capital Area MPO |  | Region C |  |  |  | 700000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 3 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 39151000 | FY 2028: 6594000; FY 2029: 9891000; FY 2030: 9891000; FY 2031: 4945000; FY 2032: 7830000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 3 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 3300000 | FY 2028: 1650000; FY 2029: 1650000
U-5751 | Highway | STI (Prioritization) | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 3 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 82897000 | FY 2031: 7498000; FY 2032: 24580000; FY 2033: 21467000 | 29352000
U-5753 | Highway | STI (Prioritization) | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | HOKE | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 800000
U-5753 | Highway | STI (Prioritization) | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | HOKE | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BGANY | RIGHT-OF-WAY | 42100000 | FY 2024: 20000000; FY 2025: 4200000; FY 2026: 4200000
U-5753 | Highway | STI (Prioritization) | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | HOKE | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BGANY | UTILITIES | 5000000
U-5753 | Highway | STI (Prioritization) | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | HOKE | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | BUILD NC CON | 12870000 |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 6006000
U-5753 | Highway | STI (Prioritization) | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | HOKE | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 35400000 | FY 2026: 0; FY 2027: 4794000; FY 2028: 14800000; FY 2029: 10813000; FY 2030: 4993000
U-5754 | Highway | STI (Prioritization) | US 29 / US 70 / US 220 (O'HENRY BOULEVARD) | I-40 / BUSINESS 85 TO SOUTH OF FLORIDA STREET IN GREENSBORO. ADD LANE ON I-40 / BUSINESS 85 EASTBOUND RAMP ONTO NORTHBOUND US 29 / US 70 / US 220 AND EXTEND US 29 / US 70 / US 220 SOUTHBOUND RAMP ONTO SR 3762 (MARTIN LUTHER KING, JR. DRIVE) | 0.69 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | T | CONSTRUCTION | 6750000 | FY 2024: 237000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 3.94 | MOORE | 8 | Central Pines RPO |  | Region E |  |  |  | 2800000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 3.94 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 8600000 | FY 2024: 6300000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 3.94 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | UTILITIES | 13200000 | FY 2024: 9100000
U-5756 | Highway | STI (Prioritization) | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 3.94 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 119700000 | FY 2025: 1197000; FY 2026: 33860000; FY 2027: 33530000; FY 2028: 28656000; FY 2029: 22457000
U-5757 | Highway | STI (Prioritization) | NC 8 (WINSTON ROAD) | US 29 / US 70 TO SR 1846 (ARRINGTON DRIVE) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.51 | DAVIDSON | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  |  |  | 1861000
U-5757 | Highway | STI (Prioritization) | NC 8 (WINSTON ROAD) | US 29 / US 70 TO SR 1846 (ARRINGTON DRIVE) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.51 | DAVIDSON | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 17575000
U-5757 | Highway | STI (Prioritization) | NC 8 (WINSTON ROAD) | US 29 / US 70 TO SR 1846 (ARRINGTON DRIVE) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.51 | DAVIDSON | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 14400000 | FY 2025: 4419000; FY 2026: 6099000; FY 2027: 3882000
U-5760 | Highway | STI (Prioritization) | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  |  |  | 2905000
U-5760 | Highway | STI (Prioritization) | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | RIGHT-OF-WAY | 11500000 | FY 2024: 5500000
U-5760 | Highway | STI (Prioritization) | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | UTILITIES | 4000000 | FY 2024: 1900000
U-5760 | Highway | STI (Prioritization) | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | BUILD NC CON | 12870000 |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 6006000
U-5760 | Highway | STI (Prioritization) | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | CONSTRUCTION | 31200000 | FY 2025: 24000; FY 2026: 15584000; FY 2027: 2796000; FY 2028: 8957000; FY 2029: 3839000
U-5761 | Highway | STI (Prioritization) | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  |  |  | 3660000
U-5761 | Highway | STI (Prioritization) | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 8100000 | FY 2027: 3963000; FY 2028: 3430000; FY 2029: 707000
U-5763 | Highway | STI (Prioritization) | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1000000
U-5763 | Highway | STI (Prioritization) | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 16000000 | FY 2026: 2422000; FY 2027: 4151000; FY 2028: 4151000; FY 2029: 2076000; FY 2030: 3200000
U-5763 | Highway | STI (Prioritization) | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 5600000 | FY 2026: 2800000; FY 2027: 2800000
U-5763 | Highway | STI (Prioritization) | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 0.75 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 21701000 | FY 2029: 217000; FY 2030: 9986000; FY 2031: 7628000; FY 2032: 3870000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 2.8 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  |  |  | 10572000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 2.8 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | RIGHT-OF-WAY | 24501000 |  | 1000000 | 3356000 | 5227000 | 5227000 | 4791000 | 4900000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 2.8 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | UTILITIES | 7400000 | FY 2025: 3700000; FY 2026: 3700000
U-5764 | Highway | STI (Prioritization) | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 2.8 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | Region E |  | BGANY | CONSTRUCTION | 74700000 | FY 2030: 747000; FY 2031: 27955000; FY 2032: 24347000; FY 2033: 14384000 | 7267000
U-5765 | Highway | STI (Prioritization) | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 1.12 | MECKLENBURG | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | Region E |  |  |  | 510000
U-5765 | Highway | STI (Prioritization) | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 1.12 | MECKLENBURG | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | RIGHT-OF-WAY | 58430000 | FY 2024: 14023000; FY 2025: 14023000; FY 2026: 11686000; FY 2027: 11686000
U-5765 | Highway | STI (Prioritization) | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 1.12 | MECKLENBURG | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 7500000 | FY 2024: 3750000
U-5765 | Highway | STI (Prioritization) | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 1.12 | MECKLENBURG | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 29201000 | FY 2027: 292000; FY 2028: 11987000; FY 2029: 9884000; FY 2030: 5491000; FY 2031: 1547000
U-5766 | Highway | STI (Prioritization) | NC 160 | SOUTH CAROLINA LINE TO I-485. WIDEN TO MULTI-LANES. | 6.8 | MECKLENBURG | 10 | Charlotte Regional TPO | [5 empty] | 3000000
U-5766A | Highway | STI (Prioritization) | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 2.04 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 20500000 | FY 2025: 3364000; FY 2026: 5046000; FY 2027: 5046000; FY 2028: 2944000; FY 2029: 4100000
U-5766A | Highway | STI (Prioritization) | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 2.04 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 4100000 | FY 2025: 2050000; FY 2026: 2050000
U-5766A | Highway | STI (Prioritization) | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 2.04 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 65399000 | FY 2028: 654000; FY 2029: 25482000; FY 2030: 23858000; FY 2031: 12866000; FY 2032: 2539000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (SOUTH TRYON ROAD) TO SR 1116 (SHOPTON ROAD WEST). WIDEN TO MULTI-LANES. | 4.31 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 59400000 | FY 2026: 11181000; FY 2027: 16772000; FY 2028: 16772000; FY 2029: 2795000; FY 2030: 11880000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (SOUTH TRYON ROAD) TO SR 1116 (SHOPTON ROAD WEST). WIDEN TO MULTI-LANES. | 4.31 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 6500000 | FY 2026: 3250000; FY 2027: 3250000
U-5766B | Highway | STI (Prioritization) | NC 160 | NC 49 (SOUTH TRYON ROAD) TO SR 1116 (SHOPTON ROAD WEST). WIDEN TO MULTI-LANES. | 4.31 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 65801000 | FY 2029: 14434000; FY 2030: 22599000; FY 2031: 15409000; FY 2032: 9539000; FY 2033: 3820000
U-5767 | Highway | STI (Prioritization) | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | Region E |  |  |  | 4593000
U-5767 | Highway | STI (Prioritization) | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | Region E |  | T | BUILD NC ROW | 15180000 |  |  | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 7084000
U-5767 | Highway | STI (Prioritization) | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | Region E |  | T | RIGHT-OF-WAY | 23900000 | FY 2026: 239000; FY 2027: 2241000; FY 2028: 9520000; FY 2029: 4760000; FY 2030: 7140000
U-5767 | Highway | STI (Prioritization) | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | Region E |  | T | UTILITIES | 2700000 | FY 2026: 1350000; FY 2027: 1350000
U-5767 | Highway | STI (Prioritization) | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | Region E |  | T | CONSTRUCTION | 27303000 | FY 2030: 9036000; FY 2031: 10467000; FY 2033: 7800000
U-5768 | Highway | STI (Prioritization) | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  |  |  | 2000000
U-5768 | Highway | STI (Prioritization) | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | RIGHT-OF-WAY | 29400000 | FY 2027: 4181000; FY 2028: 6272000; FY 2029: 6272000; FY 2030: 6272000; FY 2031: 6403000
U-5768 | Highway | STI (Prioritization) | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | UTILITIES | 7500000 | FY 2027: 3750000; FY 2028: 3750000
U-5768 | Highway | STI (Prioritization) | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | T | CONSTRUCTION | 55400000 | FY 2031: 14958000; FY 2032: 17174000; FY 2033: 11634000 | 11634000
U-5768 | Highway | STI (Prioritization) | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | Region E |  | L | CONSTRUCTION | 25000000 | FY 2031: 6750000; FY 2032: 7750000; FY 2033: 5250000 | 5250000
U-5769 | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 5.7 | UNION | 10 | Charlotte Regional TPO | [5 empty] | 3840000
U-5769A | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 4.05 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 29801000 | FY 2025: 954000; FY 2026: 5722000; FY 2027: 5722000; FY 2028: 5722000; FY 2029: 11681000
U-5769A | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 4.05 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 10000 | FY 2025: 10000
U-5769A | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 4.05 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 26402000 | FY 2029: 9769000; FY 2030: 9505000; FY 2031: 5016000; FY 2032: 2112000
U-5769AA | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 4000000 | FY 2024: 4000000
U-5769AA | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 1000000 | FY 2024: 1000000
U-5769AA | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 1100000 | FY 2026: 435000; FY 2027: 665000
U-5769B | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 1.73 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 18200000 | FY 2025: 582000; FY 2026: 3495000; FY 2027: 3495000; FY 2028: 3495000; FY 2029: 7133000
U-5769B | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 1.73 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 10000 | FY 2025: 10000
U-5769B | Highway | STI (Prioritization) | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 1.73 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 31400000 | FY 2029: 10990000; FY 2030: 10990000; FY 2031: 6280000; FY 2032: 3140000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 1 | RANDOLPH | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  |  |  | 1702000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 1 | RANDOLPH | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  | T | RIGHT-OF-WAY | 6358000
U-5770 | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 1 | RANDOLPH | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | Region E |  | T | UTILITIES | 2200000
U-5770A | Highway | STI (Prioritization) | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | 1.07 | RANDOLPH | 8 | High Point Urban Area MPO |  | Region E |  | S | CONSTRUCTION | 669000 | FY 2024: 580000
U-5770A | Highway | STI (Prioritization) | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | 1.07 | RANDOLPH | 8 | High Point Urban Area MPO |  | Region E |  | T | CONSTRUCTION | 1024000 | FY 2024: 888000
U-5770B | Highway | STI (Prioritization) | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | 0.99 | RANDOLPH | 8 | High Point Urban Area MPO |  | Region E |  | T | CONSTRUCTION | 17501000 | FY 2027: 3068000; FY 2028: 7226000; FY 2029: 5046000; FY 2030: 2161000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  |  |  | 2098000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | BA | RIGHT-OF-WAY | 450000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | RIGHT-OF-WAY | 52600000 | FY 2024: 12525000; FY 2025: 14000000; FY 2026: 5000000; FY 2027: 5000000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 1600000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T(DA) | CONSTRUCTION | 2560000 | FY 2027: 403000; FY 2028: 1176000; FY 2029: 698000; FY 2030: 283000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 32100000 | FY 2027: 5051000; FY 2028: 14745000; FY 2029: 8750000; FY 2030: 3554000
U-5771 | Highway | STI (Prioritization) | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | L | CONSTRUCTION | 650000 | FY 2027: 650000
U-5772 | Highway | STI (Prioritization) | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 2.16 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 3500000
U-5772 | Highway | STI (Prioritization) | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 2.16 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 6500000 | FY 2028: 709000; FY 2029: 2836000; FY 2030: 1655000; FY 2031: 650000; FY 2032: 650000
U-5772 | Highway | STI (Prioritization) | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 2.16 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 4300000 | FY 2028: 2150000; FY 2029: 2150000
U-5772 | Highway | STI (Prioritization) | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 2.16 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 33700000 | FY 2031: 337000; FY 2032: 13569000; FY 2033: 11258000 | 8536000
U-5774 | Highway | STI (Prioritization) | NC 54 | US 15 / US 501 IN CHAPEL HILL TO NC 55 IN DURHAM. UPGRADE ROADWAY CORRIDOR. | 8.4 | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | PARTS A THROUGH F ON EXPANDED NHS |  |  |  |  | 1905000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2800000 | [10 empty] | 2800000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 140000 | [10 empty] | 140000
U-5774A | Highway | STI (Prioritization) | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 16100000 | [10 empty] | 16100000
U-5774B | Highway | STI (Prioritization) | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 1.22 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 43001000
U-5774B | Highway | STI (Prioritization) | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 1.22 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 74000
U-5774B | Highway | STI (Prioritization) | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 1.22 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 23300000
U-5774C | Highway | STI (Prioritization) | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 1.64 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 934000
U-5774C | Highway | STI (Prioritization) | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 1.64 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 267000
U-5774C | Highway | STI (Prioritization) | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 1.64 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11599000
U-5774D | Highway | STI (Prioritization) | NC 54 | FALCONBBRIDGE ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE INCLUDED IN U-5774F
U-5774E | Highway | STI (Prioritization) | NC 54 | SR 1110 (FARRINGTON ROAD). CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE INCLUDED IN U-5774F
U-5774F | Highway | STI (Prioritization) | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 91470000 | FY 2028: 16726000; FY 2029: 25089000; FY 2030: 25089000; FY 2031: 6272000; FY 2032: 18294000
U-5774F | Highway | STI (Prioritization) | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | UTILITIES | 2100000 | FY 2028: 2100000
U-5774F | Highway | STI (Prioritization) | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 88399000 | FY 2031: 16971000; FY 2032: 24714000; FY 2033: 20889000 | 25825000
U-5774G | Highway | STI (Prioritization) | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 1800000 | [10 empty] | 1800000
U-5774G | Highway | STI (Prioritization) | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 800000 | [10 empty] | 800000
U-5774G | Highway | STI (Prioritization) | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 16900000 | [10 empty] | 16900000
U-5774H | Highway | STI (Prioritization) | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5900000 | [10 empty] | 5900000
U-5774H | Highway | STI (Prioritization) | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 726000 | [10 empty] | 726000
U-5774H | Highway | STI (Prioritization) | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 18000000 | [10 empty] | 18000000
U-5774I | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2500000 | [10 empty] | 2500000
U-5774I | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 617000 | [10 empty] | 617000
U-5774I | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 12300000 | [10 empty] | 12300000
U-5774J | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3200000 | [10 empty] | 3200000
U-5774J | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | UTILITIES | 420000 | [10 empty] | 420000
U-5774J | Highway | STI (Prioritization) | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Not Funded |  | T | CONSTRUCTION | 17100000 | [10 empty] | 17100000
U-5775 | Highway | STI (Prioritization) | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | Region F |  |  |  | 1153000
U-5775 | Highway | STI (Prioritization) | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | Region F |  | T | CONSTRUCTION | 9663000
U-5775 | Highway | STI (Prioritization) | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | Region F |  | L | CONSTRUCTION | 703000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  |  |  | 275000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | RIGHT-OF-WAY | 2150000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | UTILITIES | 436000 | FY 2025: 436000
U-5777 | Highway | STI (Prioritization) | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | CONSTRUCTION | 3951000 | FY 2025: 1767000; FY 2026: 2184000
U-5779 | Highway | STI (Prioritization) | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 0.91 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5779 | Highway | STI (Prioritization) | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 0.91 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6400000
U-5779 | Highway | STI (Prioritization) | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 0.91 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9100000
U-5779 | Highway | STI (Prioritization) | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 0.91 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22098000
U-5780 | Highway | STI (Prioritization) | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  |  |  | 223000
U-5780 | Highway | STI (Prioritization) | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | RIGHT-OF-WAY | 550000
U-5780 | Highway | STI (Prioritization) | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | UTILITIES | 750000 | FY 2025: 750000
U-5780 | Highway | STI (Prioritization) | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | Region F |  | T | CONSTRUCTION | 3500000 | FY 2025: 36000; FY 2026: 3279000; FY 2027: 185000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 0.99 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  |  |  | 1500000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 0.99 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | RIGHT-OF-WAY | 19900000 | FY 2024: 2500000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 0.99 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | UTILITIES | 3900000 | FY 2024: 1750000
U-5783 | Highway | STI (Prioritization) | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 0.99 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | CONSTRUCTION | 26000000 | FY 2025: 8332000; FY 2026: 8678000; FY 2027: 5929000; FY 2028: 3061000
U-5785 | Highway | STI (Prioritization) | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 0.6 | PITT | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5870. | Division 2 |  |  |  | 18000000
U-5785 | Highway | STI (Prioritization) | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 0.6 | PITT | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5870. | Division 2 |  | T | RIGHT-OF-WAY | 58201000 | FY 2025: 5079000; FY 2026: 10159000; FY 2027: 10159000; FY 2028: 10159000; FY 2029: 22645000
U-5785 | Highway | STI (Prioritization) | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 0.6 | PITT | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5870. | Division 2 |  | T | UTILITIES | 7500000 | FY 2027: 3750000; FY 2028: 3750000
U-5785 | Highway | STI (Prioritization) | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 0.6 | PITT | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5870. | Division 2 |  | T | CONSTRUCTION | 48700000 | FY 2030: 19480000; FY 2031: 18019000; FY 2032: 11201000
U-5786 | Highway | STI (Prioritization) | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 2.91 | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  |  |  | 890000
U-5786 | Highway | STI (Prioritization) | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 2.91 | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 5000000 | FY 2026: 762000; FY 2027: 2286000; FY 2028: 952000; FY 2029: 500000; FY 2030: 500000
U-5786 | Highway | STI (Prioritization) | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 2.91 | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | UTILITIES | 5100000 | FY 2028: 2550000; FY 2029: 2550000
U-5786 | Highway | STI (Prioritization) | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 2.91 | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGANY | CONSTRUCTION | 21999000 | FY 2029: 7982000; FY 2030: 7879000; FY 2031: 5403000; FY 2032: 735000
U-5787 | Highway | STI (Prioritization) | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.28 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  |  |  | 800000
U-5787 | Highway | STI (Prioritization) | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.28 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T | RIGHT-OF-WAY | 2599000 | FY 2025: 371000; FY 2026: 891000; FY 2027: 817000; FY 2028: 260000; FY 2029: 260000
U-5787 | Highway | STI (Prioritization) | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.28 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T | UTILITIES | 890000 | FY 2025: 890000
U-5787 | Highway | STI (Prioritization) | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.28 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T | CONSTRUCTION | 5900000 | FY 2027: 59000; FY 2028: 3651000; FY 2029: 2190000
U-5788 | Highway | STI (Prioritization) | US 17 BUSINESS (MAIN STREET) | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | 0.5 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  |  |  | 1245000
U-5788 | Highway | STI (Prioritization) | US 17 BUSINESS (MAIN STREET) | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | 0.5 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 1964000 | FY 2024: 25000
U-5789 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  |  |  | 1983000
U-5789 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | CONSTRUCTION | 4551000 | FY 2025: 1552000; FY 2026: 2837000; FY 2027: 162000
U-5790 | Highway | STI (Prioritization) | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 1.03 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 1500000
U-5790 | Highway | STI (Prioritization) | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 1.03 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 6064000 | FY 2027: 485000; FY 2028: 2911000; FY 2029: 1456000; FY 2030: 606000; FY 2031: 606000
U-5790 | Highway | STI (Prioritization) | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 1.03 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | UTILITIES | 6428000 | FY 2027: 3214000; FY 2028: 3214000
U-5790 | Highway | STI (Prioritization) | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 1.03 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 20499000 | FY 2029: 1275000; FY 2030: 9206000; FY 2031: 6958000; FY 2032: 3060000
U-5791 | Highway | STI (Prioritization) | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) | NC 53 (WESTERN BOULEVARD) TO US 17 (NEW BERN HIGHWAY). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.83 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 1750000
U-5791A | Highway | STI (Prioritization) | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 1.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | RIGHT-OF-WAY | 16300000 | FY 2027: 163000; FY 2028: 5379000; FY 2029: 7498000; FY 2030: 1630000; FY 2031: 1630000
U-5791A | Highway | STI (Prioritization) | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 1.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | UTILITIES | 850000 | FY 2027: 425000; FY 2028: 425000
U-5791A | Highway | STI (Prioritization) | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 1.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | BUILD NC CON | 12870000 | FY 2029: 1716000; FY 2030: 858000; FY 2031: 858000; FY 2032: 858000; FY 2033: 858000 | 7722000
U-5791A | Highway | STI (Prioritization) | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 1.55 | ONSLOW | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | CONSTRUCTION | 49800000 | FY 2029: 0; FY 2030: 8538000; FY 2031: 17940000; FY 2032: 13754000; FY 2033: 9568000
U-5791B | Highway | STI (Prioritization) | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 7900000 | [10 empty] | 7900000
U-5791B | Highway | STI (Prioritization) | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 4100000 | [10 empty] | 4100000
U-5791B | Highway | STI (Prioritization) | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 22600000 | [10 empty] | 22600000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 1.9 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 1500000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 1.9 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | RIGHT-OF-WAY | 29100000 |  | 1330000 | 7982000 | 7982000 | 5986000 | 2910000 | 2910000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 1.9 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | UTILITIES | 3200000 | FY 2025: 1600000; FY 2026: 1600000
U-5792 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 1.9 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | CONSTRUCTION | 109600000 | FY 2028: 9407000; FY 2029: 31429000; FY 2030: 28389000; FY 2031: 23149000; FY 2032: 17226000
U-5793 | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3.8 | ONSLOW | 3 | Jacksonville Urban Area MPO | [5 empty] | 10000
U-5793A | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 0.68 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6200000
U-5793A | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 0.68 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-5793A | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 0.68 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9199000
U-5793B | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3.1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 15600000
U-5793B | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3.1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7100000
U-5793B | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3.1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40100000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  |  |  | 750000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 717000 | [10 empty] | 717000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 73000 | [10 empty] | 73000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000 | [10 empty] | 10000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 100000 | [10 empty] | 100000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 100000 | [10 empty] | 100000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | UTILITIES | 946000 | [10 empty] | 946000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | CONSTRUCTION | 3388000 | [10 empty] | 3388000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | CONSTRUCTION | 4393000 | [10 empty] | 4393000
U-5794 | Highway | STI (Prioritization) | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 3.46 | WILSON | 4 | Upper Coastal Plain RPO |  | Not Funded |  | T | CONSTRUCTION | 1418000 | [10 empty] | 1418000
U-5796 | Highway | STI (Prioritization) | US 117 | SR 1120 (O'BERRY ROAD) IN GOLDSBORO. CONSTRUCT INTERCHANGE. | 1 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 1980000
U-5797 | Highway | STI (Prioritization) | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 1.26 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  |  |  | 1334000
U-5797 | Highway | STI (Prioritization) | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 1.26 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | RIGHT-OF-WAY | 8200000 | FY 2024: 5101000
U-5797 | Highway | STI (Prioritization) | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 1.26 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | UTILITIES | 2600000 | FY 2024: 1300000; FY 2025: 1300000
U-5797 | Highway | STI (Prioritization) | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 1.26 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | T | CONSTRUCTION | 33799000 | FY 2025: 338000; FY 2026: 12135000; FY 2027: 11168000; FY 2028: 7949000; FY 2029: 2209000
U-5798 | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | US 401 (RAEFORD ROAD) TO SR 1418 (LINDSAY ROAD). WIDEN TO FOUR LANES. | 2.4 | CUMBERLAND, HOKE | 6, 8 | Fayetteville Area MPO | COORDINATE WITH U-5753, U-5857, AND U-5858. | Division 6, 8 |  |  |  | 1010000
U-5798A | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 1.07 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | RIGHT-OF-WAY | 9322000 | FY 2024: 2000000; FY 2025: 3000000
U-5798A | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 1.07 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | UTILITIES | 475000
U-5798A | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 1.07 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 26036000 | FY 2024: 9111000; FY 2025: 3905000
U-5798B | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 1.21 | CUMBERLAND, HOKE | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | RIGHT-OF-WAY | 3700000 | FY 2024: 1741000; FY 2025: 1219000; FY 2026: 370000; FY 2027: 370000
U-5798B | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 1.21 | CUMBERLAND, HOKE | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | UTILITIES | 710000 | FY 2024: 710000
U-5798B | Highway | STI (Prioritization) | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 1.21 | CUMBERLAND, HOKE | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 6, 8 |  | T | CONSTRUCTION | 15500000 | FY 2026: 1720000; FY 2027: 7174000; FY 2028: 5314000; FY 2029: 1292000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  |  |  | 543000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | ENGINEERING | 2265000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | BUILD NC ROW | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | RIGHT-OF-WAY | 22300000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | UTILITIES | 4000000 | FY 2024: 1950000; FY 2025: 1950000
U-5799 | Highway | STI (Prioritization) | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 0.81 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Region F |  | T | CONSTRUCTION | 22118000 | FY 2026: 9914000; FY 2027: 7693000; FY 2028: 4511000
U-5800 | Highway | STI (Prioritization) | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | Region F |  |  |  | 180000
U-5800 | Highway | STI (Prioritization) | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | Region F |  | BG50200 | RIGHT-OF-WAY | 5200000 | FY 2025: 52000; FY 2026: 2028000; FY 2027: 2080000; FY 2028: 520000; FY 2029: 520000
U-5800 | Highway | STI (Prioritization) | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | Region F |  | BG50200 | UTILITIES | 3700000 | FY 2025: 1850000; FY 2026: 1850000
U-5800 | Highway | STI (Prioritization) | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | Region F |  | BG50200 | CONSTRUCTION | 8900000 | FY 2025: 851000; FY 2026: 6157000; FY 2027: 1892000
U-5802 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 1.21 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2500000
U-5802 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 1.21 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 33200000
U-5802 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 1.21 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4800000
U-5802 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 1.21 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25100000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  |  |  | 705000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 2400000 | FY 2025: 1200000; FY 2026: 1200000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 600000 | FY 2025: 600000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 5600000 | FY 2026: 2800000; FY 2027: 2800000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 7819000 | FY 2026: 3910000; FY 2027: 3909000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 4400000 | FY 2026: 2200000; FY 2027: 2200000
U-5803 | Highway | STI (Prioritization) | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 7819000 | FY 2026: 3910000; FY 2027: 3909000
U-5804 | Highway | STI (Prioritization) | SR 3448 (SOUTH TRADE STREET) | FULLWOOD LANE TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | [5 empty] | 2223000
U-5804A | Highway | STI (Prioritization) | SR 3448 (SOUTH TRADE STREET) | FULLWOOD LANE TO FOUR MILE CREEK. WIDEN TO FOUR-LANES. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
U-5804B | Highway | STI (Prioritization) | SR 3448 (SOUTH TRADE STREET) | FOUR MILE CREEK TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 0.13 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE). | Division 10 |  | T | BUILD NC CON | 1470000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000
U-5805 | Highway | STI (Prioritization) | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  |  |  | 42000
U-5805 | Highway | STI (Prioritization) | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | T | RIGHT-OF-WAY | 1218000
U-5805 | Highway | STI (Prioritization) | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 5952000 | FY 2025: 2976000; FY 2026: 2976000
U-5805 | Highway | STI (Prioritization) | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 1060000 | FY 2025: 530000; FY 2026: 530000
U-5805 | Highway | STI (Prioritization) | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | S(M) | CONSTRUCTION | 428000 | FY 2025: 214000; FY 2026: 214000
U-5806 | Highway | STI (Prioritization) | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 1 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  |  |  | 13096000
U-5806 | Highway | STI (Prioritization) | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 1 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  | T | ENGINEERING | 1755000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 234000
U-5806 | Highway | STI (Prioritization) | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 1 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 10 |  | T | BUILD NC CON | 10380000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 1384000
U-5807 | Highway | STI (Prioritization) | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 0.68 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | Division 10 |  |  |  | 1757000
U-5807 | Highway | STI (Prioritization) | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 0.68 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | Division 10 |  | T | BUILD NC ROW | 20595000 |  |  |  |  | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 12357000
U-5807 | Highway | STI (Prioritization) | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 0.68 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | Division 10 |  | T | RIGHT-OF-WAY | 17700000 | FY 2028: 0; FY 2029: 2790000; FY 2030: 8170000; FY 2031: 3370000; FY 2032: 3370000
U-5807 | Highway | STI (Prioritization) | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 0.68 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | Division 10 |  | T | UTILITIES | 2000000 | FY 2028: 1000000; FY 2029: 1000000
U-5807 | Highway | STI (Prioritization) | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 0.68 | MECKLENBURG | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | Division 10 |  | T | CONSTRUCTION | 8700000 | FY 2031: 87000; FY 2032: 5742000; FY 2033: 2523000 | 348000
U-5808 | Highway | STI (Prioritization) | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.39 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  |  |  | 2500000
U-5808 | Highway | STI (Prioritization) | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.39 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | T | BUILD NC CON | 15255000 |  | 1017000 | 1017000 | 1017000 | 1017000 | 2034000 | 1017000 | 1017000 | 1017000 | 1017000 | 5085000
U-5808 | Highway | STI (Prioritization) | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.39 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | T | CONSTRUCTION | 8061000 | FY 2024: 3599000; FY 2026: 3049000; FY 2027: 1413000
U-5809 | Highway | STI (Prioritization) | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 0.68 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  |  |  | 2450000
U-5809 | Highway | STI (Prioritization) | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 0.68 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  | T | UTILITIES | 800000
U-5809 | Highway | STI (Prioritization) | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 0.68 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | Division 11 |  | T | CONSTRUCTION | 18900000 | FY 2024: 189000; FY 2025: 7046000; FY 2026: 6931000; FY 2027: 4734000
U-5810 | Highway | STI (Prioritization) | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 11 |  |  |  | 883000
U-5810 | Highway | STI (Prioritization) | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 11 |  | T | BUILD NC ROW | 4500000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 900000
U-5810 | Highway | STI (Prioritization) | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 11 |  | T | RIGHT-OF-WAY | 8900000 | FY 2024: 4900000
U-5810 | Highway | STI (Prioritization) | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 11 |  | T | UTILITIES | 1500000
U-5810 | Highway | STI (Prioritization) | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | Division 11 |  | BG5T50 | CONSTRUCTION | 42400000 | FY 2025: 424000; FY 2026: 14840000; FY 2027: 13144000; FY 2028: 9328000; FY 2029: 4664000
U-5811 | Highway | STI (Prioritization) | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | 2.45 | WAKE | 5 | Capital Area MPO |  | Division 5 |  |  |  | 2000000
U-5811 | Highway | STI (Prioritization) | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | 2.45 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 13000000 | FY 2026: 5200000; FY 2027: 5200000; FY 2028: 1300000; FY 2029: 1300000
U-5811 | Highway | STI (Prioritization) | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | 2.45 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | UTILITIES | 2100000 | FY 2028: 1050000; FY 2029: 1050000
U-5811 | Highway | STI (Prioritization) | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | 2.45 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 42199000 | FY 2030: 422000; FY 2031: 15322000; FY 2032: 12515000; FY 2033: 8856000 | 5084000
U-5812 | Highway | STI (Prioritization) | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 525000
U-5812 | Highway | STI (Prioritization) | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 144000
U-5812 | Highway | STI (Prioritization) | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 36000
U-5812 | Highway | STI (Prioritization) | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 600000
U-5812 | Highway | STI (Prioritization) | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 150000
U-5813 | Highway | STI (Prioritization) | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 2.31 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  |  |  | 3000000
U-5813 | Highway | STI (Prioritization) | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 2.31 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | RIGHT-OF-WAY | 7967000
U-5813 | Highway | STI (Prioritization) | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 2.31 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | UTILITIES | 3000000
U-5813 | Highway | STI (Prioritization) | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 2.31 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | Region E |  | NHP | CONSTRUCTION | 62200000 | FY 2024: 622000; FY 2025: 24258000; FY 2026: 18038000; FY 2027: 13062000; FY 2028: 6220000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 1.24 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  |  |  | 3750000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 1.24 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  | T | RIGHT-OF-WAY | 11500000 | FY 2024: 6000000; FY 2025: 3000000
U-5814 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 1.24 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING. | Region E |  | T | UTILITIES | 1250000 | FY 2024: 1000000
U-5815 | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 2.9 | MOORE | 8 | Central Pines RPO |  | Region E |  |  |  | 4650000
U-5815A | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 0.58 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 4230000 | FY 2026: 2350000; FY 2027: 940000; FY 2028: 470000; FY 2029: 470000
U-5815A | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 0.58 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | RIGHT-OF-WAY | 470000 | FY 2025: 470000
U-5815A | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 0.58 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | UTILITIES | 3200000 | FY 2025: 1600000; FY 2026: 1600000
U-5815A | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 0.58 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 12700000 | FY 2027: 6064000; FY 2028: 5937000; FY 2029: 699000
U-5815B | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | 2.36 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814. | Region E |  | T | RIGHT-OF-WAY | 6650000 | FY 2024: 3325000
U-5815B | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | 2.36 | MOORE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814. | Region E |  | T | CONSTRUCTION | 154300000 | FY 2025: 18516000; FY 2026: 43204000; FY 2027: 38575000; FY 2028: 29317000; FY 2029: 24688000
U-5815BA | Highway | STI (Prioritization) | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. RELOCATE WATER TRANSMISSION LINE. | 2.36 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 17900000 | FY 2024: 6651000
U-5816 | Highway | STI (Prioritization) | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 1.56 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  |  |  | 500000
U-5816 | Highway | STI (Prioritization) | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 1.56 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | RIGHT-OF-WAY | 12600000 | FY 2026: 796000; FY 2027: 3183000; FY 2028: 3183000; FY 2029: 2918000; FY 2030: 2520000
U-5816 | Highway | STI (Prioritization) | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 1.56 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | UTILITIES | 3200000 | FY 2026: 1600000; FY 2027: 1600000
U-5816 | Highway | STI (Prioritization) | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 1.56 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | CONSTRUCTION | 29600000 | FY 2029: 296000; FY 2030: 10718000; FY 2031: 9740000; FY 2032: 6756000; FY 2033: 2090000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  |  |  | 4853000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | RIGHT-OF-WAY | 672000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGDA | RIGHT-OF-WAY | 2403000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BA | RIGHT-OF-WAY | 2725000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | UTILITIES | 1900000
U-5817 | Highway | STI (Prioritization) | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | Division 12 |  | BGANY | CONSTRUCTION | 25200000 | FY 2027: 252000; FY 2028: 9175000; FY 2029: 8365000; FY 2030: 5602000; FY 2031: 1806000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  |  |  | 2536000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 150000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 20000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 1560000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC ROW | 90000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 7725000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 1030000
U-5818 | Highway | STI (Prioritization) | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 5505000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000
U-5819 | Highway | STI (Prioritization) | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 200000
U-5819 | Highway | STI (Prioritization) | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 700000 | FY 2028: 700000
U-5819 | Highway | STI (Prioritization) | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | UTILITIES | 600000 | FY 2028: 600000
U-5819 | Highway | STI (Prioritization) | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | CONSTRUCTION | 2799000 | FY 2030: 710000; FY 2031: 1989000; FY 2032: 100000
U-5820 | Highway | STI (Prioritization) | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO US 52 (EAST INNES STREET) AT NEWSOME ROAD IN SALISBURY. CONSTRUCT A NEW MULTI-LANE ROADWAY. | 0.6 | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY |  |  |  |  | 5151000
U-5820A | Highway | STI (Prioritization) | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO SR 1006 (FAITH ROAD) IN SALISBURY. | 0.42 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 9 |  | T | BUILD NC CON | 2609000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000
U-5820B | Highway | STI (Prioritization) | NEW ROUTE | SR 1006 (FAITH ROAD) TO US 52 (EAST INNES STREET) IN SALISBURY. | 0.1 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | T | CONSTRUCTION | 1100000
U-5821 | Highway | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 3.79 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 1300000
U-5821 | Highway | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 3.79 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | BUILD NC ROW | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 8580000
U-5821 | Highway | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 3.79 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | RIGHT-OF-WAY | 31200000 | FY 2024: 0; FY 2025: 11508000; FY 2026: 9452000; FY 2027: 5120000; FY 2028: 5120000
U-5821 | Highway | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 3.79 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | UTILITIES | 6010000 | FY 2024: 3000000; FY 2025: 3000000
U-5821 | Highway | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 3.79 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | CONSTRUCTION | 51700000 | FY 2026: 5714000; FY 2027: 16610000; FY 2028: 14287000; FY 2029: 10141000; FY 2030: 4948000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  |  |  | 595000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | RIGHT-OF-WAY | 720000 | FY 2025: 720000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L | RIGHT-OF-WAY | 180000 | FY 2025: 180000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | UTILITIES | 320000 | FY 2025: 320000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L | UTILITIES | 80000 | FY 2025: 80000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | BGANY | CONSTRUCTION | 3000000 | FY 2026: 3000000
U-5823 | Highway | STI (Prioritization) | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | Division 5 |  | L | CONSTRUCTION | 750000 | FY 2026: 750000
U-5824 | Highway | STI (Prioritization) | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 1.61 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 24197000
U-5824 | Highway | STI (Prioritization) | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 1.61 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | BUILD NC CON | 12870000 |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 5148000
U-5824 | Highway | STI (Prioritization) | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 1.61 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 6318000 | FY 2026: 4328000; FY 2027: 1990000
U-5825 | Highway | STI (Prioritization) | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 3.3 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-6066 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3000000
U-5825 | Highway | STI (Prioritization) | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 3.3 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-6066 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 26800000
U-5825 | Highway | STI (Prioritization) | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 3.3 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-6066 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4700000
U-5825 | Highway | STI (Prioritization) | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 3.3 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-6066 | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 63901000
U-5826 | Highway | STI (Prioritization) | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 0.89 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  |  |  | 4569000
U-5826 | Highway | STI (Prioritization) | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 0.89 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T | RIGHT-OF-WAY | 280000 | FY 2024: 280000
U-5826 | Highway | STI (Prioritization) | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 0.89 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T | BUILD NC CON | 8100000 |  | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 540000 | 3240000
U-5826 | Highway | STI (Prioritization) | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 0.89 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | T | CONSTRUCTION | 23686000 | FY 2024: 18116000; FY 2025: 1456000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  |  |  | 54000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | ENGINEERING | 1215000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | ENGINEERING | 16000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 3000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC ROW | 1340000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 94000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC CON | 6987000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 562000
U-5827 | Highway | STI (Prioritization) | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | CONSTRUCTION | 712000
U-5828 | Highway | STI (Prioritization) | MCCRIMMON PARKWAY | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | 1.42 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 5 |  |  |  | 10935000
U-5828 | Highway | STI (Prioritization) | MCCRIMMON PARKWAY | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | 1.42 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Division 5 |  | T | BUILD NC CON | 3097000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 213000
U-5832 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 1.62 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  |  |  | 500000
U-5832 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 1.62 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 24400000 | FY 2028: 1952000; FY 2029: 11712000; FY 2030: 5856000; FY 2031: 2440000; FY 2032: 2440000
U-5832 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 1.62 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | UTILITIES | 1700000 | FY 2028: 850000; FY 2029: 850000
U-5832 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 1.62 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 21901000 | FY 2030: 2684000; FY 2031: 9207000; FY 2032: 7150000; FY 2033: 2860000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  |  |  | 3114000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 10000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | ENGINEERING | 975000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC ROW | 435000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 2805000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000
U-5833 | Highway | STI (Prioritization) | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | RUTHERFORD | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 4725000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 630000
U-5834 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 1.91 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | Division 13 |  |  |  | 6844000
U-5834 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 1.91 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | Division 13 |  | T | RIGHT-OF-WAY | 12333000
U-5834 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 1.91 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | Division 13 |  | BGANY | CONSTRUCTION | 13200000 | FY 2026: 1570000; FY 2027: 5834000; FY 2028: 4386000; FY 2029: 1410000
U-5835 | Highway | STI (Prioritization) | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 1.48 | McDOWELL | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  |  |  | 415000
U-5835 | Highway | STI (Prioritization) | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 1.48 | McDOWELL | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGANY | RIGHT-OF-WAY | 6600000 | FY 2024: 6600000
U-5835 | Highway | STI (Prioritization) | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 1.48 | McDOWELL | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGANY | UTILITIES | 2000000 | FY 2024: 1000000; FY 2025: 1000000
U-5835 | Highway | STI (Prioritization) | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 1.48 | McDOWELL | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGANY | CONSTRUCTION | 14800000 | FY 2025: 4291000; FY 2026: 6212000; FY 2027: 4297000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 0.92 | BURKE | 13 | Greater Hickory MPO |  | Region G |  |  |  | 3571000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 0.92 | BURKE | 13 | Greater Hickory MPO |  | Region G |  | T | RIGHT-OF-WAY | 3000000 | FY 2027: 497000; FY 2028: 993000; FY 2029: 910000; FY 2030: 300000; FY 2031: 300000
U-5836 | Highway | STI (Prioritization) | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 0.92 | BURKE | 13 | Greater Hickory MPO |  | Region G |  | T | CONSTRUCTION | 7799000 | FY 2029: 78000; FY 2030: 3596000; FY 2031: 3350000; FY 2032: 775000
U-5837 | Highway | STI (Prioritization) | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 1.05 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 250000
U-5837 | Highway | STI (Prioritization) | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 1.05 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9600000
U-5837 | Highway | STI (Prioritization) | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 1.05 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7000000
U-5837 | Highway | STI (Prioritization) | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 1.05 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9100000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  |  |  | 2743000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | ENGINEERING | 3330000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | BUILD NC ROW | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | RIGHT-OF-WAY | 4040000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | UTILITIES | 750000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | BUILD NC CON | 25985000 |  | 1799000 | 1799000 | 1799000 | 1799000 | 2598000 | 1799000 | 1799000 | 1799000 | 1799000 | 8995000
U-5839 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | Division 14 |  | T | CONSTRUCTION | 26873000 | FY 2026: 11408000; FY 2027: 10533000; FY 2028: 4932000
U-5840 | Highway | STI (Prioritization) | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | HENDERSON | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  |  |  | 5430000
U-5840 | Highway | STI (Prioritization) | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | HENDERSON | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | ENGINEERING | 1575000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
U-5840 | Highway | STI (Prioritization) | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | HENDERSON | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | BUILD NC ROW | 855000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000
U-5840 | Highway | STI (Prioritization) | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | HENDERSON | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | BUILD NC CON | 7545000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000
U-5840 | Highway | STI (Prioritization) | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | HENDERSON | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | Division 14 |  | T | BUILD NC CON | 4605000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 614000
U-5841 | Highway | STI (Prioritization) | FRIENDLY AVENUE | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 1050000
U-5841 | Highway | STI (Prioritization) | FRIENDLY AVENUE | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 1400000 | FY 2025: 14000; FY 2026: 1327000; FY 2027: 59000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  |  |  | 100000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | ENGINEERING | 600000 | FY 2024: 600000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L | ENGINEERING | 150000 | FY 2024: 150000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | RIGHT-OF-WAY | 144000 | FY 2026: 144000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L | RIGHT-OF-WAY | 36000 | FY 2026: 36000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | BGANY | CONSTRUCTION | 600000 | FY 2027: 600000
U-5842 | Highway | STI (Prioritization) | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | Division 7 |  | L | CONSTRUCTION | 150000 | FY 2027: 150000
U-5843 | Highway | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  |  |  | 1032000
U-5843 | Highway | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | ENGINEERING | 810000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 108000
U-5843 | Highway | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 1383000 | 99000 | 99000 | 99000 | 99000 | 99000 |  | 99000 | 99000 | 99000 | 99000 | 195000
U-5843 | Highway | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 784000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 1.13 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  |  |  | 1750000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 1.13 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 13300000 | FY 2024: 4092000; FY 2025: 6548000; FY 2026: 1330000; FY 2027: 1330000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 1.13 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | T | UTILITIES | 2600000 | FY 2025: 1300000; FY 2026: 1300000
U-5844 | Highway | STI (Prioritization) | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 1.13 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | T | CONSTRUCTION | 21000000 | FY 2027: 2478000; FY 2028: 10264000; FY 2029: 5719000; FY 2030: 2539000
U-5845 | Highway | STI (Prioritization) | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 2.22 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  |  |  | 2500000
U-5845 | Highway | STI (Prioritization) | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 2.22 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 10200000 | FY 2028: 604000; FY 2029: 3627000; FY 2030: 3627000; FY 2031: 302000; FY 2032: 2040000
U-5845 | Highway | STI (Prioritization) | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 2.22 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | T | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
U-5845 | Highway | STI (Prioritization) | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 2.22 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | T | CONSTRUCTION | 24001000 | FY 2031: 9001000; FY 2032: 9557000; FY 2033: 4465000 | 978000
U-5846 | Highway | STI (Prioritization) | SR 1772 (GREENSBORO STREET) | SR 1780 (ESTES DRIVE) IN CARRBORO. CONSTRUCT ROUNDABOUT. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 3185000
U-5850 | Highway | STI (Prioritization) | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 0.36 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 830000
U-5850 | Highway | STI (Prioritization) | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 0.36 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 600000
U-5850 | Highway | STI (Prioritization) | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 0.36 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 400000
U-5850 | Highway | STI (Prioritization) | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 0.36 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 3703000 | FY 2026: 2501000; FY 2027: 1202000
U-5851 | Highway | STI (Prioritization) | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 1.65 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 650000
U-5851 | Highway | STI (Prioritization) | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 1.65 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 9400000 | FY 2028: 1367000; FY 2029: 4102000; FY 2030: 2051000; FY 2031: 940000; FY 2032: 940000
U-5851 | Highway | STI (Prioritization) | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 1.65 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | UTILITIES | 997000 | FY 2028: 997000
U-5851 | Highway | STI (Prioritization) | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 1.65 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | CONSTRUCTION | 11999000 | FY 2030: 5530000; FY 2031: 4924000; FY 2032: 1545000
U-5852 | Highway | STI (Prioritization) | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 1.28 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1140000
U-5852 | Highway | STI (Prioritization) | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 1.28 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 855000
U-5852 | Highway | STI (Prioritization) | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 1.28 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 600000
U-5852 | Highway | STI (Prioritization) | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 1.28 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11600000
U-5857 | Highway | STI (Prioritization) | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.19 | HOKE | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  |  |  | 800000
U-5857 | Highway | STI (Prioritization) | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.19 | HOKE | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | RIGHT-OF-WAY | 18000000 | FY 2027: 11520000; FY 2028: 2880000; FY 2029: 1800000; FY 2030: 1800000
U-5857 | Highway | STI (Prioritization) | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.19 | HOKE | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | UTILITIES | 5700000 | FY 2027: 2850000; FY 2028: 2850000
U-5857 | Highway | STI (Prioritization) | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.19 | HOKE | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | Division 8 |  | T | CONSTRUCTION | 46001000 | FY 2029: 9439000; FY 2030: 15913000; FY 2031: 12356000; FY 2032: 8293000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 1.56 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  |  |  | 914000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 1.56 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 8900000 | FY 2026: 2191000; FY 2027: 3286000; FY 2028: 1643000; FY 2029: 890000; FY 2030: 890000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 1.56 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  | T | UTILITIES | 7500000 | FY 2026: 3750000; FY 2027: 3750000
U-5860 | Highway | STI (Prioritization) | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 1.56 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  | T | CONSTRUCTION | 22200000 | FY 2028: 222000; FY 2029: 8886000; FY 2030: 8120000; FY 2031: 4972000
U-5862 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Region B |  |  |  | 1000000
U-5862 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | RIGHT-OF-WAY | 8500000 | FY 2028: 1407000; FY 2029: 2814000; FY 2030: 2579000; FY 2031: 850000; FY 2032: 850000
U-5862 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | UTILITIES | 3500000 | FY 2028: 1750000; FY 2029: 1750000
U-5862 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Region B |  | T | CONSTRUCTION | 32401000 | FY 2030: 324000; FY 2031: 13763000; FY 2032: 11733000; FY 2033: 6581000
U-5863 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  |  |  | 1300000
U-5863 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4800000 | [10 empty] | 4800000
U-5863 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | UTILITIES | 3800000 | [10 empty] | 3800000
U-5863 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.66 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 26800000 | [10 empty] | 26800000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 3.22 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  |  |  | 3512000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 3.22 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | RIGHT-OF-WAY | 5063000 | FY 2026: 506000; FY 2027: 1079000; FY 2028: 2114000; FY 2029: 352000; FY 2030: 1012000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 3.22 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | UTILITIES | 5100000 | FY 2026: 2550000; FY 2027: 2550000
U-5864 | Highway | STI (Prioritization) | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 3.22 | RANDOLPH, GUILFORD | 7, 8 | High Point Urban Area MPO |  | Division 7, 8 |  | BGANY | CONSTRUCTION | 23700000 | FY 2029: 237000; FY 2030: 9756000; FY 2031: 8429000; FY 2032: 5278000
U-5866 | Highway | STI (Prioritization) | NEW ROUTE | US 129 (RODNEY ORR BYPASS) TO ROBINSVILLE HIGH SCHOOL AND MIDDLE SCHOOL. CONSTRUCT NEW ROUTE INCLUDING BRIDGE OVER CHEOAH RIVER. | 0.31 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION | Division 14 |  |  |  | 6284000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(DA) | ENGINEERING | 115000 | FY 2024: 115000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | ENGINEERING | 274000 | FY 2024: 86000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | ENGINEERING | 900000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | ENGINEERING | 115000 | FY 2024: 115000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | RIGHT-OF-WAY | 1000000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BA | RIGHT-OF-WAY | 1700000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(DA) | RIGHT-OF-WAY | 665000 | FY 2024: 665000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(DA) | RIGHT-OF-WAY | 224000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 665000 | FY 2024: 665000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | CONSTRUCTION | 2414000 | FY 2024: 1489000; FY 2025: 925000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | CONSTRUCTION | 3946000 | FY 2026: 3946000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | T(M) | CONSTRUCTION | 604000 | FY 2024: 372000; FY 2025: 232000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L(M) | CONSTRUCTION | 2200000 | FY 2024: 2200000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L(M) | CONSTRUCTION | 3946000 | FY 2026: 3946000
U-5873 | Highway | Locally Selected | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | Exempt |  | L(M) | CONSTRUCTION | 3882000 | FY 2024: 3882000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  |  |  | 75000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGDA | RIGHT-OF-WAY | 1750000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | L | RIGHT-OF-WAY | 1750000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGANY | CONSTRUCTION | 7096000 | FY 2024: 7096000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | BGDA | CONSTRUCTION | 8810000 | FY 2024: 8810000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | O | CONSTRUCTION | 11442000 | FY 2024: 11442000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | L | CONSTRUCTION | 1774000 | FY 2024: 1774000
U-5874 | Highway | Locally Selected | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | Division 10 |  | L | CONSTRUCTION | 2202000 | FY 2024: 2202000
U-5875 | Highway | STI (Prioritization) | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2.33 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  |  |  | 5063000
U-5875 | Highway | STI (Prioritization) | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2.33 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T | RIGHT-OF-WAY | 485000 | FY 2024: 485000
U-5875 | Highway | STI (Prioritization) | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2.33 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T | UTILITIES | 650000 | FY 2024: 650000
U-5875 | Highway | STI (Prioritization) | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2.33 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | T | CONSTRUCTION | 45800000 | FY 2026: 8702000; FY 2027: 16946000; FY 2028: 12366000; FY 2029: 7786000
U-5876 | Highway | STI (Prioritization) | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 1.35 | CARTERET | 2 | Down East RPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-5876 | Highway | STI (Prioritization) | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 1.35 | CARTERET | 2 | Down East RPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 10800000
U-5876 | Highway | STI (Prioritization) | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 1.35 | CARTERET | 2 | Down East RPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 4000000
U-5876 | Highway | STI (Prioritization) | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 1.35 | CARTERET | 2 | Down East RPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 85202000
U-5878 | Highway | STI (Prioritization) | COMMERCE DRIVE EXTENSION | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.24 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 2225000
U-5878 | Highway | STI (Prioritization) | COMMERCE DRIVE EXTENSION | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.24 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 3698000 | FY 2024: 380000
U-5881 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 2.88 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
U-5881 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 2.88 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 179000
U-5881 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 2.88 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 180000
U-5881 | Highway | STI (Prioritization) | US 117 / NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 2.88 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 39099000
U-5886 | Highway | STI (Prioritization) | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 0.42 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  |  |  | 1470000
U-5886 | Highway | STI (Prioritization) | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 0.42 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | RIGHT-OF-WAY | 18700000 | FY 2024: 5791000; FY 2025: 5791000; FY 2026: 1930000; FY 2027: 3740000
U-5886 | Highway | STI (Prioritization) | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 0.42 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | UTILITIES | 2600000 | FY 2024: 1300000
U-5886 | Highway | STI (Prioritization) | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 0.42 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | Division 14 |  | T | CONSTRUCTION | 15101000 | FY 2027: 3104000; FY 2028: 6683000; FY 2029: 4356000; FY 2030: 958000
U-5887 | Highway | STI (Prioritization) | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 1.07 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  |  |  | 810000
U-5887 | Highway | STI (Prioritization) | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 1.07 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | T | RIGHT-OF-WAY | 2295000
U-5887 | Highway | STI (Prioritization) | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 1.07 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Division 14 |  | T | CONSTRUCTION | 7676000
U-5888 | Highway | STI (Prioritization) | US 23 BUSINESS | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | Division 14 |  |  |  | 1411000
U-5888 | Highway | STI (Prioritization) | US 23 BUSINESS | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | Division 14 |  | T | CONSTRUCTION | 7022000 | FY 2024: 1505000
U-5889 | Highway | STI (Prioritization) | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 1.02 | WAKE | 5 | Capital Area MPO |  | Division 5 |  |  |  | 10000
U-5889 | Highway | STI (Prioritization) | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 1.02 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 1200000 | FY 2026: 1200000
U-5889 | Highway | STI (Prioritization) | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 1.02 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | UTILITIES | 500000 | FY 2026: 500000
U-5889 | Highway | STI (Prioritization) | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 1.02 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 7300000 | FY 2028: 7300000
U-5890 | Highway | STI (Prioritization) | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 0.65 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  |  |  | 1000000
U-5890 | Highway | STI (Prioritization) | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 0.65 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | T | RIGHT-OF-WAY | 25000000 | FY 2026: 8182000; FY 2027: 10909000; FY 2028: 909000; FY 2029: 2500000; FY 2030: 2500000
U-5890 | Highway | STI (Prioritization) | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 0.65 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | T | UTILITIES | 7300000 | FY 2026: 3650000; FY 2027: 3650000
U-5890 | Highway | STI (Prioritization) | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 0.65 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | T | CONSTRUCTION | 24400000 | FY 2028: 8784000; FY 2029: 10248000; FY 2030: 5368000
U-5891 | Highway | STI (Prioritization) | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5.12 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 300000
U-5891 | Highway | STI (Prioritization) | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5.12 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 56401000
U-5891 | Highway | STI (Prioritization) | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5.12 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-5891 | Highway | STI (Prioritization) | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5.12 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 66001000
U-5892 | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 1.42 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  |  |  | 2350000
U-5892 | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 1.42 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | RIGHT-OF-WAY | 7531000 | FY 2024: 2524000; FY 2025: 2781000; FY 2026: 695000; FY 2027: 1506000
U-5892 | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 1.42 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | UTILITIES | 1472000 | FY 2024: 736000
U-5892 | Highway | STI (Prioritization) | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 1.42 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | NHP | CONSTRUCTION | 12400000 | FY 2027: 5214000; FY 2028: 5372000; FY 2029: 1814000
U-5893 | Highway | STI (Prioritization) | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 645000
U-5893 | Highway | STI (Prioritization) | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | RIGHT-OF-WAY | 1643000
U-5893 | Highway | STI (Prioritization) | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | UTILITIES | 717000
U-5893 | Highway | STI (Prioritization) | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG5T50 | CONSTRUCTION | 12198000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  |  |  | 3138000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | ENGINEERING | 1820000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | BUILD NC ROW | 8834000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000
U-5896 | Highway | STI (Prioritization) | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | Division 7 |  | T | CONSTRUCTION | 15400000 | FY 2024: 3946000; FY 2025: 945000
U-5899 | Highway | STI (Prioritization) | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 2730000
U-5899 | Highway | STI (Prioritization) | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 4300000
U-5899 | Highway | STI (Prioritization) | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 1300000
U-5899 | Highway | STI (Prioritization) | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 16000000 | FY 2025: 160000; FY 2026: 7200000; FY 2027: 5760000; FY 2028: 2880000
U-5901 | Highway | STI (Prioritization) | NEW ROUTE (AIRPORT PARKWAY) | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  |  |  | 1000000
U-5901 | Highway | STI (Prioritization) | NEW ROUTE (AIRPORT PARKWAY) | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 8900000 | FY 2027: 445000; FY 2028: 2670000; FY 2029: 2670000; FY 2030: 1335000; FY 2031: 1780000
U-5901 | Highway | STI (Prioritization) | NEW ROUTE (AIRPORT PARKWAY) | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | UTILITIES | 6900000 | FY 2027: 3450000; FY 2028: 3450000
U-5901 | Highway | STI (Prioritization) | NEW ROUTE (AIRPORT PARKWAY) | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGANY | CONSTRUCTION | 39502000 | FY 2030: 4540000; FY 2031: 14041000; FY 2032: 11330000; FY 2033: 7720000 | 1871000
U-5903 | Highway | STI (Prioritization) | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.13 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 1000000
U-5903 | Highway | STI (Prioritization) | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.13 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 5900000 | FY 2028: 864000; FY 2029: 2347000; FY 2030: 1369000; FY 2031: 660000; FY 2032: 660000
U-5903 | Highway | STI (Prioritization) | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.13 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | UTILITIES | 4200000 | FY 2028: 2100000; FY 2029: 2100000
U-5903 | Highway | STI (Prioritization) | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.13 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 43600000 | FY 2030: 4910000; FY 2031: 15410000; FY 2032: 12796000; FY 2033: 8748000 | 1736000
U-5905 | Highway | Locally Selected | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 2.1 | MECKLENBURG | 10 | Charlotte Regional TPO | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. |  |  |  |  | 3000000
U-5905A | Highway | Locally Selected | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 1.72 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | BGDA | CONSTRUCTION | 155000
U-5905A | Highway | Locally Selected | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 1.72 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 10 |  | BA | CONSTRUCTION | 8506000
U-5905B | Highway | Locally Selected | SR 2112 (LAKEVIEW ROAD) | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | BGDA | CONSTRUCTION | 162000
U-5905B | Highway | Locally Selected | SR 2112 (LAKEVIEW ROAD) | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | BA | CONSTRUCTION | 3000000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | BA | ENGINEERING | 1941000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | T | ENGINEERING | 100000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | BA | RIGHT-OF-WAY | 3153000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | T | RIGHT-OF-WAY | 8000000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 2276000 | FY 2025: 801000; FY 2026: 1239000; FY 2027: 236000
U-5906 | Highway | Locally Selected | CHAPEL ROAD) SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | T | CONSTRUCTION | 1372000 | FY 2025: 483000; FY 2026: 747000; FY 2027: 142000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | ENGINEERING | 900000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | ENGINEERING | 430000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | RIGHT-OF-WAY | 548000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 500000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | RIGHT-OF-WAY | 750000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | BA | CONSTRUCTION | 2937000 | FY 2024: 1409000; FY 2025: 1166000; FY 2026: 362000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | T(DA) | CONSTRUCTION | 5703000 | FY 2024: 616000; FY 2025: 3883000; FY 2026: 1204000
U-5907 | Highway | Locally Selected | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907. | Division 10 |  | L | CONSTRUCTION | 2200000 | FY 2024: 2200000
U-5908 | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP. |  |  |  |  | 3050000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGANY | RIGHT-OF-WAY | 660000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | RIGHT-OF-WAY | 165000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGANY | CONSTRUCTION | 2748000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 44000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 1832000
U-5908A | Highway | Locally Selected | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 29000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGANY | RIGHT-OF-WAY | 660000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDA | RIGHT-OF-WAY | 1318000 | FY 2024: 1318000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | RIGHT-OF-WAY | 165000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | RIGHT-OF-WAY | 329000 | FY 2024: 329000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGANY | CONSTRUCTION | 2032000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDA | CONSTRUCTION | 3490000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDA | CONSTRUCTION | 1827000 | FY 2024: 1827000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 2327000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 1355000
U-5908B | Highway | Locally Selected | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 1218000 | FY 2024: 1218000
U-5910 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  |  |  | 26000
U-5910 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  | BGDA | PLANNING | 392000 | FY 2025: 180000
U-5910 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | IN PROGRESS | Division 3 |  | L | PLANNING | 148000 | FY 2025: 70000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.42 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  |  |  | 50000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.42 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 69000 | FY 2025: 69000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.42 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T | UTILITIES | 2136000 | FY 2025: 1068000; FY 2026: 1068000
U-5911 | Highway | STI (Prioritization) | NC 48 | NC 4 INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.42 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 5625000 | FY 2027: 1842000; FY 2028: 3483000; FY 2029: 300000
U-5914 | Highway | STI (Prioritization) | NC 133 | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | 0.48 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  |  |  | 140000
U-5914 | Highway | STI (Prioritization) | NC 133 | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | 0.48 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | T | CONSTRUCTION | 3828000 | FY 2024: 194000; FY 2025: 1400000
U-5917 | Highway | STI (Prioritization) | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 2 |  |  |  | 5897000
U-5917 | Highway | STI (Prioritization) | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 2 |  | T | ENGINEERING | 1740000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000
U-5917 | Highway | STI (Prioritization) | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 2 |  | T | BUILD NC ROW | 952000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000
U-5917 | Highway | STI (Prioritization) | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 2 |  | T | UTILITIES | 2772000 | FY 2024: 1386000; FY 2025: 1386000
U-5917 | Highway | STI (Prioritization) | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 2 |  | T | CONSTRUCTION | 22700000 | FY 2027: 227000; FY 2028: 9092000; FY 2029: 8285000; FY 2030: 5096000
U-5924 | Highway | Locally Selected | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. |  | CATAWBA, ALEXANDER, BURKE, CALDWELL | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  |  |  | 125000
U-5924 | Highway | Locally Selected | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. |  | CATAWBA, ALEXANDER, BURKE, CALDWELL | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | BGDA | PLANNING | 1400000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
U-5924 | Highway | Locally Selected | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. |  | CATAWBA, ALEXANDER, BURKE, CALDWELL | 11, 12, 13 | Greater Hickory MPO |  | Division 11, 12, 13 |  | L | PLANNING | 350000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
U-5926 | Highway | Economic Development | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | Division 3 |  |  |  | 3410000
U-5926 | Highway | Economic Development | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | Division 3 |  | T | RIGHT-OF-WAY | 420000 | FY 2024: 420000
U-5926 | Highway | Economic Development | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | Division 3 |  | L | RIGHT-OF-WAY | 420000 | FY 2024: 420000
U-5926 | Highway | Economic Development | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | Division 3 |  | T | UTILITIES | 172000 | FY 2024: 172000
U-5926 | Highway | Economic Development | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | NEW HANOVER | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | Division 3 |  | L | UTILITIES | 172000 | FY 2024: 172000
U-5928 | Highway | Locally Selected | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | RR | CONSTRUCTION | 10000000 | FY 2024: 10000000
U-5928 | Highway | Locally Selected | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 2500000 | FY 2024: 2500000
U-5928 | Highway | Locally Selected | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 12500000 | FY 2024: 12500000
U-5929 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5929 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7200000
U-5929 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2000000
U-5929 | Highway | STI (Prioritization) | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 0.5 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6500000
U-5930 | Highway | STI (Prioritization) | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-5930 | Highway | STI (Prioritization) | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 22400000
U-5930 | Highway | STI (Prioritization) | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7500000
U-5930 | Highway | STI (Prioritization) | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 67500000
U-5931 | Highway | STI (Prioritization) | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  |  |  | 3500000
U-5931 | Highway | STI (Prioritization) | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | RIGHT-OF-WAY | 1099000 | FY 2025: 24000; FY 2026: 285000; FY 2027: 285000; FY 2028: 285000; FY 2029: 220000
U-5931 | Highway | STI (Prioritization) | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | UTILITIES | 520000 | FY 2025: 260000; FY 2026: 260000
U-5931 | Highway | STI (Prioritization) | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | Statewide Mobility |  | T | CONSTRUCTION | 4600000 | FY 2029: 46000; FY 2030: 3116000; FY 2031: 1438000
U-5932 | Highway | STI (Prioritization) | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-5932 | Highway | STI (Prioritization) | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 41400000
U-5932 | Highway | STI (Prioritization) | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2300000
U-5932 | Highway | STI (Prioritization) | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 1 | BRUNSWICK | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 43000000
U-5933 | Highway | STI (Prioritization) | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  |  |  | 700000
U-5933 | Highway | STI (Prioritization) | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 17000
U-5933 | Highway | STI (Prioritization) | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 23000
U-5933 | Highway | STI (Prioritization) | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 2675000 | FY 2024: 2167000; FY 2025: 482000
U-5933 | Highway | STI (Prioritization) | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | S(M) | CONSTRUCTION | 670000 | FY 2024: 542000; FY 2025: 120000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND PRIORITIZE THE ADDITION OF TRANSIT ACCOMMODATIONS. | 4.82 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  |  |  | 300000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND PRIORITIZE THE ADDITION OF TRANSIT ACCOMMODATIONS. | 4.82 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 100000 | FY 2028: 100000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND PRIORITIZE THE ADDITION OF TRANSIT ACCOMMODATIONS. | 4.82 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | UTILITIES | 300000 | FY 2028: 300000
U-5934 | Highway | STI (Prioritization) | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND PRIORITIZE THE ADDITION OF TRANSIT ACCOMMODATIONS. | 4.82 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 142300000 | FY 2029: 17488000; FY 2030: 39330000; FY 2031: 34813000; FY 2032: 28696000; FY 2033: 21973000
U-5936 | Highway | STI (Prioritization) | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 3.08 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5936 | Highway | STI (Prioritization) | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 3.08 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 900000
U-5936 | Highway | STI (Prioritization) | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 3.08 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-5936 | Highway | STI (Prioritization) | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 3.08 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 74499000
U-5937 | Highway | STI (Prioritization) | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 1.79 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 200000
U-5937 | Highway | STI (Prioritization) | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 1.79 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9300000
U-5937 | Highway | STI (Prioritization) | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 1.79 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7750000
U-5937 | Highway | STI (Prioritization) | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 1.79 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 64301000
U-5939 | Highway | STI (Prioritization) | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 0.5 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  |  |  | 500000
U-5939 | Highway | STI (Prioritization) | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 0.5 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | BG5T50 | RIGHT-OF-WAY | 5400000 |  | 508000 | 1525000 | 1525000 | 762000 | 540000 | 540000
U-5939 | Highway | STI (Prioritization) | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 0.5 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | BG5T50 | UTILITIES | 530000 | FY 2025: 530000
U-5939 | Highway | STI (Prioritization) | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 0.5 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | BG5T50 | CONSTRUCTION | 17300000 | FY 2028: 8650000; FY 2029: 4325000; FY 2030: 4325000
U-5940 | Highway | STI (Prioritization) | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1.49 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  |  |  | 2000000
U-5940 | Highway | STI (Prioritization) | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1.49 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | NHP | RIGHT-OF-WAY | 15989000 | FY 2027: 160000; FY 2028: 5322000; FY 2029: 7309000; FY 2030: 1599000; FY 2031: 1599000
U-5940 | Highway | STI (Prioritization) | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1.49 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | NHP | UTILITIES | 476000 | FY 2027: 476000
U-5940 | Highway | STI (Prioritization) | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1.49 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | NHP | CONSTRUCTION | 12900000 | FY 2029: 129000; FY 2030: 5805000; FY 2031: 4644000; FY 2032: 2322000
U-5941 | Highway | STI (Prioritization) | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 1.12 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  |  |  | 50000
U-5941 | Highway | STI (Prioritization) | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 1.12 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | RIGHT-OF-WAY | 12100000 | FY 2026: 2420000; FY 2027: 5808000; FY 2028: 1452000; FY 2029: 1210000; FY 2030: 1210000
U-5941 | Highway | STI (Prioritization) | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 1.12 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | UTILITIES | 3900000 | FY 2026: 1950000; FY 2027: 1950000
U-5941 | Highway | STI (Prioritization) | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 1.12 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | BG5T50 | CONSTRUCTION | 11000000 | FY 2028: 1792000; FY 2029: 5899000; FY 2030: 3309000
U-5942 | Highway | STI (Prioritization) | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 20 | PASQUOTANK | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  |  |  | 540000
U-5942 | Highway | STI (Prioritization) | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 20 | PASQUOTANK | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  | HP | CONSTRUCTION | 62000
U-5942 | Highway | STI (Prioritization) | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 20 | PASQUOTANK | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | Region A |  | BG5T50 | CONSTRUCTION | 5297000
U-5943 | Highway | STI (Prioritization) | CLAYTON | CLAYTON SIGNAL SYSTEM. | 6.2 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  |  |  | 328000
U-5943 | Highway | STI (Prioritization) | CLAYTON | CLAYTON SIGNAL SYSTEM. | 6.2 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | BG50200 | UTILITIES | 260000 | FY 2025: 260000
U-5943 | Highway | STI (Prioritization) | CLAYTON | CLAYTON SIGNAL SYSTEM. | 6.2 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | BG50200 | CONSTRUCTION | 4500000 | FY 2025: 2167000; FY 2026: 2333000
U-5945 | Highway | STI (Prioritization) | WILSON | WILSON CITY SIGNAL SYSTEM. | 26.1 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  |  |  | 10000
U-5945 | Highway | STI (Prioritization) | WILSON | WILSON CITY SIGNAL SYSTEM. | 26.1 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | UTILITIES | 2300000 | FY 2024: 2300000
U-5945 | Highway | STI (Prioritization) | WILSON | WILSON CITY SIGNAL SYSTEM. | 26.1 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BG5T50 | CONSTRUCTION | 1700000 | FY 2025: 340000; FY 2026: 969000; FY 2027: 391000
U-5947 | Highway | STI (Prioritization) | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  |  |  | 51000
U-5947 | Highway | STI (Prioritization) | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | RIGHT-OF-WAY | 80000
U-5947 | Highway | STI (Prioritization) | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | UTILITIES | 800000
U-5947 | Highway | STI (Prioritization) | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 1 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | T | CONSTRUCTION | 5725000 | FY 2024: 2271000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 5.76 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1150000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 5.76 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 28664000 | FY 2028: 4748000; FY 2029: 11481000; FY 2030: 6697000; FY 2031: 2869000; FY 2032: 2869000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 5.76 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | UTILITIES | 20100000 | FY 2028: 10050000; FY 2029: 10050000
U-5949 | Highway | STI (Prioritization) | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 5.76 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | T | CONSTRUCTION | 76701000 | FY 2032: 767000; FY 2033: 21685000 | 54249000
U-5950 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 500000
U-5950 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | RIGHT-OF-WAY | 90000 | FY 2025: 90000
U-5950 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 200000 | FY 2025: 200000
U-5950 | Highway | STI (Prioritization) | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 1300000 | FY 2027: 163000; FY 2028: 1137000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  |  |  | 1350000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | RIGHT-OF-WAY | 630000 | FY 2026: 630000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 70000 | FY 2026: 70000
U-5951 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 18299000 | FY 2028: 1156000; FY 2029: 8361000; FY 2030: 6196000; FY 2031: 2586000
U-5952 | Highway | STI (Prioritization) | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 25 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  |  |  | 1610000
U-5952 | Highway | STI (Prioritization) | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 25 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | BG50200 | UTILITIES | 750000 | FY 2026: 750000
U-5952 | Highway | STI (Prioritization) | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 25 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | BG50200 | CONSTRUCTION | 12000000 | FY 2028: 4894000; FY 2029: 5400000; FY 2030: 1706000
U-5954 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  |  |  | 500000
U-5954 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGLT5 | RIGHT-OF-WAY | 721000 | FY 2025: 721000
U-5954 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGLT5 | UTILITIES | 600000 | FY 2025: 600000
U-5954 | Highway | STI (Prioritization) | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGLT5 | CONSTRUCTION | 5200000 | FY 2027: 397000; FY 2028: 3633000; FY 2029: 1170000
U-5955 | Highway | STI (Prioritization) | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. | 0.38 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1095000
U-5955A | Highway | STI (Prioritization) | NC 16 (BROOKSHIRE BOULEVARD) | IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 2700000 | FY 2024: 1109000
U-5955B | Highway | STI (Prioritization) | NC 16 (BROOKSHIRE BOULEVARD) | IDAHO DRIVE INTERSECTION. CONVERT INTERSECTION TO AN INTERCHANGE. | 0.38 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | RIGHT-OF-WAY | 4300000 | FY 2026: 43000; FY 2027: 969000; FY 2028: 1214000; FY 2029: 1214000; FY 2030: 860000
U-5955B | Highway | STI (Prioritization) | NC 16 (BROOKSHIRE BOULEVARD) | IDAHO DRIVE INTERSECTION. CONVERT INTERSECTION TO AN INTERCHANGE. | 0.38 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | UTILITIES | 345000 | FY 2026: 345000
U-5955B | Highway | STI (Prioritization) | NC 16 (BROOKSHIRE BOULEVARD) | IDAHO DRIVE INTERSECTION. CONVERT INTERSECTION TO AN INTERCHANGE. | 0.38 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | CONSTRUCTION | 12700000 | FY 2029: 3937000; FY 2030: 5588000; FY 2031: 3175000
U-5956 | Highway | STI (Prioritization) | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  |  |  | 450000
U-5956 | Highway | STI (Prioritization) | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | RIGHT-OF-WAY | 3400000
U-5956 | Highway | STI (Prioritization) | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 2050000 | FY 2025: 500000; FY 2026: 1550000
U-5956 | Highway | STI (Prioritization) | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 21900000 | FY 2026: 4599000; FY 2027: 9855000; FY 2028: 5256000; FY 2029: 2190000
U-5957 | Highway | STI (Prioritization) | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 1.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 1920000
U-5957 | Highway | STI (Prioritization) | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 1.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | RIGHT-OF-WAY | 13100000 | FY 2026: 2620000; FY 2027: 5240000; FY 2028: 2620000; FY 2029: 1310000; FY 2030: 1310000
U-5957 | Highway | STI (Prioritization) | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 1.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | UTILITIES | 1750000 | FY 2026: 1750000
U-5957 | Highway | STI (Prioritization) | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 1.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | T | CONSTRUCTION | 17900000 | FY 2030: 179000; FY 2031: 7833000; FY 2032: 6856000; FY 2033: 3032000
U-5959 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 153000
U-5959 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9400000
U-5959 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-5959 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5999000
U-5960 | Highway | STI (Prioritization) | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 1.32 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 400000
U-5960 | Highway | STI (Prioritization) | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 1.32 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 18700000
U-5960 | Highway | STI (Prioritization) | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 1.32 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3800000
U-5960 | Highway | STI (Prioritization) | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 1.32 | IREDELL | 12 | Charlotte Regional TPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 27000000
U-5961 | Highway | STI (Prioritization) | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 1.02 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | RIGHT-OF-WAY | 13400000 | FY 2024: 1072000; FY 2025: 3216000; FY 2026: 3216000; FY 2027: 3216000; FY 2028: 2680000
U-5961 | Highway | STI (Prioritization) | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 1.02 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | UTILITIES | 3700000 | FY 2024: 1850000; FY 2025: 1850000
U-5961 | Highway | STI (Prioritization) | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 1.02 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | BG50200 | CONSTRUCTION | 6399000 | FY 2027: 2767000; FY 2028: 2821000; FY 2029: 811000
U-5961 | Highway | STI (Prioritization) | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 1.02 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | Region F |  | O | CONSTRUCTION | 5000000 | FY 2027: 1502000; FY 2028: 2486000; FY 2029: 1012000
U-5962 | Highway | STI (Prioritization) | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F |  |  |  | 700000
U-5962 | Highway | STI (Prioritization) | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F |  | T | RIGHT-OF-WAY | 3300000 | FY 2025: 33000; FY 2026: 1098000; FY 2027: 1509000; FY 2028: 330000; FY 2029: 330000
U-5962 | Highway | STI (Prioritization) | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F |  | T | UTILITIES | 300000 | FY 2025: 300000
U-5962 | Highway | STI (Prioritization) | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F |  | T | CONSTRUCTION | 3912000 | FY 2027: 39000; FY 2028: 2417000; FY 2029: 1456000
U-5962 | Highway | STI (Prioritization) | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | Region F |  | O | CONSTRUCTION | 288000 | FY 2027: 3000; FY 2028: 180000; FY 2029: 105000
U-5964 | Highway | STI (Prioritization) | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | IREDELL | 12 | Charlotte Regional TPO |  | Region F |  |  |  | 150000
U-5964 | Highway | STI (Prioritization) | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | IREDELL | 12 | Charlotte Regional TPO |  | Region F |  | T | RIGHT-OF-WAY | 3800000 | FY 2024: 1824000; FY 2025: 1216000; FY 2026: 380000; FY 2027: 380000
U-5964 | Highway | STI (Prioritization) | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | IREDELL | 12 | Charlotte Regional TPO |  | Region F |  | T | UTILITIES | 700000 | FY 2024: 700000
U-5964 | Highway | STI (Prioritization) | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | IREDELL | 12 | Charlotte Regional TPO |  | Region F |  | T | CONSTRUCTION | 3300000 | FY 2026: 228000; FY 2027: 2495000; FY 2028: 577000
U-5965 | Highway | STI (Prioritization) | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  |  |  | 450000
U-5965 | Highway | STI (Prioritization) | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T | RIGHT-OF-WAY | 6900000 | FY 2024: 3680000; FY 2025: 920000; FY 2026: 690000; FY 2027: 690000
U-5965 | Highway | STI (Prioritization) | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T | UTILITIES | 300000
U-5965 | Highway | STI (Prioritization) | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | T | CONSTRUCTION | 3600000 | FY 2025: 1610000; FY 2026: 1990000
U-5966 | Highway | STI (Prioritization) | NEW ROUTE | SR 1613 (DAVIS DRIVE) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 0.9 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 750000
U-5966 | Highway | STI (Prioritization) | NEW ROUTE | SR 1613 (DAVIS DRIVE) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 0.9 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 12900000
U-5966 | Highway | STI (Prioritization) | NEW ROUTE | SR 1613 (DAVIS DRIVE) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 0.9 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2398000
U-5966 | Highway | STI (Prioritization) | NEW ROUTE | SR 1613 (DAVIS DRIVE) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 0.9 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 93701000
U-5967 | Highway | STI (Prioritization) | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Region C |  |  |  | 163000
U-5967 | Highway | STI (Prioritization) | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | BGANY | UTILITIES | 25000 | FY 2028: 25000
U-5967 | Highway | STI (Prioritization) | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 8000 | FY 2028: 8000
U-5967 | Highway | STI (Prioritization) | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | BGANY | CONSTRUCTION | 603000 | FY 2029: 473000; FY 2030: 130000
U-5967 | Highway | STI (Prioritization) | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 350000 | FY 2029: 274000; FY 2030: 76000
U-5968 | Highway | STI (Prioritization) | VARIOUS | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  |  |  | 14315000
U-5968 | Highway | STI (Prioritization) | VARIOUS | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | BUILD NC CON | 13000000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 1729000
U-5969 | Highway | STI (Prioritization) | US 501 | SOUTH OF US 158 TO SR 1601 (NORTH MAIN STREET) IN ROXBORO. CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | 3 | PERSON | 5 | Kerr-Tar RPO | [5 empty] | 1700000
U-5969A | Highway | STI (Prioritization) | US 501 | SOUTH OF US 158 TO NC 157. | 0.88 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | T | RIGHT-OF-WAY | 7200000 | FY 2028: 2356000; FY 2029: 3142000; FY 2030: 262000; FY 2031: 720000; FY 2032: 720000
U-5969A | Highway | STI (Prioritization) | US 501 | SOUTH OF US 158 TO NC 157. | 0.88 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | T | UTILITIES | 1288000 | FY 2028: 644000; FY 2029: 644000
U-5969A | Highway | STI (Prioritization) | US 501 | SOUTH OF US 158 TO NC 157. | 0.88 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | T | CONSTRUCTION | 6400000 | FY 2030: 3264000; FY 2031: 2752000; FY 2032: 384000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 1.03 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6700000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 1.03 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 917000
U-5969B | Highway | STI (Prioritization) | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 1.03 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9200000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 1.11 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6300000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 1.11 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1346000
U-5969C | Highway | STI (Prioritization) | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 1.11 | PERSON | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6600000
U-5970 | Highway | STI (Prioritization) | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.16 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 700000
U-5970 | Highway | STI (Prioritization) | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.16 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2100000
U-5970 | Highway | STI (Prioritization) | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.16 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
U-5970 | Highway | STI (Prioritization) | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.16 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1900000
U-5971 | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY) . CONSTRUCTION INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | [5 empty] | 1369000
U-5971A | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT INITIAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION | Region G
U-5971AA | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | Region G |  | T | RIGHT-OF-WAY | 100000
U-5971AA | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | Region G |  | T | CONSTRUCTION | 550000
U-5971B | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 35590000 | [10 empty] | 35590000
U-5971B | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | UTILITIES | 300000 | [10 empty] | 300000
U-5971B | Highway | STI (Prioritization) | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 6500000 | [10 empty] | 6500000
U-5972 | Highway | STI (Prioritization) | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4.44 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  |  |  | 4260000
U-5972 | Highway | STI (Prioritization) | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4.44 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 66000000 | [10 empty] | 66000000
U-5972 | Highway | STI (Prioritization) | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4.44 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | UTILITIES | 6700000 | [10 empty] | 6700000
U-5972 | Highway | STI (Prioritization) | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4.44 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 31899000 | [10 empty] | 31899000
U-5973 | Highway | STI (Prioritization) | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  |  |  | 260000
U-5973 | Highway | STI (Prioritization) | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 200000 | [10 empty] | 200000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.92 | GUILFORD | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | Region D |  |  |  | 1675000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.92 | GUILFORD | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | Region D |  | T | RIGHT-OF-WAY | 10200000 | FY 2027: 9169000; FY 2028: 1031000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.92 | GUILFORD | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | Region D |  | T | UTILITIES | 6600000 | FY 2027: 3300000; FY 2028: 3300000
U-5974 | Highway | STI (Prioritization) | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.92 | GUILFORD | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | Region D |  | T | CONSTRUCTION | 27301000 | FY 2029: 9711000; FY 2030: 10622000; FY 2031: 5129000; FY 2032: 1839000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.17 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | Region E |  |  |  | 3846000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.17 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | Region E |  | T | RIGHT-OF-WAY | 4100000 | FY 2024: 1357000; FY 2025: 1357000; FY 2026: 226000; FY 2027: 821000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.17 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | Region E |  | T | UTILITIES | 3300000 | FY 2024: 1600000; FY 2025: 1600000
U-5975 | Highway | STI (Prioritization) | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.17 | LEE | 8 | Central Pines RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 29899000 | FY 2026: 299000; FY 2027: 11608000; FY 2028: 10295000; FY 2029: 6873000; FY 2030: 824000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | MOORE | 8 | Central Pines RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | Division 8 |  |  |  | 600000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | MOORE | 8 | Central Pines RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | Division 8 |  | T | RIGHT-OF-WAY | 25800000 | FY 2028: 6880000; FY 2029: 11794000; FY 2030: 1966000; FY 2031: 2580000; FY 2032: 2580000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | MOORE | 8 | Central Pines RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | Division 8 |  | T | UTILITIES | 630000 | FY 2028: 630000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | MOORE | 8 | Central Pines RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | Division 8 |  | T | BUILD NC CON | 12870000 | FY 2030: 858000; FY 2031: 858000; FY 2032: 858000; FY 2033: 858000 | 9438000
U-5976 | Highway | STI (Prioritization) | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | MOORE | 8 | Central Pines RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | Division 8 |  | T | CONSTRUCTION | 18101000 | FY 2030: 0; FY 2031: 8695000; FY 2032: 7401000; FY 2033: 2005000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 3.44 | SCOTLAND | 8 | Lumber River RPO |  | Region E |  |  |  | 3888000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 3.44 | SCOTLAND | 8 | Lumber River RPO |  | Region E |  | T | RIGHT-OF-WAY | 7700000 | FY 2028: 1797000; FY 2029: 3080000; FY 2030: 1283000; FY 2031: 770000; FY 2032: 770000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 3.44 | SCOTLAND | 8 | Lumber River RPO |  | Region E |  | T | UTILITIES | 3000000 | FY 2028: 1500000; FY 2029: 1500000
U-5977 | Highway | STI (Prioritization) | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 3.44 | SCOTLAND | 8 | Lumber River RPO |  | Region E |  | T | CONSTRUCTION | 22000000 | FY 2030: 4019000; FY 2031: 9361000; FY 2032: 6485000; FY 2033: 2135000
U-5978 | Highway | STI (Prioritization) | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 2.82 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  |  |  | 2760000
U-5978 | Highway | STI (Prioritization) | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 2.82 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 8500000 | [10 empty] | 8500000
U-5978 | Highway | STI (Prioritization) | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 2.82 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | UTILITIES | 1700000 | [10 empty] | 1700000
U-5978 | Highway | STI (Prioritization) | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 2.82 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | CONSTRUCTION | 14000000 | [10 empty] | 14000000
U-5989 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3
U-5989 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGANY | CONSTRUCTION | 17006000 | FY 2024: 17006000
U-5989 | Highway | Locally Selected | VARIOUS | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 104956000 | 15002000 | 15604000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 3914000 | 35226000
U-5990 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Division 3 |  |  |  | 825000
U-5990 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | BGANY | CONSTRUCTION | 2425000 | FY 2024: 2425000
U-5990 | Highway | Locally Selected | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | BGDA | CONSTRUCTION | 11552000 | 0 | 2293000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 3744000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 3.19 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  |  |  | 900000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 3.19 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | RIGHT-OF-WAY | 14000000 | FY 2027: 140000; FY 2028: 4660000; FY 2029: 6400000; FY 2030: 1400000; FY 2031: 1400000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 3.19 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | UTILITIES | 7500000 | FY 2027: 3750000; FY 2028: 3750000
U-5991 | Highway | STI (Prioritization) | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 3.19 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BGANY | CONSTRUCTION | 30200000 | FY 2029: 302000; FY 2030: 11185000; FY 2031: 10562000; FY 2032: 6961000; FY 2033: 1190000
U-5993 | Highway | STI (Prioritization) | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  |  |  | 750000
U-5993 | Highway | STI (Prioritization) | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 790000 | FY 2026: 790000
U-5993 | Highway | STI (Prioritization) | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  | T | CONSTRUCTION | 4200000 | FY 2028: 42000; FY 2029: 2865000; FY 2030: 1293000
U-5994 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.26 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 800000
U-5994 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.26 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | CONSTRUCTION | 450000
U-5996 | Highway | STI (Prioritization) | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 1.33 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  |  |  | 1000000
U-5996 | Highway | STI (Prioritization) | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 1.33 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | RIGHT-OF-WAY | 529000
U-5996 | Highway | STI (Prioritization) | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 1.33 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | T | CONSTRUCTION | 23940000 | FY 2024: 7307000; FY 2025: 3374000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 11.43 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4 |  |  |  | 10000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 11.43 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4 |  | BGANY | RIGHT-OF-WAY | 3300000 | FY 2024: 695000; FY 2025: 1667000; FY 2026: 278000; FY 2027: 330000; FY 2028: 330000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 11.43 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4 |  | BGANY | UTILITIES | 2100000 | FY 2024: 1050000; FY 2025: 1050000
U-5998 | Highway | STI (Prioritization) | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 11.43 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4 |  | BGANY | CONSTRUCTION | 14801000 | FY 2027: 2400000; FY 2028: 7536000; FY 2029: 4865000
U-6001 | Highway | STI (Prioritization) | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 1.19 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-6001 | Highway | STI (Prioritization) | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 1.19 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 700000
U-6001 | Highway | STI (Prioritization) | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 1.19 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1028000
U-6001 | Highway | STI (Prioritization) | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 1.19 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 10699000
U-6002 | Highway | STI (Prioritization) | WILKESBORO STREET | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | 0.5 | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 750000
U-6002 | Highway | STI (Prioritization) | WILKESBORO STREET | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | 0.5 | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 1800000 | FY 2024: 373000
U-6003 | Highway | STI (Prioritization) | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.94 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 2670000
U-6003 | Highway | STI (Prioritization) | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.94 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 12400000 | FY 2024: 2614000; FY 2025: 6146000; FY 2026: 3640000
U-6004 | Highway | STI (Prioritization) | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  |  |  | 750000
U-6004 | Highway | STI (Prioritization) | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | BGANY | RIGHT-OF-WAY | 33600000 | FY 2024: 1280000; FY 2025: 15360000; FY 2026: 10240000; FY 2027: 3360000; FY 2028: 3360000
U-6004 | Highway | STI (Prioritization) | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | BGANY | UTILITIES | 3000000 | FY 2026: 1500000; FY 2027: 1500000
U-6004 | Highway | STI (Prioritization) | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | BUILD NC CON | 6435000 |  |  |  | 858000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-6004 | Highway | STI (Prioritization) | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | CONSTRUCTION | 27700000 | FY 2027: 559000; FY 2028: 13080000; FY 2029: 9483000; FY 2030: 4578000
U-6005 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.17 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 500000
U-6005 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.17 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 3800000 | FY 2024: 1920000; FY 2026: 380000; FY 2027: 380000
U-6005 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.17 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 900000
U-6005 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.17 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 14000000 | FY 2026: 5740000; FY 2027: 5600000; FY 2028: 2660000
U-6006 | Highway | STI (Prioritization) | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.72 | RANDOLPH | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | Division 8 |  |  |  | 944000
U-6006 | Highway | STI (Prioritization) | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.72 | RANDOLPH | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | Division 8 |  | T | RIGHT-OF-WAY | 1000000 | FY 2024: 348000; FY 2025: 417000; FY 2026: 35000; FY 2027: 100000; FY 2028: 100000
U-6006 | Highway | STI (Prioritization) | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.72 | RANDOLPH | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | Division 8 |  | T | UTILITIES | 2748000 | FY 2024: 2748000
U-6006 | Highway | STI (Prioritization) | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.72 | RANDOLPH | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | Division 8 |  | T | CONSTRUCTION | 8499000 | FY 2027: 2213000; FY 2028: 4595000; FY 2029: 1691000
U-6007 | Highway | STI (Prioritization) | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 0.47 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  |  |  | 876000
U-6007 | Highway | STI (Prioritization) | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 0.47 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 300000
U-6007 | Highway | STI (Prioritization) | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 0.47 | RANDOLPH | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 1400000 | FY 2024: 813000; FY 2025: 587000
U-6008 | Highway | STI (Prioritization) | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 680000
U-6008 | Highway | STI (Prioritization) | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 1600000 | FY 2027: 7000; FY 2028: 671000; FY 2029: 602000; FY 2030: 160000; FY 2031: 160000
U-6008 | Highway | STI (Prioritization) | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | UTILITIES | 300000 | FY 2027: 300000
U-6008 | Highway | STI (Prioritization) | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | CONSTRUCTION | 4600000 | FY 2029: 713000; FY 2030: 3213000; FY 2031: 674000
U-6009 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 0.93 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 650000
U-6009 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 0.93 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | T | RIGHT-OF-WAY | 26600000 | FY 2028: 14187000; FY 2029: 7093000; FY 2030: 2660000; FY 2031: 2660000
U-6009 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 0.93 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | T | UTILITIES | 5100000 | FY 2028: 2550000; FY 2029: 2550000
U-6009 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 0.93 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | T | CONSTRUCTION | 11700000 | FY 2030: 2036000; FY 2031: 6521000; FY 2032: 2830000; FY 2033: 313000
U-6010 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  |  |  | 3450000
U-6010 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | T | RIGHT-OF-WAY | 6000000 | FY 2024: 2500000; FY 2025: 2500000
U-6010 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 5 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Region D |  | T | CONSTRUCTION | 16100000 | FY 2024: 4794000
U-6011 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  |  |  | 450000
U-6011 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 3000000
U-6011 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | UTILITIES | 630000
U-6011 | Highway | STI (Prioritization) | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 3000000 | FY 2025: 1830000; FY 2026: 1170000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 0.52 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 1391000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 0.52 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 5500000 | FY 2024: 1571000; FY 2025: 550000; FY 2026: 550000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 0.52 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 900000
U-6013 | Highway | STI (Prioritization) | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 0.52 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 9999000 | FY 2028: 2577000; FY 2029: 5396000; FY 2030: 2026000
U-6014 | Highway | STI (Prioritization) | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.38 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 1205000
U-6014 | Highway | STI (Prioritization) | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.38 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 1500000 | FY 2024: 57000; FY 2025: 686000; FY 2026: 457000; FY 2027: 150000; FY 2028: 150000
U-6014 | Highway | STI (Prioritization) | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.38 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 1200000 | FY 2025: 600000; FY 2026: 600000
U-6014 | Highway | STI (Prioritization) | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.38 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 19100000 | FY 2027: 191000; FY 2028: 10123000; FY 2029: 5921000; FY 2030: 2865000
U-6015 | Highway | STI (Prioritization) | VARIOUS | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. |  | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  |  |  | 3094000
U-6015 | Highway | STI (Prioritization) | VARIOUS | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. |  | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 7 |  | T | BUILD NC CON | 6125000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 821000
U-6016 | Highway | STI (Prioritization) | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 350000
U-6016 | Highway | STI (Prioritization) | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 836000
U-6016 | Highway | STI (Prioritization) | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 215000
U-6016 | Highway | STI (Prioritization) | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 87000 | FY 2024: 87000
U-6016 | Highway | STI (Prioritization) | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 2049000 | FY 2025: 20000; FY 2026: 1866000; FY 2027: 163000
U-6017 | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 949000
U-6017 | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 2000000
U-6017 | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 550000
U-6017 | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 2100000 | FY 2024: 1150000; FY 2025: 950000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 1 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  |  |  | 17000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 1 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | RIGHT-OF-WAY | 2600000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 1 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | UTILITIES | 1500000 | FY 2024: 1500000
U-6018 | Highway | STI (Prioritization) | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 1 | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T | CONSTRUCTION | 24100000 | FY 2025: 241000; FY 2026: 12773000; FY 2027: 8194000; FY 2028: 2892000
U-6019 | Highway | STI (Prioritization) | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  |  |  | 425000
U-6019 | Highway | STI (Prioritization) | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 286000 | FY 2025: 286000
U-6019 | Highway | STI (Prioritization) | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | T | CONSTRUCTION | 1300000
U-6020 | Highway | STI (Prioritization) | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  |  |  | 1500000
U-6020 | Highway | STI (Prioritization) | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | T | RIGHT-OF-WAY | 100000 | FY 2024: 100000
U-6020 | Highway | STI (Prioritization) | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | T | CONSTRUCTION | 5024000 | FY 2025: 2546000; FY 2026: 2171000; FY 2027: 307000
U-6020 | Highway | STI (Prioritization) | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | Division 5 |  | L | CONSTRUCTION | 1675000 | FY 2025: 870000; FY 2026: 750000; FY 2027: 55000
U-6021 | Highway | STI (Prioritization) | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.37 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-6021 | Highway | STI (Prioritization) | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.37 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9100000
U-6021 | Highway | STI (Prioritization) | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.37 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-6021 | Highway | STI (Prioritization) | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.37 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15199000
U-6022 | Highway | STI (Prioritization) | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  |  |  | 325000
U-6022 | Highway | STI (Prioritization) | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | BGANY | UTILITIES | 451000
U-6022 | Highway | STI (Prioritization) | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | BGANY | CONSTRUCTION | 4092000 | FY 2024: 2864000; FY 2025: 655000
U-6023 | Highway | STI (Prioritization) | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  |  |  | 451000
U-6023 | Highway | STI (Prioritization) | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGANY | UTILITIES | 250000
U-6023 | Highway | STI (Prioritization) | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGANY | CONSTRUCTION | 4176000 | FY 2024: 2278000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.38 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 |  |  |  | 750000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.38 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 |  | T | RIGHT-OF-WAY | 3200000 | FY 2028: 80000; FY 2029: 960000; FY 2030: 960000; FY 2031: 560000; FY 2032: 640000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.38 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 |  | T | UTILITIES | 2800000 | FY 2028: 1400000; FY 2029: 1400000
U-6024 | Highway | STI (Prioritization) | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.38 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | Division 5 |  | T | CONSTRUCTION | 15998000 | FY 2031: 5671000; FY 2032: 6678000; FY 2033: 3649000
U-6026 | Highway | STI (Prioritization) | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | Division 5 |  |  |  | 324000
U-6026 | Highway | STI (Prioritization) | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | Division 5 |  | BGANY | UTILITIES | 450000
U-6026 | Highway | STI (Prioritization) | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | Division 5 |  | BGANY | CONSTRUCTION | 2320000 | FY 2024: 981000
U-6027 | Highway | STI (Prioritization) | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 0.54 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  |  |  | 650000
U-6027 | Highway | STI (Prioritization) | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 0.54 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 2101000 | FY 2025: 88000; FY 2026: 531000; FY 2027: 531000; FY 2028: 531000; FY 2029: 420000
U-6027 | Highway | STI (Prioritization) | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 0.54 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | T | UTILITIES | 2000000 | FY 2025: 2000000
U-6027 | Highway | STI (Prioritization) | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 0.54 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 4700000 | FY 2028: 47000; FY 2029: 3485000; FY 2030: 1168000
U-6028 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 1.48 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  |  |  | 2340000
U-6028 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 1.48 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | RIGHT-OF-WAY | 7700000 | FY 2027: 1680000; FY 2028: 2240000; FY 2029: 2240000; FY 2030: 770000; FY 2031: 770000
U-6028 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 1.48 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | UTILITIES | 4000000 | FY 2027: 2000000; FY 2028: 2000000
U-6028 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 1.48 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | CONSTRUCTION | 20400000 | FY 2031: 7344000; FY 2032: 7956000; FY 2033: 4284000 | 816000
U-6029 | Highway | STI (Prioritization) | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 4.24 | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | Not Funded |  |  |  | 6540000
U-6029 | Highway | STI (Prioritization) | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 4.24 | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 43403000 | [10 empty] | 43403000
U-6029 | Highway | STI (Prioritization) | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 4.24 | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 1085000 | [10 empty] | 1085000
U-6029 | Highway | STI (Prioritization) | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 4.24 | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 80200000 | [10 empty] | 80200000
U-6030 | Highway | STI (Prioritization) | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 1.71 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 3540000
U-6030 | Highway | STI (Prioritization) | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 1.71 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 22700000 | [10 empty] | 22700000
U-6030 | Highway | STI (Prioritization) | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 1.71 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 4610000 | [10 empty] | 4610000
U-6030 | Highway | STI (Prioritization) | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 1.71 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 24298000 | [10 empty] | 24298000
U-6031 | Highway | STI (Prioritization) | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 0.37 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  |  |  | 330000
U-6031 | Highway | STI (Prioritization) | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 0.37 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | RIGHT-OF-WAY | 7700000 | FY 2028: 1339000; FY 2029: 3214000; FY 2030: 1607000; FY 2031: 770000; FY 2032: 770000
U-6031 | Highway | STI (Prioritization) | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 0.37 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | UTILITIES | 4500000 | FY 2028: 2250000; FY 2029: 2250000
U-6031 | Highway | STI (Prioritization) | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 0.37 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | CONSTRUCTION | 10101000 | FY 2031: 1379000; FY 2032: 5802000; FY 2033: 2920000
U-6032 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | Division 10 |  |  |  | 1050000
U-6032 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | RIGHT-OF-WAY | 11500000 | FY 2024: 0; FY 2025: 4000000; FY 2026: 4800000
U-6032 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | UTILITIES | 2600000
U-6032 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | BUILD NC CON | 7725000 |  |  |  | 1030000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 3605000
U-6032 | Highway | STI (Prioritization) | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | Division 10 |  | T | CONSTRUCTION | 19800000 | FY 2027: 0; FY 2028: 9996000; FY 2029: 6708000; FY 2030: 3096000
U-6033 | Highway | STI (Prioritization) | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  |  |  | 137000
U-6033 | Highway | STI (Prioritization) | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | RIGHT-OF-WAY | 400000
U-6033 | Highway | STI (Prioritization) | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | UTILITIES | 668000 | FY 2024: 210000; FY 2025: 8000
U-6033 | Highway | STI (Prioritization) | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | T | CONSTRUCTION | 4261000 | FY 2024: 3369000; FY 2025: 863000
U-6034 | Highway | STI (Prioritization) | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 1.33 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  |  |  | 349000
U-6034 | Highway | STI (Prioritization) | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 1.33 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | RIGHT-OF-WAY | 9000000 | FY 2024: 4320000; FY 2025: 2880000; FY 2026: 900000; FY 2027: 900000
U-6034 | Highway | STI (Prioritization) | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 1.33 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | UTILITIES | 2200000 | FY 2024: 1100000; FY 2025: 1100000
U-6034 | Highway | STI (Prioritization) | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 1.33 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | CONSTRUCTION | 14400000 | FY 2027: 1817000; FY 2028: 6457000; FY 2029: 4677000; FY 2030: 1449000
U-6035 | Highway | STI (Prioritization) | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  |  |  | 150000
U-6035 | Highway | STI (Prioritization) | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | RIGHT-OF-WAY | 200000
U-6035 | Highway | STI (Prioritization) | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | UTILITIES | 305000 | FY 2024: 75000
U-6035 | Highway | STI (Prioritization) | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 2400000 | FY 2024: 845000; FY 2025: 1555000
U-6035 | Highway | STI (Prioritization) | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 400000 | FY 2025: 400000
U-6036 | Highway | STI (Prioritization) | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 0.6 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  |  |  | 800000
U-6036 | Highway | STI (Prioritization) | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 0.6 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | RIGHT-OF-WAY | 1500000
U-6036 | Highway | STI (Prioritization) | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 0.6 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | UTILITIES | 560000 | FY 2024: 160000
U-6036 | Highway | STI (Prioritization) | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 0.6 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 13317000 | FY 2024: 133000; FY 2025: 6525000; FY 2026: 4528000; FY 2027: 2131000
U-6037 | Highway | STI (Prioritization) | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 2.64 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  |  |  | 5000000
U-6037 | Highway | STI (Prioritization) | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 2.64 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | RIGHT-OF-WAY | 15500000 | FY 2027: 155000; FY 2028: 3978000; FY 2029: 5511000; FY 2030: 2756000; FY 2031: 3100000
U-6037 | Highway | STI (Prioritization) | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 2.64 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | UTILITIES | 4600000 | FY 2027: 2300000; FY 2028: 2300000
U-6037 | Highway | STI (Prioritization) | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 2.64 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | T | CONSTRUCTION | 23799000 | FY 2030: 2988000; FY 2031: 9661000; FY 2032: 7464000; FY 2033: 3686000
U-6038 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | 3.87 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Division 12 |  |  |  | 735000
U-6038 | Highway | STI (Prioritization) | US 74 (WILKINSON BOULEVARD) | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | 3.87 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | Division 12 |  | T | BUILD NC CON | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
U-6039 | Highway | STI (Prioritization) | SR 2321 (EAST BROAD STREET) | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | 0.68 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | Division 12 |  |  |  | 10050000
U-6039 | Highway | STI (Prioritization) | SR 2321 (EAST BROAD STREET) | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | 0.68 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | Division 12 |  | T | CONSTRUCTION | 5350000
U-6041 | Highway | STI (Prioritization) | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 |  | ALEXANDER | 12 | Greater Hickory MPO |  | Division 12 |  |  |  | 100000
U-6041 | Highway | STI (Prioritization) | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 |  | ALEXANDER | 12 | Greater Hickory MPO |  | Division 12 |  | BGLT5 | RIGHT-OF-WAY | 200000 | FY 2024: 200000
U-6041 | Highway | STI (Prioritization) | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 |  | ALEXANDER | 12 | Greater Hickory MPO |  | Division 12 |  | BGLT5 | UTILITIES | 400000 | FY 2024: 400000
U-6041 | Highway | STI (Prioritization) | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 |  | ALEXANDER | 12 | Greater Hickory MPO |  | Division 12 |  | BGLT5 | CONSTRUCTION | 1450000 | FY 2025: 966000; FY 2026: 484000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 0.5 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  |  |  | 375000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 0.5 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 1400000 | FY 2027: 14000; FY 2028: 658000; FY 2029: 448000; FY 2030: 140000; FY 2031: 140000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 0.5 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | T | UTILITIES | 200000 | FY 2027: 200000
U-6042 | Highway | STI (Prioritization) | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 0.5 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | T | CONSTRUCTION | 3300000 | FY 2029: 785000; FY 2030: 2243000; FY 2031: 272000
U-6043 | Highway | STI (Prioritization) | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 1.06 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 1300000
U-6043 | Highway | STI (Prioritization) | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 1.06 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | RIGHT-OF-WAY | 1300000 | FY 2024: 480000; FY 2025: 480000; FY 2026: 130000; FY 2027: 130000
U-6043 | Highway | STI (Prioritization) | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 1.06 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | UTILITIES | 900000
U-6043 | Highway | STI (Prioritization) | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 1.06 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | T | CONSTRUCTION | 2700000 | FY 2025: 27000; FY 2026: 1906000; FY 2027: 767000
U-6044 | Highway | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 0.27 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 1000000
U-6044 | Highway | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 0.27 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BG50200 | RIGHT-OF-WAY | 21100000 | FY 2028: 211000; FY 2029: 6138000; FY 2030: 6138000; FY 2031: 4604000; FY 2032: 4009000
U-6044 | Highway | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 0.27 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BG50200 | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
U-6044 | Highway | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 0.27 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BG50200 | CONSTRUCTION | 5400000 | FY 2028: 2592000; FY 2029: 2484000; FY 2030: 324000
U-6045 | Highway | STI (Prioritization) | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 0.69 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 250000
U-6045 | Highway | STI (Prioritization) | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 0.69 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 6800000 | FY 2027: 21000; FY 2028: 2085000; FY 2029: 2106000; FY 2030: 1228000; FY 2031: 1360000
U-6045 | Highway | STI (Prioritization) | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 0.69 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | UTILITIES | 1200000 | FY 2027: 600000; FY 2028: 600000
U-6045 | Highway | STI (Prioritization) | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 0.69 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | T | CONSTRUCTION | 23101000 | FY 2030: 3295000; FY 2031: 11230000; FY 2032: 6182000; FY 2033: 2394000
U-6046 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 2.33 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH U-5832. | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3443000
U-6046 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 2.33 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH U-5832. | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 16300000
U-6046 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 2.33 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH U-5832. | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4500000
U-6046 | Highway | STI (Prioritization) | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 2.33 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH U-5832. | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25600000
U-6047 | Highway | STI (Prioritization) | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 3.59 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  |  |  | 6100000
U-6047 | Highway | STI (Prioritization) | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 3.59 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 60799000 | FY 2028: 608000; FY 2029: 17079000; FY 2030: 17687000; FY 2031: 13265000; FY 2032: 12160000
U-6047 | Highway | STI (Prioritization) | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 3.59 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | UTILITIES | 6800000 | FY 2028: 3400000; FY 2029: 3400000
U-6047 | Highway | STI (Prioritization) | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 3.59 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 68999000 | FY 2031: 3313000; FY 2032: 20767000; FY 2033: 18268000 | 26651000
U-6048 | Highway | STI (Prioritization) | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 3.85 | HAYWOOD, BUNCOMBE | 13, 14 | French Broad River MPO |  | Division 13, 14 |  |  |  | 2226000
U-6048 | Highway | STI (Prioritization) | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 3.85 | HAYWOOD, BUNCOMBE | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | RIGHT-OF-WAY | 300000 | FY 2028: 300000
U-6048 | Highway | STI (Prioritization) | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 3.85 | HAYWOOD, BUNCOMBE | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | UTILITIES | 700000 | FY 2028: 700000
U-6048 | Highway | STI (Prioritization) | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 3.85 | HAYWOOD, BUNCOMBE | 13, 14 | French Broad River MPO |  | Division 13, 14 |  | T | CONSTRUCTION | 28201000 | FY 2030: 3860000; FY 2031: 10809000; FY 2032: 8282000; FY 2033: 5250000
U-6049 | Highway | STI (Prioritization) | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 0.24 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  |  |  | 680000
U-6049 | Highway | STI (Prioritization) | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 0.24 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | T | RIGHT-OF-WAY | 3400000 | FY 2024: 1053000; FY 2025: 1053000; FY 2026: 351000; FY 2027: 680000
U-6049 | Highway | STI (Prioritization) | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 0.24 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | T | UTILITIES | 400000
U-6049 | Highway | STI (Prioritization) | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 0.24 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | Region G |  | T | CONSTRUCTION | 4000000 | FY 2027: 1296000; FY 2028: 2324000; FY 2029: 380000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  |  |  | 166000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGDA | ENGINEERING | 225000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | ENGINEERING | 101000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BG5T50 | RIGHT-OF-WAY | 331000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGDA | RIGHT-OF-WAY | 732000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | RIGHT-OF-WAY | 374000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | RIGHT-OF-WAY | 103000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BG5T50 | CONSTRUCTION | 824000 | FY 2024: 824000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BG5T50 | CONSTRUCTION | 820000 | FY 2024: 820000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | CONSTRUCTION | 206000 | FY 2024: 206000
U-6054 | Highway | Locally Selected | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | IREDELL | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | L | CONSTRUCTION | 368000 | FY 2024: 368000
U-6055 | Highway | Locally Selected | CANTON | NC 110 (PISGAH DRIVE) AT LOCUST STREET. IMPROVE INTERSECTION. | 0.5 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST | Exempt |  |  |  | 1816000
U-6058 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  |  |  | 300000
U-6058 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | T | RIGHT-OF-WAY | 1359000 | FY 2024: 500000
U-6058 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | T | UTILITIES | 1200000 | FY 2024: 1200000
U-6058 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | BG5T50 | CONSTRUCTION | 5040000 | FY 2025: 50000; FY 2026: 3780000; FY 2027: 1210000
U-6058 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | Region B |  | L | CONSTRUCTION | 1260000 | FY 2025: 13000; FY 2026: 945000; FY 2027: 302000
U-6059 | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD) IN WINSTON-SALEM. UPGRADE INTERCHANGE AND REPLACE BRIDGE 330211 ON SR 2377 (OLD GREENSBORO ROAD NE) OVER NORFOLK SOUTHERN RAILROAD. | 1.5 | FORSYTH | 9 | Winston-Salem Area TPO | [5 empty] | 150000
U-6059A | Highway | Bridges | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 4229000 | FY 2026: 16000; FY 2027: 1595000; FY 2028: 1772000; FY 2029: 423000; FY 2030: 423000
U-6059A | Highway | Bridges | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 1100000 | FY 2026: 550000; FY 2027: 550000
U-6059A | Highway | Bridges | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 6800000 | FY 2028: 68000; FY 2029: 4057000; FY 2030: 2675000
U-6059B | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 1 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | RIGHT-OF-WAY | 11100000 | [10 empty] | 11100000
U-6059B | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 1 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | UTILITIES | 1332000 | [10 empty] | 1332000
U-6059B | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 1 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-6068 | Not Funded |  | T | CONSTRUCTION | 28860000 | [10 empty] | 28860000
U-6062 | Highway | STI (Prioritization) | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 4.26 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 |  |  |  | 750000
U-6062 | Highway | STI (Prioritization) | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 4.26 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 |  | T | RIGHT-OF-WAY | 28043000 |  |  |  |  | 83000 | 8174000 | 9498000 | 4748000 | 2770000 | 2770000
U-6062 | Highway | STI (Prioritization) | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 4.26 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 |  | T | UTILITIES | 11400000 | FY 2028: 5700000; FY 2029: 5700000
U-6062 | Highway | STI (Prioritization) | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 4.26 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | Division 9 |  | T | CONSTRUCTION | 25501000 | FY 2031: 1311000; FY 2032: 10676000; FY 2033: 8242000 | 5272000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  |  |  | 750000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 1000000 | FY 2025: 10000; FY 2026: 490000; FY 2027: 300000; FY 2028: 100000; FY 2029: 100000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BGLT5 | UTILITIES | 1178000 | FY 2025: 589000; FY 2026: 589000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1499000 | FY 2028: 717000; FY 2029: 678000; FY 2030: 104000
U-6065 | Highway | STI (Prioritization) | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 7201000 | FY 2028: 3444000; FY 2029: 3256000; FY 2030: 501000
U-6066 | Highway | STI (Prioritization) | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 3.14 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5825 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6066 | Highway | STI (Prioritization) | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 3.14 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5825 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 32400000
U-6066 | Highway | STI (Prioritization) | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 3.14 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5825 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-6066 | Highway | STI (Prioritization) | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 3.14 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5825 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40799000
U-6067 | Highway | STI (Prioritization) | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6067 | Highway | STI (Prioritization) | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 58701000
U-6067 | Highway | STI (Prioritization) | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1100000
U-6067 | Highway | STI (Prioritization) | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 217800000
U-6068 | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 6.69 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | Not Funded |  |  |  | 10000
U-6068 | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 6.69 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | Not Funded |  | T | RIGHT-OF-WAY | 15956000 | [10 empty] | 15956000
U-6068 | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 6.69 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | Not Funded |  | T | UTILITIES | 1600000 | [10 empty] | 1600000
U-6068 | Highway | STI (Prioritization) | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 6.69 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | Not Funded |  | T | CONSTRUCTION | 110500000 | [10 empty] | 110500000
U-6072 | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | STRICKLAND BRIDGE ROAD TO GOLFVIEW ROAD. WIDEN TO MULTI-LANES. | 5.8 | CUMBERLAND | 6 | Fayetteville Area MPO | [5 empty] | 4500000
U-6072A | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 4.8 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13600000 | [10 empty] | 13600000
U-6072A | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 4.8 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 4960000 | [10 empty] | 4960000
U-6072A | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 4.8 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 24500000 | [10 empty] | 24500000
U-6072B | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10400000 | [10 empty] | 10400000
U-6072B | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 1100000 | [10 empty] | 1100000
U-6072B | Highway | STI (Prioritization) | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 4300000 | [10 empty] | 4300000
U-6073 | Highway | STI (Prioritization) | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 2.1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  |  |  | 2010000
U-6073 | Highway | STI (Prioritization) | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 2.1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | RIGHT-OF-WAY | 17600000 | FY 2026: 5760000; FY 2027: 7680000; FY 2028: 640000; FY 2029: 1760000; FY 2030: 1760000
U-6073 | Highway | STI (Prioritization) | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 2.1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | UTILITIES | 2400000 | FY 2026: 1200000; FY 2027: 1200000
U-6073 | Highway | STI (Prioritization) | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 2.1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGANY | CONSTRUCTION | 25100000 | FY 2028: 8153000; FY 2029: 9580000; FY 2030: 6581000; FY 2031: 786000
U-6078 | Highway | STI (Prioritization) | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 1.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  |  |  | 200000
U-6078 | Highway | STI (Prioritization) | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 1.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | RIGHT-OF-WAY | 1400000 | FY 2025: 373000; FY 2026: 640000; FY 2027: 107000; FY 2028: 140000; FY 2029: 140000
U-6078 | Highway | STI (Prioritization) | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 1.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | UTILITIES | 733000 | FY 2025: 733000
U-6078 | Highway | STI (Prioritization) | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 1.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGANY | CONSTRUCTION | 5500000 | FY 2027: 1521000; FY 2028: 3192000; FY 2029: 787000
U-6081 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3.39 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  |  |  | 1000000
U-6081 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3.39 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2400000 | [10 empty] | 2400000
U-6081 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3.39 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 1000000 | [10 empty] | 1000000
U-6081 | Highway | STI (Prioritization) | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3.39 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 50800000 | [10 empty] | 50800000
U-6082 | Highway | STI (Prioritization) | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  |  |  | 500000
U-6082 | Highway | STI (Prioritization) | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | RIGHT-OF-WAY | 2800000 |  | 100000 | 670000 | 840000 | 630000 | 280000 | 280000
U-6082 | Highway | STI (Prioritization) | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | UTILITIES | 870000 | FY 2025: 870000
U-6082 | Highway | STI (Prioritization) | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 1 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BG50200 | CONSTRUCTION | 4300000 | FY 2028: 352000; FY 2029: 3175000; FY 2030: 773000
U-6084 | Highway | Economic Development | NC 16 (BROOKSHIRE BOULEVARD) | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | Region E |  |  |  | 6135000
U-6084 | Highway | Economic Development | NC 16 (BROOKSHIRE BOULEVARD) | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | Region E |  | T | CONSTRUCTION | 1963000
U-6085 | Highway | Locally Selected | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  |  |  | 153000
U-6085 | Highway | Locally Selected | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  | BGDA | PLANNING | 6960000 | FY 2024: 840000; FY 2025: 1280000; FY 2026: 1280000; FY 2027: 1280000; FY 2028: 1280000
U-6085 | Highway | Locally Selected | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS | Division 7 |  | L | PLANNING | 1740000 | FY 2024: 210000; FY 2025: 320000; FY 2026: 320000; FY 2027: 320000; FY 2028: 320000
U-6086 | Highway | Locally Selected | NC 51 | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.46 | MECKLENBURG | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | Exempt |  | BGANY | CONSTRUCTION | 5643000 | FY 2026: 1567000; FY 2027: 2813000; FY 2028: 1263000
U-6086 | Highway | Locally Selected | NC 51 | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.46 | MECKLENBURG | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | Exempt |  | L | CONSTRUCTION | 1910000 | FY 2026: 1910000
U-6087 | Highway | Locally Selected | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  |  |  | 297000
U-6087 | Highway | Locally Selected | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1006000 | FY 2025: 10000; FY 2026: 939000; FY 2027: 57000
U-6087 | Highway | Locally Selected | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 262000 | FY 2025: 262000
U-6087 | Highway | Locally Selected | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 319000 | FY 2025: 319000
U-6087 | Highway | Locally Selected | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | Division 10 |  | HF(M) | CONSTRUCTION | 293000 | FY 2025: 3000; FY 2026: 273000; FY 2027: 17000
U-6088 | Highway | Locally Selected | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  |  |  | 800000
U-6088 | Highway | Locally Selected | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1192000
U-6088 | Highway | Locally Selected | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 362000
U-6088 | Highway | Locally Selected | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 96000
U-6088 | Highway | Locally Selected | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | Division 10 |  | S(M) | CONSTRUCTION | 293000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  |  |  | 200000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | ENGINEERING | 258000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | S(M) | ENGINEERING | 133000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 193000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 27000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | S(M) | RIGHT-OF-WAY | 41000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1955000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 182000
U-6090 | Highway | Locally Selected | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | S(M) | CONSTRUCTION | 306000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  |  |  | 150000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 120000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | ENGINEERING | 30000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | RIGHT-OF-WAY | 515000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | RIGHT-OF-WAY | 120000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 30000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 130000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | CONSTRUCTION | 240000 | FY 2025: 240000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | CMAQ | CONSTRUCTION | 967000 | FY 2025: 967000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | BGDA | CONSTRUCTION | 771000 | FY 2025: 771000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | CONSTRUCTION | 242000 | FY 2025: 242000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | CONSTRUCTION | 60000 | FY 2025: 60000
U-6092 | Highway | Locally Selected | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Exempt |  | L | CONSTRUCTION | 192000 | FY 2025: 192000
U-6093 | Highway | Locally Selected | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  |  |  | 1230000
U-6093 | Highway | Locally Selected | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 1324000
U-6093 | Highway | Locally Selected | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 567000
U-6093 | Highway | Locally Selected | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 7743000
U-6093 | Highway | Locally Selected | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 3319000
U-6094 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  |  |  | 1022000
U-6094 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | RIGHT-OF-WAY | 1184000
U-6094 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | RIGHT-OF-WAY | 296000
U-6094 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | BGDA | CONSTRUCTION | 1217000 | FY 2025: 1217000
U-6094 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | Division 5 |  | L | CONSTRUCTION | 304000 | FY 2025: 304000
U-6096 | Highway | Locally Selected | SR 2763 (OLD HONEYCUTT ROAD) SR 1301 (PURFOY ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD (SR 2763) AND PURFOY ROAD (SR 1301) IN FUQUAY-VARINA. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  |  |  | 1142000
U-6098 | Highway | Economic Development | VARIOUS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | CABARRUS | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | Division 10 |  |  |  | 850000
U-6098 | Highway | Economic Development | VARIOUS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | CABARRUS | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | Division 10 |  | T | CONSTRUCTION | 1450000 | FY 2024: 600000
U-6099 | Highway | Economic Development | SR 5220 (JONES SAUSAGE ROAD) | SR 1004 (EAST GARNER ROAD) TO I-40 IN GARNER. WIDEN ROADWAY FROM SOUTH OF SR 2585 (WILMINGTON ROAD) TO I-40, INCLUDING ACCESS POINT IMPROVEMENTS, AND CONSTRUCT IMPROVEMENTS AT SR 1004 INTERSECTION AND I-40 INTERCHANGE. | 1.44 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON | Division 5 |  |  |  | 5100000
U-6100 | Highway | STI (Prioritization) | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 5.09 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6100 | Highway | STI (Prioritization) | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 5.09 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4400000 | [10 empty] | 4400000
U-6100 | Highway | STI (Prioritization) | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 5.09 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 2200000 | [10 empty] | 2200000
U-6100 | Highway | STI (Prioritization) | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 5.09 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 24000000 | [10 empty] | 24000000
U-6101 | Highway | STI (Prioritization) | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 50.54 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO |  | Not Funded |  |  |  | 10000
U-6101 | Highway | STI (Prioritization) | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 50.54 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 1000000 | [10 empty] | 1000000
U-6101 | Highway | STI (Prioritization) | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 50.54 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO |  | Not Funded |  | NHP | UTILITIES | 500000 | [10 empty] | 500000
U-6101 | Highway | STI (Prioritization) | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 50.54 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 138201000 | [10 empty] | 138201000
U-6102 | Highway | STI (Prioritization) | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  |  |  | 110000
U-6102 | Highway | STI (Prioritization) | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2700000 | [10 empty] | 2700000
U-6102 | Highway | STI (Prioritization) | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | UTILITIES | 500000 | [10 empty] | 500000
U-6102 | Highway | STI (Prioritization) | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | CONSTRUCTION | 21200000 | [10 empty] | 21200000
U-6103 | Highway | STI (Prioritization) | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 4.85 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  |  |  | 1010000
U-6103 | Highway | STI (Prioritization) | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 4.85 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 10500000 | FY 2026: 105000; FY 2027: 4095000; FY 2028: 4200000; FY 2029: 1050000; FY 2030: 1050000
U-6103 | Highway | STI (Prioritization) | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 4.85 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | UTILITIES | 1100000 | FY 2026: 550000; FY 2027: 550000
U-6103 | Highway | STI (Prioritization) | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 4.85 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 93200000 | FY 2029: 20084000; FY 2030: 29131000; FY 2031: 21565000; FY 2032: 13897000; FY 2033: 8523000
U-6104 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 2 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Not Funded |  |  |  | 760000
U-6104 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 2 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Not Funded |  | NHP | RIGHT-OF-WAY | 4233000 | [10 empty] | 4233000
U-6104 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 2 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Not Funded |  | NHP | UTILITIES | 300000 | [10 empty] | 300000
U-6104 | Highway | STI (Prioritization) | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 2 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Not Funded |  | NHP | CONSTRUCTION | 19200000 | [10 empty] | 19200000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  |  |  | 490000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGANY | RIGHT-OF-WAY | 756000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGDA | RIGHT-OF-WAY | 276000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | L | RIGHT-OF-WAY | 1032000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | BGANY | CONSTRUCTION | 2244000 | FY 2026: 1010000; FY 2027: 1003000; FY 2028: 231000
U-6105 | Highway | Locally Selected | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | Division 10 |  | L | CONSTRUCTION | 2389000 | FY 2026: 2389000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 1840000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGDA | RIGHT-OF-WAY | 667000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 167000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 460000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 1343000 | FY 2025: 1323000; FY 2026: 20000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 6910000 | FY 2025: 3455000; FY 2026: 3455000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 2095000 | FY 2025: 2095000
U-6106 | Highway | Locally Selected | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 336000 | FY 2025: 331000; FY 2026: 5000
U-6107 | Highway | STI (Prioritization) | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6107 | Highway | STI (Prioritization) | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1600000
U-6107 | Highway | STI (Prioritization) | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 460000
U-6107 | Highway | STI (Prioritization) | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 3900000
U-6108 | Highway | STI (Prioritization) | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 1.97 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6108 | Highway | STI (Prioritization) | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 1.97 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 44600000
U-6108 | Highway | STI (Prioritization) | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 1.97 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-6108 | Highway | STI (Prioritization) | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 1.97 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 12500000
U-6109 | Highway | STI (Prioritization) | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 2.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  |  |  | 10000
U-6109 | Highway | STI (Prioritization) | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 2.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | RIGHT-OF-WAY | 5000000 | FY 2026: 353000; FY 2027: 1412000; FY 2028: 1412000; FY 2029: 823000; FY 2030: 1000000
U-6109 | Highway | STI (Prioritization) | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 2.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | UTILITIES | 1700000 | FY 2026: 850000; FY 2027: 850000
U-6109 | Highway | STI (Prioritization) | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 2.95 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | NHP | CONSTRUCTION | 47400000 | FY 2029: 12324000; FY 2030: 16590000; FY 2031: 10428000; FY 2032: 6636000; FY 2033: 1422000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  |  |  | 10000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | RIGHT-OF-WAY | 200000 | FY 2025: 200000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | UTILITIES | 2200000 | FY 2025: 1100000; FY 2026: 1100000
U-6110 | Highway | STI (Prioritization) | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | NHP | CONSTRUCTION | 4100000 | FY 2027: 1533000; FY 2028: 2360000; FY 2029: 207000
U-6111 | Highway | STI (Prioritization) | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  |  |  | 10000
U-6111 | Highway | STI (Prioritization) | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | RIGHT-OF-WAY | 700000 | FY 2027: 700000
U-6111 | Highway | STI (Prioritization) | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6111 | Highway | STI (Prioritization) | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | CONSTRUCTION | 5400000 | FY 2029: 2193000; FY 2030: 3207000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 18000000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2600000
U-6112 | Highway | STI (Prioritization) | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 19100000
U-6113 | Highway | STI (Prioritization) | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 7.08 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Not Funded |  |  |  | 10000
U-6113 | Highway | STI (Prioritization) | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 7.08 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 7600000 | [10 empty] | 7600000
U-6113 | Highway | STI (Prioritization) | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 7.08 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 1500000 | [10 empty] | 1500000
U-6113 | Highway | STI (Prioritization) | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 7.08 | JOHNSTON, WAKE | 4, 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 83200000 | [10 empty] | 83200000
U-6114 | Highway | STI (Prioritization) | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6114 | Highway | STI (Prioritization) | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 840000
U-6114 | Highway | STI (Prioritization) | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 270000
U-6114 | Highway | STI (Prioritization) | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1100000
U-6115 | Highway | STI (Prioritization) | NC 54 | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) TO SOUTH OF SR 2107 (WHITTEMORE ROAD) IN GRAHAM. IMPROVE SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTION, UPGRADE RAMP INTERSECTIONS AT I-40 / I-85, IMPROVE SR 2106 (WOODY ROAD) INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 10000
U-6115A | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1300000
U-6115A | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6115A | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3501000
U-6115B | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1100000
U-6115B | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6115B | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8001000
U-6115C | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2700000
U-6115C | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 250000
U-6115C | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3200000
U-6115D | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 490000
U-6115D | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 120000
U-6115D | Highway | STI (Prioritization) | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2100000
U-6116 | Highway | STI (Prioritization) | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 1.99 | WAKE | 5 | Capital Area MPO |  | Not Funded |  |  |  | 10000
U-6116 | Highway | STI (Prioritization) | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 1.99 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2200000 | [10 empty] | 2200000
U-6116 | Highway | STI (Prioritization) | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 1.99 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 1400000 | [10 empty] | 1400000
U-6116 | Highway | STI (Prioritization) | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 1.99 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 4500000 | [10 empty] | 4500000
U-6117 | Highway | STI (Prioritization) | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6117 | Highway | STI (Prioritization) | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | UTILITIES | 300000 | FY 2027: 300000
U-6117 | Highway | STI (Prioritization) | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 3800000 | FY 2028: 1838000; FY 2029: 1962000
U-6118 | Highway | STI (Prioritization) | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE, UPGRADE RAMP TERMINALS, AND INCLUDE BIKE-PED FACILITIES. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  |  |  | 10000
U-6118 | Highway | STI (Prioritization) | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE, UPGRADE RAMP TERMINALS, AND INCLUDE BIKE-PED FACILITIES. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 400000 | FY 2028: 400000
U-6118 | Highway | STI (Prioritization) | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE, UPGRADE RAMP TERMINALS, AND INCLUDE BIKE-PED FACILITIES. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | UTILITIES | 350000 | FY 2028: 350000
U-6118 | Highway | STI (Prioritization) | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE, UPGRADE RAMP TERMINALS, AND INCLUDE BIKE-PED FACILITIES. | 2 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | CONSTRUCTION | 4799000 | FY 2029: 2516000; FY 2030: 2283000
U-6119 | Highway | STI (Prioritization) | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6119 | Highway | STI (Prioritization) | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | UTILITIES | 200000 | FY 2027: 200000
U-6119 | Highway | STI (Prioritization) | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 4700000 | FY 2028: 4700000
U-6120 | Highway | STI (Prioritization) | NC 98 (HOLLOWAY STREET) | SR 1838 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT THE ENTIRETY OF THE PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. | 0.83 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  |  |  | 10000
U-6120 | Highway | STI (Prioritization) | NC 98 (HOLLOWAY STREET) | SR 1838 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT THE ENTIRETY OF THE PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. | 0.83 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 7000000 | FY 2028: 1723000; FY 2029: 2585000; FY 2030: 1292000; FY 2031: 700000; FY 2032: 700000
U-6120 | Highway | STI (Prioritization) | NC 98 (HOLLOWAY STREET) | SR 1838 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT THE ENTIRETY OF THE PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. | 0.83 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
U-6120 | Highway | STI (Prioritization) | NC 98 (HOLLOWAY STREET) | SR 1838 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT THE ENTIRETY OF THE PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. | 0.83 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | T | CONSTRUCTION | 9998000 | FY 2030: 3974000; FY 2031: 4355000; FY 2032: 1669000
U-6121 | Highway | STI (Prioritization) | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 3.06 | GUILFORD | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13000000
U-6121 | Highway | STI (Prioritization) | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 3.06 | GUILFORD | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1000000
U-6121 | Highway | STI (Prioritization) | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 3.06 | GUILFORD | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 39499000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 2.12 | GUILFORD | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 2.12 | GUILFORD | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 2.12 | GUILFORD | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3500000
U-6122 | Highway | STI (Prioritization) | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 2.12 | GUILFORD | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 14199000
U-6123 | Highway | STI (Prioritization) | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  |  |  | 10000
U-6123 | Highway | STI (Prioritization) | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 200000 | [10 empty] | 200000
U-6123 | Highway | STI (Prioritization) | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | NHP | UTILITIES | 300000 | [10 empty] | 300000
U-6123 | Highway | STI (Prioritization) | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | NHP | CONSTRUCTION | 2000000 | [10 empty] | 2000000
U-6124 | Highway | STI (Prioritization) | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 1.09 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  |  |  | 10000
U-6124 | Highway | STI (Prioritization) | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 1.09 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 3300000 | [10 empty] | 3300000
U-6124 | Highway | STI (Prioritization) | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 1.09 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | UTILITIES | 1800000 | [10 empty] | 1800000
U-6124 | Highway | STI (Prioritization) | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 1.09 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | CONSTRUCTION | 23000000 | [10 empty] | 23000000
U-6125 | Highway | STI (Prioritization) | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 3 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6125 | Highway | STI (Prioritization) | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 3 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 6800000 | [10 empty] | 6800000
U-6125 | Highway | STI (Prioritization) | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 3 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 3500000 | [10 empty] | 3500000
U-6125 | Highway | STI (Prioritization) | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 3 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 14199000 | [10 empty] | 14199000
U-6126 | Highway | STI (Prioritization) | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 0.5 | SAMPSON | 3 | Mid-Carolina RPO |  | Not Funded |  |  |  | 260000
U-6126 | Highway | STI (Prioritization) | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 0.5 | SAMPSON | 3 | Mid-Carolina RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 302000 | [10 empty] | 302000
U-6126 | Highway | STI (Prioritization) | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 0.5 | SAMPSON | 3 | Mid-Carolina RPO |  | Not Funded |  | NHP | UTILITIES | 126000 | [10 empty] | 126000
U-6126 | Highway | STI (Prioritization) | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 0.5 | SAMPSON | 3 | Mid-Carolina RPO |  | Not Funded |  | NHP | CONSTRUCTION | 2500000 | [10 empty] | 2500000
U-6127 | Highway | STI (Prioritization) | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 0.89 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6127 | Highway | STI (Prioritization) | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 0.89 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1500000
U-6127 | Highway | STI (Prioritization) | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 0.89 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1000000
U-6127 | Highway | STI (Prioritization) | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 0.89 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9800000
U-6128 | Highway | STI (Prioritization) | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  |  |  | 260000
U-6128 | Highway | STI (Prioritization) | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | RIGHT-OF-WAY | 3700000 | FY 2027: 37000; FY 2028: 1443000; FY 2029: 1480000; FY 2030: 370000; FY 2031: 370000
U-6128 | Highway | STI (Prioritization) | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | UTILITIES | 600000 | FY 2027: 600000
U-6128 | Highway | STI (Prioritization) | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | BGANY | CONSTRUCTION | 3600000 | FY 2029: 305000; FY 2030: 2709000; FY 2031: 586000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 120000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 30000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 42000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 10000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 440000
U-6129 | Highway | STI (Prioritization) | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 0.19 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 110000
U-6130 | Highway | STI (Prioritization) | US 29 | NC 152 IN CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6130 | Highway | STI (Prioritization) | US 29 | NC 152 IN CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2500000
U-6130 | Highway | STI (Prioritization) | US 29 | NC 152 IN CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6130 | Highway | STI (Prioritization) | US 29 | NC 152 IN CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2000000
U-6131 | Highway | STI (Prioritization) | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  |  |  | 10000
U-6131 | Highway | STI (Prioritization) | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | RIGHT-OF-WAY | 4100000 | FY 2025: 2187000; FY 2026: 1093000; FY 2027: 410000; FY 2028: 410000
U-6131 | Highway | STI (Prioritization) | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
U-6131 | Highway | STI (Prioritization) | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | BG50200 | CONSTRUCTION | 3500000 | FY 2026: 1920000; FY 2027: 1580000
U-6132 | Highway | STI (Prioritization) | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 300000
U-6132 | Highway | STI (Prioritization) | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6132 | Highway | STI (Prioritization) | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
U-6133 | Highway | STI (Prioritization) | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6133 | Highway | STI (Prioritization) | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7900000
U-6133 | Highway | STI (Prioritization) | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1100000
U-6133 | Highway | STI (Prioritization) | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6900000
U-6134 | Highway | STI (Prioritization) | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  |  |  | 10000
U-6134 | Highway | STI (Prioritization) | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | RIGHT-OF-WAY | 500000 | FY 2024: 500000
U-6134 | Highway | STI (Prioritization) | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | UTILITIES | 100000 | FY 2024: 100000
U-6134 | Highway | STI (Prioritization) | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BGLT5 | CONSTRUCTION | 25400000 | FY 2026: 6592000; FY 2027: 9714000; FY 2028: 6887000; FY 2029: 2207000
U-6135 | Highway | STI (Prioritization) | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.1 | CATAWBA | 12 | Greater Hickory MPO |  | Not Funded |  |  |  | 10000
U-6135 | Highway | STI (Prioritization) | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.1 | CATAWBA | 12 | Greater Hickory MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 19700000 | [10 empty] | 19700000
U-6135 | Highway | STI (Prioritization) | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.1 | CATAWBA | 12 | Greater Hickory MPO |  | Not Funded |  | T | UTILITIES | 6100000 | [10 empty] | 6100000
U-6135 | Highway | STI (Prioritization) | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.1 | CATAWBA | 12 | Greater Hickory MPO |  | Not Funded |  | T | CONSTRUCTION | 23299000 | [10 empty] | 23299000
U-6138 | Highway | STI (Prioritization) | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  |  |  | 10000
U-6138 | Highway | STI (Prioritization) | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BG50200 | RIGHT-OF-WAY | 880000 | FY 2025: 440000; FY 2026: 440000
U-6138 | Highway | STI (Prioritization) | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BG50200 | UTILITIES | 70000 | FY 2025: 70000
U-6138 | Highway | STI (Prioritization) | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | BG50200 | CONSTRUCTION | 2000000 | FY 2026: 820000; FY 2027: 1180000
U-6139 | Highway | STI (Prioritization) | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 1.84 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  |  |  | 10000
U-6139 | Highway | STI (Prioritization) | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 1.84 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 5900000 | [10 empty] | 5900000
U-6139 | Highway | STI (Prioritization) | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 1.84 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | UTILITIES | 1500000 | [10 empty] | 1500000
U-6139 | Highway | STI (Prioritization) | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 1.84 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | CONSTRUCTION | 42000000 | [10 empty] | 42000000
U-6140 | Highway | STI (Prioritization) | NC 27 (EAST MAIN STREET) | US 321 BUSINESS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 2.37 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6140 | Highway | STI (Prioritization) | NC 27 (EAST MAIN STREET) | US 321 BUSINESS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 2.37 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 34999000
U-6140 | Highway | STI (Prioritization) | NC 27 (EAST MAIN STREET) | US 321 BUSINESS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 2.37 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9300000
U-6140 | Highway | STI (Prioritization) | NC 27 (EAST MAIN STREET) | US 321 BUSINESS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 2.37 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 33501000
U-6141 | Highway | STI (Prioritization) | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  |  |  | 10000
U-6141 | Highway | STI (Prioritization) | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 12200000 | [10 empty] | 12200000
U-6141 | Highway | STI (Prioritization) | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | UTILITIES | 900000 | [10 empty] | 900000
U-6141 | Highway | STI (Prioritization) | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | NHP | CONSTRUCTION | 8800000 | [10 empty] | 8800000
U-6142 | Highway | STI (Prioritization) | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 3.88 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  |  |  | 10000
U-6142 | Highway | STI (Prioritization) | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 3.88 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 32300000 | [10 empty] | 32300000
U-6142 | Highway | STI (Prioritization) | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 3.88 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | UTILITIES | 4800000 | [10 empty] | 4800000
U-6142 | Highway | STI (Prioritization) | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 3.88 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | CONSTRUCTION | 69302000 | [10 empty] | 69302000
U-6143 | Highway | STI (Prioritization) | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  |  |  | 10000
U-6143 | Highway | STI (Prioritization) | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | RIGHT-OF-WAY | 630000
U-6143 | Highway | STI (Prioritization) | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | UTILITIES | 280000
U-6143 | Highway | STI (Prioritization) | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | NHP | CONSTRUCTION | 2800000 | FY 2025: 532000; FY 2026: 1736000; FY 2027: 532000
U-6143 | Highway | STI (Prioritization) | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | Region F |  | L | CONSTRUCTION | 2200000 | FY 2025: 418000; FY 2026: 1364000; FY 2027: 418000
U-6144 | Highway | STI (Prioritization) | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 1.49 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  |  |  | 10000
U-6144 | Highway | STI (Prioritization) | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 1.49 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5500000 | [10 empty] | 5500000
U-6144 | Highway | STI (Prioritization) | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 1.49 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | UTILITIES | 4900000 | [10 empty] | 4900000
U-6144 | Highway | STI (Prioritization) | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 1.49 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | CONSTRUCTION | 21599000 | [10 empty] | 21599000
U-6145 | Highway | STI (Prioritization) | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 2.93 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6145 | Highway | STI (Prioritization) | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 2.93 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5200000 | [10 empty] | 5200000
U-6145 | Highway | STI (Prioritization) | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 2.93 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 3300000 | [10 empty] | 3300000
U-6145 | Highway | STI (Prioritization) | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 2.93 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 28801000 | [10 empty] | 28801000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  |  |  | 10000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | BUILD NC ROW | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 516000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | RIGHT-OF-WAY | 5800000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | UTILITIES | 5500000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 5975000 | FY 2027: 5975000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 4103000 | FY 2028: 4103000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 7113000 | FY 2026: 7113000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 1941000 | FY 2025: 1941000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | T | CONSTRUCTION | 966000 | FY 2029: 966000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 4311000 | FY 2027: 4311000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 5133000 | FY 2026: 5133000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 1400000 | FY 2025: 1400000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 697000 | FY 2029: 697000
U-6146 | Highway | STI (Prioritization) | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | Region F |  | HFB | CONSTRUCTION | 2961000 | FY 2028: 2961000
U-6147 | Highway | STI (Prioritization) | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 1.96 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6147 | Highway | STI (Prioritization) | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 1.96 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5900000 | [10 empty] | 5900000
U-6147 | Highway | STI (Prioritization) | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 1.96 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 800000 | [10 empty] | 800000
U-6147 | Highway | STI (Prioritization) | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 1.96 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 12001000 | [10 empty] | 12001000
U-6148 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  |  |  | 260000
U-6148 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 329000 | [10 empty] | 329000
U-6148 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 140000 | [10 empty] | 140000
U-6148 | Highway | STI (Prioritization) | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 750000 | [10 empty] | 750000
U-6149 | Highway | STI (Prioritization) | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 15.14 | NASH, EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6149 | Highway | STI (Prioritization) | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 15.14 | NASH, EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 11800000 | [10 empty] | 11800000
U-6149 | Highway | STI (Prioritization) | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 15.14 | NASH, EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 2200000 | [10 empty] | 2200000
U-6149 | Highway | STI (Prioritization) | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 15.14 | NASH, EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 137000000 | [10 empty] | 137000000
U-6150 | Highway | STI (Prioritization) | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  |  |  | 10000
U-6150 | Highway | STI (Prioritization) | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 300000 | [10 empty] | 300000
U-6150 | Highway | STI (Prioritization) | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | UTILITIES | 1500000 | [10 empty] | 1500000
U-6150 | Highway | STI (Prioritization) | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Not Funded |  | T | CONSTRUCTION | 1700000 | [10 empty] | 1700000
U-6151 | Highway | STI (Prioritization) | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 6.21 | ALEXANDER | 12 | Greater Hickory MPO |  | Not Funded |  |  |  | 10000
U-6151 | Highway | STI (Prioritization) | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 6.21 | ALEXANDER | 12 | Greater Hickory MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 17300000 | [10 empty] | 17300000
U-6151 | Highway | STI (Prioritization) | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 6.21 | ALEXANDER | 12 | Greater Hickory MPO |  | Not Funded |  | T | UTILITIES | 3500000 | [10 empty] | 3500000
U-6151 | Highway | STI (Prioritization) | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 6.21 | ALEXANDER | 12 | Greater Hickory MPO |  | Not Funded |  | T | CONSTRUCTION | 55000000 | [10 empty] | 55000000
U-6152 | Highway | STI (Prioritization) | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 2.09 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  |  |  | 10000
U-6152 | Highway | STI (Prioritization) | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 2.09 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 17500000 | [10 empty] | 17500000
U-6152 | Highway | STI (Prioritization) | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 2.09 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | NHP | UTILITIES | 19700000 | [10 empty] | 19700000
U-6152 | Highway | STI (Prioritization) | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 2.09 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 19900000 | [10 empty] | 19900000
U-6153 | Highway | Locally Selected | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 0.76 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  |  |  | 10000
U-6153 | Highway | Locally Selected | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 0.76 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | BA | ENGINEERING | 452000
U-6153 | Highway | Locally Selected | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 0.76 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | T | CONSTRUCTION | 2098000 | FY 2026: 1049000; FY 2027: 1049000
U-6153 | Highway | Locally Selected | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 0.76 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | Division 12 |  | O | CONSTRUCTION | 2550000 | FY 2026: 2550000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  |  |  | 120000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 273000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | ENGINEERING | 68000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 200000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 179000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 50000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 45000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 1494000 | FY 2024: 1494000
U-6154 | Highway | Locally Selected | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 373000 | FY 2024: 373000
U-6157 | Highway | STI (Prioritization) | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 3.39 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  |  |  | 10000
U-6157 | Highway | STI (Prioritization) | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 3.39 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | RIGHT-OF-WAY | 13000000 | FY 2025: 3467000; FY 2026: 3782000; FY 2027: 3151000; FY 2028: 1300000; FY 2029: 1300000
U-6157 | Highway | STI (Prioritization) | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 3.39 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | UTILITIES | 10200000 | FY 2025: 5100000; FY 2026: 5100000
U-6157 | Highway | STI (Prioritization) | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 3.39 | CALDWELL | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGANY | CONSTRUCTION | 23901000 | FY 2027: 239000; FY 2028: 8975000; FY 2029: 8026000; FY 2030: 5403000; FY 2031: 1258000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 0.5 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  |  |  | 10000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 0.5 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | RIGHT-OF-WAY | 500000 | FY 2028: 250000; FY 2029: 250000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 0.5 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | UTILITIES | 200000 | FY 2028: 200000
U-6158 | Highway | STI (Prioritization) | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 0.5 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | T | CONSTRUCTION | 3101000 | FY 2030: 798000; FY 2031: 1957000; FY 2032: 346000
U-6159 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 1.32 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  |  |  | 10000
U-6159 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 1.32 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BG5T50 | RIGHT-OF-WAY | 14500000 | FY 2028: 4350000; FY 2029: 5800000; FY 2030: 1450000; FY 2031: 1450000; FY 2032: 1450000
U-6159 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 1.32 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BG5T50 | UTILITIES | 2300000 | FY 2028: 1150000; FY 2029: 1150000
U-6159 | Highway | STI (Prioritization) | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 1.32 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BG5T50 | CONSTRUCTION | 13401000 | FY 2030: 4189000; FY 2031: 5556000; FY 2032: 3656000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 1 | CALDWELL | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  |  |  | 10000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 1 | CALDWELL | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | RIGHT-OF-WAY | 800000 | FY 2025: 400000; FY 2026: 400000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 1 | CALDWELL | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | UTILITIES | 200000 | FY 2025: 200000
U-6161 | Highway | STI (Prioritization) | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 1 | CALDWELL | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | Division 11 |  | NHP | CONSTRUCTION | 4000000 | FY 2027: 1241000; FY 2028: 2236000; FY 2029: 523000
U-6162 | Highway | STI (Prioritization) | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 0.66 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6162 | Highway | STI (Prioritization) | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 0.66 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 13200000
U-6162 | Highway | STI (Prioritization) | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 0.66 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 800000
U-6162 | Highway | STI (Prioritization) | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 0.66 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 6000000
U-6163 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | HF | RIGHT-OF-WAY | 100000 | FY 2024: 100000
U-6163 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | HF | UTILITIES | 300000 | FY 2024: 300000
U-6163 | Highway | STI (Prioritization) | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | Division 13 |  | BGANY | CONSTRUCTION | 2400000 | FY 2025: 24000; FY 2026: 1868000; FY 2027: 508000
U-6164 | Highway | STI (Prioritization) | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 6.6 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  |  |  | 10000
U-6164 | Highway | STI (Prioritization) | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 6.6 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | BGLT5 | RIGHT-OF-WAY | 4000000 | [10 empty] | 4000000
U-6164 | Highway | STI (Prioritization) | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 6.6 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | BGLT5 | UTILITIES | 6500000 | [10 empty] | 6500000
U-6164 | Highway | STI (Prioritization) | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 6.6 | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | BGLT5 | CONSTRUCTION | 36300000 | [10 empty] | 36300000
U-6165 | Highway | STI (Prioritization) | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 0.88 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6165 | Highway | STI (Prioritization) | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 0.88 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 21255000 | [10 empty] | 21255000
U-6165 | Highway | STI (Prioritization) | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 0.88 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | UTILITIES | 2000000 | [10 empty] | 2000000
U-6165 | Highway | STI (Prioritization) | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 0.88 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | CONSTRUCTION | 9400000 | [10 empty] | 9400000
U-6166 | Highway | STI (Prioritization) | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 0.46 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6166 | Highway | STI (Prioritization) | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 0.46 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 6600000 | [10 empty] | 6600000
U-6166 | Highway | STI (Prioritization) | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 0.46 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 500000 | [10 empty] | 500000
U-6166 | Highway | STI (Prioritization) | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 0.46 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 8498000 | [10 empty] | 8498000
U-6167 | Highway | STI (Prioritization) | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 2.68 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6167 | Highway | STI (Prioritization) | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 2.68 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 94300000 | [10 empty] | 94300000
U-6167 | Highway | STI (Prioritization) | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 2.68 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | UTILITIES | 1500000 | [10 empty] | 1500000
U-6167 | Highway | STI (Prioritization) | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 2.68 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | CONSTRUCTION | 31401000 | [10 empty] | 31401000
U-6168 | Highway | STI (Prioritization) | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 1.6 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6168 | Highway | STI (Prioritization) | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 1.6 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9700000 | [10 empty] | 9700000
U-6168 | Highway | STI (Prioritization) | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 1.6 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 1600000 | [10 empty] | 1600000
U-6168 | Highway | STI (Prioritization) | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 1.6 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 18800000 | [10 empty] | 18800000
U-6169 | Highway | STI (Prioritization) | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 2.01 | UNION | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6169 | Highway | STI (Prioritization) | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 2.01 | UNION | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 3000000 | [10 empty] | 3000000
U-6169 | Highway | STI (Prioritization) | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 2.01 | UNION | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | UTILITIES | 2800000 | [10 empty] | 2800000
U-6169 | Highway | STI (Prioritization) | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 2.01 | UNION | 10 | Charlotte Regional TPO |  | Not Funded |  | BGANY | CONSTRUCTION | 26100000 | [10 empty] | 26100000
U-6170 | Highway | STI (Prioritization) | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  |  |  | 10000
U-6170 | Highway | STI (Prioritization) | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | RIGHT-OF-WAY | 3000000 | FY 2027: 686000; FY 2028: 1371000; FY 2029: 343000; FY 2030: 300000; FY 2031: 300000
U-6170 | Highway | STI (Prioritization) | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | UTILITIES | 1400000 | FY 2027: 14000; FY 2028: 1386000
U-6170 | Highway | STI (Prioritization) | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | T | CONSTRUCTION | 8800000 | FY 2030: 88000; FY 2031: 5456000; FY 2032: 2640000; FY 2033: 616000
U-6171 | Highway | STI (Prioritization) | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 0.24 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6171 | Highway | STI (Prioritization) | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 0.24 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 900000 | [10 empty] | 900000
U-6171 | Highway | STI (Prioritization) | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 0.24 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | UTILITIES | 2300000 | [10 empty] | 2300000
U-6171 | Highway | STI (Prioritization) | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 0.24 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Not Funded |  | T | CONSTRUCTION | 19500000 | [10 empty] | 19500000
U-6172 | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 1.86 | HAYWOOD, JACKSON | 14 | French Broad River MPO, Southwestern RPO |  | Division 14 |  |  |  | 10000
U-6172A | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 1 | JACKSON, HAYWOOD | 14 | Southwestern RPO, French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 110000
U-6172A | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 1 | JACKSON, HAYWOOD | 14 | Southwestern RPO, French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 110000
U-6172A | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 1 | JACKSON, HAYWOOD | 14 | Southwestern RPO, French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 1700000
U-6172B | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 1.86 | HAYWOOD, JACKSON | 14 | French Broad River MPO, Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 80000
U-6172B | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 1.86 | HAYWOOD, JACKSON | 14 | French Broad River MPO, Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 250000
U-6172B | Highway | STI (Prioritization) | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 1.86 | HAYWOOD, JACKSON | 14 | French Broad River MPO, Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 2800000
U-6173 | Highway | STI (Prioritization) | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 8.37 | BUNCOMBE, MADISON | 13 | French Broad River MPO, Land-of-Sky RPO |  | Not Funded |  |  |  | 10000
U-6173 | Highway | STI (Prioritization) | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 8.37 | BUNCOMBE, MADISON | 13 | French Broad River MPO, Land-of-Sky RPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 300000 | [10 empty] | 300000
U-6173 | Highway | STI (Prioritization) | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 8.37 | BUNCOMBE, MADISON | 13 | French Broad River MPO, Land-of-Sky RPO |  | Not Funded |  | BGANY | UTILITIES | 600000 | [10 empty] | 600000
U-6173 | Highway | STI (Prioritization) | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 8.37 | BUNCOMBE, MADISON | 13 | French Broad River MPO, Land-of-Sky RPO |  | Not Funded |  | BGANY | CONSTRUCTION | 33249000 | [10 empty] | 33249000
U-6175 | Highway | STI (Prioritization) | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 3.17 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  |  |  | 10000
U-6175 | Highway | STI (Prioritization) | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 3.17 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 21800000 | [10 empty] | 21800000
U-6175 | Highway | STI (Prioritization) | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 3.17 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | BGANY | UTILITIES | 3540000 | [10 empty] | 3540000
U-6175 | Highway | STI (Prioritization) | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 3.17 | IREDELL | 12 | Charlotte Regional TPO |  | Not Funded |  | BGANY | CONSTRUCTION | 28602000 | [10 empty] | 28602000
U-6176 | Highway | STI (Prioritization) | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3.83 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6176 | Highway | STI (Prioritization) | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3.83 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 26200000
U-6176 | Highway | STI (Prioritization) | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3.83 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2900000
U-6176 | Highway | STI (Prioritization) | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3.83 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 20499000
U-6181 | Highway | STI (Prioritization) | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 216000
U-6181 | Highway | STI (Prioritization) | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6181 | Highway | STI (Prioritization) | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1400000
U-6182 | Highway | STI (Prioritization) | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1200000
U-6182 | Highway | STI (Prioritization) | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 180000
U-6182 | Highway | STI (Prioritization) | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1100000
U-6183 | Highway | STI (Prioritization) | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 400000
U-6183 | Highway | STI (Prioritization) | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
U-6183 | Highway | STI (Prioritization) | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2900000
U-6184 | Highway | STI (Prioritization) | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5800000
U-6184 | Highway | STI (Prioritization) | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6184 | Highway | STI (Prioritization) | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8399000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 480000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 120000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 160000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 40000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1040000
U-6185 | Highway | STI (Prioritization) | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 260000
U-6186 | Highway | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 530000
U-6186 | Highway | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 890000
U-6186 | Highway | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4100000
U-6187 | Highway | STI (Prioritization) | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 0.71 | DAVIE | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | BGANY | RIGHT-OF-WAY | 4000000 | FY 2024: 312000; FY 2025: 2908000; FY 2026: 390000; FY 2027: 390000
U-6187 | Highway | STI (Prioritization) | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 0.71 | DAVIE | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | BGANY | UTILITIES | 1000000 | FY 2025: 1000000
U-6187 | Highway | STI (Prioritization) | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 0.71 | DAVIE | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | BUILD NC CON | 6435000 |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-6187 | Highway | STI (Prioritization) | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 0.71 | DAVIE | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | Division 9 |  | T | CONSTRUCTION | 31600000 | FY 2026: 366000; FY 2027: 8542000; FY 2028: 11712000; FY 2029: 7686000; FY 2030: 3294000
U-6188 | Highway | STI (Prioritization) | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 1100000 | FY 2027: 160000; FY 2028: 480000; FY 2029: 240000; FY 2030: 110000; FY 2031: 110000
U-6188 | Highway | STI (Prioritization) | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6188 | Highway | STI (Prioritization) | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 4100000 | FY 2029: 697000; FY 2030: 2696000; FY 2031: 707000
U-6189 | Highway | STI (Prioritization) | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 2.31 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 14500000 | FY 2027: 612000; FY 2028: 7325000; FY 2029: 3663000; FY 2030: 1450000; FY 2031: 1450000
U-6189 | Highway | STI (Prioritization) | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 2.31 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 3100000 | FY 2029: 3100000
U-6189 | Highway | STI (Prioritization) | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 2.31 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 19200000 | FY 2030: 3105000; FY 2031: 7868000; FY 2032: 5492000; FY 2033: 2735000
U-6190 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | RIGHT-OF-WAY | 1700000 | FY 2027: 8000; FY 2028: 792000; FY 2029: 560000; FY 2030: 170000; FY 2031: 170000
U-6190 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6190 | Highway | STI (Prioritization) | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 3100000 | FY 2029: 313000; FY 2030: 2307000; FY 2031: 480000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 3.18 | RANDOLPH | 8 | High Point Urban Area MPO |  | Division 8 |  | T | RIGHT-OF-WAY | 5701000 | FY 2028: 1086000; FY 2029: 2606000; FY 2030: 869000; FY 2031: 570000; FY 2032: 570000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 3.18 | RANDOLPH | 8 | High Point Urban Area MPO |  | Division 8 |  | T | UTILITIES | 4700000 | FY 2028: 2350000; FY 2029: 2350000
U-6191 | Highway | STI (Prioritization) | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 3.18 | RANDOLPH | 8 | High Point Urban Area MPO |  | Division 8 |  | T | CONSTRUCTION | 12400000 | FY 2030: 124000; FY 2031: 6702000; FY 2032: 4561000; FY 2033: 1013000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 10.46 | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | T | RIGHT-OF-WAY | 9299000 | FY 2028: 451000; FY 2029: 2705000; FY 2030: 2705000; FY 2031: 1578000; FY 2032: 1860000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 10.46 | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | T | UTILITIES | 30000000 | FY 2028: 15000000; FY 2029: 15000000
U-6192 | Highway | STI (Prioritization) | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 10.46 | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | T | CONSTRUCTION | 78400000 | FY 2031: 784000; FY 2032: 23811000; FY 2033: 22582000 | 31223000
U-6193 | Highway | STI (Prioritization) | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 0.5 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5300000 | [10 empty] | 5300000
U-6193 | Highway | STI (Prioritization) | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 0.5 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 770000 | [10 empty] | 770000
U-6193 | Highway | STI (Prioritization) | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 0.5 | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 16500000 | [10 empty] | 16500000
U-6194 | Highway | STI (Prioritization) | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6194 | Highway | STI (Prioritization) | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | UTILITIES | 360000 | FY 2027: 360000
U-6194 | Highway | STI (Prioritization) | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGANY | CONSTRUCTION | 3200000 | FY 2028: 1653000; FY 2029: 1547000
U-6195 | Highway | STI (Prioritization) | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 1.99 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6195 | Highway | STI (Prioritization) | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 1.99 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9000000 | [10 empty] | 9000000
U-6195 | Highway | STI (Prioritization) | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 1.99 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 2100000 | [10 empty] | 2100000
U-6195 | Highway | STI (Prioritization) | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 1.99 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 21601000 | [10 empty] | 21601000
U-6196 | Highway | STI (Prioritization) | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 1.8 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6196 | Highway | STI (Prioritization) | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 1.8 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10500000 | [10 empty] | 10500000
U-6196 | Highway | STI (Prioritization) | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 1.8 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 900000 | [10 empty] | 900000
U-6196 | Highway | STI (Prioritization) | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 1.8 | PITT | 2 | Greenville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 9300000 | [10 empty] | 9300000
U-6197 | Highway | STI (Prioritization) | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  |  |  | 10000
U-6197 | Highway | STI (Prioritization) | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | RIGHT-OF-WAY | 1300000 | FY 2027: 1300000
U-6197 | Highway | STI (Prioritization) | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | UTILITIES | 730000 | FY 2027: 730000
U-6197 | Highway | STI (Prioritization) | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | T | CONSTRUCTION | 3100000 | FY 2029: 31000; FY 2030: 2852000; FY 2031: 217000
U-6198 | Highway | STI (Prioritization) | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.56 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  |  |  | 10000
U-6198 | Highway | STI (Prioritization) | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.56 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 18000000 | [10 empty] | 18000000
U-6198 | Highway | STI (Prioritization) | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.56 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | UTILITIES | 3100000 | [10 empty] | 3100000
U-6198 | Highway | STI (Prioritization) | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.56 | CRAVEN | 2 | New Bern Area MPO |  | Not Funded |  | T | CONSTRUCTION | 24700000 | [10 empty] | 24700000
U-6199 | Highway | STI (Prioritization) | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 39.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 10000
U-6199 | Highway | STI (Prioritization) | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 39.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 100000 | FY 2028: 100000
U-6199 | Highway | STI (Prioritization) | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 39.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | UTILITIES | 950000 | FY 2028: 950000
U-6199 | Highway | STI (Prioritization) | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 39.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 15361000 | FY 2030: 2288000; FY 2031: 7346000; FY 2032: 4931000; FY 2033: 796000
U-6200 | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 0.86 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  |  |  | 10000
U-6200 | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 0.86 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3500000 | [10 empty] | 3500000
U-6200 | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 0.86 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | UTILITIES | 1600000 | [10 empty] | 1600000
U-6200 | Highway | STI (Prioritization) | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 0.86 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 9700000 | [10 empty] | 9700000
U-6201 | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  |  |  | 10000
U-6201 | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | RIGHT-OF-WAY | 4200000 | FY 2028: 1120000; FY 2029: 1493000; FY 2030: 747000; FY 2031: 420000; FY 2032: 420000
U-6201 | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | UTILITIES | 400000 | FY 2028: 400000
U-6201 | Highway | STI (Prioritization) | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 4498000 | FY 2030: 1071000; FY 2031: 2982000; FY 2032: 445000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  |  |  | 10000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  | T | BUILD NC ROW | 5148000 |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 1287000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  | T | RIGHT-OF-WAY | 5000000 | FY 2024: 5000000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  | T | UTILITIES | 2626000 | FY 2025: 2626000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  | T | BUILD NC CON | 18300000 |  | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 7320000
U-6202 | Highway | STI (Prioritization) | SR 2048 (GORDON ROAD) | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | Division 3 |  | T | CONSTRUCTION | 26800000 | FY 2026: 8952000; FY 2027: 10864000; FY 2028: 6984000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  |  |  | 10000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 28963000 | FY 2026: 6620000; FY 2027: 13241000; FY 2028: 3310000; FY 2029: 2896000; FY 2030: 2896000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | UTILITIES | 4360000 | FY 2026: 2180000; FY 2027: 2180000
U-6203 | Highway | STI (Prioritization) | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 45201000 | FY 2029: 7053000; FY 2030: 16754000; FY 2031: 12863000; FY 2032: 8531000
U-6204 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 1.08 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6204 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 1.08 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BG50200 | RIGHT-OF-WAY | 4101000 | FY 2025: 1406000; FY 2026: 1406000; FY 2027: 469000; FY 2028: 410000; FY 2029: 410000
U-6204 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 1.08 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BG50200 | UTILITIES | 1400000 | FY 2025: 1400000
U-6204 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 1.08 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BG50200 | CONSTRUCTION | 11401000 | FY 2028: 3523000; FY 2029: 5456000; FY 2030: 2422000
U-6205 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 2.79 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6205 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 2.79 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 1100000 | FY 2027: 11000; FY 2028: 561000; FY 2029: 308000; FY 2030: 110000; FY 2031: 110000
U-6205 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 2.79 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | UTILITIES | 1600000 | FY 2027: 800000; FY 2028: 800000
U-6205 | Highway | STI (Prioritization) | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 2.79 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 4800000 | FY 2029: 424000; FY 2030: 3302000; FY 2031: 1074000
U-6206 | Highway | STI (Prioritization) | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6206 | Highway | STI (Prioritization) | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 2500000 | FY 2027: 480000; FY 2028: 960000; FY 2029: 560000; FY 2030: 250000; FY 2031: 250000
U-6206 | Highway | STI (Prioritization) | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | UTILITIES | 900000 | FY 2027: 900000
U-6206 | Highway | STI (Prioritization) | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 5600000 | FY 2029: 2274000; FY 2030: 3326000
U-6207 | Highway | STI (Prioritization) | NC 581 (BILL LANE BOULEVARD / ARLINGTON BRIDGE ROA | NEUSE RIVER JUST SOUTH OF SR 1919 (WESTBROOK ROAD) TO NC 111. MODERNIZE ROADWAY. | 2.1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  |  |  | 10000
U-6207 | Highway | STI (Prioritization) | NC 581 (BILL LANE BOULEVARD / ARLINGTON BRIDGE ROA | NEUSE RIVER JUST SOUTH OF SR 1919 (WESTBROOK ROAD) TO NC 111. MODERNIZE ROADWAY. | 2.1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 1700000 | FY 2027: 136000; FY 2028: 816000; FY 2029: 408000; FY 2030: 170000; FY 2031: 170000
U-6207 | Highway | STI (Prioritization) | NC 581 (BILL LANE BOULEVARD / ARLINGTON BRIDGE ROA | NEUSE RIVER JUST SOUTH OF SR 1919 (WESTBROOK ROAD) TO NC 111. MODERNIZE ROADWAY. | 2.1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6207 | Highway | STI (Prioritization) | NC 581 (BILL LANE BOULEVARD / ARLINGTON BRIDGE ROA | NEUSE RIVER JUST SOUTH OF SR 1919 (WESTBROOK ROAD) TO NC 111. MODERNIZE ROADWAY. | 2.1 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | T | CONSTRUCTION | 5001000 | FY 2029: 2148000; FY 2030: 2853000
U-6208 | Highway | STI (Prioritization) | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.46 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  |  |  | 10000
U-6208 | Highway | STI (Prioritization) | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.46 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 15900000 | FY 2027: 1272000; FY 2028: 7632000; FY 2029: 3816000; FY 2030: 1590000; FY 2031: 1590000
U-6208 | Highway | STI (Prioritization) | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.46 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | UTILITIES | 6200000 | FY 2027: 3100000; FY 2028: 3100000
U-6208 | Highway | STI (Prioritization) | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.46 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 17000000 | FY 2029: 4504000; FY 2030: 7811000; FY 2031: 4685000
U-6209 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 3.12 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6209 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 3.12 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 32300000
U-6209 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 3.12 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 17300000
U-6209 | Highway | STI (Prioritization) | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 3.12 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 36400000
U-6210 | Highway | STI (Prioritization) | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  |  |  | 10000
U-6210 | Highway | STI (Prioritization) | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 15000000 | [10 empty] | 15000000
U-6210 | Highway | STI (Prioritization) | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 7900000 | [10 empty] | 7900000
U-6210 | Highway | STI (Prioritization) | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 1.89 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 22800000 | [10 empty] | 22800000
U-6211 | Highway | STI (Prioritization) | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1100000
U-6211 | Highway | STI (Prioritization) | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6211 | Highway | STI (Prioritization) | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2100000
U-6212 | Highway | STI (Prioritization) | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 200000
U-6212 | Highway | STI (Prioritization) | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
U-6212 | Highway | STI (Prioritization) | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
U-6213 | Highway | STI (Prioritization) | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 2.2 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  |  |  | 10000
U-6213 | Highway | STI (Prioritization) | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 2.2 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 16600000 | [10 empty] | 16600000
U-6213 | Highway | STI (Prioritization) | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 2.2 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | UTILITIES | 19750000 | [10 empty] | 19750000
U-6213 | Highway | STI (Prioritization) | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 2.2 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Not Funded |  | T | CONSTRUCTION | 22500000 | [10 empty] | 22500000
U-6214 | Highway | STI (Prioritization) | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3401000
U-6214 | Highway | STI (Prioritization) | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2400000
U-6214 | Highway | STI (Prioritization) | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5600000
U-6215 | Highway | STI (Prioritization) | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 5.6 | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Not Funded |  |  |  | 10000
U-6215 | Highway | STI (Prioritization) | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 5.6 | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 30100000 | [10 empty] | 30100000
U-6215 | Highway | STI (Prioritization) | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 5.6 | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Not Funded |  | T | UTILITIES | 2900000 | [10 empty] | 2900000
U-6215 | Highway | STI (Prioritization) | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 5.6 | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Not Funded |  | T | CONSTRUCTION | 68100000 | [10 empty] | 68100000
U-6216 | Highway | STI (Prioritization) | SR 1010 (CLEVELAND ROAD) | NORTH OF SR 2231 (SOUTHFORT DRIVE) TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 5.13 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 34300000 | FY 2027: 9147000; FY 2028: 12195000; FY 2029: 6098000; FY 2030: 3430000; FY 2031: 3430000
U-6216 | Highway | STI (Prioritization) | SR 1010 (CLEVELAND ROAD) | NORTH OF SR 2231 (SOUTHFORT DRIVE) TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 5.13 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | UTILITIES | 6654000 | FY 2027: 3327000; FY 2028: 3327000
U-6216 | Highway | STI (Prioritization) | SR 1010 (CLEVELAND ROAD) | NORTH OF SR 2231 (SOUTHFORT DRIVE) TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 5.13 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 43700000 | FY 2029: 8519000; FY 2030: 15956000; FY 2031: 11905000; FY 2032: 7320000
U-6217 | Highway | STI (Prioritization) | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 3.44 | WAKE | 5 | Capital Area MPO |  | Division 5 |  |  |  | 10000
U-6217 | Highway | STI (Prioritization) | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 3.44 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 13401000 | FY 2028: 346000; FY 2029: 4150000; FY 2030: 4150000; FY 2031: 2075000; FY 2032: 2680000
U-6217 | Highway | STI (Prioritization) | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 3.44 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | UTILITIES | 1142000 | FY 2028: 571000; FY 2029: 571000
U-6217 | Highway | STI (Prioritization) | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 3.44 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 27100000 | FY 2031: 7871000; FY 2032: 9801000; FY 2033: 6710000 | 2718000
U-6218 | Bike & Ped | Locally Selected | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6 |  | TADA | CONSTRUCTION | 21180000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000
U-6219 | Bike & Ped | Locally Selected | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | Division 5, 7, 8 |  | TADA | CONSTRUCTION | 9449000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000
U-6220 | Bike & Ped | Locally Selected | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TADA | CONSTRUCTION | 11164000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000
U-6221 | Bike & Ped | Locally Selected | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 12941000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000
U-6222 | Highway | Locally Selected | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 0.75 | WAKE | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | S | ENGINEERING | 30000
U-6222 | Highway | Locally Selected | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 0.75 | WAKE | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 120000
U-6222 | Highway | Locally Selected | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 0.75 | WAKE | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | S | CONSTRUCTION | 210000
U-6222 | Highway | Locally Selected | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 0.75 | WAKE | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 840000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | S | RIGHT-OF-WAY | 434000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | BGDA | RIGHT-OF-WAY | 1735000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | HF | CONSTRUCTION | 1000000 | FY 2024: 224000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | S | CONSTRUCTION | 1250000 | FY 2024: 281000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | BGDA | CONSTRUCTION | 7500000 | FY 2024: 1683000
U-6223 | Highway | Locally Selected | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | Division 4 |  | L | CONSTRUCTION | 1500000 | FY 2024: 337000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  |  |  | 28000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | RIGHT-OF-WAY | 56000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | RIGHT-OF-WAY | 19000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | CONSTRUCTION | 1560000 | FY 2024: 1560000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | CONSTRUCTION | 1021000 | FY 2025: 1021000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | CONSTRUCTION | 520000 | FY 2024: 520000
U-6225 | Highway | Locally Selected | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | CONSTRUCTION | 340000 | FY 2025: 340000
U-6227 | Highway | Locally Selected | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,191,847 IN STBG-ANY RESULTING FROM FUND SWAP | Division 5 |  | BGDA | RIGHT-OF-WAY | 2533000
U-6227 | Highway | Locally Selected | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,191,847 IN STBG-ANY RESULTING FROM FUND SWAP | Division 5 |  | L | RIGHT-OF-WAY | 3096000
U-6227 | Highway | Locally Selected | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,191,847 IN STBG-ANY RESULTING FROM FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 1841000 | FY 2025: 1841000
U-6227 | Highway | Locally Selected | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,191,847 IN STBG-ANY RESULTING FROM FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 1804000 | FY 2025: 1804000
U-6227 | Highway | Locally Selected | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. $3,191,847 IN STBG-ANY RESULTING FROM FUND SWAP | Division 5 |  | L | CONSTRUCTION | 4455000 | FY 2025: 4455000
U-6229 | Highway | Safety | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 2.53 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | UTILITIES | 200000
U-6229 | Highway | Safety | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 2.53 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 2367000
U-6229 | Highway | Safety | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 2.53 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 4133000
U-6230 | Highway | Economic Development | WALK OFF WAY | CONSTRUCT WALK OFF WAY EXTENSION FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 0.27 | BUNCOMBE | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE. | Division 13 |  | T | CONSTRUCTION | 1300000
U-6231 | Highway | Economic Development | NEW ROUTE | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | Division 9 |  | T | CONSTRUCTION | 1300000
U-6231 | Highway | Economic Development | NEW ROUTE | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | Division 9 |  | L | CONSTRUCTION | 2700000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | S | ENGINEERING | 4000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | ENGINEERING | 14000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | S | RIGHT-OF-WAY | 8000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | RIGHT-OF-WAY | 32000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | S | CONSTRUCTION | 51000 | FY 2024: 51000
U-6233 | Highway | Locally Selected | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | Division 3 |  | BGDA | CONSTRUCTION | 205000 | FY 2024: 205000
U-6235 | Highway | Locally Selected | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 390000
U-6235 | Highway | Locally Selected | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 97000
U-6235 | Highway | Locally Selected | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 824000 | FY 2025: 824000
U-6235 | Highway | Locally Selected | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 206000 | FY 2025: 206000
U-6237 | Highway | Economic Development | SR 2120 (LONG FERRY ROAD) | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | 0.6 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | Division 9 |  | T | UTILITIES | 50000
U-6237 | Highway | Economic Development | SR 2120 (LONG FERRY ROAD) | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | 0.6 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | Division 9 |  | T | CONSTRUCTION | 365000
U-6238 | Highway | Economic Development | TRIVIUM PARKWAY, NEW ROUTE | EXTEND TRIVIUM PARKWAY AND CONSTRUCT NEW ROADWAY IN TRIVIUM CORPORATE CENTER. | 0.2 | CATAWBA | 12 | Greater Hickory MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA. | Division 12 |  | T | CONSTRUCTION | 1316000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | DP | ENGINEERING | 420000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | L | ENGINEERING | 105000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | DP | RIGHT-OF-WAY | 1014000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | L | RIGHT-OF-WAY | 5135000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | DP | CONSTRUCTION | 12175000
U-6239 | Highway | Locally Selected | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | Exempt |  | L | CONSTRUCTION | 2881000
U-6240 | Highway | Locally Selected | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 1.07 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  |  |  | 2900000
U-6240 | Highway | Locally Selected | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 1.07 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 14800000 | FY 2024: 3010000
U-6240 | Highway | Locally Selected | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 1.07 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | L | CONSTRUCTION | 19277000 | FY 2024: 12587000
U-6241 | Highway | Locally Selected | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 12041000
U-6241 | Highway | Locally Selected | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 8411000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | RIGHT-OF-WAY | 1360000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | RIGHT-OF-WAY | 340000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | UTILITIES | 880000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | UTILITIES | 220000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | BGDA | CONSTRUCTION | 8918000 | FY 2025: 8918000
U-6242 | Highway | Locally Selected | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | L | CONSTRUCTION | 2230000 | FY 2025: 2230000
U-6243 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | 1.52 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 3600000
U-6243 | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | 1.52 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 14400000
U-6244 | Highway | Locally Selected | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | BGDA | RIGHT-OF-WAY | 83000
U-6244 | Highway | Locally Selected | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L | RIGHT-OF-WAY | 27000
U-6244 | Highway | Locally Selected | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | BGDA | CONSTRUCTION | 487000 | FY 2024: 487000
U-6244 | Highway | Locally Selected | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L | CONSTRUCTION | 162000 | FY 2024: 162000
U-6245 | Highway | Economic Development | SR 1146 (WEST TEN ROAD) | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | 1.68 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE. | Division 7 |  | T | ENGINEERING | 109000
U-6245 | Highway | Economic Development | SR 1146 (WEST TEN ROAD) | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | 1.68 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE. | Division 7 |  | T | CONSTRUCTION | 829000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | BGDA | ENGINEERING | 160000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | S(M) | ENGINEERING | 40000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | T(DA) | RIGHT-OF-WAY | 280000 | FY 2025: 280000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 70000 | FY 2025: 70000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | T(DA) | CONSTRUCTION | 1365000 | FY 2027: 639000; FY 2028: 726000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | L | CONSTRUCTION | 100000 | FY 2027: 100000
U-6246 | Highway | Locally Selected | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 615000 | FY 2027: 288000; FY 2028: 327000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | BGDA | ENGINEERING | 254000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | S(M) | ENGINEERING | 109000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | RIGHT-OF-WAY | 189000 | FY 2027: 189000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | RIGHT-OF-WAY | 81000 | FY 2028: 81000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 18000 | FY 2028: 18000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 253000 | FY 2030: 253000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 1516000 | FY 2029: 1516000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | CONSTRUCTION | 387000 | FY 2028: 387000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | CONSTRUCTION | 323000 | FY 2029: 323000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | CONSTRUCTION | 4000 | FY 2028: 4000
U-6247 | Highway | Locally Selected | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | UNION | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | HF(M) | CONSTRUCTION | 54000 | FY 2030: 54000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | ENGINEERING | 160000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | ENGINEERING | 40000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | RIGHT-OF-WAY | 380000 | FY 2025: 380000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | RIGHT-OF-WAY | 898000 | FY 2025: 898000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | RIGHT-OF-WAY | 225000 | FY 2025: 225000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | RIGHT-OF-WAY | 95000 | FY 2025: 95000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | T(DA) | CONSTRUCTION | 2835000 | FY 2027: 29000; FY 2028: 2074000; FY 2029: 732000
U-6248 | Highway | Locally Selected | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Exempt |  | L | CONSTRUCTION | 709000 | FY 2027: 428000; FY 2028: 281000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | BGDA | ENGINEERING | 448000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L | ENGINEERING | 112000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | T(DA) | RIGHT-OF-WAY | 400000 | FY 2024: 400000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L | RIGHT-OF-WAY | 100000 | FY 2024: 100000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | T(DA) | CONSTRUCTION | 3205000 | FY 2026: 3205000
U-6249 | Highway | Locally Selected | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23 | Exempt |  | L | CONSTRUCTION | 801000 | FY 2026: 801000
U-6251 | Highway | Appalachian Development Highway System | NEW ROUTE- ENKA HERITAGE ROAD | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 0.3 | BUNCOMBE | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS. | Exempt |  |  |  | 250000
U-6251 | Highway | Appalachian Development Highway System | NEW ROUTE- ENKA HERITAGE ROAD | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 0.3 | BUNCOMBE | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS. | Exempt |  | ADHSL | MITIGATION | 140000
U-6251A | Highway | Appalachian Development Highway System | NEW ROUTE - ENKA HERITAGE ROAD | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | 0.3 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 1850000
U-6251A | Highway | Appalachian Development Highway System | NEW ROUTE - ENKA HERITAGE ROAD | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | 0.3 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 1000000
U-6251B | Highway | Appalachian Development Highway System | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | RIGHT-OF-WAY | 900000
U-6251B | Highway | Appalachian Development Highway System | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 160000
U-6251B | Highway | Appalachian Development Highway System | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | S | CONSTRUCTION | 200000
U-6251B | Highway | Appalachian Development Highway System | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 35000
W-5201 | Highway | Safety | VARIOUS | DIVISION 1 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 695000
W-5202 | Highway | Safety | VARIOUS | DIVISION 2 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS | Region B |  |  |  | 8819000
W-5203 | Highway | Safety | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 21485000
W-5203DIV | Highway | Safety | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ONSLOW, BRUNSWICK, NEW HANOVER | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO |  | Division 3
W-5203REG | Highway | Safety | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B
W-5203SW | Highway | Safety | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | BRUNSWICK, ONSLOW, NEW HANOVER | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO |  | Statewide Mobility
W-5203U | Highway | Transition | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | UTILITIES | 61000
W-5203U | Highway | Transition | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 1863000 | FY 2024: 1844000
W-5203U | Highway | Transition | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | S(M) | CONSTRUCTION | 500000
W-5204 | Highway | Safety | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 7548000
W-5204DIV | Highway | Safety | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | JOHNSTON, WILSON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Division 4
W-5204E | Highway | Safety | SR 1524 (OLD DRUG STORE ROAD) | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | 0.5 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | HSIP | RIGHT-OF-WAY | 200000
W-5204E | Highway | Safety | SR 1524 (OLD DRUG STORE ROAD) | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | 0.5 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 4 |  | HSIP | CONSTRUCTION | 972000 | FY 2024: 822000; FY 2025: 150000
W-5204REG | Highway | Safety | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | JOHNSTON, WILSON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A
W-5205 | Highway | Safety | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION |  |  |  |  | 10184000
W-5205DIV | Highway | Safety | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - DIVISION NEEDS CATEGORY |  | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 5
W-5205REG | Highway | Safety | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - REGIONAL IMPACT CATEGORY |  | WAKE | 5 | Capital Area MPO |  | Region C
W-5206 | Highway | Safety | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 49662000
W-5206DIV | Highway | Safety | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6
W-5206REG | Highway | Safety | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ROBESON, HARNETT | 6 | Lumber River RPO, Mid-Carolina RPO |  | Region C
W-5206SW | Highway | Safety | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility
W-5207 | Highway | Safety | VARIOUS | DIVISION 7 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | COMPLETED |  |  |  |  | 5636000
W-5208 | Highway | Safety | VARIOUS | DIVISION 8 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION |  |  |  |  | 5463000
W-5208MA | Highway | Safety | US 15 / US 501 | NC 144 INTERSECTION. CONSTRUCT ROUNDABOUT | 0.5 | SCOTLAND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Region E
W-5209 | Highway | Safety | VARIOUS | DIVISION 9 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | COMPELTE |  |  |  |  | 4925000
W-5210 | Highway | Safety | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 12515000
W-5210DIV | Highway | Safety | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN DIVISION CATEGORY. |  | UNION, MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10
W-5210REG | Highway | Safety | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E
W-5210SW | Highway | Safety | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN STATEWIDE CATEGORY. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility
W-5211 | Highway | Safety | VARIOUS | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 292000
W-5211REG | Highway | Safety | VARIOUS | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. |  | YADKIN | 11 | Northwest Piedmont RPO |  | Region F
W-5212 | Highway | Safety | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. STATE MATCH TO BE FUNDED WITH SPOT SAFETY FUNDS. |  |  |  |  | 19025000
W-5212DIV | Highway | Safety | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 50000
W-5212DIV | Highway | Safety | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 2500000
W-5212J | Highway | Transition | SR 1303 (PERTH ROAD) | SR 1303 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | ENGINEERING | 178000
W-5212J | Highway | Transition | SR 1303 (PERTH ROAD) | SR 1303 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | S(M) | ENGINEERING | 178000
W-5212JA | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AT SR 1303 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | BGDA | RIGHT-OF-WAY | 13000
W-5212JA | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AT SR 1303 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | S(M) | RIGHT-OF-WAY | 12000
W-5212JA | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AT SR 1303 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 62000
W-5212JA | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AT SR 1303 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Division 12 |  | S(M) | CONSTRUCTION | 63000
W-5212JB | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | RIGHT-OF-WAY | 100000
W-5212JB | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | S(M) | RIGHT-OF-WAY | 25000
W-5212JB | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | CONSTRUCTION | 873000 | FY 2024: 863000
W-5212JB | Highway | Safety | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | S(M) | CONSTRUCTION | 218000 | FY 2024: 216000
W-5212N | Highway | Safety | NC 279 (DALLAS CHERRYVILLE HIGHWAY) | SOUTH OF (ST MARK'S CHURCH ROAD) TO NORTH OF NC 275 - CONSTRUCT SAFETY IMPROVEMENTS, INCLUDING PASSING ZONES | 8.02 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Region F |  | T | BUILD NC CON | 12750000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1700000
W-5212REG | Highway | Safety | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE REGIONAL CATEGORY. |  | GASTON, IREDELL, CATAWBA | 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO, Greater Hickory MPO |  | Region F
W-5213 | Highway | Safety | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 4768000
W-5213DIV | Highway | Safety | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | BUNCOMBE | 13 | French Broad River MPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 50000
W-5213DIV | Highway | Safety | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | BUNCOMBE | 13 | French Broad River MPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 700000
W-5213G | Highway | Safety | SR 2002 (RICEVILLE ROAD) | US 70 TO SR 2419 (BULL CREEK ROAD) NEAR HAW CREEK. | 3.64 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 909000 | FY 2024: 9000; FY 2025: 900000
W-5214 | Highway | Safety | VARIOUS | DIVISION 14 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, Land-of-Sky RPO, French Broad River MPO, Foothills RPO | IN PROGRESS - DIVISION PURCHASE ORDER CONTRACT (DPOC) |  |  |  |  | 6673000
W-5303 | Highway | Safety | SR 1004 (STOKES FERRY ROAD) | SR 2380 (ODDIE ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION - LET WITH B-4257 |  |  |  |  | 230000
W-5503 | Highway | Transition | NC 268 | NC 268 EAST OF NORTH WILKESBORO. WIDEN MULTIPLE SECTIONS, IMPROVE SHOULDERS, AND INSTALL GUARDRAIL, RUMBLE STRIPS, AND PAVEMENT MARKINGS. |  | WILKES | 11 | High Country RPO | PART COMPLETE | Region F |  |  |  | 3850000
W-5503A | Highway | Safety | NC 268 | SR 1966 (AIRPORT ROAD) TO SR 2026 (AUSTIN TRAPHILL ROAD). INSTALL GUARDRAIL AND PAVEMENT MARKINGS. | 13.75 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | HSIP | CONSTRUCTION | 1000000
W-5508 | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. TRAFFIC ENGINEERING BRANCH TO PARTICIPATE IN A THREE YEAR DATA COLLECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT | [5 empty] | 1500000
W-5517 | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT | [5 empty] | 22101000
W-5517DIV | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99
W-5517REG | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW
W-5517SW | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility
W-5519 | Highway | Safety | I-95 BUSINESS/US 301 | NC 87 SOUTH TO NC 59. SAFETY IMPROVEMENTS. | 7.29 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Region C |  |  |  | 10123000
W-5600 | Highway | STI (Prioritization) | US 70 | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | 5.63 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  |  |  | 9292000
W-5600 | Highway | STI (Prioritization) | US 70 | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | 5.63 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHP | CONSTRUCTION | 87693000 | FY 2024: 11000000
W-5601 | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 130411000
W-5601DIV | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | RIGHT-OF-WAY | 68000
W-5601DIV | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | CONSTRUCTION | 3670000
W-5601R | Highway | Safety | NC 274 | SR 1443 (DAMERON ROAD) TO SR 1405 (RAMSEUR ROAD). INSTALL RUMBLE STRIPS. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 90000 | FY 2024: 89000
W-5601REG | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | RIGHT-OF-WAY | 68000
W-5601REG | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | CONSTRUCTION | 6170000 | FY 2024: 3650000
W-5601SW | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 90000
W-5601SW | Highway | Safety | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 3360000
W-5601U | Highway | Safety | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 472000
W-5601U | Highway | Safety | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HF | CONSTRUCTION | 815000 | FY 2025: 815000
W-5601U | Highway | Safety | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 1150000 | FY 2025: 1150000
W-5602 | Highway | Safety | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3.74 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  |  |  | 13657000
W-5602 | Highway | Safety | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3.74 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  | T | BUILD NC CON | 7080000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 944000
W-5602 | Highway | Safety | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3.74 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Region B |  | T | CONSTRUCTION | 5103000
W-5700 | Highway | Safety | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 3500000
W-5700DIV | Highway | Safety | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99
W-5700REG | Highway | Safety | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW
W-5700SW | Highway | Safety | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility
W-5701 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | IN PROGRESS. |  |  |  |  | 970000
W-5701C | Highway | Safety | SR 1333 (WEST MAIN STREET EXTENSION) | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). IMPROVE HORIZONTAL ALIGNMENT WITH VARIOUS CURVE IMPROVEMENTS. | 0.8 | PASQUOTANK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | HSIP | RIGHT-OF-WAY | 170000 | FY 2024: 170000
W-5701C | Highway | Safety | SR 1333 (WEST MAIN STREET EXTENSION) | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). IMPROVE HORIZONTAL ALIGNMENT WITH VARIOUS CURVE IMPROVEMENTS. | 0.8 | PASQUOTANK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | HSIP | CONSTRUCTION | 1700000 | FY 2025: 17000; FY 2026: 1683000
W-5701DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | HSIP | RIGHT-OF-WAY | 30000
W-5701DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | HSIP | CONSTRUCTION | 375000
W-5701REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 30000
W-5701REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 375000
W-5701SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5701SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5702 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | IN PROGRESS |  |  |  |  | 17780000
W-5702DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | HSIP | RIGHT-OF-WAY | 30000
W-5702DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 375000
W-5702REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 131000
W-5702REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 3125000
W-5702SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5702SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5703 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | IN PROGRESS |  |  |  |  | 2536000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | RIGHT-OF-WAY | 363000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | BGDA | RIGHT-OF-WAY | 190000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | L | RIGHT-OF-WAY | 47000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | UTILITIES | 127000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | CONSTRUCTION | 667000 | FY 2027: 667000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | CONSTRUCTION | 35000 | FY 2025: 35000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | HSIP | CONSTRUCTION | 2796000 | FY 2026: 2796000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | BGDA | CONSTRUCTION | 272000 | FY 2025: 272000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | T | CONSTRUCTION | 84000 | FY 2027: 84000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | T | CONSTRUCTION | 356000 | FY 2025: 4000; FY 2026: 352000
W-5703C | Highway | Safety | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | Region B |  | L(M) | CONSTRUCTION | 68000 | FY 2025: 68000
W-5703DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 30000
W-5703DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Division 3 |  | HSIP | CONSTRUCTION | 375000
W-5703REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Region B |  | HSIP | RIGHT-OF-WAY | 30000
W-5703REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Region B |  | HSIP | CONSTRUCTION | 375000
W-5703SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5703SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5704 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | IN PROGRESS |  |  |  |  | 20827000
W-5704DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | RIGHT-OF-WAY | 144000
W-5704DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 360000
W-5704E | Highway | Safety | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 1.41 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | HSIP | RIGHT-OF-WAY | 1200000
W-5704E | Highway | Safety | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 1.41 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | RIGHT-OF-WAY | 600000
W-5704E | Highway | Safety | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 1.41 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 4200000 | FY 2025: 42000; FY 2026: 2460000; FY 2027: 1698000
W-5704E | Highway | Safety | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 1.41 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 8400000 | FY 2025: 84000; FY 2026: 4920000; FY 2027: 3396000
W-5704K | Highway | Safety | SR 1927 (GENOA ROAD) | SR 1927 (GENOA ROAD) AT CRESCENT DRIVE. INTERSECTION IMPROVEMENTS. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2024: 40000
W-5704K | Highway | Safety | SR 1927 (GENOA ROAD) | SR 1927 (GENOA ROAD) AT CRESCENT DRIVE. INTERSECTION IMPROVEMENTS. | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 857000 | FY 2024: 857000
W-5704REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 30000
W-5704REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 455000
W-5704SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5704SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 480000
W-5705 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS; |  |  |  |  | 6001000
W-5705AI | Highway | Safety | US 501 BUSINESS (ROXBORO STREET) | US 501 BUSINESS (ROXBORO STREET) AT SR 1443 (HORTON ROAD) AND SR 1641 (DENFIELD STREET). CONSTRUCT LEFT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 1320000 | FY 2025: 754000; FY 2026: 566000
W-5705DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 104000
W-5705DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 540000
W-5705G | Highway | Safety | SR 1001 (WARRENTON ROAD) | SR 1001 (WARRENTON ROAD) AT SR 1507 (BROOKSTON ROAD). SAFETY IMPROVEMENTS. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 503000 | FY 2025: 503000
W-5705REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 104000
W-5705REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 540000
W-5705SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 137000
W-5705SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 720000
W-5706 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | IN PROGRESS. "S" FUNDING REPRESENTS HIGH IMPACT / LOW COST (HILC) FUNDS. |  |  |  |  | 14907000
W-5706DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | HSIP | RIGHT-OF-WAY | 30000
W-5706DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 375000
W-5706L | Highway | Safety | NC 27 | CONSTRUCT ROUNDABOUT AT SR 2084 (LESLIE CAMPBELL AVENUE) INTERSECTION. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HF | UTILITIES | 30000 | FY 2024: 30000
W-5706L | Highway | Safety | NC 27 | CONSTRUCT ROUNDABOUT AT SR 2084 (LESLIE CAMPBELL AVENUE) INTERSECTION. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | UTILITIES | 248000 | FY 2024: 248000
W-5706L | Highway | Safety | NC 27 | CONSTRUCT ROUNDABOUT AT SR 2084 (LESLIE CAMPBELL AVENUE) INTERSECTION. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | CONSTRUCTION | 3150000 | FY 2024: 1703000; FY 2025: 1447000
W-5706N | Highway | Safety | NC 710 | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HF | CONSTRUCTION | 500000 | FY 2024: 500000
W-5706N | Highway | Safety | NC 710 | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | CRPLT5 | CONSTRUCTION | 2880000 | FY 2024: 2880000
W-5706N | Highway | Safety | NC 710 | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T(M) | CONSTRUCTION | 720000 | FY 2024: 720000
W-5706N | Highway | Safety | NC 710 | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | L | CONSTRUCTION | 121000 | FY 2024: 121000
W-5706REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 135000
W-5706REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 519000
W-5706SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 90000
W-5706SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 500000
W-5706U | Highway | Safety | SR 1404 (HAY STREET / MORGANTON ROAD) | AT THE SR 3578 (FORT BRAGG ROAD), OAKRIDGE AVENUE, AND HIGHLAND AVENUE INTERSECTION IN FAYETTEVILLE. UPGRADE TRAFFIC SIGNALS AND IMPROVE PEDESTRIAN CROSSINGS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 100000 | FY 2025: 100000
W-5707 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | IN PROGRESS |  |  |  |  | 4057000
W-5707DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 90000
W-5707DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | HSIP | CONSTRUCTION | 555000
W-5707REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFOR D, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 90000
W-5707REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFOR D, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | HSIP | CONSTRUCTION | 555000
W-5707SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5707SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 740000
W-5708 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS |  |  |  |  | 8324000
W-5708DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | HSIP | RIGHT-OF-WAY | 90000
W-5708DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | HSIP | CONSTRUCTION | 540000
W-5708L | Highway | Safety | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) FROM BEASLEY STREET TO BALFOUR AVENUE IN ASHEBORO. CONSTRUCT TWO-WAY LEFT TURN LANE. | 0.37 | RANDOLPH | 8 | Piedmont Triad RPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 150000 | FY 2025: 150000
W-5708L | Highway | Safety | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) FROM BEASLEY STREET TO BALFOUR AVENUE IN ASHEBORO. CONSTRUCT TWO-WAY LEFT TURN LANE. | 0.37 | RANDOLPH | 8 | Piedmont Triad RPO |  | Region E |  | HSIP | CONSTRUCTION | 320000 | FY 2027: 3000; FY 2028: 317000
W-5708REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 90000
W-5708REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region E |  | HSIP | CONSTRUCTION | 540000
W-5708SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5708SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 720000
W-5709 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; $1.3M NHP FUNDING APPLIED TO W-5709E |  |  |  |  | 6306000
W-5709DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | RIGHT-OF-WAY | 90000
W-5709DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 555000
W-5709E | Highway | Safety | NC 153 (RICE STREET) | NC 153 (RICE STREET) AT SR 1197 (CANNON FARM ROAD / MT MORIAH CHURCH ROAD) IN CHINA GROVE. CONSTRUCT ROUNDABOUT. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | BGANY | CONSTRUCTION | 2500000 | FY 2024: 25000; FY 2025: 2475000
W-5709REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 90000
W-5709REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 555000
W-5709SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 120000
W-5709SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 740000
W-5710 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | STATE MATCH FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. |  |  |  |  | 15485000
W-5710AD | Highway | Safety | SR 1005 (LANDSFORD ROAD) | SR 1937 (OLD PAGELAND MARSHVILLE ROAD). INSTALL AN ALL WAY STOP. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 30000 | FY 2024: 30000
W-5710AH | Highway | Safety | NC 200 (LANCASTER HIGHWAY) | SR 1137 (POTTER ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 2623000 | FY 2024: 1089000; FY 2025: 1534000
W-5710AH | Highway | Safety | NC 200 (LANCASTER HIGHWAY) | SR 1137 (POTTER ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | HF(M) | CONSTRUCTION | 291000 | FY 2024: 121000; FY 2025: 170000
W-5710AI | Highway | Safety | NC 218 | SR 1606 (SIKES MILLS ROAD) INTERSECTION NEAR FAIRVIEW. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 1217000 | FY 2024: 1217000
W-5710AN | Highway | Safety | SR 1009 (OLD CHARLOTTE HIGHWAY) | WILLIAMS ROAD IN MONROE. CONSTRUCT SAFETY IMPROVEMENTS. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 952000 | FY 2024: 952000
W-5710AO | Highway | Safety | SR 1002 (OLD SALISBURY CONCORD ROAD) | SR 2400 (IRISH POTATO ROAD) NEAR KANNAPOLIS. CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 1296000 | FY 2024: 1296000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | RIGHT-OF-WAY | 320000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | CONSTRUCTION | 180000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | CONSTRUCTION | 1485000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | CONSTRUCTION | 180000
W-5710DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Division 10 |  | HSIP | CONSTRUCTION | 180000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 450000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 180000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 180000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 180000
W-5710REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 180000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5710SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | ENGINEERING | 336000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | HSIP | ENGINEERING | 255000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | ENGINEERING | 67000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | T(M) | ENGINEERING | 28000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 84000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | ENGINEERING | 18000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 841000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 960000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 240000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 37000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 210000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 400000 | FY 2026: 400000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | HSIP | CONSTRUCTION | 1355000 | FY 2026: 1355000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 2455000 | FY 2026: 2455000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | T(M) | CONSTRUCTION | 151000 | FY 2026: 151000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 714000 | FY 2026: 714000
W-5710X | Highway | Safety | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 1426000 | FY 2026: 1426000
W-5710Y | Highway | Safety | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 0.5 | UNION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | HSIP | CONSTRUCTION | 850000
W-5710Y | Highway | Safety | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 0.5 | UNION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | CONSTRUCTION | 1385000
W-5710Y | Highway | Safety | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 0.5 | UNION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | S(M) | CONSTRUCTION | 346000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGDA | ENGINEERING | 156000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | S(M) | ENGINEERING | 39000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGDA | RIGHT-OF-WAY | 28000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | S(M) | RIGHT-OF-WAY | 7000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | HSIP | CONSTRUCTION | 671000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | BGANY | CONSTRUCTION | 1486000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | L | CONSTRUCTION | 200000
W-5710Z | Highway | Safety | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | Region E |  | S(M) | CONSTRUCTION | 214000
W-5711 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | [5 empty] | 1178000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Division 11 |  | HSIP | CONSTRUCTION | 180000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Region F |  | HSIP | CONSTRUCTION | 180000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5711SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5712 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS |  |  |  |  | 5273000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 180000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 180000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 180000
W-5712DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Division 12 |  | HSIP | CONSTRUCTION | 180000
W-5712R | Highway | Safety | SR 1003 (BUFFALO SHOALS ROAD) | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | RIGHT-OF-WAY | 42000 | FY 2024: 42000
W-5712R | Highway | Safety | SR 1003 (BUFFALO SHOALS ROAD) | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | UTILITIES | 5000 | FY 2024: 5000
W-5712R | Highway | Safety | SR 1003 (BUFFALO SHOALS ROAD) | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | HSIP | CONSTRUCTION | 610000 | FY 2025: 610000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Region F |  | HSIP | CONSTRUCTION | 180000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5712SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5712U | Highway | Safety | NC 150 | MILEPOST 19.3 TO GASTON COUNTY LINE AND FROM THE CLEVELAND COUNTY LINE TO MILEPOST 1.2. CONSTRUCT SAFETY IMPROVEMENTS. | 5.88 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 625000 | FY 2025: 625000
W-5713 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | COMPLETE |  |  |  |  | 6567000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Division 13 |  | HSIP | CONSTRUCTION | 180000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5713SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5714 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS |  |  |  |  | 1499000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Division 14 |  | HSIP | CONSTRUCTION | 180000
W-5714E | Highway | Safety | US 64 | SR 1119 (SAPPHIRE POSTOFFICE ROAD) AT CHRYSLER CURVE NEAR SAPPHIRE. CONSTRUCT SAFETY IMPROVEMENTS. | 0.68 | JACKSON | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 975000 | FY 2024: 10000; FY 2025: 965000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Region G |  | HSIP | CONSTRUCTION | 180000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5714SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | Statewide Mobility |  | HSIP | CONSTRUCTION | 240000
W-5715 | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT
W-5715DIV | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | ENGINEERING | 9180000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715REG | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | ENGINEERING | 9180000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715SW | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | ENGINEERING | 12240000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
W-5716 | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT
W-5716DIV | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | ENGINEERING | 11250000 | FY 2024: 4650000
W-5716REG | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | ENGINEERING | 11250000 | FY 2024: 4650000
W-5716SW | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | ENGINEERING | 15000000 | FY 2024: 6200000
W-5717 | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT
W-5717DIV | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717REG | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717SW | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | ENGINEERING | 13600000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
W-5801 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5801DIV | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1
W-5801REG | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A
W-5801SW | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility
W-5802 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO
W-5802A | Highway | Safety | SR 1493 | SR 1493 (LIVE OAK STREET) AT CAMPEN ROAD. REVISE TRAFFIC SIGNAL, INSTALL PEDESTRIAN CROSSING WITH SIGNAL HEADS, AND UPGRADE SIDEWALK. | 0.5 | CARTERET | 2 | Down East RPO | COMPLETED. | Division 2 |  | HSIP | CONSTRUCTION | 38000
W-5802B | Highway | Safety | NC 58 | NC 58 (E. FORT MACON ROAD) AT BROOKS STREET. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 0.5 | CARTERET | 2 | Down East RPO | COMPLETED. | Region B |  | HSIP | CONSTRUCTION | 30000
W-5802C | Highway | Safety | NC 58 | NC 58 (E. FORT MACON ROAD) AT E. BOGUE SOUND DRIVE. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 0.5 | CARTERET | 2 | Down East RPO | COMPLETED. | Region B |  | HSIP | CONSTRUCTION | 30000
W-5802E | Highway | Safety | US 70, NC 55 | US 70 BETWEEN NUNN STREET AND SR 1605 (FRIENDLY ROAD) IN MOREHEAD CITY, AND NC 55 BETWEEN US 17 IN BRIDGETON AND SR 1210 (1ST STREET) IN BAYBORO. INSTALL 6 INCH LONG LIFE PAVEMENT MARKINGS. | 28.28 | PAMLICO, CARTERET, CRAVEN | 2 | Down East RPO | COMPLETED. | Statewide Mobility |  | HSIP | CONSTRUCTION | 865000
W-5803 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study
W-5803A | Highway | Safety | US 74 | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 42000
W-5803B | Highway | Safety | US 17 | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | 34.89 | ONSLOW, PENDER | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 476000
W-5803C | Highway | Safety | US 17 BUSINESS | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 85000
W-5803D | Highway | Safety | NC 24 | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED. | Statewide Mobility |  | HSIP | CONSTRUCTION | 17000
W-5803E | Highway | Safety | NC 53 | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED. | Region B |  | HSIP | CONSTRUCTION | 57000
W-5804 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO
W-5804A | Highway | Safety | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 1 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 100000
W-5804A | Highway | Safety | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 1 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2584000
W-5804B | Highway | Safety | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 0.75 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 45000
W-5804B | Highway | Safety | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 0.75 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 892000 | FY 2024: 885000
W-5805 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5 |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
W-5805A | Highway | Safety | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 235000 | FY 2025: 235000
W-5805A | Highway | Safety | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 725000 | FY 2026: 725000
W-5805B | Highway | Safety | NC 98 BUSINESS | US 1, CLOVERLEAF DRIVE, AND RETAIL DRIVE / HAMPTON WAY IN WAKE FOREST. REVISE TRAFFIC SIGNALS. | 0.5 | WAKE | 5 | Capital Area MPO | PROJECT DELETED; WORK TO BE ACCOMPLISHED UNDER U-6023. | Region C
W-5805C | Highway | Safety | SR 1820 (LEAD MINE ROAD) | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 292000
W-5805D | Highway | Safety | NC 42 | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 184000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD). CONSTRUCT ROUNDABOUT. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | RIGHT-OF-WAY | 140000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD). CONSTRUCT ROUNDABOUT. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | UTILITIES | 125000 | FY 2025: 125000
W-5805E | Highway | Safety | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD). CONSTRUCT ROUNDABOUT. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | HSIP | CONSTRUCTION | 1540000 | FY 2025: 15000; FY 2026: 1525000
W-5805F | Highway | Safety | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS |  | WAKE, FRANKLIN, WARREN | 5 | Capital Area MPO, Kerr-Tar RPO | COMPLETE | Division 5 |  | HSIP | CONSTRUCTION | 2553000
W-5805G | Highway | Safety | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | CRPLT5 | RIGHT-OF-WAY | 80000 | FY 2024: 80000
W-5805G | Highway | Safety | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2024: 20000
W-5805G | Highway | Safety | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 955000 | FY 2025: 726000; FY 2026: 229000
W-5805H | Highway | Safety | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | 1 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 75000
W-5806 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO
W-5806A | Highway | Safety | NC 11 | SR 1740 (OLD LAKE ROAD) INTERSECTION SOUTH OF SANDYFIELD. IMPROVE INTERSECTION INCLUDING MILLING AND GRADING. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 50000 | FY 2025: 50000
W-5806B | Highway | Safety | SR 1117, SR 3242, SR 1615 | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | 11.01 | HARNETT | 6 | Fayetteville Area MPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 400000
W-5806C | Highway | Safety | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 75000
W-5806C | Highway | Safety | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 3205000 | FY 2024: 2895000; FY 2025: 278000
W-5806D | Highway | Safety | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | RIGHT-OF-WAY | 100000
W-5806D | Highway | Safety | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 606000 | FY 2024: 20000
W-5806E | Highway | Safety | NC 41 (MARTIN LUTHER KING JR DRIVE) | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | 0.5 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 315000
W-5807 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO
W-5807A | Highway | Safety | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | HSIP | RIGHT-OF-WAY | 150000
W-5807A | Highway | Safety | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | HSIP | CONSTRUCTION | 315000 | FY 2024: 315000
W-5807A | Highway | Safety | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | VRU | CONSTRUCTION | 135000 | FY 2024: 135000
W-5807B | Highway | Safety | SR 1301 (BOONE STATION DRIVE) | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 75000
W-5808 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO
W-5808A | Highway | Safety | US 74 / FUTURE I-74 WESTBOUND | EXITS 183 AND 184 IN LAURINBURG. UPGRADE SIGNING AND PAVEMENT MARKINGS. |  | SCOTLAND | 8 | Lumber River RPO | PROJECT DELETED AT REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. PROJECT WILL UTILZE NON-STIP FUNDS. | Statewide Mobility
W-5808B | Highway | Safety | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 0.5 | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 100000 | FY 2024: 100000
W-5808B | Highway | Safety | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 0.5 | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | HSIP | CONSTRUCTION | 736000 | FY 2025: 736000
W-5808C | Highway | Safety | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 0.5 | MOORE | 8 | Central Pines RPO | UNDER CONSTRUCTION. | Division 8 |  | HSIP | RIGHT-OF-WAY | 2000
W-5808C | Highway | Safety | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 0.5 | MOORE | 8 | Central Pines RPO | UNDER CONSTRUCTION. | Division 8 |  | HSIP | CONSTRUCTION | 15000
W-5809 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO
W-5809A | Highway | Safety | NC 109 | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | 15.99 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 1100000
W-5810 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5811 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5812 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
W-5813 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO
W-5813A | Highway | Safety | US 25 | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 64000
W-5813B | Highway | Safety | VARIOUS | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | RUTHERFORD, BURKE, MITCHELL, YANCEY | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 1600000
W-5813C | Highway | Safety | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | RIGHT-OF-WAY | 2000
W-5813C | Highway | Safety | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 155000
W-5813D | Highway | Safety | US 25; US 25 ALT (LODGE STREET) | ALL SOULS CRESCENT INTERSECTION; NC 81 (HENDERSONVILLE ROAD) INTERSECTION. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 96000 | FY 2024: 1000; FY 2025: 95000
W-5813E | Highway | Safety | US 19-23-74 ALT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 145000
W-5813F | Highway | Safety | US 19-23-74 ALT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 105000 | FY 2024: 30000
W-5813G | Highway | Safety | US 70; US 74 ALT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 1 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 336000 | FY 2024: 30000
W-5813H | Highway | Safety | NC 197 | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | 3.74 | YANCEY | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 474000
W-5813I | Highway | Safety | SR 2806 | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | 6.53 | BUNCOMBE | 13 | Land-of-Sky RPO | COMPLETE | Division 13 |  | HSIP | CONSTRUCTION | 460000
W-5813J | Highway | Safety | US 221 | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFOD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | 18.99 | McDOWELL, RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 501000
W-5814 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO
W-5814A | Highway | Safety | US 276 | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | 0.5 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 380000
W-5814B | Highway | Safety | US 74 WB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 12.65 | POLK | 14 | Foothills RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 199000
W-5814C | Highway | Safety | US 74 EB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 12.65 | POLK | 14 | Foothills RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 179000
W-9999 | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT
W-9999DIV | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | CONSTRUCTION | 45163000
W-9999REG | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | CONSTRUCTION | 55935000
W-9999SW | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 74580000
X-0002 | Highway | Pre-STI (Historic) | I-295 (FAYETTEVILLE OUTER LOOP) | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO I-95. FREEWAY ON NEW LOCATION WITH STRUCTURE OVER THE CAPE FEAR RIVER. | 14.3 | CUMBERLAND | 6 | Fayetteville Area MPO | [5 empty] | 320483000
X-0002B | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). - GRADING AND STRUCTURES | 2.7 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002BB | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). PAVING |  | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002BC | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | NC 210 (MURCHISON ROAD) TO 1.1 MILES EAST OF NC 210. GRADING AND STRUCTURES |  | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002CA | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | 1.1 MILES EAST OF NC 210 (MURCHISON ROAD) TO EAST OF SR 1600 (MCARTHUR ROAD). GRADING AND STRUCTURES | 2.6 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002CB | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1600 (MCARTHUR ROAD) TO US 401. - GRADING AND STRUCTURES |  | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002CC | Highway | Transition | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1007 (ALL AMERICAN FREEWAY) TO EAST OF US 401 (RAMSEY STREET). PAVING | 7.37 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
X-0002DA | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | WEST OF US 401 TO EAST OF SR 1714 (RIVER ROAD). | 2.928 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002DB | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1714 (RIVER ROAD) TO WEST OF US 301. | 3.474 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002DC | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | CONNECTOR FROM US 301 TO US 13. | 0.843 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002DD | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | WEST OF US 301 TO EAST OF I-95. | 0.97 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002DF | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | SR 1714 (RIVER ROAD) TO WEST OF US 301. | 3.754 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002E | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | EAST OF NORFOLK SOUTHERN RAILWAY TO SR 1714 (RIVER ROAD). | 1.578 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED.
X-0002F | Highway | Pre-STI (Historic) | I-295 FAYETTEVILLE OUTER LOOP | ITS FOR FAYETTEVILLE OUTER LOOP. | 14.07 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
Y-4805F | Rail | Rail-Highway Grade Crossing Closure | FAYETTEVILLE STREET (SR 2513) | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | RR | CONSTRUCTION | 1600000
Y-4807B | Rail | Rail-Highway Grade Crossing Closure | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE (722957L) AND LOWDERMILK STREET / SYKES AVENUE (722958T) REALIGNMENT IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  |  |  | 2430000
Y-4807B | Rail | Rail-Highway Grade Crossing Closure | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE (722957L) AND LOWDERMILK STREET / SYKES AVENUE (722958T) REALIGNMENT IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | RR | CONSTRUCTION | 5000000 | FY 2024: 2908000; FY 2025: 2092000
Y-4810K | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  |  |  | 2800000
Y-4810K | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  | T | CONSTRUCTION | 18720000 | FY 2024: 9675000; FY 2025: 4413000
Y-4810K | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | Statewide Mobility |  | O | CONSTRUCTION | 450000 | FY 2024: 233000; FY 2025: 106000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  |  |  | 1944000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | RR | RIGHT-OF-WAY | 1500000
Y-5500 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | RR | CONSTRUCTION | 7560000
Y-5500EC | Rail | Rail-Highway Grade Crossing Closure | SR 1136 (TALLY HO ROAD) | NORFOLK SOUTHERN CROSSING 734 895A IN STEM. CLOSE RAILWAY-HIGHWAY CROSSING. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Division 5 |  | RR | CONSTRUCTION | 150000 | FY 2025: 150000
Y-5500ED | Rail | Rail-Highway Grade Crossing Closure | CHURCH STREET | NORFOLK SOUTHERN CROSSING 734 896G IN STEM. CLOSE RAILWAY-HIGHWAY CROSSING. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Division 5 |  | RR | CONSTRUCTION | 300000 | FY 2025: 300000
Y-5500IA | Rail | Rail-Highway Grade Crossing Closure | HENDERSON GROVE CHURCH ROAD | CLOSE RAILROAD CROSSING #724 362M AND CONSTRUCT NEW LOCATION TO SR 2528 (JULIAN ROAD) IN SALISBURY. | 0.65 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | RR | CONSTRUCTION | 4900000 | FY 2024: 4900000
Z-5400 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  |  |  | 28841000
Z-5700 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  |  |  | 16738000
Z-5800 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | RR | RIGHT-OF-WAY | 500000
Z-5800 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | RR | CONSTRUCTION | 3280000
Z-9999 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | RR | RIGHT-OF-WAY | 500000
Z-9999 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | RR | CONSTRUCTION | 3000000

## Fund Sources
Fund Source | Fund Type | Description | Subject to STI
3037 | Federal | Job Assistance and Reverse Commute | No
5303 | Federal | Metropolitan Planning (FMPL) | No
5305 | Federal | FTA Discretionary Grant Funds | No
5307 | Federal | Urbanized Area Formula Program (FUZ) | No
5309 | Federal | Capital Program - Bus Earmark (FBUS) | No
5310 | Federal | Elderly and Persons with Disability (FEPD) | No
5311 | Federal | Non Urbanised Area Formula Program (FNU) | No
5312 | Federal | FUZ 5312 | No
5316 | Federal | Job Assistance And Reverse Commute (JARC) | No
5317 | Federal | New Freedom Program | No
5337 | Federal | Urbanized Area Formula Program (FUZ) | No
5339 | Federal | Capital Program - Bus Earmark (FBUS) | No
5339(b) | Federal | Capital Program - Bus Earmark (FBUS) - Discretionary Grant | No
20005(b) | Federal | Pilot Program for Transit-Oriented Development Planning | No
ADHS | Federal | Appalachian Development Highway System | No
ADHSL | Federal | Appalachian Development Highway System (Local Access Roads) | No
ADTAP | Federal | Appalachian Development portion of 5311 - Non Urbanised Area Formula Program (FNU) | No
ARP | Federal | American Rescue Plan | No
BA | State | Bonus Allocation | No
BFP | Federal | Federal Bridge Improvement Program - Formula | Yes
BFPOFF | Federal | Federal Bridge Improvement Program - Formula (Off System) | Yes
BG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
BG50200 | Federal | Surface Transportation Block Grant Program (50K - 200K) | Yes
BG5200 | Federal | Surface Transportation Block Grant Program (5K - 200K) | Yes
BG5T50 | Federal | Surface Transportation Block Grant Program (5K - 50K) | Yes
BGANY | Federal | Surface Transportation Block Grant Program (Any Area) | Yes
BGBA | Federal | Surface Transportation Block Grant Program (Bonus Allocation) | No
BGDA | Federal | Surface Transportation Block Grant Program (Direct Attributable) | Yes
BGDACV | Federal | COVID Relief Funds | Yes
BGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
BGLT5 | Federal | Surface Transportation Block Grant Program (Less than 5K) | Yes
BGOFF | Federal | Surface Transportation Block Grant Program (Off System) | Yes
BOND R | Other | Revenue Bond | No
BONDRT | Other | Revenue Bond (Loan Advance from Highway Trust Fund) | No
BRGI | Federal | Bridge Inspection | Yes
CARES | Federal | CARES Act Funding | No
CMAQ | Federal | Congestion Mitigation | No
CPF | Federal | Community Project Funding/Congressionally Directed Spending (Grants) | No
CRP550 | Federal | Carbon Reduction Program - (5K - 50K) | No
CRPANY | Federal | Carbon Reduction Program - Any Area | No
CRPDA | Federal | Carbon Reduction Program - Direct Attributable (All MPOs) | No
CRPLT5 | Federal | Carbon Reduction Program - (Less than 5K) | No
DOD | Federal | Department of Defense | No
DP | Federal | Discretionary or Demonstration | No
ER | Federal | Emergency Relief | No
ERFO | Federal | Emergency Relief for Federally Owned Roads | No
FBP | Federal | Ferry Boat Program | Yes
FED | Federal | Unidentified Federal Funding | No
FEDT | Federal | Undesignated Federal Transit Funding | No
FF | Federal | FEDERAL FERRY | Yes
FLAP | Federal | Federal Lands Access Program (Park Roads) | No
FLPF | Federal | Federal Lands Program (Forest Roads) | No
FLTP | Federal | Federal Lands Transportation Program | No
FMOD | Federal | Fixed Guideway Modifications | Yes
FSPR | Federal | State Planning and Research | No
FTTP | Federal | Federal Tribal Transportation Program | No
FUZ | Federal | Capital Program - Bus Earmark (5309) | No
HF | State | Highway Fund | No
HFB | State | Highway Fund Bridge Replacement Program | Yes
HIB | Federal | Highway Infrastructure Bridge Replacement | Yes
HP | Federal | High Priority | Yes
HRRR | Federal | High Risk Rural Roads | Yes
HSIP | Federal | HIGHWAY SAFETY IMPROVEMENT PROGRAM | Yes
L | Other | Local | No
NEVI | Federal | National Electric Vehicle Infrasructure Program Funds | Yes
NHFP | Federal | National Highway Freight Program | Yes
NHP | Federal | National Highway Performance Program | Yes
NHPB | Federal | National Highway Performance Program(Bridge) | Yes
NHPBA | Federal | National Highway Performance Program(Bonus Allocation) | No
NHPIM | Federal | National Highway Performance Program (Interstate Maintenance) | Yes
NRT | Federal | National Recreation Trails | Yes
O | Other | Local, Non Federal or State Funds | No
PROTCT | Federal | PROTECT Formula Program (Promoting Resilient Operations…) | Yes
RR | Federal | Rail-Highway Safety | Yes
RTAP | Federal | Rural Transit Assistance Program | No
S | State | State | No
S(M) | State | State Match for STP-DA or Garvee Projects | Yes
S(M)BA | State | State Match for Bonus Allocation Projects using Federal funds | No
SBG | Federal | Scenic Byway Grant | Yes
SF | State | Ferries | Yes
SMAP | State | Operating Assistance and State Maintenance | No
SRTS | Federal | Safe Roads to School | Yes
SSO | Federal | Safety System Oversight | No
STBG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
STBGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
STHSR | Federal | Stimulus High Speed Rail | No
STPE | Federal | Surface Transportation Program (Enhancement) | Yes
STPOFF | Federal | Surface Transportation Program (Off System) | Yes
T | State | Highway Trust Funds | Yes
T(DA) | State | Highway Trust Funds - Fund Swaps for DA Projects | Yes
TA | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TA50200 | Federal | Transportation Alternatives Program (50K - 200K) | Yes
TA5200 | Federal | Transportation Alternatives Program (5K - 200K) | Yes
TA5T50 | Federal | Transportation Alternatives Program (5K - 50K) | Yes
TAANY | Federal | Transportation Alternatives Program (Any Area) | Yes
TADA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
TALT5 | Federal | Transportation Alternatives Program (Less than 5K) | Yes
TAP | Federal | Transportation Alternatives Program (Uncategorized) | Yes
VRU | Federal | Vulnerable Road User | Yes