## CP4B
Project Name |  | U-5749 NC49 and Back Creek Church Rd |  | Review Status | Date
Submittal Number: Description |  | CP4B Plans |  | Submitted for Review | 2021-08-11
|  |  |  | Comments Provided | 2021-08-30
ITEMS BELOW ARE ASSUMED TO BE COMMENT AS NOTED
ID | Reviewer | Sheet No. | Comment | Response | Resolved
1 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | General | We recommend turning off drainage areas at this stage | Comment incorporated
2 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | General | Wetland symbology should show up as blue. The “marsh” symbols and dashed wetland boundary seem large, so please verify that the referenced files are drawn at the correct scale | Comment incorporated
3 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | 5 | Recommend showing rip rap in base of channel at outfall Sta. 36+20 -L- LT unless you know for sure it is not going to be needed. | Comment incorporated
4 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | 12 | Recommend showing rip rap in base of channel at outfall Sta. 19+60 -Y4- LT unless you know for sure it is not going to be needed | Comment incorporated
5 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | 15 | Recommend showing rip rap in base of channel at outfall Sta. 54+40 -Y4- LT, Sta. 60+40 -Y4- RT, and 63+40 -Y4- RT unless you know for sure it is not going to be needed. | Comment incorporated
6 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | 15 | Consider adding Channel Change Detail CCX to this sheet. | Comment incorporated
7 | NCDOT Hydraulics - David Webb and Ryan Mahjoub | 16 | Recommend showing rip rap in base of channel at outfall of Sta. 73+50 -Y4- RT unless you know for sure it is not going to be needed. | Comment incorporated
8 | ECAP - Michael Turchy | 12 | I've not seen the blue lines shown before. What are these representing? | They were drainage areas. They have been turned off with the revised plans submittal
9 | ECAP - Michael Turchy | 12 | To assist with agency review, I recommend a small block like the below (if this is correct): | Comment incorporated. Note added to sheets with no impacts
10 | ECAP - Michael Turchy | 12 | No jurisdictional resources impacted on this page. | Correct
11 | ECAP - Michael Turchy | 14 | No jurisdictional resources on this page, correct? | Correct
12 | ECAP - Michael Turchy | 15 | Two wetlands on this page. At meeting: can point out avoidance. | Noted
13 | ECAP - Michael Turchy | 17 | No jurisdictional resources on this page, correct? | Correct
14 | ECAP - Michael Turchy | 18 | No jurisdictional resources on this page, correct? | Correct
15 | ECAP - Michael Turchy | 19 | 2 jurisdictional resources on this page, however, we have no impacts, correct? | Correct
16 | ECAP - Michael Turchy | 13 | Be prepared for question: not buried, since JS begins at outlet, correct? | Noted
17 | ECAP - Michael Turchy | 13 | Be prepared at meeting: Any photos from hydro survey? | Noted
18 | ECAP - Michael Turchy | 23 | why is there a need to modify the stream channel at this location? | The stream is very unstable is this location. The CP4B show a worst case scenario for the channel modification and relocation
19 | ECAP - Michael Turchy | 20 | Recommend for meeting: photos of these smaller sites. | Noted
20 | ECAP - Michael Turchy | 21 | Be prepared to be asked for Class II. | Noted
21 | ECAP - Michael Turchy | 12 | Information like this will invoke agency comment. If you are not looking for agency comment, I recommend turning off of the CP4B planset. | Comment incorporated. The outfall analysis note has been turned off.